## Capgemini Migration - Java Sec
Redeploy w/log4j2 Complete? | Original Scope | Redeploy Needed? | Application Dependency | Pending Secrets Mitigation? | Application | App Group | Pending AO Review of Log4J | App Status | Health | Planned Month to be in Step 6.2? | Planned Month to Deploy to Prod (i.e. Done)? | Tshirt Size | Current (AO) Status - Start Date | Duration of Current Status (weeks) | Department Directors | AO Manager | AO Assigned | AO Assigned Email | File Total Count | Bamboo JDK8 Compliant? | Log4j? | Secrets? | Bamboo Plan is Java v1.8? REQUIRED (AO) | Bamboo? | BitBucket? | Maven? | Module (Not Confirmed) | Cap Contacts | Project Completion Date | CAP Migration (y/n) | Start Date for Major Blocker | Refresh Helper | Start Date for Waiting On AO | Start Date for (AO) Need Dev Envir Built | Start Date for (AO) Log4J | Start Date of (AO) Secrets Mitigation | Start Date for (AO) BitBucket | Start Date for (AO) Maven | Start Date for (AO) Bamboo | Start Date for (AO) QA Deploy | Start Date for (AO) App Deployed
| Yes | No |  |  | tririga_integrations | Finance & Business Process Automation (Admin) |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Dec 2023 |  | 2023-11-10 | 1.2 | Stephen McMullen | Steve McMullen | Charles Csoky | Charles Csoky | 30 |  | Needed |  |  | Needed | Needed | Needed | Tririga- Integrations | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-06-15 |  |  |  |  | 2023-07-12 | 2023-07-14 | 2023-11-10
| Yes | No |  |  | ach.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-14 | 18.8 | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 131 |  | Needed | Not Needed |  | Needed | Needed | Needed | Customer File | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [6 empty] | 2023-03-30 |  | 2023-08-14
| Yes | No |  |  | achbatch | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-14 | 18.8 | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 44 |  | Needed | Not Needed |  | Needed | Needed | Needed | Cash Application | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-02-06 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-03-01 | 2023-03-29 |  | 2023-08-14
| Yes | No |  |  | achsvc.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-14 | 18.8 | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 26 |  | Needed | Not Needed |  | Needed | Needed | Needed | Customer File | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [8 empty] | 2023-08-14
| Yes | No |  |  | cmsplus.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-30 | 15.6 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Mark Weaver | 310 |  | Needed | Not Needed |  | Needed | Needed | Needed | Collection Management Systems Enhanced | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | 2023-02-15 | 2023-11-16 | 2023-05-11 |  |  |  |  | 2023-07-19 | 2023-07-24 | 2023-08-22 | 2023-08-30
| Yes | No |  |  | ecm.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-23 | 17 | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 180 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | e-Credit Memo | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [7 empty] | 2023-05-16 | 2023-08-23
| No |  |  |  | employeemasterbatch | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-21 | 17.4 | Stephen McMullen | Kalrav Khamar | [15 empty] | 2023-11-16 | 2023-06-06 |  |  |  |  | 2023-06-27 |  | 2023-06-29 | 2023-08-21
| Yes | No |  |  | eram.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA |  | 0 | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 50 |  | Needed |  | Yes | Needed | Needed | Needed | eRam | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-02-28 | 2023-03-10
| Yes | No |  |  | esr.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Sept 2023 | Sept 2023 |  | 2023-10-20 | 5.4 | Stephen McMullen | Steve McMullen | Charles Csoky | Charles Csoky | 72 |  | Needed | Not Needed |  | Needed | Needed | Needed | Environmental Self Review | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-01-31 | [5 empty] | 2023-06-12 | 2023-08-23 | 2023-10-20
| Yes | Yes |  |  | esrbatch | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Sept 2023 | Sept 2023 | Large | 2023-09-29 | 9.6 | Stephen McMullen | Steve McMullen | Charles Csoky | Charles Csoky | 31 |  | Needed | Needed |  | Needed | Needed | Needed | Environmental Self Review - Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-02-16 | 2023-03-29 | 2023-05-24 | 2023-09-29
| Yes | No |  |  | gewebcash | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | Oct 2023 |  | 2023-09-26 | 10.2 | Stephen McMullen | Kalrav Khamar | Srinivasan Narayanan | Sreekanth, Srinivasan Narayanan |  |  | Needed | Not Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [6 empty] | 2023-03-23 | 2023-09-05 | 2023-09-26
| Yes | No |  |  | hrcc.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-30 | 15.6 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 83 |  | Needed | Not Needed |  | Needed | Not Needed | Needed | HRCC Highradius Collection Cloud | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-04-18 |  | 2023-05-24 | 2023-08-30
| Yes | No |  |  | mailreader_2_0 | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Sept 2023 | Oct 2023 | XL | 2023-10-12 | 7 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth |  |  | Needed | Not Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-05-01 | 2023-05-09 | 2023-09-05 | 2023-10-12
| Yes | No |  |  | pettycash.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA |  | 0 | Stephen McMullen | Kalrav Khamar | Srinivasan Narayanan | Sreekanth, Srinivasan Narayanan | 72 |  | Needed | Needed |  | Needed | Needed | Needed | AP Petty Cash | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  | 2023-02-24 |  |  | 2023-03-10
| Yes | No |  |  | pextfl | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | Sept 2023 | Medium | 2023-09-15 | 12.4 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 9 |  | Needed | Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-07-26 |  | 2023-08-21 | 2023-09-15
| Yes | No |  |  | pops.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Sept 2023 | Oct 2023 |  | 2023-10-25 | 4.4 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 300 |  | Needed |  |  | Needed | Needed | Needed | POPS - Penske On-Line Payment System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-02-24 |  |  |  |  | 2023-03-16 |  | 2023-09-15 | 2023-10-25
| Yes | No |  |  | pops_batch | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Sept 2023 | Oct 2023 | XL | 2023-10-25 | 4.4 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 85 |  | Needed |  |  | Needed | Needed | Needed | POPS - Batch Process | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-02-27 |  |  |  |  | 2023-03-15 |  | 2023-03-28 | 2023-10-25
| No | No |  |  | psndmail | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Sept 2023 | Oct 2023 | Large | 2023-10-05 | 8.4 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | [13 empty] | 2023-11-16 |  |  |  | 2023-02-23 |  | 2023-03-01 | 2023-03-20 | 2023-08-21 | 2023-10-05
| Yes | No |  |  | sics.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-17 | 18.2 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 204 |  | Needed | Not Needed |  | Needed | Needed | Needed | SICS - Sales Incentives Commission System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [7 empty] | 2023-07-05 | 2023-08-17
| Yes | No |  |  | sicsbatch | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-17 | 18.2 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 108 |  | Needed | Not Needed |  | Needed | Needed | Needed | SICS Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [7 empty] | 2023-07-05 | 2023-08-17
| Yes | No |  |  | sicssvc.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-17 | 18.2 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 83 |  | Needed | Not Needed |  | Needed | Needed | Needed | SICS Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [7 empty] | 2023-07-05 | 2023-08-17
| Yes | No |  |  | wje.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | Sept 2023 | Large | 2023-09-20 | 11.4 | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 67 |  | Needed |  |  | Needed | Needed | Needed | Web Journal Entry | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-02-13 |  |  | 2023-02-23 |  | 2023-03-08 |  | 2023-08-24 | 2023-09-20
| Yes | No |  |  | ebill | Finance & Business Process Automation (Admin) |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth |  |  | Needed |  |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-06-05
| Yes | No |  |  | mailreader_1_0 | Finance & Business Process Automation (Admin) |  | Dup App | Green | Done | Done | Done | 2023-08-03 | 21 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth |  |  | Needed |  |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-08-14
| Yes | No |  |  | sics | Finance & Business Process Automation (Admin) |  | Retire App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | NA |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed |  |  |  | 2023-11-16
| Yes | No |  |  | vendorinfo.war | Finance & Business Process Automation (Admin) |  | Retire App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Kalrav Khamar | Narayanan-Srinivasan | Srinivasan Narayanan |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed | [5 empty] | 2023-11-16
| No |  | football.war |  | highavail | Architect |  | 1.2 (AO)Log4i Review | Green |  |  | Large | 2023-09-06 | 14.2 | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers | [14 empty] | 2023-08-24 |  | 2023-09-06
| Yes | No |  |  | contribreport | Architect | TRUE | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Sept 2023 | Medium | 2023-10-31 | 3.2 | Victor Chelladurai | Shane Myers | Mahipal Podduturi | David Graf, Shane Myers | 50 |  | Needed |  | Yes | Needed | Needed | Needed | Contribution Reports | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-02-16 |  |  |  |  | 2023-09-28 |  | 2023-10-31
| No |  |  |  | docserviceclient.jar | Architect | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-07-20 | 23.8 | Victor Chelladurai | Don Kichline | Sarvesh Sharma | Sarvesh Sharma | [13 empty] | 2023-11-16 | [5 empty] | 2023-07-20
| No | No |  |  | penske-watchlist-client jar | Architect | TRUE | 6.2 (AO)QA Deploy/Test | Green | Oct 2023 | Nov 2023 | Small | 2023-11-14 | 0.4 | Victor Chelladurai | Don Kichline | Mahipal Podduturi | David Graf |  |  | Not Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-10-25 |  | 2023-11-14
| Yes | No |  |  | penskesso-ws-client.jar | Architect | TRUE | 4.2 (AO)Maven | Green | Oct 2023 | Dec 2023 | Small | 2023-09-06 | 14.2 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Not Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-09-06 |  |  |  |  | 2023-09-06
| Yes | No |  |  | techchallenge.war | Architect | TRUE | 4.2 (AO)Maven | Green | Sept 2023 | Nov 2023 | Small | 2023-09-06 | 14.2 | Victor Chelladurai | Don Kichline | Sarvesh Sharma | David Graf, Sama |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | ASP - Tech Challenge | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-09-06 |  |  |  |  | 2023-09-06
| Yes | No |  |  | userstoreclient_rest.jar | Architect | TRUE | 4.2 (AO)Maven | Green | Jan 2024 | Jan 2024 | Small | 2023-02-15 | 54.8 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | User Store Client - Rest | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-02-15
| Yes | No |  |  | userstoresvcjws.war | Architect | TRUE | 4.2 (AO)Maven | Green | Jan 2024 | Jan 2024 | Small | 2023-09-06 | 14.2 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Userstore Service - jax-ws | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-09-06 |  |  |  |  | 2023-09-06
| Yes | No |  |  | vendorreg.war | Architect | TRUE | 4.2 (AO)Maven | Green | Nov 2023 | Dec 2023 | Small | 2023-05-30 | 34 | Victor Chelladurai | Don Kichline | David Graf - Mahendra | David Graf, Kalyan |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | vendorregistration | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-05-30
| Yes | Yes |  |  | watchlistsvc.war | Architect | TRUE | 6.1 (Cap/AO)Dev Deploy/Test | Green | Oct 2023 | Nov 2023 | Small | 2023-09-06 | 14.2 | Victor Chelladurai | Don Kichline | Mahipal Podduturi | Shane Myers |  |  | Needed | Needed | Yes | Needed | Not Needed | Needed | Watch List Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-09-06 |  |  |  |  | 2023-09-06
| Yes | No |  |  | ws_authorizationfilter.jar | Architect | TRUE | 4.2 (AO)Maven | Green | Dec 2023 | Jan 2024 | Small | 2023-09-06 | 14.2 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | 2023-06-05 | 2023-11-16 | 2023-09-06 |  |  |  |  | 2023-09-06 | 2023-03-01
| Yes | No |  |  | b2busercreation.war | Architect | TRUE | 6.1 (Cap/AO)Dev Deploy/Test | Green | Nov 2023 | Jan 2024 | Small | 2023-10-25 | 4.4 | Victor Chelladurai | Don Kichline | Sama Bhagya - Mahendra | David Graf, Kalyan, Sama |  |  | Needed |  | Yes | Needed | Needed | Needed | B2B User Creation | Kalyan, Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-04-17 |  |  | 2023-02-24 |  | 2023-10-18 | 2023-10-25
| Yes | No |  |  | connectionmaint.war | Architect |  | 5.2 (AO)Bamboo Review | Green | Nov 2023 | Jan 2024 | Medium | 2023-02-09 | 56 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Needed | Yes | Needed | Needed | Needed | Connection Maintenance | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [6 empty] | 2023-02-09
| Yes | No |  |  | contextframework | Architect |  | 5.2 (AO)Bamboo Review | Green | Nov 2023 | Jan 2024 | Small | 2023-07-09 | 26 | Victor Chelladurai | Don Kichline | David Graf - Amit | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Connection Mangement Framework | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [6 empty] | 2023-07-09
| Yes | No |  |  | ebsadmin.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Nov 2023 | Small | 2023-11-15 | 0.2 | Victor Chelladurai | Don Kichline | Sama Bhagya - Ankita | David Graf, Sama |  |  | Needed |  | Yes | Needed | Needed | Needed | EBS - Admin | ankita.tiwary@penske.com, Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-09-06 |  |  |  |  | 2023-09-06 | 2023-09-28 | 2023-11-15
| Yes | No |  |  | ebsservice.war | Architect |  | 5.2 (AO)Bamboo Review | Green | Oct 2023 | Dec 2023 | Small | 2023-10-02 | 9 | Victor Chelladurai | Don Kichline | David Graf - Amit | David Graf, Sama |  |  | Needed |  | Yes | Needed | Not Needed | Needed | WSV - EBSservice | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  | 2023-02-22 |  | 2023-03-03 | 2023-10-02
| No |  |  |  | ebsserviceclient.jar | Architect |  | 5.2 (AO)Bamboo Review | Green | Oct 2023 | Dec 2023 | Small | 2023-09-27 | 10 | Victor Chelladurai | Don Kichline | David Graf - Amit | David Graf, Sama | [13 empty] | 2023-11-16 | [5 empty] | 2023-06-13 | 2023-09-27
| Yes | No |  |  | javapostop | Architect |  | 5.2 (AO)Bamboo Review | Green | Oct 2023 | Dec 2023 | Medium | 2023-10-04 | 8.6 | Victor Chelladurai | Don Kichline | Maitri Chokshi | Chokshi |  |  | Needed | Needed | Yes | Needed | Needed | Needed | JAVAPOSTOP | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-04-05 |  |  |  |  | 2023-07-13 | 2023-10-04
| Yes | No |  |  | restfilter.jar | Architect |  | 5.2 (AO)Bamboo Review | Green | Nov 2023 | Jan 2024 | Small | 2023-09-27 | 10 | Victor Chelladurai | Don Kichline | Sama Bhagya | Sama |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-01-24 | 2023-09-27
| No | No |  |  | security_author_filter.jar | Architect |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-02-13 | 55.2 | Victor Chelladurai | Don Kichline | Sivagamasundari Suresh | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  | 2023-02-08 |  |  | 2023-02-13
| No | No |  |  | security_util.jar | Architect |  | 5.2 (AO)Bamboo Review | Green | Done | NA | NA | 2023-10-20 | 5.4 | Victor Chelladurai | Don Kichline | Sivagamasundari Suresh | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [6 empty] | 2023-10-20 |  | 2023-02-15
| No |  |  |  | usrcreationsvc-client.jar | Architect |  | 5.2 (AO)Bamboo Review | Green | Oct 2023 | Dec 2023 | Small | 2023-06-09 | 32 | Victor Chelladurai | Don Kichline | David Graf - Mahendra | David Graf | [13 empty] | 2023-11-16 | 2023-04-18 |  |  | 2023-04-25 |  | 2023-05-24 | 2023-06-09
| Yes | No |  |  | wlstandalone.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Oct 2023 | Nov 2023 | Small | 2023-11-14 | 0.4 | Victor Chelladurai | Don Kichline | Mahipal Podduturi | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Not Needed | FBI Watch List (Web) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-05-22 | 2023-09-05 | 2023-11-14
| Yes | No |  |  | billingservice.war | Billing | TRUE | 6.2 (AO)QA Deploy/Test | Green | Nov 2023 | Dec 2023 | Medium | 2023-11-10 | 1.2 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed |  |  | Needed | Needed | Needed | WSV - Billing Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-08-25 |  |  |  |  | 2023-09-15 |  | 2023-11-10
| Yes | No | BillingUtility.jar | TRUE | cnsmailer | Billing | TRUE | 4.2 (AO)Maven | Yellow | Dec 2023 | Dec 2023 | Small | 2023-09-28 | 9.8 | Stephen McMullen | Rafiq Melath | Mark Weaver | manish sisodiya |  |  | Needed | Needed |  | Needed | Needed | Needed | CMNS - CNSMAILER | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-06-09 |  |  |  |  | 2023-09-28
| Yes | No |  |  | csb.war | Billing | TRUE | 4.2 (AO)Maven | Green | Dec 2023 | Dec 2023 |  | 2023-08-24 | 16.8 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  |  | Not Needed |  |  |  |  | PBS - Contract Support Billing (Lease) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-03-24 |  |  |  |  | 2023-08-24
| Yes | Yes |  |  | fuelpromos.war | Billing | TRUE | 4.2 (AO)Maven | Green | Nov 2023 | Nov 2023 |  | 2023-09-01 | 15.2 | Stephen McMullen | Rafiq Melath | Elliott Eames | Elliott | [8 empty] | Fuel Promotion Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-01-09 |  |  | 2023-07-17 |  | 2023-09-01
| Yes | No | BillingUtility.jar |  | wambea | Billing | TRUE | 4.2 (AO)Maven | Green | Dec 2023 | Dec 2023 | Small | 2023-09-11 | 13.2 | Stephen McMullen | Rafiq Melath | Manish Sisodiya | manish sisodiya |  |  | Needed |  |  | Needed | Needed | Needed | CMNS - WAMBEA | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-06-13 |  |  | 2023-05-12 |  | 2023-09-11
| Yes | No |  |  | wbmusernotifier | Billing | TRUE | 4.2 (AO)Maven | Green | Dec 2023 | Dec 2023 |  | 2023-09-26 | 10.2 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  |  | Not Needed |  |  |  |  | WSV - wbmuserservice | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-09-26
| Yes | No |  |  | darptbatch | Architect | TRUE | 2.2 (AO)Secrets Mitigate | Green | Oct 2023 | Jan 2024 | Medium | 2023-07-16 | 24.6 | Victor Chelladurai | Don Kichline | Elan Arulsamy | ARULSAMY, David Graf |  |  | Needed | Needed | Yes | Needed | Needed | Needed | Delegated Admin - Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  | 2023-07-16
| Yes | No |  |  | dasservice.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Nov 2023 | Small | 2023-09-12 | 13 | Victor Chelladurai | Don Kichline | Sarvesh Sharma | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Document Archive | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [7 empty] | 2023-09-12
| Yes | No |  |  | dlinkappremoval | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Oct 2023 | Small | 2023-05-24 | 35.2 | Victor Chelladurai | Don Kichline | Chokshi, Maitri | Chokshi, Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Not Needed | Dlinks Application Removal | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-05-22 |  | 2023-05-24
| Yes | No |  |  | dlinks.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Dec 2023 | Small | 2023-05-16 | 36.8 | Victor Chelladurai | Don Kichline | Sama Bhagya | Sama |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | Dlinks | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-05-01 | 2023-04-12 | 2023-05-16
| Yes | No |  |  | international.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Dec 2023 | Small | 2023-05-09 | 38.2 | Victor Chelladurai | Don Kichline | Sarvesh Sharma - Ankita | David Graf, Sarvesh Sharma |  |  | Needed | Needed | Yes | Needed | Needed | Needed | ASP - International Link (eLearning) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-04-11 |  |  |  |  | 2023-02-22 |  | 2023-05-09
| Yes | No |  |  | oracle2ldap | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Nov 2023 | Small | 2023-06-23 | 29.2 | Victor Chelladurai | Don Kichline | Chokshi, Maitri | Chokshi |  |  | Needed | Needed | Yes | Needed | Needed | Needed | Oracle2LDAP | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-04-19 | 2023-04-13 | 2023-06-23
| Yes | Yes |  |  | usermgmtsvc.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Oct 2023 | Oct 2023 | Medium | 2023-09-26 | 10.2 | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | User Management Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  | 2023-02-08 |  |  |  | 2023-09-26
| Yes | No |  |  | usrcreationsvc.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Dec 2023 | Small | 2023-06-19 | 30 | Victor Chelladurai | Don Kichline | David Graf - Mahendra | David Graf |  |  | Needed | Needed | Yes | Needed | Not Needed | Needed | User Creation Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-04-11 |  | 2023-06-19
| Yes | No |  |  | vdrfilebatch | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Dec 2023 | Small | 2023-06-26 | 28.6 | Victor Chelladurai | Don Kichline | Sarvesh Sharma | Sarvesh Sharma |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | VDR File Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [7 empty] | 2023-06-26
| Yes | No |  |  | vdrfilesvc.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Dec 2023 | Small | 2023-08-11 | 19.4 | Victor Chelladurai | Don Kichline | Sarvesh Sharma | Sarvesh Sharma |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | VDR File SVC | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [7 empty] | 2023-08-11
| Yes | No |  |  | watchlistbatch | Architect | TRUE | 6.2 (AO)QA Deploy/Test | Green | Oct 2023 | Nov 2023 | Medium | 2023-10-24 | 4.6 | Victor Chelladurai | Don Kichline | Mahipal Podduturi | David Graf, Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | Watch List Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-11-29 | Yes - Capgemini |  | 2023-11-16 | 2023-09-06 |  |  |  |  | 2023-09-28 |  | 2023-10-24
| Yes | No |  |  | csar.war | Architect |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Oct 2023 | Nov 2023 | Large |  | 0 | Victor Chelladurai | Don Kichline | David Graf | David Graf | [8 empty] | CSAR - Computer Security Access Request | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16
| Yes | No |  |  | dlinks_filter.jar | Architect |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Sept 2023 | Nov 2023 | Small |  | 0 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed |  | Yes | Needed | Not Needed | Needed | DLinks Authentication Filter | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16
| Yes | No |  |  | ebs.war | Architect | TRUE | 5.2 (AO)Bamboo Review | Green | Sept 2023 | Nov 2023 | Medium | 2023-11-01 | 3 | Victor Chelladurai | Don Kichline | Sama Bhagya - Ankita | David Graf |  |  | Needed |  | Yes | Needed | Needed | Needed | EBS - Email Broadcast System | ankita.tiwary@penske.com, Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-09-06 |  |  |  |  | 2023-09-06 | 2023-11-01
| Yes | No |  |  | hrldapcomparision | Architect |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Oct 2023 | Nov 2023 | Small |  | 0 | Victor Chelladurai | Don Kichline | Chokshi, Maitri | Chokshi |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | HRLDAP Comparison | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16
| Yes | No |  |  | reuse.jar | Architect |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Jan 2024 | Jan 2024 | XL |  | 0 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Needed | Yes | Needed | Needed | Needed | Reusable Web Code | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16
| Yes | No |  |  | fbwatermark.jar | Billing |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - CBOS - Watermark | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16
| Yes | No |  |  | Flex Billing | Billing |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - CBOS - Invoice and Profile Control | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-01-09
| Yes | No |  |  | flexbilling | Billing |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Elliott Eames | Elliott | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-01-09
| Yes | No |  |  | fuelnet | Billing |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-05-03 |  |  | 2023-05-12
| Yes | No |  |  | invarcbatch | Billing |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - Invoice Archive Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2022-12-15 |  |  | 2023-05-12
| Yes | No |  |  | trs_extract | Billing |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Manish Sisodiya | manish sisodiya | [8 empty] | Trust Extract | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16
| Yes | No |  |  | ccms.war | Fleet Services & Asset Mngmt (Corp) |  | Dup App | Green | Done | Done | Done |  | 0 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh |  |  | Not Needed | Not Needed | Yes | Not Needed | Not Needed | Not Needed | CCMS - Arch Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16
| No |  |  |  | IRS Dependency Jar Here | Fleet Services & Asset Mngmt (Corp) |  | Dup App | Green | Done | Done | Done |  | 0 | Krishna Tanga | Veronique Labeille | Sreekanth Kancharla | Kancharla, Sreekanth (Penske, Capgemini) <Sreekanth.Kancharla@penske.com> | [13 empty] | 2023-11-16
| Yes | No |  |  | safetydata | Fleet Services & Asset Mngmt (Corp) |  | Dup App | Green | Done | Done | Done |  | 0 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Non-Critical | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-02-16 |  |  |  |  | 2023-02-15
| No |  |  |  | captchabatchjob | Customer Digital Engineer (eBusiness) |  | 4.1 (Cap)Maven | Yellow |  | Jan 2024 | Large | 2023-11-06 | 2 | Michael Hintenach | Gopal-Sree | Joseph-Brian | Brian | [13 empty] | 2023-11-16 | 2023-08-14 |  | 2023-09-19 | 2023-11-06
| No |  |  |  | cookie.war | Customer Digital Engineer (eBusiness) |  | 4.1 (Cap)Maven | Yellow |  | Jan 2024 | Large | 2023-08-28 | 16 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-11-16 | 2023-08-28
| No |  |  |  | etservice.war | Customer Digital Engineer (eBusiness) | TRUE | 4.1 (Cap)Maven | Yellow | Nov 2023 | Dec 2023 | Large | 2023-08-28 | 16 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth |  | Needed | Needed | Needed | Needed | Not Needed | Not Needed | Needed | [5 empty] | 2023-11-16 |  |  |  | 2023-08-28
| No |  |  |  | locationsearch | Customer Digital Engineer (eBusiness) | TRUE | 2.2 (AO)Secrets Mitigate | Yellow |  | Jan 2024 | XL | 2023-09-13 | 12.8 | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | shweta.gupta@penske.com | [13 empty] | 2023-11-16 | 2023-09-07 |  |  | 2023-09-13
| No |  |  |  | mapservice.war | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Yellow | Nov 2023 | Dec 2023 | Large | 2023-11-14 | 0.4 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth |  | Needed | Needed | Needed | Needed | Not Needed | Not Needed | Needed | [5 empty] | 2023-11-16 |  |  |  | 2023-08-04 |  | 2023-11-14
| No | No |  |  | ebsworkerbatch | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-03-20 | 48.2 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed |  | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [8 empty] | 2023-03-20
| Yes | No |  |  | fuelrecptbatch | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-05-16 | 36.8 | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | CE - Fuel Receipt Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  |  | 2023-08-14
| No | No |  |  | fuelrecptbatch | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16
| Yes | No |  |  | ldapismgr | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | Sherin |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | ldapismgr | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-04-06
| No | No |  |  | penske-secure-logger-1.0.0.jar | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-04-14 | 43.2 | Victor Chelladurai | Don Kichline | David Graf | Don Kichline |  |  | Needed |  | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [8 empty] | 2023-04-14
| No | No |  |  | penskesso.jar | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-04-14 | 43.2 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [8 empty] | 2023-04-14
| Yes | No |  |  | ptldao.jar | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA |  | 0 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Was Needed - AO Done | Was Needed - AO Done | Yes | Not Needed | Was Needed - AO Done | Was Needed - AO Done | PTL DAO | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16
| Yes | No |  |  | queryrunner | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA |  | 0 | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed |  | Yes | Needed | Needed | Needed | need to create one | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed |  |  |  | 2023-11-16 |  |  |  |  | 2023-02-22 |  |  |  | 2023-05-16
| Yes | No |  |  | roforms.war | Architect |  | DONE - (AO)App Deployed | Green | Sept 2023 | Oct 2023 | Medium | 2023-10-26 | 4.2 | Victor Chelladurai | Don Kichline | Chokshi, Maitri | Chokshi |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | ASP - RO Forms | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [7 empty] | 2023-04-05 | 2023-10-26
| Yes | Yes |  |  | sessionmgmtsvc.war | Architect |  | DONE - (AO)App Deployed | Green | Sept 2023 |  | Small | 2023-09-27 | 10 | Victor Chelladurai | Don Kichline | Sivagamasundari Suresh | David Graf |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | Session Management Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [7 empty] | 2023-09-12 | 2023-09-27
| Yes | No |  |  | userlookup.war | Architect |  | DONE - (AO)App Deployed | Green | Sept 2023 | Nov 2023 | Small | 2023-09-29 | 9.6 | Victor Chelladurai | Don Kichline | David Graf - Ankita | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | User Lookup Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-06-19 | 2023-06-30 | 2023-07-05 | 2023-09-29
| Yes | No |  |  | usermgmt.war | Architect |  | DONE - (AO)App Deployed | Green | Oct 2023 | Oct 2023 | Medium | 2023-10-30 | 3.4 | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf, Sama |  |  | Needed | Was Needed - AO Done | Yes | Needed | Not Needed | Needed | User Management | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [6 empty] | 2023-09-11 | 2023-10-17 | 2023-10-30
| Yes | No |  |  | webrptportal.war | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-24 | 16.8 | Victor Chelladurai | Don Kichline | David Graf - Amit | David Graf, Sama |  |  | Needed | Needed | Yes | Needed | Not Needed | Not Needed | Web Report Portal | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [6 empty] | 2023-03-01 | 2023-08-11 | 2023-08-24
| Yes | No |  |  | cntxfrmwrk | Architect |  | Dup App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Not Needed | Not Needed | Yes | Not Needed | Not Needed | Not Needed | Connection Mangement Framework | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed |  | Yes - Capgemini |  | 2023-11-16
| Yes | No |  |  | da.war | Architect |  | Dup App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Not Needed | Not Needed | Yes | Not Needed | Not Needed | Not Needed | Delegated Admin | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16
| Yes | No |  |  | dasservice.war | Architect |  | Dup App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16
| Yes | No |  |  | oraemail | Architect |  | Retire App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | OraEmail | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16
| Yes | No |  |  | reuse-changemode | Architect |  | Retire App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Not Needed | Not Needed | Yes | Not Needed | Not Needed | Not Needed | Reusable Web Code | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed |  |  |  | 2023-11-16
| Yes | No |  |  | shoptalkreg.war | Architect |  | Retire App | Green | Done | Done | Done | 2023-05-16 | 36.8 | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Shop Talk Registration | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [6 empty] | 2023-03-23 | 2023-05-16
| Yes | No |  |  | synchghdbc | Architect |  | Retire App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed |  | Yes | Needed | Needed | Needed | SynchGHDBC | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2022-12-15 |  |  |  |  | 2023-03-01
| Yes | No |  |  | telematicssvc.war | Architect |  | Retire App | Green | Done | Done | Done | 2023-05-15 | 37 | Victor Chelladurai | Don Kichline | Myers-Shane | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Telematics Service (eDTR) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-05-15
| Yes | No |  |  | vehicledatarepo | Architect |  | Retire App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed |  | Yes | Needed | Needed | Needed | Vehicle Data Repository Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed |  |  |  | 2023-11-16
| Yes | No | billingutility.jar | TRUE | cmns.war | Billing | TRUE | 4.2 (AO)Maven | Yellow | Dec 2023 | Dec 2023 | Medium | 2023-11-09 | 1.4 | Stephen McMullen | Rafiq Melath | Mark Weaver | manish sisodiya |  |  | Needed |  |  | Needed | Needed | Needed | CE - Customer Maintenance Notification System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-06-09 |  |  | 2023-09-27 |  | 2023-11-09
| Yes | No |  |  | fbwatermark | Billing |  | 6.2 (AO)QA Deploy/Test | Green | Nov 2023 | Dec 2023 |  | 2023-11-15 | 0.2 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | PBS - CBOS - Watermark | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2022-12-20 |  |  | 2023-03-23 |  | 2023-08-24 | 2023-09-20 | 2023-11-15
| Yes | No |  |  | flex_billing_acl.jar | Billing |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Nov 2023 | Dec 2023 |  | 2023-08-29 | 15.8 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Flex Billing Account Context Loader (not in PC2) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-04-17 |  |  |  |  | 2023-08-24 | 2023-08-29
| Yes | No |  |  | lbs.war | Billing |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Dec 2023 |  |  |  | 0 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | PBS - LBS - Logistics Billing System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-06-05
| Yes | No |  |  | mileagereporting.war | Billing |  | DONE - (AO)App Deployed | Green |  | Nov 2023 |  | 2023-11-15 | 0.2 | Stephen McMullen | Rafiq Melath | Nicolas Hernandez | Hernandez |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Web Mileage Entry | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-08-24 | 2023-10-19 | 2023-11-10 | 2023-11-15
| Yes | No |  |  | ssptktportal.war | Billing |  | DONE - (AO)App Deployed | Green |  | Nov 2023 |  | 2023-11-15 | 0.2 | Stephen McMullen | Rafiq Melath | Spohn-Bill | William Spohn | [8 empty] | Fuel Reconciliation-Suspended Tkts Portal | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2022-12-07 |  |  | 2023-03-23 |  | 2023-04-24 | 2023-08-16 | 2023-08-03 | 2023-11-15
| No |  | cmns, cnsmailer, wambea, billingservice depends on this utility |  | billingutility.jar | Billing |  | 5.2 (AO)Bamboo Review | Green | Dec 2023 | Dec 2023 |  | 2023-08-28 | 16 | Stephen McMullen |  | Mark Weaver | Mark Weaver | [13 empty] | 2023-11-16 | [5 empty] | 2023-06-27 | 2023-08-28
| Yes | No |  |  | fuelpricing.war | Billing |  | DONE - (AO)App Deployed | Green |  | Nov 2023 |  | 2023-11-15 | 0.2 | Stephen McMullen | Rafiq Melath | Bill Spohn | Elliott |  |  | Needed | Needed |  | Needed | Needed | Needed | Fuel Purchasing - Fuel Pricing | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-01-10 |  |  |  |  | 2023-04-04 | 2023-06-23 | 2023-11-10 | 2023-11-15
| Yes | No |  |  | ias-broker | Billing |  | 5.2 (AO)Bamboo Review | Green | Dec 2023 | Dec 2023 |  | 2023-09-13 | 12.8 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | IASBATCHBROKER (not in PC2) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2022-12-13 |  |  | 2023-06-27 |  | 2023-09-06 | 2023-09-13
| Yes | No |  |  | ias-invoiceimage | Billing |  | 5.2 (AO)Bamboo Review | Green | Dec 2023 | Dec 2023 |  | 2023-09-12 | 13 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | invoiceimagebatch (not in PC2) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | 2023-06-29 | 2023-11-16 | 2023-08-14 |  |  | 2023-05-12 |  | 2023-08-29 | 2023-09-12
| Yes | No |  |  | ias-lbs | Billing |  | 5.2 (AO)Bamboo Review | Green | Dec 2023 | Dec 2023 |  | 2023-09-12 | 13 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | PBS - LBS - Logistics Billing System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-08-14 |  |  | 2023-03-23 |  | 2023-08-30 | 2023-09-12
| Yes | No |  |  | ias.war | Billing |  | 5.2 (AO)Bamboo Review | Green | Dec 2023 | Dec 2023 |  | 2023-09-12 | 13 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Invoice Archive System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-08-24 | 2023-09-12
| Yes | No |  |  | iasarchiver | Billing |  | 5.2 (AO)Bamboo Review | Green | Dec 2023 | Dec 2023 |  | 2023-09-12 | 13 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | IASARCHIVER (not in PC2) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2022-12-13 |  |  | 2023-05-12 |  | 2023-08-29 | 2023-09-12
| Yes | No |  |  | iasinvservice.war | Billing |  | 5.2 (AO)Bamboo Review | Green | Dec 2023 | Dec 2023 |  | 2023-09-12 | 13 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  | Needed | Not Needed |  | Needed | Needed | Needed | WSV - IASInvService | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-08-24 | 2023-09-12
| Yes | No |  |  | invarcbatch | Billing |  | 5.2 (AO)Bamboo Review | Green | Dec 2023 | Dec 2023 |  | 2023-09-12 | 13 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | PBS - Invoice Archive Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2022-12-15 |  |  | 2023-04-18 |  | 2023-08-24 | 2023-09-12
| Yes | Yes |  |  | ccmsxservice.war | Fleet Services & Asset Mngmt (Corp) |  | 6.1 (Cap/AO)Dev Deploy/Test | Green |  | Nov 2023 |  |  | 0 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 50 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | CCMS - Extranet Services | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-02-15 | 2023-06-09
| Yes | No |  |  | domservice.war | Fleet Services & Asset Mngmt (Corp) |  | 6.1 (Cap/AO)Dev Deploy/Test | Green |  | Dec 2023 |  |  | 0 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 46 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Domicile Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  |  | 2023-02-15 | 2023-02-16 | 2023-06-08
| Yes | No |  |  | vehicleimageupdate | Fleet Services & Asset Mngmt (Corp) |  | 6.2 (AO)QA Deploy/Test | Green |  | Nov 2023 |  | 2023-09-11 | 13.2 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 13 |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-02-16 |  |  | 2023-02-24 |  | 2023-05-01 | 2023-07-10 | 2023-09-11
| Yes | No |  |  | billingcommons.jar | Customer Digital Engineer (eBusiness) |  | Dup App | Green | Done | Done | Done | 2023-03-24 | 47.4 | Michael Hintenach | D'Angelo-Frank | Shweta Gupta | shweta.gupta@penske.com | [8 empty] | Billing Commons | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-08-14
| No |  |  |  | updtimezon | Customer Digital Engineer (eBusiness) |  | Dup App | Green | Done | Done | Done | 2023-07-27 | 22.4 | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | shweta.gupta@penske.com | [13 empty] | 2023-11-16 | 2023-08-14
| Yes | No |  |  | bill_apprunner | Billing |  | 6.2 (AO)QA Deploy/Test | Green | Nov 2023 | Nov 2023 |  | 2023-09-15 | 12.4 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | 15 |  |  | Needed |  |  |  |  | PBS - CBOS - Invoice Job | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-05-18 |  |  |  |  | 2023-04-17 |  | 2023-09-15
| Yes | No |  |  | bill_rpginvoker | Billing |  | 6.2 (AO)QA Deploy/Test | Green | Nov 2023 | Nov 2023 |  | 2023-09-15 | 12.4 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | 12 |  |  | Needed |  |  |  |  | PBS - CBOS - RPG Invoker | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2022-12-20 |  |  | 2023-05-12 |  | 2023-08-24 | 2023-09-12 | 2023-09-15
| Yes | No |  |  | bill_xmlloader_mp | Billing |  | 6.2 (AO)QA Deploy/Test | Green | Nov 2023 | Dec 2023 |  | 2023-10-23 | 4.8 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  |  | Needed |  |  |  |  | PBS - CBOS - Invoice XML Generator | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-06-13 |  |  |  |  | 2023-05-10 | 2023-08-24 | 2023-10-23
| Yes | No |  |  | bill_xmlloader_st | Billing |  | 6.2 (AO)QA Deploy/Test | Green | Nov 2023 | Dec 2023 |  | 2023-10-23 | 4.8 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | PBS - CBOS - Invoice XML Generator | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  | 2023-04-18 |  | 2023-07-13 | 2023-09-12 | 2023-10-23
| Yes | No |  |  | flexbilling.war | Billing |  | DONE - (AO)App Deployed | Green |  | Nov 2023 |  | 2023-11-15 | 0.2 | Stephen McMullen | Rafiq Melath | Nicolas Hernandez | Hernandez | [8 empty] | PBS - CBOS - Profile Maintenance | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-08-24 |  |  | 2023-05-12 |  | 2023-08-29 |  | 2023-10-23 | 2023-11-15
| Yes | No |  |  | fuelbatch | Billing | TRUE | DONE - (AO)App Deployed | Green |  | Nov 2023 |  | 2023-11-15 | 0.2 | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn | [8 empty] | FuelNet - Fuel Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-05-23 |  |  | 2023-05-04 |  | 2023-08-31 |  | 2023-10-09 | 2023-11-15
| Yes | No |  |  | fuelnetsvc.war | Billing | TRUE | 6.2 (AO)QA Deploy/Test | Green | Nov 2023 | Nov 2023 |  | 2023-10-19 | 5.6 | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn |  |  | Needed | Not Needed |  | Needed | Needed | Not Needed | FuelNet - Web Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-08-21 | 2023-10-17 | 2023-10-19
| Yes | No |  |  | trs_extract.jar | Billing |  | 6.2 (AO)QA Deploy/Test | Green | Nov 2023 | Dec 2023 |  | 2023-09-15 | 12.4 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | Trust Extract | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2022-12-14 |  |  | 2023-03-23 |  | 2023-08-24 | 2023-09-12 | 2023-09-15
| Yes | No |  |  | cbosdbmonitor | Billing |  | Retire App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Sreenivasulu Mupparaju | Sreenivasulu | [8 empty] | CCMS | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-06-07 |  |  | 2023-05-12
| Yes | No |  |  | edi_encryption | Billing | TRUE | Retire App | Green |  |  |  | 2023-04-12 | 43.6 | Stephen McMullen | Brian Hug | Sreenivasulu Mupparaju | Sreenivasulu |  |  | Needed | Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-04-12
| Yes | No |  |  | mileageforecast.war | Billing |  | Retire App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Dylan Price |  |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Iron Mountain Excel upload (Mileage Forecast) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-03-23
| Yes | No |  |  | rentalnet.war | Billing |  | Retire App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | 1050 |  | Needed |  |  | Needed | Needed | Needed | PBS - Contract Support Billing (RentalNet/VAR) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-01-23 |  |  | 2023-05-12
| Yes | No |  |  | viewpdf.war | Billing |  | Retire App | Green |  |  |  | 2023-08-24 | 16.8 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  | Needed | Not Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-08-24
| Yes | Yes |  |  | irm.war | Fleet Services & Asset Mngmt (Corp) | TRUE | 2.2 (AO)Secrets Mitigate | Green |  | Dec 2023 |  | 2023-09-15 | 12.4 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 208 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | IRM Prism / Web Application | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-08-14 |  |  | 2023-09-15 |  |  | 2023-04-17
| Yes | No |  |  | taebatch | Fleet Services & Asset Mngmt (Corp) | TRUE | DONE - (AO)App Deployed | Green |  |  | Medium | 2023-11-03 | 2.6 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Ravi | 60 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | T&E Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [8 empty] | 2023-11-03
| Yes | Yes |  |  | ccms.war (Web Application) | Fleet Services & Asset Mngmt (Corp) | TRUE | 4.2 (AO)Maven | Green |  | Nov 2023 |  | 2023-08-16 | 18.4 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 152 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | CCMS | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-08-16 | 2023-08-16
| No |  |  |  | domicileservice.jar | Fleet Services & Asset Mngmt (Corp) | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-04-24 | 41.2 | Krishna Tanga |  | Rajesh Harvade | Rajesh | [13 empty] | 2023-11-16 |  |  |  | 2023-04-14 |  | 2023-04-24
| Yes | No |  |  | sellsheet | Fleet Services & Asset Mngmt (Corp) | TRUE | 4.2 (AO)Maven | Green |  | Dec 2023 | XL | 2023-10-18 | 5.8 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 26 |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | 2023-04-13 | 2023-11-16 | 2023-08-14 |  |  |  |  | 2023-10-18
| No |  |  |  | utimageservice.jar | Fleet Services & Asset Mngmt (Corp) |  | 5.2 (AO)Bamboo Review | Yellow |  |  | Large | 2023-10-20 | 5.4 | Krishna Tanga |  | Brain Joseph | [14 empty] | 2023-11-16 | 2023-08-14 | [5 empty] | 2023-10-20
| Yes | No |  |  | vfjexcel | Fleet Services & Asset Mngmt (Corp) |  | 5.2 (AO)Bamboo Review | Green |  | Dec 2023 |  | 2023-09-25 | 10.4 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh |  |  | Needed |  |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-08-14 |  |  | 2023-08-30 |  | 2023-09-06 | 2023-09-25
| No |  |  |  | cedabatchjob | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  | Jan 2024 | Medium | 2023-10-18 | 5.8 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-11-16 | 2023-08-14 |  |  | 2023-09-13 |  | 2023-10-18
| No |  |  |  | cedanotifybatch | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  | Jan 2024 |  | 2023-09-13 | 12.8 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-11-16 |  |  |  | 2023-08-21 |  | 2023-09-13
| No |  |  |  | fcservice.war | Customer Digital Engineer (eBusiness) | TRUE | 6.1 (Cap/AO)Dev Deploy/Test | Green | Nov 2023 | Nov 2023 | Small | 2023-10-24 | 4.6 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth |  | Needed | Needed | Not Needed |  | Not Needed | Not Needed | Needed | [5 empty] | 2023-11-16 | [5 empty] | 2023-10-24
| No |  |  |  | fdtypes | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  | Jan 2024 |  | 2023-10-18 | 5.8 | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | shweta.gupta@penske.com | [13 empty] | 2023-11-16 |  |  |  | 2023-08-09 |  | 2023-10-18
| No |  |  |  | fuelcalc.war | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green | Nov 2023 | Nov 2023 |  | 2023-09-25 | 10.4 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth |  | Needed | Needed | Not Needed |  | Not Needed | Not Needed | Needed | [5 empty] | 2023-11-16 |  |  |  | 2023-08-09 |  | 2023-09-25
| No |  |  |  | intsecuritysvc.war | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  | Jan 2024 |  | 2023-10-12 | 7 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-11-16 | [5 empty] | 2023-10-12
| No |  |  |  | ldapcompanybatch | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  | Jan 2024 |  | 2023-09-20 | 11.4 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-11-16 |  |  |  | 2023-08-09 |  | 2023-09-20
| No |  |  |  | mapadmin.war | Customer Digital Engineer (eBusiness) | TRUE | 5.1 (Cap)Bamboo | Green | Nov 2023 | Nov 2023 |  | 2023-10-24 | 4.6 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth |  | Needed | Needed | Not Needed |  | Not Needed | Not Needed | Needed | [5 empty] | 2023-11-16 |  |  |  | 2023-08-21 |  | 2023-10-24
| No |  |  |  | mfaservice | Customer Digital Engineer (eBusiness) | TRUE | 5.1 (Cap)Bamboo | Green | Nov 2023 | Nov 2023 | Large | 2023-09-18 | 11.8 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth |  | Not Needed | Needed | Not Needed | Not Needed | Not Needed | Not Needed | Not Needed | [5 empty] | 2023-11-16 | 2023-08-14 |  |  | 2023-09-13 |  | 2023-09-18
| No |  |  |  | notificationbatch | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  | Jan 2024 |  | 2023-10-10 | 7.4 | Michael Hintenach | D'Angelo-Frank | Ashway, Jeremiah | Jeremiah Ashway | [13 empty] | 2023-11-16 | 2023-08-17 |  |  |  |  | 2023-10-10
| No |  |  |  | shorturlservice | Customer Digital Engineer (eBusiness) | TRUE | 6.1 (Cap/AO)Dev Deploy/Test | Green | Nov 2023 | Nov 2023 | Medium | 2023-10-10 | 7.4 | Michael Hintenach | Gopal, Sree | French-Kenneth | Kenneth |  | Not Needed | Needed | Not Needed | Not Needed | Not Needed | Not Needed | Not Needed | [5 empty] | 2023-11-16 |  |  |  | 2023-09-13 |  | 2023-10-10
| No |  |  |  | updlatlong | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  | Jan 2024 |  | 2023-10-17 | 6 | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | shweta.gupta@penske.com | [13 empty] | 2023-11-16 | 2023-09-06 |  |  |  |  | 2023-10-17
| No |  |  |  | usedtrucksadmin.war | Customer Digital Engineer (eBusiness) | TRUE | 5.1 (Cap)Bamboo | Green |  | Jan 2024 |  | 2023-10-19 | 5.6 | Michael Hintenach | Gopal-Sree | Joseph-Brian | Brian | [13 empty] | 2023-11-16 |  |  |  | 2023-08-04 |  | 2023-10-19
| Yes | No |  |  | bill_avobatch | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-10 | 7.4 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | 20 |  |  | Needed |  |  |  |  | PBS - CBOS - Avo Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-06-02 |  |  |  |  | 2023-04-14 | 2023-06-15 | 2023-08-03 | 2023-10-10
| Yes | No |  |  | buzonebatch | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-09-15 | 12.4 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  | Needed | Not Needed |  | Needed | Needed | Needed | PBS - LBS - Buzone Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-01-19 |  |  |  |  | 2023-04-02 | 2023-06-08 | 2023-09-07 | 2023-09-15
| Yes | No |  |  | edibatch | Billing | TRUE | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-23 | 4.8 | Stephen McMullen | Rafiq Melath | Sreenivasulu Mupparaju | Sreenivasulu |  |  |  | Not Needed |  |  |  |  | EDI Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-05-12 |  |  | 2023-10-23
| Yes | No |  |  | edicbos.war | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-23 | 4.8 | Stephen McMullen | Rafiq Melath | Sreenivasulu Mupparaju | Sreenivasulu |  |  |  | Not Needed |  |  |  |  | EDI/CBOS | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-05-17 | 2023-07-27 |  | 2023-10-23
| Yes | No |  |  | edipostclient | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-23 | 4.8 | Stephen McMullen | Rafiq Melath | Sreenivasulu Mupparaju | Sreenivasulu |  |  |  | Not Needed |  |  |  |  | EDI Post Client Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-01-10 |  |  |  |  | 2023-05-09 | 2023-05-17 | 2023-10-19 | 2023-10-23
| Yes | No |  |  | efuel.war | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-09 | 7.6 | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn |  |  |  | Not Needed |  |  |  |  | eFuel | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-04-18 | 2023-04-18 | 2023-06-12 | 2023-10-09
| Yes | No |  |  | efueladmin.war | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-03 | 8.8 | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn |  |  |  | Not Needed |  |  |  |  | eFuel Admin | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2022-12-08 |  |  |  |  | 2023-06-19 |  |  | 2023-10-03
| Yes | No |  |  | fuelcardsplit.war | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-17 | 6 | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Truckstop Fuel | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-09-28 | 2023-08-21 | 2023-10-05 | 2023-10-17
| Yes | No |  |  | High Radius | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-03 | 8.8 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | invarcbatch-sftp | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2022-12-07 |  |  | 2023-03-23 |  | 2023-06-29 |  | 2023-08-03 | 2023-10-03
| Yes | No |  |  | printapp | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-23 | 4.8 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  | Needed | Needed |  | Needed | Needed | Needed | PRINTAPP | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-03-30 | 2023-08-23 | 2023-10-05 | 2023-10-23
| Yes | No |  |  | stopbilling.war | Billing |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-15 | 18.6 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | IT Docs - Stop Billing | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-05-11 |  | 2023-08-02 | 2023-08-15
| Yes | No |  |  | webmileagesvc.war | Billing | TRUE | DONE - (AO)App Deployed | Green |  |  | Medium | 2023-10-24 | 4.6 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed |  |  | Needed | Needed | Needed | Web Mileage Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-08-14 |  |  |  |  | 2023-09-14 | 2023-10-17 |  | 2023-10-24
| Yes | No |  |  | bbupload.war | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done |  |  | 2023-09-22 | 11 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 120 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Blue Book Upload | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-02-15 | 2023-06-08 | 2023-09-11 | 2023-09-22
| Yes | No |  |  | ccmsservice.war | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-09-11 | 13.2 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 35 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | CCMSSERVICE | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-02-15 | 2023-05-31 |  | 2023-09-11
| Yes | Yes |  |  | cvi.war | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done |  |  | 2023-09-22 | 11 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 179 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | IT Docs Lease/Cmaint Vehicle Installation | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-03-02 | 2023-06-09 | 2023-09-11 | 2023-09-22
| Yes | No |  |  | fixedasset.war | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done |  |  | 2023-09-15 | 12.4 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 14 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Fixed Assets (Web) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-06-08 | 2023-05-17 | 2023-09-11 | 2023-09-15
| Yes | No |  |  | hvutefile | Fleet Services & Asset Mngmt (Corp) | TRUE | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-12 | 7 | Krishna Tanga | Veronique Labeille | Veronique Labeille | Sreekanth, Veronique Labeille |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-05-24 |  |  | 2023-02-24 |  | 2023-07-09 |  |  | 2023-10-12
| Yes | No |  |  | irmbatch | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done |  |  | 2023-09-22 | 11 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 110 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | IRM Prism / Savvion Transfer | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-02-16 | 2023-06-08 |  | 2023-09-22
| Yes |  |  |  | irs.jar | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-12 | 7 | Krishna Tanga | Veronique Labeille | Sreekanth Kancharla | Kancharla, Sreekanth (Penske, Capgemini) <Sreekanth.Kancharla@penske.com> | [13 empty] | 2023-11-16 | 2023-05-02 |  |  |  |  | 2023-06-23 | 2023-08-01 |  | 2023-10-12
| Yes | Yes |  |  | rsi.war | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done |  |  | 2023-09-22 | 11 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 84 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | IT DOCS Rental Vehicle Installation | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | [5 empty] | 2023-02-15 | 2023-06-08 | 2023-09-11 | 2023-09-22
| Yes | Yes |  |  | safetydata.war | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done |  |  | 2023-09-22 | 11 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh |  | No | Needed | Not Needed | Yes | Needed | Needed | Needed | Insurance Safety Data | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2022-12-26 |  |  | 2023-02-24 |  | 2023-06-15 |  |  | 2023-09-22
| Yes | No |  |  | schedule1reprint | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-23 | 17 | Krishna Tanga | Veronique Labeille | Veronique Labeille | Sreekanth, Veronique Labeille |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  | 2023-02-24 |  | 2023-04-14 |  | 2023-05-22 | 2023-08-23
| No | No |  |  | scorecard - Batch | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-09-15 | 12.4 | Krishna Tanga | Veronique Labeille | Veronique Labeille | Sreekanth, Veronique Labeille | [13 empty] | 2023-11-16 |  |  |  | 2023-02-24 |  | 2023-05-02 | 2023-05-11 | 2023-05-22 | 2023-09-15
| Yes | No |  |  | scorecard - Web | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-09-15 | 12.4 | Krishna Tanga | Veronique Labeille | Veronique Labeille | Sreekanth, Veronique Labeille |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  | 2023-02-19 |  | 2023-03-17 |  | 2023-05-22 | 2023-09-15
| No |  |  |  | locrulesrv.war | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green | Nov 2023 | Nov 2023 |  | 2023-11-12 | 0.8 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth |  | Needed | Needed | Not Needed |  | Not Needed | Not Needed | Needed | [5 empty] | 2023-11-16 | 2023-08-14 |  |  | 2023-08-21 |  | 2023-11-12
| No |  |  |  | modifyuserdaemon | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  | Jan 2024 |  | 2023-11-01 | 3 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-11-16 |  |  |  | 2023-08-04 |  | 2023-11-01
| No |  |  |  | emetrics.war | Customer Digital Engineer (eBusiness) |  | Retire App | Green |  | NA |  | 2023-08-21 | 17.4 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-11-16 |  |  |  | 2023-08-21
| Yes | No |  |  | fedexrental.war | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done | 2023-02-14 | 55 | Michael Hintenach | D'Angelo-Frank | Frank D'Angelo | Frank D'Angelo | [8 empty] | Federated SSO | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-08-14
| No |  |  |  | fimigration | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done | 2023-07-26 | 22.6 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-11-16 | 2023-08-14
| No |  |  |  | fuelcalcadmin.war | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done | 2023-08-17 | 18.2 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth |  | Not Needed | Not Needed | Not Needed | Not Needed | Not Needed | Not Needed | Not Needed | [5 empty] | 2023-11-16 | 2023-08-17 |  |  | 2023-08-04
| No |  |  |  | locationfinder.war | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done | 2023-08-21 | 17.4 | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | shweta.gupta@penske.com | [13 empty] | 2023-11-16 |  |  |  | 2023-08-21
| No |  |  |  | reconcilebatch | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done | 2023-08-04 | 20.8 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-11-16 |  |  |  | 2023-08-04
| No |  |  |  | rentaladmin.war | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done |  | 0 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth |  | Not Needed | Not Needed | Not Needed | Not Needed | Not Needed | Not Needed | Not Needed | [5 empty] | 2023-11-16
| No |  |  |  | ssoservice.war | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done | 2023-07-31 | 21.6 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-11-16 | 2023-08-14
| No |  |  |  | LRS.war (Cap doing Log4J ONLY) | HR Systems |  | 1.1 (Cap)Log4j |  | Dec 2023 | Jan 2024 | Small |  | 0 | David Kost | Fox-Tim | Satish Polubothu | Satish, Shabeer
| No |  |  |  | lrsinvoicebatch (Cap doing Log4J ONLY) | HR Systems |  | 1.1 (Cap)Log4j |  | Dec 2023 | Jan 2024 | Small |  | 0 | David Kost | Fox-Tim | Satish Polubothu | Satish, Shabeer
| No |  |  |  | lrsmiscbatch (Cap doing Log4J ONLY) | HR Systems |  | 1.2 (AO)Log4i Review |  | Dec 2023 | Jan 2024 | Small | 2023-11-10 | 1.2 | David Kost | Fox-Tim | Satish Polubothu | Satish, Shabeer | [16 empty] | 2023-11-10
| No |  |  |  | lrspaymentbatch (Cap doing Log4J ONLY) | HR Systems |  | 1.2 (AO)Log4i Review |  | Dec 2023 | Jan 2024 | Small | 2023-11-08 | 1.6 | David Kost | Fox-Tim | Satish Polubothu | Satish, Shabeer | [16 empty] | 2023-11-08
| No |  |  |  | lrsratechangebatch (Cap doing Log4J ONLY) | HR Systems |  | 1.2 (AO)Log4i Review |  | Dec 2023 | Jan 2024 | Small | 2023-11-10 | 1.2 | David Kost | Fox-Tim | Satish Polubothu | Satish, Shabeer | [16 empty] | 2023-11-10
| No |  |  |  | lrsservice.war (Cap doing Log4J ONLY) | HR Systems |  | 1.1 (Cap)Log4j |  | Dec 2023 | Jan 2024 | Small |  | 0 | David Kost | Fox-Tim | Satish Polubothu | Satish, Shabeer
| No |  |  |  | lrstimesynchbatch (Cap doing Log4J ONLY) | HR Systems |  | 1.1 (Cap)Log4j |  | Dec 2023 | Jan 2024 | Small |  | 0 | David Kost | Fox-Tim | Satish Polubothu | Satish, Shabeer
| Yes | No |  |  | bos.war | HR Systems | TRUE | 4.1 (Cap)Maven | Green | Nov 2023 | Jan 2024 | Medium | 2023-11-02 | 2.8 | David Kost | Tim Fox | Satish Polubothu | Satish, Shabeer |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | BOS - Breach of Security | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  | 2023-03-09 |  | 2023-11-02
| Yes | No |  |  | cds.war | HR Systems | TRUE | 4.2 (AO)Maven | Green | Nov 2023 | Jan 2024 | Medium | 2023-11-07 | 1.8 | David Kost | Tim Fox | Satish Polubothu | Satish, Shabeer |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | CDS E-Learning | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  | 2023-03-09 |  | 2023-11-07
| Yes | No |  |  | itcontact.war | HR Systems | TRUE | 4.2 (AO)Maven | Yellow | Dec 2023 | Jan 2024 | Large | 2023-10-30 | 3.4 | David Kost | Tim Fox | Satish Polubothu | Satish, Shabeer |  |  | Needed |  | Yes | Needed | Needed | Needed | IT Contact Information | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 |  |  |  | 2023-03-09 |  | 2023-10-30
| Yes | No |  |  | pcc | HR Systems | TRUE | 4.2 (AO)Maven | Yellow | Dec 2023 | Jan 2024 | Large | 2023-11-14 | 0.4 | David Kost | Tim Fox | Satish Polubothu | Satish, Shabeer |  |  | Needed |  | Yes | Needed | Needed | Needed | PC2- Penske Change Control Batch App | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-08-14 |  |  | 2023-10-03 |  | 2023-11-14
| Yes | No |  |  | pcc.war | HR Systems | TRUE | 4.2 (AO)Maven | Yellow | Dec 2023 | Jan 2024 | Large | 2023-11-14 | 0.4 | David Kost | Tim Fox | Satish Polubothu | Satish, Shabeer |  |  | Needed |  | Yes | Needed | Needed | Needed | PCÂ² - Penske Change Control | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-08-14 |  |  | 2023-10-03 |  | 2023-11-14
| No |  |  |  | captchaservice.war | Customer Digital Engineer (eBusiness) | TRUE | 6.1 (Cap/AO)Dev Deploy/Test | Green |  | Jan 2024 |  | 2023-10-04 | 8.6 | Michael Hintenach | Gopal-Sree | Joseph-Brian | Brian | [13 empty] | 2023-11-16 | [5 empty] | 2023-10-04
| Yes | No |  |  | iseriessavvionwebserviceclient | Savvion |  | Retire App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Peter MacMahon | Peter MacMahon | Peter | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-03-24
| Yes | No |  |  | sem.war (aka Security Exception Maintenance) | Security |  | Retire App | Green | Done | Done | Done |  | 0 | Scott Bortzel | Scott Bortzel <scott.bortzel@penske.com> | [10 empty] | Security Exception Maintenance | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-03-24
| Yes | No |  |  | fmea.war | Web Services | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-08-18 | 18 | Gary Galyas | Gary Galyas | Gary Galyas | [9 empty] | FMEA | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-06-12 |  |  | 2023-06-01 |  | 2023-08-18
| Yes | No |  |  | cyclops.war | Web Services |  | Retire App | Green | Done | Done | Done |  | 0 | Scott Pemrick | Scott Bortzel | Scott Pemrick | Scott Pemrick | [8 empty] | 3rd Party SSO Utility | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-03-24
| Yes | No |  |  | smvendors | Web Services |  | Retire App | Green | Done | Done | Done |  | 0 | Scott Pemrick | Scott Bortzel | Scott Pemrick | Scott Pemrick | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-11-16 | 2023-03-24
| No |  |  |  | football.war | Maintenance | TRUE | 4.2 (AO)Maven | Green | Sept 2023 | Dec 2023 | Medium | 2023-11-01 | 3 | David Kost | George-Stella | Obst-Gregg | Gregg, Vaddi Mani | [13 empty] | 2023-11-16 | 2023-08-14 |  |  | 2023-06-01 |  | 2023-11-01
| No |  |  |  | smsservice.war | Maintenance | TRUE | 4.2 (AO)Maven | Yellow |  | Jan 2024 | Small | 2023-10-31 | 3.2 | David Kost | McMurtry-Shawn | McMurtry-Shawn | Shawn | [13 empty] | 2023-11-16 | 2023-07-30 |  |  | 2023-09-13 |  | 2023-10-31
| No |  |  |  | unitjkt.war | Maintenance | TRUE | DONE - (AO)App Deployed | Green | Oct 2023 | Dec 2023 | Large | 2023-11-15 | 0.2 | David Kost | Patel-Falgun | Long-David, Mikos - Kenneth | David, Mikos, Patel | [13 empty] | 2023-11-16 | 2023-08-14 |  |  | 2023-07-03 |  | 2023-10-31 | 2023-11-07 | 2023-11-09 | 2023-11-15
| No |  |  |  | partspo | Maintenance |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-09-12 | 13 | David Kost | George-Stella | Karthik | Karthikeyan, Vaddi Mani | [13 empty] | 2023-11-16 |  |  |  | 2023-06-01 |  | 2023-06-29 |  | 2023-09-06 | 2023-09-12
| No |  | spellingservice.war |  | penske_spelling_Client | Maintenance |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-22 | 17.2 | David Kost | George-Stella | Mani-Sarath | Dale Porter | [13 empty] | 2023-11-16 | 2023-07-05 |  |  |  |  | 2023-07-26 | 2023-08-02 |  | 2023-08-22
| No |  | spellingservice.war depends on this utility. |  | penske_spellingutility.jar | Maintenance |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-24 | 16.8 | David Kost | George-Stella | Mani-Sarath | Dale Porter, Vaddi Mani | [13 empty] | 2023-11-16 | [5 empty] | 2023-06-23 | 2023-07-11 |  | 2023-08-24
| No |  | Servicereqsvc,war, edvir.war, servicereqbatch, servicereqweb, webmileagesvc.war and unitjkt.war are depends on this utility |  | serviceRequestUtility.jar | Maintenance |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-09-06 | 14.2 | David Kost | George-Stella | Vennimalayan-Subramanian | Stella george, Subramanian | [13 empty] | 2023-11-16 |  |  |  | 2023-06-27 |  | 2023-07-06 | 2023-09-01 |  | 2023-09-06
| No |  |  |  | smsserviceutility | Maintenance |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-09-06 | 14.2 | David Kost | George-Stella | Shawn Mcmurtry | Shawn | [19 empty] | 2023-08-30 |  |  | 2023-09-06
| No |  | sosservice,sos.war,24x7custnotif depend on this utlity. |  | sosutility | Maintenance |  | DONE - (AO)App Deployed | Green | Done | Sept 2023 | Small | 2023-08-24 | 16.8 | David Kost | Patel-Falgun | Long-David, Patel-Falgun | David, Patel, Sreenivasa | [13 empty] | 2023-11-16 | [5 empty] | 2023-06-27 | 2023-07-12 |  | 2023-08-24
| No |  | vehicleinfosvc,football.war depend on this utility. |  | vehicleInformationUtility.jar | Maintenance |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-28 | 16 | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-11-16 | [5 empty] | 2023-06-23 | 2023-07-10 |  | 2023-08-28
| No |  |  |  | vendordvir | Maintenance |  | DONE - (AO)App Deployed | Green | Done | Sept 2023 | Small | 2023-10-09 | 7.6 | David Kost | George-Stella | Long-David, Ganguli-Payel | David, Ganguly, Vaddi Mani | [13 empty] | 2023-11-16 |  |  |  | 2023-06-14 |  | 2023-07-21 | 2023-08-17 | 2023-08-23 | 2023-10-09
| No |  |  |  | virtualpay.war | Maintenance |  | DONE - (AO)App Deployed | Green | Done | Oct 2023 | Medium | 2023-10-03 | 8.8 | David Kost | Patel-Falgun | Long-David | David, Patel | [13 empty] | 2023-11-16 | 2023-05-24 |  |  | 2023-06-14 |  | 2023-07-06 |  |  | 2023-10-03
| No |  |  |  | 24x7custnotif | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Oct 2023 | Nov 2023 | XL | 2023-10-13 | 6.8 | David Kost | Patel-Falgun | Long-David, Patel-Falgun | David, Mikos, Patel | [13 empty] | 2023-11-16 | 2023-09-06 |  |  |  |  | 2023-09-18 | 2023-09-26 | 2023-10-13
| No |  |  |  | bodyshop.war | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Nov 2023 | Large | 2023-10-10 | 7.4 | David Kost | Patel-Falgun | Vennimalayan-Subramanian, Patel-Falgun,Papannagari-Sreenivasa | Patel, Sreenivasa, Subramanian | [13 empty] | 2023-11-16 | 2023-05-10 |  |  |  |  | 2023-09-21 | 2023-09-25 | 2023-10-10
| No |  |  |  | digitech.war | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green |  |  |  | 2023-10-05 | 8.4 |  | George-Stella | Obst Gregg | [14 empty] | 2023-11-16 | 2023-08-14 |  |  | 2023-06-01 |  | 2023-09-07 | 2023-09-25 | 2023-10-05
| No |  |  |  | openrepairsumm | Maintenance |  | DONE - (AO)App Deployed | Green | Sept 2023 | Nov 2023 | Medium | 2023-11-09 | 1.4 | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-11-16 | 2023-05-31 |  |  |  |  | 2023-07-16 | 2023-07-19 | 2023-09-01 | 2023-11-09
| No |  |  |  | pmmailer | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Nov 2023 | XL | 2023-10-13 | 6.8 | David Kost | Patel-Falgun | Kenneth Mikos | Mikos | [13 empty] | 2023-11-16 | 2023-09-06 |  |  | 2023-06-01 |  | 2023-09-15 | 2023-09-26 | 2023-10-13
| No |  |  |  | servicenetbatch | Maintenance |  | DONE - (AO)App Deployed | Green | Done | Oct 2023 | Medium | 2023-10-31 | 3.2 | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-11-16 | 2023-06-20 |  |  | 2023-06-14 |  | 2023-07-27 |  | 2023-08-11 | 2023-10-31
| No |  |  |  | sos.war | Maintenance |  | DONE - (AO)App Deployed | Green | Done | Oct 2023 | XL | 2023-11-03 | 2.6 | David Kost | Patel-Falgun | Papannagari-Sreenivasa, George-Stella | Patel, Sreenivasa | [13 empty] | 2023-11-16 | 2023-08-14 |  |  | 2023-06-01 |  | 2023-09-18 |  | 2023-09-25 | 2023-11-03
| No |  |  |  | sospcard.war | Maintenance |  | DONE - (AO)App Deployed | Green | Done | Oct 2023 | XL | 2023-11-03 | 2.6 | David Kost | Patel-Falgun | Papannagari-Sreenivasa, George-Stella | Patel, Sreenivasa | [13 empty] | 2023-11-16 | 2023-09-06 |  |  | 2023-06-14 |  | 2023-09-20 | 2023-10-02 | 2023-10-25 | 2023-11-03
| No |  | sosutility.jar |  | sosservice.war | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Done | Nov 2023 | Medium | 2023-08-23 | 17 | David Kost | Patel-Falgun | Long-David | David, Patel | [13 empty] | 2023-11-16 | 2023-05-10 |  |  | 2023-07-17 |  | 2023-08-08 | 2023-08-17 | 2023-08-23
| No |  |  |  | voicepmsvc.war | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Dec 2023 | Medium | 2023-09-26 | 10.2 | David Kost | George-Stella | Mani-Sarath | Vaddi Mani | [13 empty] | 2023-11-16 |  |  |  | 2023-06-14 |  | 2023-07-20 |  | 2023-09-26
| No |  |  |  | edvir.war | Maintenance | TRUE | 5.1 (Cap)Bamboo | Green | Sept 2023 | Dec 2023 | Medium | 2023-10-26 | 4.2 | David Kost | George-Stella | Payel | Stella george, Vaddi Mani | [13 empty] | 2023-11-16 | 2023-05-17 |  |  | 2023-06-27 |  | 2023-10-26
| No |  |  |  | servicereqbatch | Maintenance | TRUE | 4.2 (AO)Maven | Green | Sept 2023 | Dec 2023 | Medium | 2023-10-22 | 5 | David Kost | George-Stella | Vennimalayan-Subramanian | Subramanian, Vaddi Mani | [13 empty] | 2023-11-16 | 2023-05-17 |  |  | 2023-08-04 |  | 2023-10-22
| No |  | serviceRequestUtility.jar |  | servicereqsvc.war | Maintenance | TRUE | 4.2 (AO)Maven | Green | Sept 2023 | Dec 2023 | Medium | 2023-09-20 | 11.4 | David Kost | George-Stella | Vennimalayan-Subramanian | Subramanian, Vaddi Mani | [13 empty] | 2023-11-16 | 2023-05-31 |  |  | 2023-09-13 |  | 2023-09-20
| No |  |  |  | smsbatch | Maintenance | TRUE | 4.2 (AO)Maven | Yellow |  | Jan 2024 | Small | 2023-11-06 | 2 | David Kost | McMurtry-Shawn | McMurtry-Shawn | Shawn | [13 empty] | 2023-11-16 | 2023-07-30 |  |  | 2023-09-13 |  | 2023-11-06
| No |  | penske_spelling_Client |  | spellingservice.war | Maintenance | TRUE | 4.2 (AO)Maven | Green | Sept 2023 | Dec 2023 | Medium | 2023-10-17 | 6 | David Kost | George-Stella | Mani-Sarath | Dale Porter, Vaddi Mani | [13 empty] | 2023-11-16 | 2023-06-20 |  |  | 2023-07-21 |  | 2023-10-17
| No |  |  |  | usermaint.war | Maintenance |  | 4.1 (Cap)Maven | Yellow | Sept 2023 | Dec 2023 | Medium | 2023-10-20 | 5.4 | David Kost | George-Stella | Srinivasan-Karthikeyan | Karthikeyan, Vaddi Mani | [13 empty] | 2023-11-16 | 2023-08-14 |  |  | 2023-09-13 |  | 2023-10-20
| No |  |  |  | vehicleinfosvc.war | Maintenance | TRUE | 4.2 (AO)Maven | Green | Sept 2023 | Nov 2023 | Medium | 2023-10-26 | 4.2 | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-11-16 | 2023-07-11 |  |  | 2023-07-25 |  | 2023-10-26
| No |  |  |  | cns.war | Maintenance |  | Retire App | Green | Done | Done | Done | 2023-07-18 | 24.2 | David Kost | McMurtry-Shawn | McMurtry-Shawn | Shawn | [13 empty] | 2023-11-16 | 2023-08-14 |  |  | 2023-06-14
| No |  |  |  | etimeservice.war | Maintenance |  | DONE - (AO)App Deployed | Green | Sept 2023 | Nov 2023 | Medium | 2023-11-15 | 0.2 | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-11-16 |  |  |  | 2023-06-01 |  | 2023-06-23 |  |  | 2023-11-15
| No |  |  |  | maintconfig.war | Maintenance | TRUE | DONE - (AO)App Deployed | Green | Done | Nov 2023 | XL | 2023-11-03 | 2.6 | David Kost | Patel-Falgun | Mani-Sarath, Patel-Falgun | Mikos, Patel, Vaddi Mani | [13 empty] | 2023-11-16 | 2023-09-06 |  |  | 2023-06-27 |  | 2023-10-11 |  |  | 2023-11-03
| No |  |  |  | phonesvc.war | Maintenance |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Sept 2023 | Nov 2023 | Medium |  | 0 | David Kost | Patel-Falgun | Long-David, Patel-Falgun | David, Patel | [13 empty] | 2023-11-16 |  |  |  | 2023-06-01 |  | 2023-07-11
| No |  |  |  | pmscheduling.war | Maintenance |  | DONE - (AO)App Deployed | Green | Oct 2023 | Nov 2023 | XL | 2023-11-15 | 0.2 | David Kost | Patel-Falgun | McMurtry-Shawn, Patel-Falgun | Mikos, Patel, Shawn | [13 empty] | 2023-11-16 |  |  |  | 2023-06-14 |  | 2023-08-16 |  |  | 2023-11-15
| No |  |  |  | rsareviewloop.war | Maintenance | TRUE | 6.1 (Cap/AO)Dev Deploy/Test | Green | Sept 2023 | Nov 2023 | Medium | 2023-09-22 | 11 | David Kost | Patel-Falgun | Long-David, Patel-Falgun | David, Patel | [13 empty] | 2023-11-16 |  |  |  | 2023-06-27 |  | 2023-09-22
| No |  |  |  | servicereqweb.war | Maintenance |  | 6.1 (Cap/AO)Dev Deploy/Test | Yellow | Sept 2023 | Dec 2023 | Medium | 2023-09-20 | 11.4 | David Kost | George-Stella | Vennimalayan-Subramanian | Subramanian, Vaddi Mani | [13 empty] | 2023-11-16 | 2023-08-14 |  |  | 2023-09-13 |  | 2023-09-20
| No |  |  |  | cmns.war | Maintenance |  | Dup App | Green | Done | Done | Done |  | 0 | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-11-16 | 2023-05-09
| No |  |  |  | peoplenetbatch | Maintenance |  | Dup App | Green | Oct 2023 | Oct 2023 | Medium | 2023-07-19 | 24 | David Kost | George-Stella | Payel | Ganguly, Stella george, Vaddi Mani | [13 empty] | 2023-11-16 |  |  |  | 2023-06-01 |  | 2023-07-19

## Comments
Row 2 | Deployed app to PROD on 08/08/2023 | Sreekanth | 08/16/23 7:52 PM
| @sreekanth.kancharla@penske.com , Thanks for the update. | Gayam | 08/18/23 1:01 AM
Row 2 | Ready to be tested in QA. | Sreekanth | 07/05/23 7:35 PM
| @sreekanth.kancharla@penske.com , QA deployment needs to complete by AO only. Please deploy and test. Thanks. | Gayam | 07/06/23 3:16 AM
Row 2 | @sreekanth.kancharla@penske.com : this app is deployed to dev. https://bamboo.penske.com/browse/ACH-ACHW/deployments | Gayam | 04/13/23 11:43 PM
Row 2 | @james.minisce@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @sreekanth.kancharla@penske.com | Gayam | 01/24/23 10:19 AM
| @praneeth.gayam@penske.com No remediations required for the shared secrets as all are valid. CC: @james.minisce@penske.com | Sreekanth | 01/26/23 1:29 AM
| Thanks @sreekanth.kancharla@penske.com. Changing back to (AO)Maven status. Please review the MR when you get a chance. MR provide above. | Gayam | 01/26/23 2:03 AM
| @praneeth.gayam@penske.com The PR is not yet merged. I've added comments. Please provide clarification. https://bitbucket.penske.com/projects/ITFIS/repos/ach-web/pull-requests/3/overview | Sreekanth | 02/16/23 8:46 PM
| @sreekanth.kancharla@penske.com , I have responnded in the PR. Please check. | Gayam | 02/17/23 1:22 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 03/24/23 5:50 PM
| Thanks @sreekanth.kancharla@penske.com . We will let you know once onboarding to Bamboo and deploymnet to Dev completed. | Gayam | 03/24/23 11:06 PM
| @sreekanth.kancharla@penske.com , this app is onboarded to Bamboo. But the build was failing. For that reason we had to change version of one dependency. Could you please approve and merge the below PR for this change. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/ach-web/pull-requests/5/overview | Gayam | 03/30/23 11:29 PM
| @praneeth.gayam@penske.com The latest PR was merged on 03/30/2023 | Sreekanth | 04/12/23 7:18 AM
Row 2 | @rafiq.melath@penske.com / @james.minisce@penske.com / @sreekanth.kancharla@penske.com , Log4j, Mavne changes are completed for this app. Please review in the below PR and merge. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/ach-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/13/22 2:58 AM
| @praneeth.gayam@penske.com I've added comment to PR. Please check and reply back to take further action. @mathumala.nachiappan@penske.com @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 3:00 AM
Row 2 | @praneeth.gayam@penske.com What is the plan once the changes are reviewed and merged ? Hope we may've to have a new Bamboo plan with latest CICD approach to deploy this app in DEV/QA for testing. | Sreekanth | 12/20/22 4:33 AM
| Yes @sreekanth.kancharla@penske.com . We will build and deploy the application to dev/qa with the new build plan. | Gayam | 12/20/22 4:54 AM
Row 3 | @sreekanth.kancharla@penske.com , Thanks for the update. | Gayam | 08/18/23 1:01 AM
Row 3 | Deployed app to PROD on 08/08/2023 | Sreekanth | 08/16/23 7:53 PM
Row 3 | Ready to be tested in QA. | Sreekanth | 07/05/23 7:35 PM
| @sreekanth.kancharla@penske.com , QA deployment needs to complete by AO only. Please deploy and test. Thanks. | Gayam | 07/06/23 3:16 AM
Row 3 | @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: achbatch-deploy New deployment project name: ach-batch-deploy Thank you. | Gayam | 05/14/23 9:15 PM
| @praneeth.gayam@penske.com Perfect! Thank you! | Sreekanth | 05/24/23 9:07 PM
Row 3 | @sreekanth.kancharla@penske.com , This app is onboarded to bamboo. Please deploy to QA and test. Thanks. https://bamboo.penske.com/browse/ACH-ACHBAP1/deployments | Gayam | 03/30/23 12:40 AM
Row 3 | @rafiq.melath@penske.com / @james.minisce@penske.com / @sreekanth.kancharla@penske.com , We have completed the secrets scanning on this application and found that there is 1 true positive and all others are false positives. I will share the excel report in the email. Could you please check and remediate the secrets. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/06/23 1:01 AM
| @sreekanth.kancharla@penske.com , Is there a standard process/practice already in place to remediate these finding(s)? | James | 01/06/23 2:06 AM
| @praneeth.gayam@penske.com No remediation is required for all False positives as those are Connection Framework setup related files as per the Penske standard. The 1 True positive seems in offshore branch only and not in DEV/QA/Trunk branches. We are not sure whether offshore branch has latest code. To make any changes, we always refer the trunk branch and then either create a new branch from trunk (OR) work with DEV branch if the source is in sync with Trunk branch. With this, hope we don't need to make any remediation for the shared secrets. Please let us know in case any further clarifications required. CC: @mathumala.nachiappan@penske.com @james.minisce@penske.com | Sreekanth | 01/06/23 2:41 AM
| Thanks @sreekanth.kancharla@penske.com . We will do the next step which is Mavanizing the application. @james.minisce@penske.com | Gayam | 01/07/23 12:50 AM
| @sreekanth.kancharla@penske.com , As discussed PR is already merged to develop branch. Could you please check and provide your approval for the Bamboo stage. | Gayam | 03/02/23 2:49 AM
| @praneeth.gayam@penske.com Please proceed with further steps. @james.minisce@penske.com | Sreekanth | 03/04/23 2:54 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to Cap Bamboo | Gayam | 03/07/23 12:19 AM
Row 4 | @sreekanth.kancharla@penske.com , Thanks for the update. | Gayam | 08/18/23 1:01 AM
Row 4 | Deployed app to PROD on 08/08/2023 | Sreekanth | 08/16/23 7:53 PM
Row 4 | Ready to be tested in QA. | Sreekanth | 07/05/23 7:35 PM
| @sreekanth.kancharla@penske.com , QA deployment needs to complete by AO only. Please deploy and test. Thanks. | Gayam | 07/06/23 3:16 AM
| @praneeth.gayam@penske.com Yes. Just updated the status for information. | Sreekanth | 07/06/23 7:50 PM
Row 4 | @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: achsvc-deploy New deployment project name: ach-service-deploy Thank you. | Gayam | 05/14/23 9:15 PM
| @praneeth.gayam@penske.com Thank you! | Sreekanth | 05/24/23 9:07 PM
Row 4 | @sreekanth.kancharla@penske.com , Dev deployment of this app is completed. Please check. Thank you. | Gayam | 03/23/23 11:45 PM
Row 4 | @james.minisce@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @sreekanth.kancharla@penske.com | Gayam | 01/24/23 10:20 AM
| @praneeth.gayam@penske.com No remediations required for the shared secrets as all are valid. CC: @james.minisce@penske.com | Sreekanth | 01/26/23 1:30 AM
| Thanks @sreekanth.kancharla@penske.com. Changing back to (AO)Maven status. Please review the MR when you get a chance. MR provide above. | Gayam | 01/26/23 2:05 AM
| @praneeth.gayam@penske.com - Still i see the status is (Cap) Bamboo.. Missing anything here? And is that PR? | Mathumala Nachiappan | 01/27/23 10:51 AM
| @mathumala.nachiappan@penske.com , Sreekanth already merged the code and provided the update above. I changed the status to Cap Bamboo. Please check | Gayam | 01/27/23 7:30 PM
Row 4 | @rafiq.melath@penske.com / @james.minisce@penske.com / @sreekanth.kancharla@penske.com , Log4j team completed log4j and maven changes. Please review them in below PR and merge. https://bitbucket.penske.com/projects/ITFIS/repos/ach-service/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/09/22 6:48 AM
| @sreekanth.kancharla@penske.com Please review the log4j changes in the link above and merge if there are no issues. Thank you. | James | 12/09/22 5:54 PM
| @praneeth.gayam@penske.com PR is merged. @mathumala.nachiappan@penske.com @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 3:12 AM
| Thanks @sreekanth.kancharla@penske.com . We will create the Bamboo for this and will deploy to Dev and let you know. Please confirm whether you are ok for Dev deployment. Thanks. Changed the status to (AO)Bamboo. | Gayam | 01/26/23 8:59 PM
Row 5 | Thanks for the update @sreekanth.kancharla@penske.com | Gayam | 08/30/23 10:39 PM
Row 5 | App deployed in PROD on 08/29/2023 | Sreekanth | 08/30/23 6:23 PM
Row 5 | @sreekanth.kancharla@penske.com , Onboarded to bamboo and dev deployment is done with develop branch. Please verify. Thanks. https://bamboo.penske.com/browse/CMSP-CMSPLP0/deployments | Gayam | 07/25/23 12:03 AM
Row 5 | @sreekanth.kancharla@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ITFIS/repos/cmsplus-web/pull-requests/3/overview | Gayam | 07/20/23 12:38 AM
| @praneeth.gayam@penske.com PR is merged. Please proceed with bamboo configuration. | Sreekanth | 07/20/23 7:16 PM
| Sure @sreekanth.kancharla@penske.com | Gayam | 07/20/23 10:51 PM
Row 5 | @praneeth.gayam@penske.com Please let me know in case any update on this application. | Sreekanth | 07/07/23 8:26 PM
Row 5 | Hugo suggests grabbing the prod jar and reuse in artifactory since Prod is the most current jar. Assigned to Kalrav | Yvette Urso | 05/12/23 12:54 AM
| @yvette.urso@penske.com / @praneeth.gayam@penske.com Please take the "dassupport.jar" & "iasservice-client.jar" from SVN location. https://svn.penske.com/svn/webprojects/admin/cmsplus/trunk/CMSplusPhaseIII/WebContent/WEB-INF/lib We are not using "IAS_Agent.jar" in CMSPlus application and not sure where we can get this jar. | Sreekanth | 06/08/23 11:21 PM
| @sreekanth.kancharla@penske.com , We required iasservice-client.jar and IAS_Agent.jar for this app. It doesn't require dassupport.jar. Without IAS_Agent.jar application is giving compilation issues and the jar exist at https://svn.penske.com/svn/webprojects/admin/cmsplus/trunk/CMSplusPhaseIII/targeted/prod/ Could you please check and provide your approval to upload the jar. | Gayam | 06/10/23 2:22 AM
| @praneeth.gayam@penske.com Yes, we can use the IAS_Agent.jar from the trunk branch. | Sreekanth | 06/13/23 2:13 AM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 06/13/23 2:29 AM
Row 5 | @dylan.price@penske.com confirmed that we can upload the 'iasservice-client.jar' to artifactory. This app depends on IAS_Agent.jar and dassupport.jar also. So could you please let us know whether we can upload these jars into artifactory. | Gayam | 04/03/23 2:47 AM
Row 5 | Thanks @yvette.urso@penske.com . @mark.weaver@penske.com - Pls. have a look on the previous discussions and confirm your approval to upload to artifactory. Suggested Artifactory details as per the package information iasservice-client.jar --------------------- Group ID - com.penske.ias.services Artifact ID - iasservice-client Version - Default IAS_Agent.jar --------------------- Group ID - com.penske.invoice Artifact ID - IAS_Agent Version - Default CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 3:31 PM
| @mark.weaver@penske.com , Could you please respond to above query. Thanks. | Gayam | 03/09/23 2:01 AM
Row 5 | This is blocked by Billing Team. Kalrav sent Rafiq the question on which Jar is needed for this Application. | Yvette Urso | 02/16/23 12:11 AM
Row 5 | @kalrav.khamar@penske.com - Hi Kalrav..Any update on this | Mathumala Nachiappan | 12/01/22 9:03 PM
| @mathumala.nachiappan@penske.com I'm working with Sreekanth.Kancharla@penske.com. He will contact you and after that will update here. | Kalrav | 12/01/22 9:21 PM
| @mathumala.nachiappan@penske.com IAS_Agent.jar and iasservice-client.jar both are provided by invoice archive systems. @mark.weaver@penske.com is application owner and he should be able to provide more details about these jar files. | Kalrav | 12/01/22 9:44 PM
| @mark.weaver@penske.com Can you update IAS_Agent.jar and iasservice-client.jar? It's been waiting for your response since long time. | Kalrav | 02/13/23 9:01 PM
Row 5 | @mathumala.nachiappan@penske.com moving to the appropriate status to assign to AO for review. I chose AO Maven. | Yvette Urso | 12/15/22 2:08 AM
| @yvette.urso@penske.com - This is not review from App Owner. This is a dependency on the approval to proceed to upload to Artifactory. For Action - @mark.weaver@penske.com . CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/15/22 10:11 AM
Row 5 | @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com @mark.weaver@penske.com - Reassigned this application from Kalrav to Mark per Kalrav response. Thank you | Yvette Urso | 12/02/22 2:13 AM
Row 5 | @rafiq.melath@penske.com / @kalrav.khamar@penske.com , cmsplus.war has a dependency on IAS_Agent.jar and iasservice-client.jar. But these jars are not available in artifactory and unable to find source code of these jars in SVN/BitBucket. Can we upload these jars into artifactory? FYI: @mathumala.nachiappan@penske.com | Gayam | 11/23/22 10:29 PM
Row 6 | App deployed to PROD on 08/22/2023 | Sreekanth | 08/23/23 7:33 PM
Row 6 | @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: ecm-deploy New deployment project name: ecm-web-deploy Thank you. | Gayam | 05/14/23 9:34 PM
Row 6 | @sreekanth.kancharla@penske.com , This app is deployed to Dev. Please verify. Thanks. | Gayam | 03/30/23 12:47 AM
| @praneeth.gayam@penske.com We are waiting on resolution from @hugo.scavino@penske.com for issues we are facing in all web based applications related to SessionValidationFilter. Please change the status. @kalrav.khamar@penske.com | Sreekanth | 03/30/23 10:49 PM
| @sreekanth.kancharla@penske.com , There is no status to represent this. I think we can keep the Dev Deploy status as this is waiting from AO side. Please correct it if you have any other thoughts. | Gayam | 03/30/23 11:10 PM
Row 6 | @sreekanth.kancharla@penske.com , Also log4j/maven changes are completed. Please review them in the below MR. https://bitbucket.penske.com/projects/ITFIS/repos/ecm-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/09/22 2:57 AM
| @praneeth.gayam@penske.com I took a glance of the code & the file you shared. All the href links seems the request URLs (which we use to maintain usually in java script) & CSS file references. I don’t see any secrets in them. Hope we can leave them as it is. | Sreekanth | 12/09/22 8:17 PM
| Thanks @sreekanth.kancharla@penske.com . In that case please review the log4j,maven changes in the below MR and merge please. https://bitbucket.penske.com/projects/ITFIS/repos/ecm-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/10/22 12:42 AM
| @praneeth.gayam@penske.com The PR is merged. Please proceed with next steps. @mathumala.nachiappan@penske.com @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/04/23 3:44 AM
Row 6 | @james.minisce@penske.com - PR is raised for this app for your review and signoff to proceed for Dev deployment. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:04 PM
| Where do I review? | James | 12/01/22 9:08 PM
| @james.minisce@penske.com , Please review in the following PR and merge. https://bitbucket.penske.com/projects/ITFIS/repos/ecm-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/07/22 11:00 PM
| @sreekanth.kancharla@penske.com Can you please review and merge as per the above? Thank you. | James | 12/08/22 6:16 PM
| @praneeth.gayam@penske.com I've added comment to PR. Please check and reply back to take further action. @mathumala.nachiappan@penske.com @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 2:58 AM
| @sreekanth.kancharla@penske.com , I think you are referring to securityfilter in web.xml is different for diff regions and keeping those in targeted folder. But @hugo.scavino@penske.com suggested not to keep targeted folder and he is working on workaround to resolve this issue. Could you please check with @hugo.scavino@penske.com on this. Thanks. @mathumala.nachiappan@penske.com @yvette.urso@penske.com | Gayam | 01/27/23 10:08 PM
| Had discussion with @hugo.scavino@penske.com and came to know that Dlinkfilter is going to take care of everything. Once we get a working project and instructions on implementation, we'll implement the same in all the web applications wherever the filters are handled either with targeted folder or with java filters. @kalrav.khamar@penske.com | Sreekanth | 02/03/23 3:19 AM
Row 6 | Thanks @sreekanth.kancharla@penske.com for the updates on secrets part. I have changed the secret status as 'Not Needed'. This is FYI. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/12/22 4:28 PM
Row 6 | @sreekanth.kancharla@penske.com - In secret scanning process, Many hardcoded href links are found. Pls. check and confirm whether they need redaction. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 7:02 PM
| @mathumala.nachiappan@penske.com This is a very old application and we've no project to migrate this application. So we've to move forward with the hardcoded href links. Please advice incase this is a stopper for Log4j migration. | Sreekanth | 12/09/22 12:15 AM
| @sreekanth.kancharla@penske.com , We can share the secrets file to you with all the hardcoded links. Please check and let us know whether those are false positives. @mathumala.nachiappan@penske.com | Gayam | 12/09/22 2:32 AM
Row 7 | App deployed to PROD on 08/20/2023 as part of Project Neo deployment. | Sreekanth | 08/21/23 7:08 PM
Row 7 | Review: @sreekanth.kancharla@penske.com , This is ready for your review. Please verify. https://bitbucket.penske.com/projects/ITFIS/repos/employee-master-batch/pull-requests/4/overview | Gayam | 06/28/23 2:47 AM
| @praneeth.gayam@penske.com I'm not sure why the PR is created to a feature branch. By mistake offshore lead merged that but I didn't want that to be merged as we've not tested log4j2 changes in QA & there is some Oracle cloud migration testing going. I couldn't revert the merged commit. I may need to manually revert the changes. | Sreekanth | 06/28/23 7:11 PM
| @sreekanth.kancharla@penske.com , I think there is a confusion whether to merge to develop branch or to the branch which contains recent commits. Do you want us to raise the PR from develop_log4j to develop branch? | Gayam | 06/29/23 2:21 AM
| @praneeth.gayam@penske.com Yes. The PRs should be always to develop branch. | Sreekanth | 06/29/23 8:46 PM
| @sreekanth.kancharla@penske.com , Raised PR to develop branch. Please check. https://bitbucket.penske.com/projects/ITFIS/repos/employee-master-batch/pull-requests/5/overview | Gayam | 06/30/23 12:35 AM
Row 7 | @sreekanth.kancharla@penske.com , we are seeing that you already worked on this app and mavanized. Do you want log4j team to work on it anything or please close the status of this app. @yvette.urso@penske.com / @shane.myers@penske.com | Gayam | 06/07/23 3:02 AM
| @praneeth.gayam@penske.com Yes, this app is already mavenized. If your team could work on Log4j migration changes, then we can test this app. | Sreekanth | 06/08/23 8:02 PM
| Sure @sreekanth.kancharla@penske.com | Gayam | 06/09/23 1:35 AM
Row 8 | This application was deployed to PROD on 07/25/2023. | Sreekanth | 07/27/23 7:24 PM
Row 8 | @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: eram-deploy New deployment project name: eram-web-deploy Thank you. | Gayam | 05/14/23 9:36 PM
Row 8 | @sreekanth.kancharla@penske.com , app is onboarded to Bamboo. https://bamboo.penske.com/browse/EBP-ERAMW/ Please let us know whether we can deploy to dev. | Gayam | 03/10/23 11:23 PM
| @praneeth.gayam@penske.com Please proceed with DEV deployment. We don't have access to add "Plan branch" for any future builds. Please provide access on all the new admin projects. | Sreekanth | 03/13/23 10:17 PM
| Hi @sreekanth.kancharla@penske.com , Deployed the code to dev. Please verify. Also, to add a plan branch you need to be part of RBAC group PTL-Admin-Production. I believe currently you are not part of it. | Gayam | 03/15/23 11:43 PM
| @praneeth.gayam@penske.com We need the access to add the plan branch if they are not automatically being created in Bamboo as we'll be deploying whatever the branch we wanted to test. Please do the need. Schedule a meeting with architect team if needed. | Sreekanth | 03/16/23 12:28 AM
| @sreekanth.kancharla@penske.com , I will send an email to add the people to 'PTL-Admin-Production' RBAC group. Could you please give us the list of people whom you want to add to that group. Once you added to that gorup you will also have permission to deploy to production. | Gayam | 03/16/23 2:29 AM
| @praneeth.gayam@penske.com Developers also need access to add Plan branch in some cases but they shouldn't have PROD deployment access. Please consider this scenario and let us know how this can be handled | Sreekanth | 03/16/23 7:51 PM
Row 8 | Maven Review: @sreekanth.kancharla@penske.com , We ahve completed the modernization on this app. Please review and confirm for the next step. https://bitbucket.penske.com/projects/ITFIS/repos/eram-web/pull-requests/3/overview Thanks. | Gayam | 03/01/23 12:29 AM
| @praneeth.gayam@penske.com The PR is already merged by Jim. We are good with the changes. Please proceed with the further steps. @james.minisce@penske.com | Sreekanth | 03/04/23 2:56 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to Cap Bamboo | Gayam | 03/07/23 12:19 AM
Row 8 | @sreekanth.kancharla@penske.com , This app has some true positive secrets. I sent the file in email. Could you please check it. Thanks. | Gayam | 01/27/23 10:45 PM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. We are good to proceed further. true positives: SearchCompanyDAO.java - This file code is commented. BaseConstants.java - PASSWORD is just a string constant. All the remain are false positives. @mathumala.nachiappan@penske.com @james.minisce@penske.com | Sreekanth | 01/28/23 12:12 AM
Row 8 | @yvette.urso@penske.com , I asked the question regarding group above. It still needs to be resolved by @sreekanth.kancharla@penske.com . @mathumala.nachiappan@penske.com | Gayam | 12/10/22 2:43 AM
| @praneeth.gayam@penske.com If this is for cpe.jar file, then please proceed with creating new group in artifactory and make the required import changes in code. @james.minisce@penske.com Regarding the Bamboo, FP ticket 1765373 is created to Architect team to confirm whether this app's Java version in Bamboo is upgraded to 1.8 or not. | Sreekanth | 12/15/22 3:23 AM
| @praneeth.gayam@penske.com & @james.minisce@penske.com The bamboo plans of ERAM application are with Java 1.8 confirmed by Architect team. | Sreekanth | 12/15/22 7:37 PM
| Thanks @sreekanth.kancharla@penske.com . We will upload the jar and continue the maven changes. @mathumala.nachiappan@penske.com | Gayam | 12/15/22 8:00 PM
Row 8 | @sreekanth.kancharla@penske.com Please review the Bamboo plan for eRAM. Thank you. | James | 12/15/22 2:20 AM
Row 8 | @james.minisce@penske.com @mathumala.nachiappan@penske.com - James can you review the Bamboo for Mathu? | Yvette Urso | 12/15/22 2:12 AM
Row 8 | @rafiq.melath@penske.com / @james.minisce@penske.com , One more issue on this app. This application is using different version of cpe.jar which is not available in artifactory. thre is a different version of cpe.jar available artifactory which is not resolving the issues in this app. Do we need to upload the different version of cpe.jar in artifactory for this application ? Following class have the import from cpe. src/main/java/eram/actions/ViewProductAction.java @mathumala.nachiappan@penske.com | Gayam | 12/08/22 3:16 AM
| @sreekanth.kancharla@penske.com Please provide review the above and provide the necessary requested input. Thank you. | James | 12/08/22 6:17 PM
| @praneeth.gayam@penske.com When I search through the application source code, I found many classes are using the cpe.jar If the jar which is already available in Artifactory doesn't resolve the errors, then we need to have this version jar in artifactory. In this case my answer is "Yes" for your question. | Sreekanth | 12/08/22 7:30 PM
| Thanks @sreekanth.kancharla@penske.com . The current artifactory version of cpe is uplaoded with group com.penske.ebus which is working fine for ebus application. Do you want us to upload the eram version of cpe with group com.penske.eram? FYI: @mathumala.nachiappan@penske.com | Gayam | 12/08/22 10:49 PM
| @praneeth.gayam@penske.com If the group has to be changed, then the imports in java files also should be changed. Please correct me if I'm wrong. Are you planning to make those changes as well. If so, we are good, so that there will not be any issues in functionality of the application. | Sreekanth | 12/09/22 12:19 AM
| @sreekanth.kancharla@penske.com , Group is for where to upload in artifactory. It doesn't affect any code. @mathumala.nachiappan@penske.com | Gayam | 12/09/22 1:34 AM
Row 8 | @praneeth - Should this status change from blocked for this app or is there another reason you are still blocked? | Yvette Urso | 12/09/22 12:41 AM
Row 8 | Yes, the bamboo plan should be with Java 1.8. | James | 12/09/22 12:03 AM
Row 8 | @james.minisce@penske.com - Pls. confirm this Artifactory details. dnbi-acctmgmt.jar -------------------- Group ID - com.dnbi.eai Artifact ID - dnbi-acctmgmt Version - Default dnbi-creditapp.jar -------------------- Group ID - com.dnbi.eai Artifact ID - dnbi-creditapp Version - Default CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:40 PM
| I can confirm the above Artifactory details. CC: @sreekanth.kancharla@penske.com | James | 12/01/22 9:38 PM
| Thanks @james.minisce@penske.com . Jars are uploaded | Mathumala Nachiappan | 12/08/22 3:33 PM
Row 8 | @rafiq.melath@penske.com , This application has cpe.jar dependency for getting loggers in one class. But as per suggestion from Hugo/Architect team, it is good to create logger independently in each class. So we are doing this in all other apps. Same thing we are following in this app. FYI: @mathumala.nachiappan@penske.com | Gayam | 12/06/22 7:42 AM
Row 8 | @rafiq.melath@penske.com / @james.minisce@penske.com eram-web depends on below 2 jars. dnbi-acctmgmt.jar dnbi-creditapp.jar We are unable to find Bamboo build plan or SVN/BB Repo for these 2 jars. So need confirmation from you for uploading these 2 jars to Artifactory. FYI: @mathumala.nachiappan@penske.com | Gayam | 11/23/22 10:56 PM
| Yes, the identified jars will need to be uploaded to Artifactory. They are jars used to connect and get data from the DnBi web services. | James | 11/24/22 2:08 AM
Row 9 | This app is deployed to PROD on 10/19/2023 | Sreekanth | 10/20/23 5:33 PM
Row 9 | @praneeth.gayam@penske.com Please proceed with Bamboo plan creation with develop branch. Once that is available, we'll test this app in DEV and if the app works fine with no issues, we'll merge our recent changes from SVN to Bitbucket. | Sreekanth | 06/08/23 6:38 PM
| @sreekanth.kancharla@penske.com , Build plan and deploy plan onboarded successfully. Deployed to dev also completed. Please verify. Thanks. | Gayam | 06/13/23 2:12 AM
Row 9 | @praneeth.gayam@penske.com We are good with all the secrets as those are in common files & used across all the Penske web applications. The java version in Bamboo DEV: 1.6, QA: 1.8, PROD: 1.6 We recommend 1.8 CC: @charles.csoky@penske.com | Sreekanth | 01/25/23 2:00 AM
| Thanks @sreekanth.kancharla@penske.com . We have completed the modernization changes. Please review and merge them. PR is https://bitbucket.penske.com/projects/ITFIS/repos/esr-web/pull-requests/3/overview Changed the status to (AO)Maven. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 11:13 PM
| @praneeth.gayam@penske.com The PR is merged to develop. We are currently working on some changes in this application. Mostly we'll deploy the changes before March. Post deployment, we can merge the same changes from SVN to the new bitbucket source code. CC: @mathumala.nachiappan@penske.com @charles.csoky@penske.com | Sreekanth | 01/26/23 2:38 AM
| Thanks @sreekanth.kancharla@penske.com . We will hold this app until you confirm. | Gayam | 01/26/23 9:05 PM
| @praneeth.gayam@penske.com Can we proceed with next step in configuring the bamboo plan, so that when we are don with our current development and get UAT sign off, we can use the new build plan and test the application in DEV. Post that we'll take care of merging the change from SVN to Bitbucket. | Sreekanth | 01/27/23 12:14 AM
| @praneeth.gayam@penske.com and @sreekanth.kancharla@penske.com - As the log4j and mven changes are done from Log4J team and the application is blocked for some other enhancements, i am chanding the status to Waiting on AO. CC: @yvette.urso@penske.com | Mathumala Nachiappan | 01/27/23 10:10 AM
| @praneeth.gayam@penske.com We are making the enhancements to this application and we'll close by this month (2/28/2023). Once that is done, we'll merge the changes to new branch and test the application. @mathumala.nachiappan@penske.com @charles.csoky@penske.com | Sreekanth | 02/15/23 3:18 AM
| @sreekanth.kancharla@penske.com , Could you please merge https://bitbucket.penske.com/projects/ITFIS/repos/esr-web/pull-requests/6/overview These changes are for making the scope of log4j2 to compile. Thanks. | Gayam | 05/30/23 8:48 AM
| @praneeth.gayam@penske.com Merge completed. | Sreekanth | 06/01/23 12:11 AM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 06/01/23 10:47 PM
Row 9 | @charles.csoky@penske.com , We sent an email with secrets for this application. We observed all are false positives. Could you please verify and confirm. Thanks. | Gayam | 01/24/23 10:15 AM
Row 9 | @steve.mcmullen@penske.com / @charles.csoky@penske.com , Log4j and Mavn changes are completed. Could you please review and merge. PR is https://bitbucket.penske.com/projects/ITFIS/repos/esr-web/pull-requests/3/overview | Gayam | 12/03/22 12:19 PM
Row 10 | App deployed to PROD on 09/28/2023 | Sreekanth | 09/29/23 10:05 PM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 10/03/23 1:36 AM
Row 10 | @praneeth.gayam@penske.com could you please change the deploy plan names as "Staging-Deploy" & "Prod-Deploy" as this is a batch application. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=142737418 | Sreekanth | 09/07/23 12:47 AM
| @sreekanth.kancharla@penske.com , I already this question to log4j CICD team and they said that core plans are defined in that way and not possible to change at this point of time. | Gayam | 09/07/23 1:24 AM
Row 10 | @sreekanth.kancharla@penske.com , App is onboarded to bamboo and ready to deploy to QA. Please deploy. https://bamboo.penske.com/browse/ESRBP-ESRBCH0/ | Gayam | 03/30/23 12:34 AM
| @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: esrbatch-deploy New deployment project name: esr-batch-deploy Thank you. | Gayam | 05/14/23 9:41 PM
| @sreekanth.kancharla@penske.com , We changed the scope of log4j jars from provided to compile. Could you please merge the changes. https://bitbucket.penske.com/projects/ITFIS/repos/esr-batch/pull-requests/6/overview | Gayam | 05/24/23 1:55 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 05/24/23 9:04 PM
Row 10 | @charles.csoky@penske.com - Found a hardcoded credential during secret scanning process. Pls. have a look for redaction. @praneeth.gayam@penske.com - Pls. share the secret report to Charles | Mathumala Nachiappan | 12/08/22 10:13 PM
| @praneeth.gayam@penske.com Please loop me while sharing the report. | Sreekanth | 12/16/22 3:34 AM
| @sreekanth.kancharla@penske.com / @charles.csoky@penske.com , Shared the secrets in the email. Please check. @mathumala.nachiappan@penske.com | Gayam | 12/16/22 3:40 AM
| @praneeth.gayam@penske.com The secrets seems fine to me. "database.properties" differs for each environment. For SUPPORT only this file is used from the source location. For QA & PROD, this file is maintained in a specific path in Batch Box server where no one has access except admins. FYI, we don't have any SUPPORT environments for Batch applications. Except this one file, all other seems good to me. One remediation I can think of is by using the Connection Framework instead of maintaining the credentials in a file which required some development effort. Hope we are not planning to make those changes as of now. Please let us know incase any issues/suggestions. CC: @charles.csoky@penske.com | Sreekanth | 12/23/22 2:07 AM
| @sreekanth.kancharla@penske.com , Any changes you are planning for this application or can we go forward for the next step? | Gayam | 01/06/23 1:16 AM
| @praneeth.gayam@penske.com we are good with all the secrets as most of them are related to database credentials and in QA & PROD those credentials are being referred from “conf” folder which admins only can access. Bamboo Java version is 1.8 for QA & PROD CC: @charles.csoky@penske.com | Sreekanth | 01/25/23 2:24 AM
| Thanks @sreekanth.kancharla@penske.com . Passwords are referred in java class files. Is that ok to keep them over there? @hugo.scavino@penske.com / @yvette.urso@penske.com / @mathumala.nachiappan@penske.com | Gayam | 01/25/23 11:16 PM
| @praneeth.gayam@penske.com The only java file that is provided in secrets is "TestCopyFilesWithJcifs.java" This file is not available in trunk branch in SVN and only available in offshore branch. Hope the log4j migration changes be done on top of trunk branch which is used for PROD deployment. If so, hope we should be good with this file. | Sreekanth | 01/26/23 3:18 AM
| Thanks @sreekanth.kancharla@penske.com for confirming. Yes we created log4j branch from trunk which is master in bitnucket. Changing the status to (Cap) Maven | Gayam | 01/26/23 8:43 PM
| @praneeth.gayam@penske.com I've added a comment to the existing PR. Please take care, so that I can merge the request. https://bitbucket.penske.com/projects/ITFIS/repos/esr-batch/pull-requests/3/overview | Sreekanth | 02/16/23 8:35 PM
| @sreekanth.kancharla@penske.com , I responded to the comment. Could you please check. | Gayam | 02/17/23 1:15 AM
| @sreekanth.kancharla@penske.com , Could you please check my response and provide your input. Thanks. | Gayam | 03/03/23 1:29 AM
| @praneeth.gayam@penske.com We've requested for new DL email for logger. Once that is created, we'll share that with you, so that can be added in log4j2.xml For now, I've approve the PR, so please proceed with further steps. @charles.csoky@penske.com @sampada.bhusari@penske.com | Sreekanth | 03/04/23 2:49 AM
Row 11 | App deployed to PROD on 09/26/2023 | Sreekanth | 09/27/23 1:32 AM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 09/27/23 2:04 AM
Row 11 | @sreekanth.kancharla@penske.com , This app is onboarded to Bamboo. Please verify. https://bamboo.penske.com/browse/GEWEBCASH-GEWEB | Gayam | 03/30/23 11:07 PM
| @sreekanth.kancharla@penske.com , We chagned the log4j2 jars scope from provided to compile. So please merge the code. https://bitbucket.penske.com/projects/ITFIS/repos/gewebcash-batch/pull-requests/5/overview | Gayam | 05/24/23 2:18 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 05/24/23 9:04 PM
Row 11 | @sreekanth.kancharla@penske.com , this app is onboarded to Bamboo. Please check and let us know whether it can be deployed to Dev. | Gayam | 03/23/23 11:05 PM
| @praneeth.gayam@penske.com Please change the name in bamboo from "gewebcash" to "gewebcash-batch" similar to bitbucket repo name. I suggest to make similar changes to keep the name in both Bamboo & Bitbucket as same for all the new plans. | Sreekanth | 03/25/23 2:22 AM
| @praneeth.gayam@penske.com Do you've any update on changing the names? This is batch app, so no DEV environment. We'll take care of deploying to QA once validated in local. | Sreekanth | 03/30/23 12:22 AM
Row 11 | @praneeth.gayam@penske.com The PR got auto declined by bitbucket, so I've re-opened it and merged also. Hope that won't cause any issues as the status is still with Cap team. | Sreekanth | 03/21/23 6:03 PM
| No Issues @sreekanth.kancharla@penske.com . Thanks. We will onbaord this app to Bamboo. | Gayam | 03/22/23 12:43 AM
Row 11 | @praneeth.gayam@penske.com Since the status is under Cap team, please remove me from the review list for the existing PR in bitbucket. https://bitbucket.penske.com/projects/ITFIS/repos/gewebcash-batch/pull-requests/3/overview You can add back, once the PR is available for my review. | Sreekanth | 03/16/23 1:01 AM
| Sure @sreekanth.kancharla@penske.com . Thanks. | Gayam | 03/17/23 2:59 AM
Row 11 | @praneeth.gayam@penske.com In that case please create a new project for this application in Bamboo as there is no existing plan available. @mathumala.nachiappan@penske.com @srinivasan.narayanan@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/03/23 2:10 AM
Row 11 | @rafiq.melath@penske.com / @srinivasan.narayanan@penske.com / @sreekanth.kancharla@penske.com , We found the SVN url for this app https://svn.penske.com/svn/webprojects/admin/gewebcash/ But there is no bamboo build. Could you please provide the production version of the branch and under which project we need to create Bamboo specs. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/11/23 9:08 AM
| @praneeth.gayam@penske.com This is a batch application running on IBMi server from IFS. There is no trunk svn source available, so we compared the production source with offshore source and committed the PROD source under https://svn.penske.com/svn/webprojects/admin/gewebcash/trunk FYI, this application has only 1 java file. @mathumala.nachiappan@penske.com @swati.saxena@penske.com @srinivasan.narayanan@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/02/23 3:06 AM
| Thanks @sreekanth.kancharla@penske.com . Do you want us to take up the https://svn.penske.com/svn/webprojects/admin/gewebcash/trunk and do the modernization? Also, under which project do you want us to create Bamboo builds for this project? | Gayam | 02/02/23 3:23 AM
| @praneeth.gayam@penske.com Yes, please continue modernization with trunk branch. Which project means? This is separate application comes under Admin group, so separate plan in Bamboo is required. OR If we can have "admin-as400-utilities" as a project and under that also we can've build plans as we've few more similar batch applications runs on IBMi. @kalrav.khamar@penske.com @srinivasan.narayanan@penske.com | Sreekanth | 02/02/23 3:47 AM
| @sreekanth.kancharla@penske.com , In Bamboo, every application or group of similar apps have project. For example, under the below project in bamboo all ACH(Batch, Service and Web) build & deploy plans are created. All these are old plans. But we know where to create the new plans for ACH as the project already exist in Bamboo. https://bamboo.penske.com/browse/ACH But for gewbcash, there is no old build plans i.e no project exist in Bamboo. So could you please let us know whether to create a new project or use any other existing Admin project? @haribabu.challa@penske.com @mathumala.nachiappan@penske.com | Gayam | 02/02/23 11:05 PM
Row 11 | @rafiq.melath@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for these applications. | Gayam | 11/23/22 12:31 AM
| @rafiq.melath@penske.com / @srinivasan.narayanan@penske.com / @sreekanth.kancharla@penske.com , Could you please respond to above question. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 1:12 AM
Row 11 | @rafiq.melath@penske.com @praneeth.gayam@penske.com @mathumala.nachiappan@penske.com Hi Rafiq, We are testing out the email functionality in Smartsheet confirming you are receiving emails from here. Regards, Yvette | Yvette Urso | 11/25/22 11:29 PM
Row 12 | App deployed in PROD on 08/29/2023 | Sreekanth | 08/30/23 6:23 PM
Row 12 | @sreekanth.kancharla@penske.com , We changed the log4j2 jars scope from provided to compile. So please merge the code. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/70/overview | Gayam | 05/24/23 2:25 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 05/24/23 9:03 PM
Row 12 | @sreekanth.kancharla@penske.com , Changes are completed for this app. For some reason, I am unable to merge the few maven changes to develop_log4j branch. Could you please merge below PR. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/66/overview Once you merge the above PR, please review the code in the below PR. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/67/overview Thanks. | Gayam | 04/19/23 3:24 AM
| @praneeth.gayam@penske.com The below PR is merged. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/66/overview I've added review comments to below PR. Please check and do the need. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/67/overview | Sreekanth | 04/19/23 9:23 PM
| @sreekanth.kancharla@penske.com , We implemented the requested changes. Could you please merge them following PR https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/68/overview Then review the changes in PR https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/67/overview Thanks. | Gayam | 04/22/23 1:55 AM
| @praneeth.gayam@penske.com Thank you for making the changes for review comments. Both the PR are merged. Since we already have bamboo plan for this app with mavenized source, if any changes requires in the plan as per the new log4j template, please proceed with those changes and update the status in the smartsheet. We'll start testing the app once it is delivered to AO. | Sreekanth | 04/24/23 8:18 PM
| @sreekanth.kancharla@penske.com , thank you. We will do the Bamboo setup and will let you know. | Gayam | 04/25/23 1:28 AM
| @sreekanth.kancharla@penske.com , this app is deployed to dev using develop branch - https://bamboo.penske.com/browse/HBP-HRCCALBP0/deployments Please verify. | Gayam | 04/27/23 1:32 AM
| @praneeth.gayam@penske.com This app source code was already available in Bitbucket and the bamboo plans also available. Separate plans for both Web & UI code. Now I see a new plan is created for web https://bamboo.penske.com/browse/HBP-HRCCALBP but no UI plan is created. Have you used existing https://bamboo.penske.com/browse/HBP-HRCCAL plan itself for DEV deployment. Since we've new plan for web, it is good to have new plan for UI also. | Sreekanth | 04/27/23 1:59 AM
| @sreekanth.kancharla@penske.com , we worked on only hrcc-web and the bamboo build for that is https://bamboo.penske.com/browse/HBP-HRCCALBP We did not work hrcc-ui project as this is not mentioned in our list or smartsheets. | Gayam | 04/27/23 3:11 AM
| @praneeth.gayam@penske.com hrcc-ui is not a separate project. That repo has front end code (angular) & hrcc-web has back end code (java). With both those sources only HRCC app can be tested. I suggest to have a new bamboo plan created for hrcc-ui as well, so that we can retire the old plans once we complete the log4j testing. If needed, please schedule a meeting with @raghuramredd.thummalapalli@penske.com / @balu.mohan@penske.com / @hugo.scavino@penske.com for further clarification. | Sreekanth | 04/27/23 6:54 PM
| Sure @sreekanth.kancharla@penske.com . But before onboarding bamboo plan for hrcc-ui, we need to modernize the hrcc-ui project. If you are ok, we can take up the work. | Gayam | 04/28/23 1:44 AM
| @praneeth.gayam@penske.com hrcc-ui is an angular app and available in bitbucket itself. Hope no need of any modernization for UI source code and new bamboo plan can be created with existing source code itself. We can discuss over call on code changes for modernization. | Sreekanth | 05/01/23 6:40 PM
| @sreekanth.kancharla@penske.com , if it contains total UI code and a Bamboo plan already exist, I don't think we need to re onboard any new plan. You can continue using the old bamboo plan of hrcc-ui. Please correct me if I am wrong. @hugo.scavino@penske.com | Gayam | 05/02/23 12:49 AM
| @praneeth.gayam@penske.com We are good to use the existing plan itself for UI. In that case, just to follow the naming convention, is it possible to change the name of the build plan https://bamboo.penske.com/browse/HBP-HRCCAL to "hrcc-ui" & the deploy plan also with the new naming convention. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=91160582 | Sreekanth | 05/02/23 7:24 PM
| @sreekanth.kancharla@penske.com , I think you need to raise a fp ticket to change the names of hrcc-ui . Because the plans of hrcc-ui not created by log4j team and we don't have control on that. Thanks. | Gayam | 05/03/23 1:49 AM
| @praneeth.gayam@penske.com Sure, thank you! | Sreekanth | 05/03/23 7:47 PM
Row 12 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:54 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets as all of them are related to mybatis xml files. You are good to proceed further. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 12:22 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (Cap) Maven | Gayam | 01/27/23 2:41 AM
Row 13 | App deployed to PROD on 10/12/2023 | Sreekanth | 10/12/23 10:28 PM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 10/13/23 6:35 AM
Row 13 | Review: @sreekanth.kancharla@penske.com / @kalrav.khamar@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ITFIS/repos/mailreader_2_0-batch/pull-requests/5/overview | Gayam | 05/02/23 2:33 AM
| @praneeth.gayam@penske.com I've merged the PR. One small suggestion. We don't need to maintain the app name as "mailreader_2_0-batch", instead we can've it as "mailreader-batch" Please change the repo name and the same new name can be used for Bamboo plan as well. @kalrav.khamar@penske.com | Sreekanth | 05/08/23 9:31 PM
| Sure @sreekanth.kancharla@penske.com . We will make the change and will let you know. Thanks. | Gayam | 05/08/23 10:16 PM
| @sreekanth.kancharla@penske.com , Repo name and Bamboo build/deploy plan names are changed to mailreader-batch. Please check and confirm. | Gayam | 05/10/23 12:24 AM
| @praneeth.gayam@penske.com the repo name & bamboo build/deploy plan names are good now. | Sreekanth | 05/10/23 2:45 AM
| @sreekanth.kancharla@penske.com , Please merge https://bitbucket.penske.com/projects/ITFIS/repos/mailreader-batch/pull-requests/7/overview The changes are for making log4j2 scope to compile. Thank you. | Gayam | 05/30/23 8:54 AM
| @praneeth.gayam@penske.com Merge completed. | Sreekanth | 06/01/23 12:10 AM
| Thanks @sreekanth.kancharla@penske.com . Build is done | Gayam | 06/01/23 10:45 PM
Row 13 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:55 AM
| @praneeth.gayam@penske.com Passowrd is used to access mailbox details. This utility extract file from mail box and load data in AP or JE system. | Kalrav | 03/08/23 2:01 AM
| @kalrav.khamar@penske.com , So it is not a secret? | Gayam | 03/08/23 2:55 AM
| @praneeth.gayam@penske.com yes, its not secrets. | Kalrav | 03/08/23 11:32 PM
Row 13 | @rafiq.melath@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:32 AM
| @praneeth.gayam@penske.com We're looking into JEUPLOAD application in SVN. It uses .jar file from this folder. We will update you as soon as, we find correct svn location. | Kalrav | 12/21/22 3:05 AM
| @praneeth.gayam@penske.com use follow svn path to update code. https://svn.penske.com/svn/webprojects/admin/as400_utilities/trunk/mailreader | Kalrav | 01/10/23 2:10 AM
Row 13 | @mathumala.nachiappan@penske.com changed status. | Yvette Urso | 12/15/22 2:21 AM
Row 14 | This application is deployed to PROD on 07/20/2023 | Sreekanth | 07/21/23 10:42 PM
Row 14 | Post reverting the dlink_filter changes, we've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD. | Sreekanth | 07/05/23 7:33 PM
Row 14 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD but waiting on dlink-filter.jar PROD deployment by Architect team. | Sreekanth | 06/08/23 11:24 PM
Row 14 | @sreekanth.kancharla@penske.com , app is on boarded to Bamboo. https://bamboo.penske.com/browse/PETBP-PETTYC/ please let us know whether we can deploy this to dev. | Gayam | 03/10/23 11:20 PM
| @praneeth.gayam@penske.com Please proceed with DEV deployment. | Sreekanth | 03/13/23 10:17 PM
| @sreekanth.kancharla@penske.com , Dev deployment is completed. Please check. | Gayam | 03/15/23 11:44 PM
| @praneeth.gayam@penske.com DEV testing is in-progress @kalrav.khamar@penske.com | Sreekanth | 04/19/23 9:35 PM
| @praneeth.gayam@penske.com Please delete the old deploy plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=132710422 | Sreekanth | 05/09/23 7:19 PM
| Sure @sreekanth.kancharla@penske.com . Will do | Gayam | 05/09/23 10:30 PM
| @sreekanth.kancharla@penske.com , Old deploy plans are deleted. | Gayam | 05/10/23 11:19 PM
Row 14 | Secrets: @srinivasan.narayanan@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file to you in the email. Could you please check and provide your response over here. | Gayam | 02/25/23 1:22 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. I've validated the trunk branch files alone even though offshore branch is also included secrets. @srinivasan.narayanan@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/25/23 1:45 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the app status to Cap Maven | Gayam | 02/27/23 11:47 PM
| @praneeth.gayam@penske.com PR is merged. Please proceed with next steps. | Sreekanth | 03/04/23 3:21 AM
| Thanks @sreekanth.kancharla@penske.com . We will implement the next step which is Cap Bamboo. | Gayam | 03/07/23 12:02 AM
Row 14 | @srinivasan.narayanan@penske.com / @yvette.urso@penske.com , in this app logger classes are getting created with custom configuration using fileappender(getallappender) and simplelayout . Not able to configure using the slf4j and log4j2. providing link for class file. https://svn.penske.com/svn/webprojects/admin/pettycash/trunk/pettycash6/JavaSource/com/penske/apps/pettyCash/util/FileFunctions.java. Also @hugo.scavino@penske.com confirmed that he needs to discuss with app owner who needs to change the code. @mathumala.nachiappan@penske.com | Gayam | 12/07/22 11:04 PM
| @praneeth.gayam@penske.com Please share the remediation plan if we've any for such kind of custom configurations. Kindly loop me for future communications. | Sreekanth | 12/16/22 3:36 AM
| @praneeth.gayam@penske.com From the FileFunctions class file, we observed that readFile & readFileLines methods alone are being used and not any other methods. We can comment those unused methods and look for any compiler errors. If no compiler errors, we should be good. Moreover, this logging is already implemented with log4j.xml which is available under JavaSource folder, so hope we can migrate that. @hugo.scavino@penske.com @srinivasan.narayanan@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/03/23 3:14 AM
| Thanks @sreekanth.kancharla@penske.com . Hugo also suggested same thing for other apps. We will make the change and let you know if we face any other issues. Thanks | Gayam | 02/03/23 11:51 PM
Row 14 | Moved to AO Log4J status. @mathumala.nachiappan@penske.com | Yvette Urso | 12/15/22 2:14 AM
Row 14 | @mathumala.nachiappan@penske.com What is this dependency? | Yvette Urso | 12/02/22 2:14 AM
Row 14 | @srinivasan.narayanan@penske.com - Log4J1 dependency to be cleared or confirmed . CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:41 PM
Row 15 | App deployed to PROD on 09/14/2023 | Sreekanth | 09/15/23 6:41 PM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 09/16/23 12:19 AM
Row 15 | @praneeth.gayam@penske.com I've already has the bamboo plan created for this application. We are good. We'll continue to test this app in DEV/QA. | Sreekanth | 07/27/23 7:26 PM
Row 15 | @sreekanth.kancharla@penske.com , I think you already merged the code to develop branch for this application and created another branch feature/IFS-1494 from develop branch. Do you want us to onboard this app to bamboo? | Gayam | 07/27/23 2:35 AM
Row 15 | Added psndmail application due to needed for the pextfl. | Yvette Urso | 02/16/23 12:23 AM
Row 15 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed few true positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:59 AM
Row 16 | App deployed to PROD on 10/24/2023 | Sreekanth | 10/25/23 7:40 PM
Row 16 | FP# 1890489 is open to architect team to get clarification on security_util.jar & security_authority_filter.jar | Sreekanth | 08/22/23 1:17 AM
Row 16 | Thanks @sreekanth.kancharla@penske.com for the secrets confirmation. We have 1 more question on this app. This application using the loggers from penske-secure-logger jar. If we use this jar we need to include log4j1 . You gave the confirmation for pops_batch app to replace the loggers from penske-secure-logger with slf4j loggers. For pops.war app also do you want us to replace the loggers from penske-secure-logger jar with slf4j? Please provide your confirmation. Thanks. | Gayam | 02/25/23 12:02 AM
| @praneeth.gayam@penske.com I could see penske-secure-logger is used only for logging. Please replace this with slf4j We'll test in DEV. Are you we good with other dependency jars which is marked as blocker security_util.jar security_author_filter.jar | Sreekanth | 02/25/23 4:00 AM
| Yes @sreekanth.kancharla@penske.com . Those 2 jars are already modernized and uploaded to artifactory. | Gayam | 02/27/23 11:19 PM
| @praneeth.gayam@penske.com Please find the commented added to the PR. | Sreekanth | 03/04/23 3:17 AM
| @sreekanth.kancharla@penske.com , Please don't review or merge until the app status is in (AO)Maven status. (Cap)Maven means, still CG/Log4j team still working on this application. We will review the comment and complete the required things. | Gayam | 03/07/23 12:06 AM
| @praneeth.gayam@penske.com Since the status is under Cap team, please remove me from the review list for the existing PR in bitbucket. https://bitbucket.penske.com/projects/ITFIS/repos/pops-web/pull-requests/3/overview You can add back, once the PR is available for my review. | Sreekanth | 03/16/23 1:02 AM
| Sure @sreekanth.kancharla@penske.com . Thanks for the notification and this is ready for the review. Changed the status to AO Maven | Gayam | 03/17/23 2:58 AM
| @praneeth.gayam@penske.com Added review comment, please check. | Sreekanth | 03/21/23 8:26 PM
| @sreekanth.kancharla@penske.com , Completed the changes provided in review comments. Please check. Thanks. | Gayam | 03/23/23 11:18 PM
| @praneeth.gayam@penske.com Thank you. PR is merged. | Sreekanth | 03/24/23 8:49 PM
| Thanks @sreekanth.kancharla@penske.com . We will let you know once onboarding to Bamboo and deploymnet to Dev completed. Thanks | Gayam | 03/24/23 11:04 PM
| @sreekanth.kancharla@penske.com , Bamboo build is onboarded. Dev deployment done using develop branch. Please verify. https://bamboo.penske.com/browse/POPBP-PP/ | Gayam | 04/20/23 2:03 AM
Row 16 | @praneeth.gayam@penske.com We've received new secrets on this application on 2/23/2023 and the secrets are on QA branch & also on offshore branches. Hope we should only worry on qa branch as that is the one you would've used for log4j changes and we are using for QA & PROD deployments. We may've multiple offshore branches and all wouldn't be in sync with production code. In QA SVN branch, no remediations required for the shared secrets. @kalrav.khamar@penske.com | Sreekanth | 02/24/23 9:18 PM
Row 16 | @rafiq.melath@penske.com - Holding on for the modernization of Dependency Jars security_util.jar security_author_filter.jar CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:37 PM
| @praneeth.gayam@penske.com we need both of following jars. security_util.jar security_author_filter.jar | Kalrav | 01/25/23 3:40 AM
| @kalrav.khamar@penske.com Thanks for confirming. Modernization is going on both of above apps. Until it completes, we can not work on this app. @hugo.scavino@penske.com / @mathumala.nachiappan@penske.com | Gayam | 01/25/23 11:35 PM
| @praneeth.gayam@penske.com @yvette.urso@penske.com Do you know who is working on these security related jars? Can we assign 'Major Blocker' to person who is working on security jars? | Kalrav | 01/31/23 10:10 PM
| @kalrav.khamar@penske.com , Hugo is working on Security_util and he almost completed the work. Security_author_filter depends on security_util. So CG team is waiting on security_util to complete. | Gayam | 02/03/23 3:02 AM
Row 16 | Blocker - security_util.jar security_author_filter.jar | Yvette Urso | 02/01/23 8:27 PM
Row 17 | App deployed to PROD on 10/24/2023 | Sreekanth | 10/25/23 7:40 PM
Row 17 | @sreekanth.kancharla@penske.com , This app is onboarded to bamboo. Following is the url. https://bamboo.penske.com/browse/POPBP-POPSBCH0/ Please deploy to QA and test it. Thanks. | Gayam | 03/29/23 12:51 AM
Row 17 | Review: @sreekanth.kancharla@penske.com , This app ready for your review. https://bitbucket.penske.com/projects/ITFIS/repos/pops-batch/pull-requests/3/overview | Gayam | 03/16/23 12:49 AM
| @praneeth.gayam@penske.com The PR is merged. | Sreekanth | 03/16/23 12:54 AM
| Thanks @sreekanth.kancharla@penske.com . We will onboard to bamboo and will let you know. | Gayam | 03/16/23 2:33 AM
Row 17 | Question: @sreekanth.kancharla@penske.com , This application having different dao-spring-context.xml files in targeted folder for each environment. But for the environment agnostic build we have to keep only 1 xml file. Which one we need to move to resouces folder? | Gayam | 02/28/23 12:00 AM
| @praneeth.gayam@penske.com We can't have single dao-spring-context.xml file as there is 1 difference in all 3 environment specific files. We should load these from targeted folder or need to see the possibility of how we can change the implementation. The difference is we are using Remoting EBS Service with URL provider and that URL changes based on the environment, so we've 3 files for 3 environments (DEV/QA/PROD) @kalrav.khamar@penske.com | Sreekanth | 03/02/23 2:41 AM
| @sreekanth.kancharla@penske.com , Once we migrate to maven and new bamboo plans there is no option trigger separate builds. It is going to be only 1 build. Are you in the plans to change the implementation? @hugo.scavino@penske.com | Gayam | 03/03/23 12:29 AM
| @praneeth.gayam@penske.com We've no plans now to make any changes, but we can plan for that under this log4j migration ITG itself. @kalrav.khamar@penske.com | Sreekanth | 03/07/23 12:39 AM
| @sreekanth.kancharla@penske.com , Log4j team shouldn't make any application level changes. As per management decision, all app level changes needs to be done by App team. Could you please let us know the next step. | Gayam | 03/07/23 1:05 AM
| @praneeth.gayam@penske.com We'll look through the possible solutions in bring this app environment agnostic and make those changes. @kalrav.khamar@penske.com | Sreekanth | 03/07/23 3:50 AM
| Thanks @sreekanth.kancharla@penske.com . Do you want us to hold this app until you confirm or can we use the prod one and complete the mavanization and gave it to you to resolve the above issue in mavanized branch? | Gayam | 03/07/23 11:44 PM
| @praneeth.gayam@penske.com Please have the mavenized branch ready. Post that we'll work on dao-spring-context.xml environment agnostic changes. @kalrav.khamar@penske.com | Sreekanth | 03/08/23 3:04 AM
| Sure @sreekanth.kancharla@penske.com . We will use the targeted/prod one for dao-spring-context.xml. Thanks | Gayam | 03/09/23 12:09 AM
Row 17 | @praneeth.gayam@penske.com We've receive email on secrets for this app on 02/23/2023. Only 1 files is valid https://svn.penske.com/svn/webprojects/admin/pops/branches/qa/pops_batch/database.properties That too, in batch box server where this application is deployed in QA & PROD, this file is being referred from different location (which admin only have access) and not from the source location. So, we don't need any remediation for this file. The other secrets seem to be on offshore branches and also seems from commit history as well. Hope we don't need to worry on those. @kalrav.khamar@penske.com | Sreekanth | 02/24/23 9:27 PM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (Cap)Maven. | Gayam | 02/25/23 12:08 AM
Row 17 | Blocker: penske-secure-logger-1.0.0.jar | Yvette Urso | 02/01/23 8:29 PM
Row 17 | @kalrav.khamar@penske.com @mathumala.nachiappan@penske.com Can you look at this blocker and let us know what the next steps should be? Thank you | Yvette Urso | 12/02/22 2:19 AM
| @praneeth.gayam@penske.com we will look into penske-secure-logger-1.0.0.jar and see it required in app or not. Will update you soon. | Kalrav | 01/25/23 3:43 AM
| @praneeth.gayam@penske.com penske-secure-logger-1.0.0.jar is being used for logger only. If you are replacing this with SLF4j logger OR If this jar is being modernized and placed in artifactory, then reusing the same logger. We should be good with both the approaches as we could see only logger object being used from this jar file. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/30/23 11:40 PM
Row 17 | @kalrav.khamar@penske.com - Waiting for the modernization of the dependent jar penske-secure-logger-1.0.0.jar CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:43 PM
Row 18 | Deployed in production on 10/5/23 | Kalrav | 10/06/23 12:44 AM
| Thanks @kalrav.khamar@penske.com | Gayam | 10/06/23 12:56 AM
Row 18 | @sreekanth.kancharla@penske.com , Build and Deploy plans are onboarded to Bamboo. As this this the batch app, AO needs to do the QA deployment. Currently the build will deploy to /var/tmp folder of QA server. | Gayam | 03/20/23 11:44 PM
Row 18 | @praneeth.gayam@penske.com PR is merged. This application is a batch app running on IFS. We should've SUPPORT environment for IFS deployed apps as it is AS400 database system. @hugo.scavino@penske.com mentioned that the deployment to IFS also can be done from bamboo. We can test that auto deploy from bamboo for this app. Please let us know incase any information required while configuring the bamboo build & deploy plans. | Sreekanth | 03/16/23 12:32 AM
| @sreekanth.kancharla@penske.com , One of the @david.w.graf@penske.com 's app was deployed to IFS. But it was manual. Bamboo deploys to regular QA server's /var/tmp folder and after that David did the manual process to deploy to IFS server. Hope David will reach out to you regarding this. Thanks. | Gayam | 03/18/23 1:00 AM
Row 18 | Review: @sreekanth.kancharla@penske.com , Please review https://bitbucket.penske.com/projects/ITFIS/repos/psndmail-batch/pull-requests/4/overview | Gayam | 03/02/23 3:04 AM
Row 18 | Secrets: @kalrav.khamar@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/24/23 2:00 AM
| @praneeth.gayam@penske.com We don't need any remediation for the shared secrets as all the secrets are just variable name "password" and no password is stored inside the code. @kalrav.khamar@penske.com | Sreekanth | 02/24/23 9:30 PM
| Thanks @sreekanth.kancharla@penske.com . Changed the app status to (Cap)Maven | Gayam | 02/25/23 12:18 AM
Row 18 | As per our discussion with @kalrav.khamar@penske.com / @yvette.urso@penske.com This is the new application which is onboarded to log4j team's scope. @mathumala.nachiappan@penske.com / @balu.mohan@penske.com | Gayam | 02/17/23 7:21 PM
Row 19 | Deployed app to PROD on 08/17/2023 | Sreekanth | 08/18/23 7:47 AM
| @sreekanth.kancharla@penske.com , Thanks for the update. | Gayam | 08/18/23 8:18 PM
Row 19 | Post reverting the dlink_filter changes, we've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD. | Sreekanth | 07/05/23 7:32 PM
Row 19 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD but waiting on dlink-filter.jar PROD deployment by Architect team. | Sreekanth | 06/08/23 11:24 PM
Row 19 | @praneeth.gayam@penske.com As per the naming convention, all the apps in bitbucket follow a standard and the same name being used in bamboo plan as well. If possible, please change the name from "sic" to "sics-web" for https://bamboo.penske.com/browse/SCSBP-SICSW | Sreekanth | 04/24/23 8:43 PM
| @sreekanth.kancharla@penske.com , we completed the change for all the apps. Please verify. Thanks. | Gayam | 04/27/23 2:13 AM
| @praneeth.gayam@penske.com Thank you for making the naming corrections as same as bitbucket repo name for both build & deploy plans. Started using new deploy plan. Please delete old deploy plan. | Sreekanth | 04/27/23 7:01 PM
| @praneeth.gayam@penske.com We've started using the new deploy plan and good to delete the old deploy plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=132710402 | Sreekanth | 05/03/23 8:00 PM
| @sreekanth.kancharla@penske.com , Not sure whether deleting the old plans part of Log4j project. But I will check and confirm. | Gayam | 05/04/23 12:17 AM
| @sreekanth.kancharla@penske.com , Deleted the old deploy plan. | Gayam | 05/08/23 10:13 PM
Row 19 | @praneeth.gayam@penske.com We started testing this application and had some issues with dlinkfilter. The issue was resolved with the help of @hugo.scavino@penske.com by removing unwanted dependency "dom.jar". Post that we are getting issue with sessionvalidationfilter which @hugo.scavino@penske.com will be working on common solution. Only then we can resume the testing. The pending sessionvalidationfilter change does applies for all the web applications to proceed with environment agnostic web.xml. @kalrav.khamar@penske.com | Sreekanth | 03/20/23 9:12 PM
| @praneeth.gayam@penske.com The latest dlinkfilter changes are working fine for this app in DEV server. Once we complete the application-level testing, we'll post update. Meanwhile we are waiting on confirmation from @hugo.scavino@penske.com to deploy the changes to QA for further testing. | Sreekanth | 04/06/23 11:59 PM
Row 19 | @praneeth.gayam@penske.com The PR is merged to develop. CC: @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 2:26 AM
| Thanks @sreekanth.kancharla@penske.com . Could you please confirm the secrets too. | Gayam | 01/26/23 8:19 PM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. Most of the files are jsp & js. The 2 files that has password as a word are CPMApplication.java & CPUReportServlet.java In both these files the code is commented and not used. You are good to proceed with next steps. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 12:33 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (Cap)Maven | Gayam | 01/27/23 2:45 AM
| @sreekanth.kancharla@penske.com , There is a small change in the artifactid. So we changed and created the PR. Could you please merge. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/sics-web/pull-requests/5/overview | Gayam | 02/02/23 11:57 PM
| Thanks @sreekanth.kancharla@penske.com for merging the code. Can we go for the next step which is build & deploy plans onboarding and Dev deployment? | Gayam | 02/03/23 12:12 AM
| @praneeth.gayam@penske.com Sure, please proceed with dev plan build & deployment. @kalrav.khamar@penske.com | Sreekanth | 02/03/23 2:15 AM
| @sreekanth.kancharla@penske.com , Dev deployment is completed for this application Could you please verify. Thanks. @haribabu.challa@penske.com | Gayam | 02/07/23 2:13 AM
| @praneeth.gayam@penske.com Dev deployment completed means, was that through Bamboo? Please share the bamboo plan as I couldn't find any new plan for SICS under existing project https://bamboo.penske.com/browse/SCSBP | Sreekanth | 02/15/23 3:06 AM
| @sreekanth.kancharla@penske.com Following is the Bamboo plan. https://bamboo.penske.com/browse/SCSBP-SICSW yes. It is deployed through Bamboo. | Gayam | 02/16/23 2:47 AM
| @praneeth.gayam@penske.com We'll wait till we get the access to Bamboo plans. Meanwhile we are getting below issue when we access the DEV application. Error: Error 500: javax.servlet.ServletException: Filter [CPUSessionValidationFilter]: com.penske.apps.sics.ui.CPUSessionValidationFilter was found, but is corrupt: URL: https://web3dev.penske.com/sics/entry/ApplicationEntry?LoginUserID=600123805 | Sreekanth | 02/18/23 12:05 AM
| @sreekanth.kancharla@penske.com , for sics.war RBAC roles are updated. Please check the access now. | Gayam | 02/18/23 12:37 AM
| @praneeth.gayam@penske.com I'm still unable to view the new plans in bamboo under https://bamboo.penske.com/browse/SCSBP | Sreekanth | 02/22/23 8:42 PM
| @sreekanth.kancharla@penske.com , Following thing mentioned by @kalrav.khamar@penske.com in the email. "PTL-Admin-Development = Can execute Build Plans Once we’ve BB-Admin role, we will add eligible developers to this role." Because of this no one added to above roles. I am expecting this is the issue. @haribabu.challa@penske.com / @balu.mohan@penske.com | Gayam | 02/23/23 3:19 AM
| @praneeth.gayam@penske.com My name is also available under BB-Admin role but still I'm unable to view the bamboo plan. If admin doesn't have the access, how can he/she provide access to developers. | Sreekanth | 02/23/23 3:32 AM
| @sreekanth.kancharla@penske.com , As discussed BB-Admin role is only bitbucket projects. We sent an email to respective person to add the provided users to the requested role. We will let you know once it is completed. | Gayam | 02/25/23 12:17 AM
| @praneeth.gayam@penske.com We got access to new bamboo plans but we are unable to add a "Plan branch". Please check and do the need. | Sreekanth | 03/13/23 10:14 PM
Row 19 | @kalrav.khamar@penske.com / @sreekanth.kancharla@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:57 AM
Row 19 | @rafiq.melath@penske.com / @sreekanth.kancharla@penske.com, This is a web application but when we check the targeted folder it contains jee-resources and batchconfig properties files for each environment. Usually these 2 files are exist for batch apps only. Could you please check and clarify us whether these are required or not. Also, there is a extra file sicsbatch.properties in targeted folder. Please check whether this file is required. Thanks. @mathumala.nachiappan@penske.com / @hugo.scavino@penske.com | Gayam | 12/17/22 2:05 AM
| @praneeth.gayam@penske.com All the 3 files jee-resources, batchconfig properties, sicsbatch.properties are not required. CC: @kalrav.khamar@penske.com @rafiq.melath@penske.com | Sreekanth | 12/22/22 12:12 AM
| Thanks @sreekanth.kancharla@penske.com . We will make the changes accordingly. @mathumala.nachiappan@penske.com | Gayam | 12/22/22 3:04 AM
Row 19 | @mathumala.nachiappan@penske.com Moved to CAP Bitbucket status - Did you create a Footprints ticket for the Bitbucket Team (plus @hugo.scavino@penske.com ) | Yvette Urso | 12/15/22 2:17 AM
| @yvette.urso@penske.com - CAP is able to rectify this issue and this is in Maven stage now.. So moving to (Cap) Maven. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/15/22 10:14 AM
Row 19 | facing SVN to BB migration issue @kalrav.khamar@penske.com . Looking forward to discuss with Architecture team regd. permission issues from SVN or BB. Planned for Monday. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:45 PM
Row 20 | Deployed app to PROD on 08/17/2023 | Sreekanth | 08/18/23 7:47 AM
| @sreekanth.kancharla@penske.com , Thanks for the update. | Gayam | 08/18/23 8:18 PM
Row 20 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD. | Sreekanth | 07/05/23 7:32 PM
Row 20 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD but waiting on dlink-filter.jar PROD deployment by Architect team. | Sreekanth | 06/08/23 11:24 PM
Row 20 | @praneeth.gayam@penske.com As per the naming convention, all the apps in bitbucket follow a standard and the same name being used in bamboo plan as well. If possible, please change the name from "sicsbatch" to "sics-batch" for https://bamboo.penske.com/browse/SCSBP-SICSB | Sreekanth | 04/24/23 8:42 PM
| Sure @sreekanth.kancharla@penske.com , We will check and get back to you. | Gayam | 04/25/23 1:17 AM
| @praneeth.gayam@penske.com I do see the changes made in bamboo plans. Thank you. Appreciate if you could make similar changes to deploy plans as well for all 3 SICS apps. | Sreekanth | 04/25/23 6:17 PM
| Sure @sreekanth.kancharla@penske.com . We are in the process of doing all the changes. | Gayam | 04/26/23 1:21 AM
| @sreekanth.kancharla@penske.com , we completed the change for all the apps. Please verify. Thanks. | Gayam | 04/27/23 2:14 AM
| @praneeth.gayam@penske.com Thank you for making the naming corrections as same as bitbucket repo name for both build & deploy plans. Started using new deploy plan. Please delete old deploy plan. | Sreekanth | 04/27/23 7:01 PM
| @praneeth.gayam@penske.com We've started using the new deploy plan and good to delete the old deploy plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=132710401 | Sreekanth | 05/03/23 8:03 PM
| @sreekanth.kancharla@penske.com , Deleted the old deploy plan. | Gayam | 05/08/23 10:14 PM
Row 20 | @praneeth.gayam@penske.com This application is deployed in QA and verified the logs. The logs are printing fine. We'll continue the integration testing of SICS Web, Service & Batch apps and post update. @kalrav.khamar@penske.com | Sreekanth | 04/07/23 12:00 AM
Row 20 | @sreekanth.kancharla@penske.com , As the PR merged we onboarded this application to bamboo. Following is the URL. https://bamboo.penske.com/browse/SCSBP-SICSB Please run the 'develop' branch to onboard the deploy plan. We can't onboard the deploy plan because if we onboard it automatically deploys it to QA as this is the batch app there is no Dev environment. As per Hugo, Log4j team can't deploy to QA. Thanks. | Gayam | 02/04/23 12:44 AM
| @praneeth.gayam@penske.com Thank you. We can't deploy the application to QA. Since no DEV environment for batch app, we need to test the changes in local first. @kalrav.khamar@penske.com | Sreekanth | 02/04/23 3:48 AM
| Sure @sreekanth.kancharla@penske.com . Changed the status to (AO)Bamboo Review. We will wait for your confirmation. | Gayam | 02/07/23 12:01 AM
| @praneeth.gayam@penske.com We've no access to bamboo plan. Please grant the access. | Sreekanth | 02/15/23 3:11 AM
| @sreekanth.kancharla@penske.com , We sent an email to AO Manager and other team to get the details about whom we need to add different Admin RBAC groups. Devops team decided that they are not going to provide the individual accesses. So could you please respond to that email. Once we add the team members to different RBAC groups, depends on the permissions members will see the build plans. | Gayam | 02/15/23 7:02 AM
| @praneeth.gayam@penske.com Please provided access to have Add Plan branch option on all the new bamboo plans. We don't have access to the plans created as part of this log4j migration. For any other new apps, we are getting the access to add the Plan branch by default. Please check with Architect team on this and do the need. | Sreekanth | 03/16/23 12:57 AM
| There is a discussion going on this in the email. | Gayam | 03/17/23 3:00 AM
Row 20 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:58 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. Most of the files are mybatis files. We are good to proceed with next steps. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 12:35 AM
Row 20 | @praneeth.gayam@penske.com - Changing the status to (AO) Maven as the PR is raised | Mathumala Nachiappan | 12/19/22 8:23 PM
| @praneeth.gayam@penske.com The PR is merged to develop. CC: @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 2:27 AM
| Thanks @sreekanth.kancharla@penske.com . Could you please check the secrets and confirm. | Gayam | 01/26/23 8:11 PM
Row 20 | @rafiq.melath@penske.com / @kalrav.khamar@penske.com , Log4j and maven changes are completed by log4j team. Could you please review the below PR and merge. https://bitbucket.penske.com/projects/ITFIS/repos/sics-batch/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/16/22 3:11 AM
Row 21 | Deployed app to PROD on 08/17/2023 | Sreekanth | 08/18/23 7:47 AM
| @sreekanth.kancharla@penske.com , Thanks for the update. | Gayam | 08/18/23 8:18 PM
Row 21 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD. | Sreekanth | 07/05/23 7:32 PM
Row 21 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD but waiting on dlink-filter.jar PROD deployment by Architect team. | Sreekanth | 06/08/23 11:24 PM
Row 21 | @praneeth.gayam@penske.com As per the naming convention, all the apps in bitbucket follow a standard and the same name being used in bamboo plan as well. If possible, please change the name from "sicssvc" to "sics-service" for https://bamboo.penske.com/browse/SCSBP-SICSSVCP | Sreekanth | 04/24/23 8:43 PM
| @sreekanth.kancharla@penske.com , we completed the change for all the apps. Please verify. Thanks. | Gayam | 04/27/23 2:14 AM
| @praneeth.gayam@penske.com Thank you for making the naming corrections as same as bitbucket repo name for both build & deploy plans. Started using new deploy plan. Please delete old deploy plan. | Sreekanth | 04/27/23 7:01 PM
| @praneeth.gayam@penske.com We've started using the new deploy plan and good to delete the old deploy plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=129728520 | Sreekanth | 05/03/23 7:59 PM
| @sreekanth.kancharla@penske.com , Deleted the old deploy plan. | Gayam | 05/08/23 10:14 PM
Row 21 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:58 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 12:36 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (AO)Maven as MR is already created and provided in above comment. | Gayam | 01/27/23 2:47 AM
| @praneeth.gayam@penske.com The MR is merged and good to proceed with next steps. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 7:43 PM
| Thanks @sreekanth.kancharla@penske.com . We will onboard to Bamboo and will deploy to dev. Please confirm whether you are ok for the Dev deployment. @mathumala.nachiappan@penske.com | Gayam | 01/27/23 8:01 PM
| @praneeth.gayam@penske.com We should be good with the Dev deployment of this application. Please share the Bamboo plan details once it is available. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 8:11 PM
| @sreekanth.kancharla@penske.com , Dev deployment is completed. Following is the Bamboo URL. https://bamboo.penske.com/browse/SCSBP-SICSSVCP Please validate dev. Thanks. | Gayam | 02/04/23 12:36 AM
| @praneeth.gayam@penske.com Seems we need to access to the new bamboo plans. Please grant the access. | Sreekanth | 02/04/23 3:49 AM
| @sreekanth.kancharla@penske.com , You need to be added to one of the admin RBAC group. I sent an email to admin group few days back whom to be added to the different groups. Waiting fthe response. | Gayam | 02/06/23 11:49 PM
Row 21 | @rafiq.melath@penske.com / @kalrav.khamar@penske.com , Log4j team completed log4j and maven changes. Could you please review them in below PR and merge. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/sics-service/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/17/22 3:05 AM
Row 22 | App deployed to PROD on 09/19/2023 | Sreekanth | 09/20/23 6:24 PM
Row 22 | Deployment: @sreekanth.kancharla@penske.com , Dev deployment is completed for this app. Please check. | Gayam | 03/17/23 2:49 AM
| @sreekanth.kancharla@penske.com , Please merge https://bitbucket.penske.com/projects/ITFIS/repos/wje-web/pull-requests/5/diff#pom.xml The changes are for making log4j2 scope to compile. Thank you. | Gayam | 05/30/23 8:58 AM
| @praneeth.gayam@penske.com Merge completed. | Sreekanth | 06/01/23 12:09 AM
| Thanks @sreekanth.kancharla@penske.com . Build is already completed | Gayam | 06/01/23 10:44 PM
Row 22 | Review: @sreekanth.kancharla@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ITFIS/repos/wje-web/pull-requests/3/overview | Gayam | 03/09/23 1:19 AM
| @praneeth.gayam@penske.com PR is merged. Please proceed with further steps. | Sreekanth | 03/13/23 10:19 PM
| Thanks @sreekanth.kancharla@penske.com . We will onboard the app to Bamboo. | Gayam | 03/13/23 11:03 PM
Row 22 | Secrets: @sreekanth.kancharla@penske.com / @kalrav.khamar@penske.com / @james.minisce@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/24/23 1:57 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/24/23 2:37 AM
| Thanks @sreekanth.kancharla@penske.com . Changing the status to (Cap)Maven | Gayam | 02/25/23 12:19 AM
Row 22 | @sreekanth.kancharla@penske.com , In this app, same db.prop file exist in dev and prod folders under targeted folder but different db.prop file exist for QA. Could you please check and clarify us. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/wje-web/browse?at=develop_log4J | Gayam | 02/14/23 12:44 AM
| @praneeth.gayam@penske.com The difference in QA is not required as the hard coded credentials are removed from prod file itself. Please keep the same db.prop for QA as well. Since there is no change between dev & prod specific files and we are going to keep the qa also the same. With this, hope we don't need to maintain this file in targeted folder at all. | Sreekanth | 02/15/23 3:03 AM
| @praneeth.gayam@penske.com Sreekanth has replied to you. Can you change the 'App Status'? | Kalrav | 02/18/23 12:43 AM
| Thanks @kalrav.khamar@penske.com . Changing the status (Cap)Log4j | Gayam | 02/18/23 12:59 AM
Row 22 | @sreekanth.kancharla@penske.com Can you address the app logger replacement query? Thank you. | James | 12/15/22 2:19 AM
| @sreekanth.kancharla@penske.com Did you address the app logger replacement question from 12/09? I think this is still outstanding. | James | 01/25/23 2:22 AM
| @james.minisce@penske.com I've replied already on 12/14. No further questions from the team. | Sreekanth | 01/25/23 7:00 AM
Row 22 | @james.minisce@penske.com - errors on fileappender configuration. @praneeth.gayam@penske.com to follow up | Mathumala Nachiappan | 12/01/22 8:47 PM
| Please be specific as to what you need from me to remove this block. | James | 12/09/22 5:52 PM
| @james.minisce@penske.com , in this app, logger classes are getting created with custom configuration using fileappender(getallappender) and simplelayout . Not able to configure using the slf4j and log4j2. providing link for class file. https://svn.penske.com/svn/webprojects/admin/wje/trunk/wje_prod/JavaSource/com/penske/ebus/journal/filter/DummySecurityFilter.java Could you please check whether these logger classes can be replaced. As we don't have enough info of athe application we can't modify other than what requested. @mathumala.nachiappan@penske.com | Gayam | 12/10/22 12:45 AM
| @praneeth.gayam@penske.com DummySecurityFilter.java is used only for DEV application. I do see in other class files also, the custom logger is implemented. This application is very old application. If these can be replaced with slf4j & log4j2, we are good. Please proceed with changes. | Sreekanth | 12/15/22 3:18 AM
Row 22 | Changed Status | Yvette Urso | 12/15/22 2:19 AM
Row 25 | Per Rafiq on 11/18/22 - Obsolete. There are other sics war/batch active | Yvette Urso | 11/19/22 12:50 AM
Row 86 | This app is completely done with all steps of modernization. | David Graf | 03/21/23 5:43 AM
Row 86 | Looks like RBAC is in place and working. I am moving this to complete. The next deploy of this app will have version 2.0.0 to signify it is modernized. | David Graf | 02/18/23 1:53 AM
Row 86 | Today's update is that we figured out the instance issue in the spec so that the jar deploys to var/tmp. Last Bamboo Item to complete is the RBAC groups. Please assign RBAC groups to ebsworker. | David Graf | 02/08/23 11:59 PM
Row 86 | @praneeth.gayam@penske.com Per @david.w.graf@penske.com this was deployed 1/19/23. I believe he may be out of the office so please give him time to complete. | Yvette Urso | 01/24/23 8:19 PM
Row 86 | @david.w.graf@penske.com , Please create a release branch from develop and run the build from release. It will create a production version of the code. Production deploy plan are already ready but till now no log4j projects deployed to production. @mathumala.nachiappan@penske.com / @hugo.scavino@penske.com | Gayam | 12/22/22 10:16 PM
Row 86 | I have merged my changes to develop and tested the Dev and QA deployments. Please confirm that prod deployment is set up correctly so that we can deploy in Jan. Also this Bamboo plan needs role based access. Right now, I have an override for my account which gives me access. @mathumala.nachiappan@penske.com @praneeth.gayam@penske.com | David Graf | 12/21/22 7:14 PM
Row 86 | No Problem @david.w.graf@penske.com . We finished the setup today and. Build and deployment to Dev is done from the bugfix branch. Please check the Bamboo https://bamboo.penske.com/chain/viewChain.action?planKey=ECBP-EBWYP6 Let us know if you need any other information. Thanks. @mathumala.nachiappan@penske.com | Gayam | 12/16/22 11:31 PM
| @praneeth.gayam@penske.com I don't have access. Link is Access Denied message | David Graf | 12/17/22 12:56 AM
Row 86 | I created a branch with the pom changes to use the suggested group id and properties. Please update the bamboo plan from template; effectively removing the manual changes. Let me know once done and I will test it out. | David Graf | 12/14/22 8:45 PM
| Sure @dave.graff@penske.com . We will let you know once build and deployment completes. @mathumala.nachiappan@penske.com | Gayam | 12/14/22 10:56 PM
| The branch is the following: https://bitbucket.penske.com/projects/ARPROJ/repos/ebsworker/browse?at=refs%2Fheads%2Fbugfix%2Fdwg-confirm-to-issue | David Graf | 12/15/22 10:36 PM
| @praneeth.gayam@penske.com I noticed in the last message that you annotated a david graff whom is not me. Please use David W Graf. my email address is david.w.graf@penske.com Sorry for the confusion. Is there any update on this request? | David Graf | 12/16/22 8:50 PM
Row 86 | @david.w.graf@penske.com - Soon will resolve the deployment issue | Mathumala Nachiappan | 12/06/22 7:55 PM
Row 86 | is there any update on the bamboo build plan from spec that was requested for this app? | David Graf | 12/02/22 2:07 AM
Row 86 | EBS worker is in QA with slf4j and log4j2. Because it is on the IFS we can deploy to production and plan to with the current changes on 11/29. | David Graf | 11/17/22 1:45 AM
Row 87 | @praneeth.gayam@penske.com merged the MR | Mahipal | 05/16/23 7:53 PM
| @mahipal.podduturi@penske.com , We will let you know once we onabord develop branch to bamboo and build it. | Gayam | 05/17/23 3:24 AM
| Onboarding develop branch to bamboo is done and build is completed. Please deploy to QA. | Gayam | 05/18/23 1:00 AM
Row 87 | @sherin.basheer@penske.com alreday tested this application good move completed status | Mahipal | 05/09/23 8:06 PM
| @mahipal.podduturi@penske.com , MR is still in open status. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelrecpt-batch/pull-requests/8/overview Could you please merge. Then we will onboard develop branch to Bamboo. | Gayam | 05/09/23 10:38 PM
Row 87 | @praneeth.gayam@penske.com can you deploy this app as well in QA | Mahipal | 05/04/23 6:34 PM
| @mahipal.podduturi@penske.com we will update the main class in pom and will let you know. | Gayam | 05/05/23 6:28 AM
| @mahipal.podduturi@penske.com , Changed the pom file and committed to develop_log4j branch. we are not supposed to do the QA deployment. Only AO needs to do the QA deployment. Please build and do the deployment from develop_log4j branch which is already onbaorded in bamboo. thanks. | Gayam | 05/06/23 2:53 AM
Row 87 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:30 AM
Row 87 | I think the error above also applies to the issue with dlinkappremoval - please verify that the main class is being set by the bamboo plan in the manifest file | William | 12/23/22 11:07 PM
Row 87 | This batch is not running properly in QA. The message in the logs says "2022-11-04 10:00:43,195 FATAL (BatchMain.java:main():75) - There was an unhandled exception java.lang.IllegalArgumentException: The batch jar main class property [batch-jar-main-class] was not set. at com.penske.architecture.batchframework.config.PropertiesConfigurator.loadConfiguration(PropertiesConfigurator.java:48) at com.penske.architecture.batchframework.launcher.Launcher.<init>(Launcher.java:51) at com.penske.architecture.batchframework.BatchMain.main(BatchMain.java:71) | William | 12/23/22 11:07 PM
Row 87 | @mathumala.nachiappan@penske.com assuming you are done with everything and ready to handoff for AO to final test - I moved it to AO Final Testing. @shane.myers@penske.com Please work with Mathu on what is needed to complete this app. Thank you | Yvette Urso | 12/09/22 12:50 AM
Row 87 | @yvette.urso@penske.com - This App is available for testing in QA. Pls. suggest the status | Mathumala Nachiappan | 11/23/22 3:30 AM
Row 87 | @sherin.basheer@penske.com - QA Deployment done on 13th Nov. | Mathumala Nachiappan | 11/23/22 3:29 AM
Row 88 | Maven log4j changes were deployed to production. | Sherin | 06/20/23 11:53 PM
Row 88 | Application threw new error: The was an error: org.springframework.beans.factory.BeanInitializationException: Could not load properties; nested exception is java.io.FileNotFoundException: class path resource [conf/fuelreceiptbatch.properties] cannot be opened because it does not exist Properties file and mappers were inside conf folder pre-mavenizing. Moving them to conf folder should fix this issue. | Sherin | 03/02/23 3:20 AM
Row 88 | App threw start up error 2022-12-16 23:57:18,272 FATAL (BatchMain.java:main():75) - There was an unhandled exception java.lang.IllegalArgumentException: The batch jar main class property [batch-jar-main-class] was not set. at com.penske.architecture.batchframework.config.PropertiesConfigurator.loadConfiguration(PropertiesConfigurator.java:48) This was fixed by adding fuelrecpt-qa.prop file and including *.prop in bin.xml file | Sherin | 03/02/23 3:18 AM
Row 88 | @yvette.urso@penske.com - Repeated entry of #37. Pls. remove this | Mathumala Nachiappan | 11/23/22 3:59 AM
Row 89 | Maven/log4j changes are moved to production | Sherin | 06/23/23 8:11 PM
Row 89 | it is moved to QA and test was successful | Sherin | 06/20/23 11:20 PM
Row 89 | Yes, we have removed the dependency and app is deployed to qa and running. | Sherin | 04/12/23 1:22 AM
| Thanks @sherin.basheer@penske.com . Changed the app status to QA Test | Gayam | 04/13/23 12:41 AM
| @sherin.basheer@penske.com , we changed the scope of log4j2 jars to compile. Could you please deploy these changes to QA and test. Thanks. | Gayam | 06/03/23 12:49 AM
Row 89 | Thanks @sherin.basheer@penske.com . We will check and get back to you | Gayam | 04/04/23 11:11 PM
| @sherin.basheer@penske.com , without spring-ldap-resource jar also build is getting successful. So can we remove that dependency from the pom? | Gayam | 04/06/23 11:58 PM
Row 89 | Here is the transitive dependency error:The POM for com.penske.mis.common.customlib:spring-ldap-resource:jar:1.0.0 is invalid, transitive dependencies (if any) will not be available, enable debug logging for more details [INFO] | Sherin | 04/04/23 1:46 AM
Row 89 | reference : https://bitbucket.penske.com/projects/ARPROJ/repos/vdrfilebatch/browse/pom.xml?at=refs%2Fheads%2Fdevelop_log4j | Sherin | 04/04/23 1:44 AM
Row 89 | Not properties file, this was missing in pom file<plugin> <groupId>org.apache.maven.plugins</groupId> <artifactId>maven-jar-plugin</artifactId> <version>2.4</version> <configuration> <archive> <manifest> <addDefaultImplementationEntries>true</addDefaultImplementationEntries> <addDefaultSpecificationEntries>true</addDefaultSpecificationEntries> <addClasspath>true</addClasspath> <mainClass>com.penske.filetransferbatch.main.FileTransferBatchMain</mainClass> <classpathPrefix>lib/</classpathPrefix> </manifest> </archive> </configuration> </plugin> | Sherin | 04/04/23 1:43 AM
Row 89 | There are 2 issues in pom file. 1.manifest section where you mention main class is missing. 2) maven build throws transitive dependency on <artifactId>spring-ldap-resource</artifactId> | Sherin | 03/31/23 7:42 PM
| @sherin.basheer@penske.com , are you referring about .prop file which has a propeorty to point to main class? If so, we did not see this kind of file in original code of this app. Could you please provide the error which throws transitive dependency. | Gayam | 04/04/23 12:00 AM
Row 89 | @sherin.basheer@penske.com , This is onboarded to Bamboo. https://bamboo.penske.com/browse/LDAPISMGERBP-LDAPISMR1 But build is failing on develop branch because log4j/maven changes are not yet merged. Could you please merge if you satisfy the changes. Thanks. https://bitbucket.penske.com/projects/AR-SEC/repos/ldapismgr-batch/pull-requests/7/overview | Gayam | 03/29/23 12:56 AM
Row 89 | @praneeth.gayam@penske.com Please create bamboo plan if it has not been created yet. | Sherin | 03/23/23 1:05 AM
Row 89 | @sivagamasundari.suresh@penske.com is working on this app. | Sherin | 03/10/23 9:28 PM
Row 89 | @sherin.basheer@penske.com - This app is available for AO Review | Mathumala Nachiappan | 11/23/22 3:38 AM
| @sherin.basheer@penske.com , Following is the PR for your review https://bitbucket.penske.com/projects/AR-SEC/repos/ldapismgr-batch/pull-requests/7/overview | Gayam | 02/16/23 2:04 AM
Row 90 | Confirmed. This JAR is at its end. It will not be modernized and is now available in artifactory if there are any dependencies. | Hugo Scavino | 04/15/23 1:36 AM
Row 90 | After further review, please add this JAR to artifactory. This JAR will not be modernized. Take JAR from here https://svn.penske.com/svn/webprojects/admin/pops/trunk/pops/WebContent/WEB-INF/lib/ group id: com.penske.architecture artifact id: penske-secure-logger version: 1.0.0 Do not add the number as the name in the artifact ID Thank You | Hugo Scavino | 02/10/23 9:45 PM
| Thanks @hugo.scavino@penske.com . We will upload and will let you know. | Gayam | 02/10/23 11:33 PM
| @hugo.scavino@penske.com , penske-secure-logger-1.0.0.jar is uploaded into artifactory <dependency> <groupId>com.penske.architecture</groupId> <artifactId>penske-secure-logger</artifactId> <version>1.0.0</version> </dependency> | Gayam | 02/13/23 11:41 PM
Row 90 | I will review on Friday Feb 10 | Hugo Scavino | 02/10/23 3:51 AM
Row 90 | Moved to AO Log4j Review | Yvette Urso | 12/15/22 2:40 AM
Row 90 | @hugo.scavino@penske.com - popsbatch app is dependent on this jar. Any suggestion on how to proceed that application? CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 3:38 PM
Row 90 | Update from @hugo.scavino@penske.com - this app totally dependent on log4j1 and it is not supposed to be modernized | Mathumala Nachiappan | 12/08/22 10:33 AM
Row 90 | @yvette.urso@penske.com - Original Scope is 'No' for this jar | Mathumala Nachiappan | 11/23/22 4:13 AM
Row 90 | @yvette.urso@penske.com - This is an additional scope. This jar is used in b2busercreation.war and pops_batch. This jar needs modernization before it is used in the above said applications. | Mathumala Nachiappan | 11/23/22 4:13 AM
Row 90 | Need to determine who can work on this application. Missing resource @hugo.scavino@penske.com | Yvette Urso | 11/22/22 2:39 AM
Row 91 | artifactory is confirmed. | Hugo Scavino | 04/15/23 2:39 AM
Row 91 | Secrets - No code changes are required | Hugo Scavino | 02/10/23 9:34 PM
Row 91 | I have deployed to artifactory. This is the JAR's final destination. | Hugo Scavino | 02/10/23 3:49 AM
| Thanks @hugo.scavino@penske.com . Also, please confirm the secrets part also whether the app requires any code changes. | Gayam | 02/10/23 9:27 PM
Row 91 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:28 AM
Row 91 | @hugo.scavino@penske.com - Artifactory upload is done for this jar. Pls. confirm and change to appropriate App Status Jar location in artifactory - https://artifactory.penske.com>artifactory>architecture-mvn-development-local>com>penske>architecture>penskesso>2.0.0-develop-SNAPSHOT>penskesso-2.0.0-develop-20221213.104211-1.jar. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/13/22 5:45 PM
| I have some questions on the "-SNAPSHOT" which was added to the version. I do not think that should be be there for artifacts we expect other teams to use. This is not a problem with WAR and application JARs but shared JARs should not be "SNAPSHOT"s. The CI/CD scripts will not allow a deployment with SNAPSHOT to PROD eventually. Please redeploy without "-SNAPSOT" in the version. <groupId>com.penske.architecture</groupId> <artifactId>penskesso</artifactId> <version>2.0.0-develop-SNAPSHOT</version> | Hugo Scavino | 12/13/22 8:57 PM
| This would be true for all shared JAR's | Hugo Scavino | 12/13/22 8:58 PM
| Hugo scheduled a meeting with Iswarya and raghu on to check whether Bamboo build is going to have multiple options to create the release or snapshot versions and other build questions. | Gayam | 12/14/22 12:31 AM
Row 91 | @hugo.scavino@penske.com - - This app is available for your final review. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/02/22 5:47 PM
Row 91 | Uploading to Artifactory is in Progress | Mathumala Nachiappan | 11/23/22 4:10 AM
Row 92 | @yvette.urso@penske.com the modernization for this JAR is complete. One for your status report. | Hugo Scavino | 01/26/23 8:34 PM
Row 92 | We confirmed there are no secrets. Also we decided not to modernize this application and instead leave the source code in bitbucket and the binary in artifactory. No Bamboo will be created. No addiational work or bug fixes are ever intended. | Hugo Scavino | 01/25/23 10:46 PM
Row 92 | @praneeth.gayam@penske.com Most likely Secrets are False Postives | Yvette Urso | 01/25/23 12:44 AM
Row 92 | @praneeth.gayam@penske.com per @shane.myers@penske.com and @hugo.scavino@penske.com - Would like to move this to Bitbucket but not upgrade Maven | Yvette Urso | 01/25/23 12:43 AM
Row 92 | This is deprecated, but is being used so must be upgraded | Yvette Urso | 01/25/23 12:38 AM
Row 92 | @hugo.scavino@penske.com , One more question for this app. There is no existing bamboo build for this app. So under which project we need to create bamboo specs for this app. | Gayam | 01/11/23 9:23 AM
| So this should be under architecture and its own project for ptldao. There does seem some clients still using this package | Hugo Scavino | 01/19/23 3:42 AM
Row 92 | @hugo.scavino@penske.com ,Secret scanning and analysis are completed and found that true positives exist. We will send the sheet in email. Please check. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/10/23 12:24 AM
Row 93 | @praneeth.gayam@penske.com this application moved to the bitbucket looks good me . you can keep in your list it is done . we are not deploying this application . | Mahipal | 05/16/23 11:58 PM
| Sure @mahipal.podduturi@penske.com . I changed to Done status as there is no deployment. | Gayam | 05/17/23 1:58 AM
Row 93 | @praneeth.gayam@penske.com please point to new bitbucket url | Mahipal | 04/06/23 2:08 AM
| https://bitbucket.penske.com/projects/ARPROJ/repos/queryrunner-batch/browse | Gayam | 04/06/23 2:43 AM
Row 93 | @ yes can point that | Mahipal | 04/06/23 2:07 AM
Row 93 | @shane.myers@penske.com / @mahipal.podduturi@penske.com , Do you want us to point out the old Bamboo builds to new bitbucket URL? | Gayam | 04/03/23 9:44 PM
Row 93 | @praneeth.gayam@penske.com can you work on next steps | Mahipal | 04/03/23 9:41 PM
Row 93 | bitbucket looks good. @praneeth.gayam@penske.com @yvette.urso@penske.com should I just change the status to 6.3 AO app deployed - DONE? Not sure if that is the right step and don't want to mess up your process. | William | 03/01/23 2:44 AM
Row 93 | @praneeth.gayam@penske.com @mathumala.nachiappan@penske.com I discussed this app with Don - please simply move to bitbucket. No other steps needed at this time. | William | 02/08/23 7:12 PM
| In that case, we just need to do following things for this app. 1. SVN to BB migration of production branch 2. Change the Bamboo build to point to bitbucket @shane.myers@penske.com / @hugo.scavino@penske.com , Correct me if you think any other tasks we need to do for this app. @mathumala.nachiappan@penske.com , @haribabu.challa@penske.com | Gayam | 02/09/23 12:05 AM
| That is correct, please just migrate to bitbucket and we can consider this complete. | William | 02/10/23 10:31 PM
| @shane.myers@penske.com , queryrunner project is migrated to bitbucket. Following is the bitbucket URL https://bitbucket.penske.com/projects/ARPROJ/repos/queryrunner-batch/browse Changed the status to '(AO)Bitbucket Review' Could you please check and push the status to final stage as there is no further work on this project. | Gayam | 02/23/23 12:23 AM
Row 93 | @praneeth.gayam@penske.com - Pls. confirm the modernization steps required for this application? | Mathumala Nachiappan | 02/08/23 11:03 AM
Row 93 | @praneeth.gayam@penske.com per @shane.myers@penske.com - Would like to move this to Bitbucket but not upgrade Maven | Yvette Urso | 01/25/23 12:42 AM
Row 94 | @praneeth.gayam@penske.com tested working as excepted you can close this | Mahipal | 04/06/23 2:07 AM
| @mahipal.podduturi@penske.com , I believe it will be closed only after prod deployment and AO is the owner to close it. And I think you tested in Dev environment only. It needs to be deployed to QA by AO and test over there. | Gayam | 04/06/23 2:40 AM
Row 94 | @praneeth.gayam@penske.com can you create the conf folder under resources folder and move db.porp | Mahipal | 04/03/23 9:59 PM
| @mahipal.podduturi@penske.com , It is done. Please check the develop branch. Thanks. | Gayam | 04/04/23 11:26 PM
Row 94 | I am doing testing it is not loading the database properties. | Mahipal | 03/31/23 6:40 PM
Row 94 | @mathumala.nachiappan@penske.com Please choose the appropriate bucket and specify what you are wanting @shane.myers@penske.com to do. Thank you | Yvette Urso | 12/09/22 12:53 AM
| Sure @yvette.urso@penske.com . Thought App Owner can understand the activity after deployment and change to their appropriate status once they start working on it. As the deployment is done long back, CAP is waiting for the confirmation on the changes | Mathumala Nachiappan | 12/12/22 4:41 PM
Row 94 | @shane - QA Deployment done on 14th Nov | Mathumala Nachiappan | 11/23/22 3:43 AM
Row 95 | @sivagamasundari.suresh@penske.com deployed this app to production on 9/26/2023. This app is complete. | David Graf | 09/27/23 5:17 PM
| Thanks @david.w.graf@penske.com | Gayam | 09/28/23 12:49 AM
Row 95 | @praneeth.gayam@penske.com Hi Praneeth, I deployed release branch to QA. "Release-Ess-38-modernization". Same issue as before, Project compilation error or so. Though logs say "Success", .war file is not deployed to var/tmp Here is the link for logs: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151200584 Please take a look at this. Thanks! | Sivagamasundari Suresh | 08/29/23 7:06 PM
| @sivagamasundari.suresh@penske.com , As discussed we will check and update you. | Gayam | 08/29/23 11:14 PM
| @sivagamasundari.suresh@penske.com , As discussed in the teams, war file is moving to var/tmp and further getting deployed to targeted location. I believe there may be timing issue when you are checking. Thanks. | Gayam | 08/30/23 6:29 PM
Row 95 | @praneeth.gayam@penske.com Please provide an update on this Bamboo plan issue for sessionmgmtsvc. Here is the logs link again: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151198753 Thanks! | Sivagamasundari Suresh | 08/22/23 7:38 PM
| @sivagamasundari.suresh@penske.com , Team is checking on this issue. We will update as soon as we fix the issue. | Gayam | 08/22/23 9:05 PM
| @sivagamasundari.suresh@penske.com , My team resolved the issue and deployed to QA var/tmp location successfully. Could you please verify. | Gayam | 08/22/23 11:37 PM
| @praneeth.gayam@penske.com It deployed and I validated the logging changes. Looks good!!. Thanks so much!! | Sivagamasundari Suresh | 08/26/23 12:55 AM
| @sivagamasundari.suresh@penske.com , Thanks for the update. When are you planning to move this to production? | Gayam | 08/26/23 1:06 AM
| @praneeth.gayam@penske.com Hi Praneeth, There are few minor changes that needs to be reviewed by David. After approval, these changes can be pushed to QA and Tested. I will update here once it is done!. Thanks! | Sivagamasundari Suresh | 08/26/23 1:19 AM
Row 95 | @praneeth.gayam@penske.com , I attempted to deploy the changes in develop -Build #12 release to QA Env, qa_was8_deploy. It was not deployed...logs show that there are JTest issues in Deploy plan. (Compilation errors or so) Here is the link for the logs: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151198753 Please check this and let me know | Sivagamasundari Suresh | 08/21/23 8:59 PM
| @sivagamasundari.suresh@penske.com , If there are test case failures please fix them. Hope that resolves your issue. Thanks. | Gayam | 08/21/23 10:04 PM
| @praneeth.gayam@penske.com Please look at this again. JTest is not a unit test, it is the dtp static analysis process. If it isn't running as part of the build then there is something missing in the build plan. The other issue is that the artifact was not delivered to the var/tmp directory. The deploy was not successful, the build shows green but it is not telling the truth. | David Graf | 08/21/23 11:07 PM
Row 95 | @praneeth.gayam@penske.com , I tested the application in DEV and checked the logs. In Develop branch, committed a small change in "Timestamp pattern" - pattern layout in log4j2.xml file. and merged the changes that created Build #3. I tried to deploy the release for this Build #3 to DEV env. This caused an error. dev_was8_deploy failed. Please find the screen shot as .png image | Sivagamasundari Suresh | 07/27/23 7:43 PM
| Sure @sivagamasundari.suresh@penske.com . We will check and get back to you. | Gayam | 07/27/23 10:46 PM
| @sivagamasundari.suresh@penske.com , Deployment issue is resolved. Please check. | Gayam | 08/01/23 12:40 AM
| Thank you!. I checked it and though the dev deployment was success, I was not able to find the deployed .war in the DEV server. I searched through folders (WInSCP). Reached out to @raghuramredd.thummalapalli@penske.com . It is resolved now. I could view changes in the logs of sessionmgmtsvc app. | Sivagamasundari Suresh | 08/04/23 9:56 PM
| Thanks @sivagamasundari.suresh@penske.com | Gayam | 08/08/23 1:03 AM
Row 95 | Develop Branch Repaired : Thank you for letting my know. I repaired the branch and Bamboo plan now runs. Also this is an API so there are no front end resources so there is no tgz required. | Hugo Scavino | 02/10/23 11:03 PM
| @hugo.scavino@penske.com , dev deployment is completed for this app. Could you please verify. Thanks. | Gayam | 03/28/23 12:35 AM
Row 95 | Bamboo: Please create a secure bamboo plan for this application. No secrets issues. All mavenized | Hugo Scavino | 02/09/23 2:50 AM
| @hugo.scavino@penske.com , There is no parent declaration in pom and bin.xml is not defined. Do you want us to take care of thise? Also, jtests are getting failed. | Gayam | 02/10/23 10:38 PM
Row 95 | @mathumala.nachiappan@penske.com @hugo.scavino@penske.com This is not blocked. Changed status to Secrets Scanning | Yvette Urso | 12/09/22 12:54 AM
Row 95 | @hugo.scavino@penske.com - Secret scanning resulted with True positives. But the respective statements are not available in the current code. For your secret analysis once. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 7:33 PM
Row 95 | @yvette.urso@penske.com - There are other related testing activities by Brad from webservices team. @hugo.scavino@penske.com to confirm to move to QA | Mathumala Nachiappan | 12/02/22 5:22 PM
Row 95 | @mathumala.nachiappan@penske.com Can you update where this is in the process? ie.. what has been complete and what is pending. | Yvette Urso | 11/30/22 12:34 AM
Row 95 | Update from Hugo - This app is available in Dev. @hugo.scavino@penske.com will move to QA | Mathumala Nachiappan | 11/23/22 3:45 AM
Row 96 | User Lookup deployed on 9/28 to production. Thank you for your support. | David Graf | 09/29/23 11:29 PM
| Thanks for the update @david.w.graf@penske.com | Gayam | 10/05/23 1:26 AM
Row 96 | I attempted the Prod deployment in bamboo which was a success. Changing status. | David Graf | 07/05/23 10:54 PM
Row 96 | if maven hasn't already been signed off on. This message is sign off for maven. | David Graf | 06/30/23 6:59 PM
Row 96 | Soon, I will attempt to run Prod deployment. This will complete the bamboo testing. | David Graf | 06/30/23 6:58 PM
Row 96 | confirmed, looks good; thanks | David Graf | 06/30/23 6:56 PM
Row 96 | We deployed to QA without issue continuing testing to run Prod deploy, but first can you clean up the two deployments? I see two: userlookup-svc-deploy userlookup-web-deploy | David Graf | 06/28/23 7:31 PM
| Sure @david.w.graf@penske.com . we will remove userlookup-web-deploy | Gayam | 06/29/23 2:35 AM
| @david.w.graf@penske.com , Deleted userlookup-web-deploy. | Gayam | 06/30/23 1:23 AM
Row 96 | @praneeth.gayam@penske.com another thing that we might have to check is the deploy pattern that it is using. If it was originally set up was a web deploy then that could be the reason that it is including a tgz with the war. The Web Services scripts only expects the war and so far the tgz has been left in the var/tmp directory each time we build. My suggestion is to have the deploy use a service implementation instead of web deploy implementation which should only deliver the war to var/tmp. | David Graf | 06/14/23 7:34 PM
| @david.w.graf@penske.com , For web applications, the tgz file contains only static content and it should be copied to the location /opt/webcontent/<instance>/<app>/. Is there anything different for this application? | Gayam | 06/15/23 12:43 AM
| this is not a web application. It is a service (svc) that deploys on wsv which has no need for static content. | David Graf | 06/16/23 4:38 PM
| Sure @david.w.graf@penske.com . We will fix the issue and will deploy the war to /var/tmp. | Gayam | 06/16/23 10:16 PM
| @david.w.graf@penske.com , WE removed the assembly configuration which generates the tgz file with static content. Please check the changes in below PR. https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-svc/pull-requests/5/overview | Gayam | 06/19/23 7:36 PM
Row 96 | @praneeth.gayam@penske.com The bamboo build plan is incorrectly labeled as userlookup-web but it should be userlookup-svc. I think @ankita.tiwary@penske.com created a footprint ticket that requests the same. Please let us know when the bamboo is fixed to have svc. | David Graf | 06/12/23 7:56 PM
| Sure @david.w.graf@penske.com . We will work on it. | Gayam | 06/13/23 1:28 AM
| @david.w.graf@penske.com , We changed the build plan name to userlookup-svc. https://bamboo.penske.com/browse/ULSBP-USELO/ Do you want us to change the deploy plan name too? | Gayam | 06/14/23 3:48 AM
| yes, please change the deploy name too. And can you link to the spec and template for this app in Bitbucket? so that I may confirm | David Graf | 06/14/23 5:12 PM
| @david.w.graf@penske.com , Deploy name changed to userlookup-svc-deploy. Please deploy to dev and qa. We will delete old deploy plan once you confirm the new deploy plans. | Gayam | 06/16/23 2:52 AM
Row 96 | we overcame an issue with logging this morning and hope to continue with dev deployment soon. | David Graf | 06/12/23 7:54 PM
Row 96 | @david.w.graf@penske.com , We did complete the mavanization on this app. But Hugo took over to add the unit tests. Latest code is in the branch https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-web/commits?until=refs%2Fheads%2Fdevelop_log4j&merges=include Bamboo plan is https://bamboo.penske.com/browse/ULSBP-USELO/ Please let us know if you are looking for any other info. Thanks | Gayam | 04/21/23 1:32 AM
Row 96 | looks like even web-inf is in svn. So during modernization it may not be needed because maven may create those directories from scratch. | David Graf | 04/20/23 6:46 PM
Row 96 | Hugo provided SVN location: https://svn.penske.com/svn/architecture/general/userlookup/branches/dev_gh/ | David Graf | 04/20/23 6:45 PM
Row 96 | shouldn't this bitbucket be userlookup-svc? https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-web/browse the app does not have a front end and is deployed to wsv instance. I'm not sure it needs a web-inf directory either. Where is the SVN archive location to refer to? | David Graf | 04/20/23 6:30 PM
Row 96 | @hugo.scavino@penske.com @sherin.basheer@penske.com We are tasking Ankita with this modernization work. Please let me know if you have any issues with that. @praneeth.gayam@penske.com let us know where this left off | David Graf | 04/20/23 5:28 PM
Row 96 | @hugo.scavino@penske.com , userlookup - build & Deploy plan onboarding completed and Dev deployment done. Please verify. https://bamboo.penske.com/browse/ULSBP-USELO/ | Gayam | 04/04/23 11:14 PM
Row 96 | Sure @hugo.scavino@penske.com . Can you also verify the secrets which we sent earlier and let us know whether any code changes required. Thanks. | Gayam | 02/10/23 12:56 AM
Row 96 | Bamboo (CAP) - I have completed my peer review and unit tests. Please proceed with the Bamboo build using the develop branch. https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-web/branches | Hugo Scavino | 02/09/23 10:06 PM
Row 96 | I will review project. It requires a new unit and integration test before deploying to DEV https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-web/browse?at=refs%2Fheads%2Fdevelop_log4j | Hugo Scavino | 01/31/23 9:49 PM
Row 96 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:28 AM
Row 96 | @hugo.scavino@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 3:51 AM
Row 97 | Hi Praneeth, verified for production and its looks good and I see that tgz is generating. I will create the FP to remove the old Bamboo plans.Thanks! cc: @david.w.graf@penske.com | Sama | 10/18/23 12:27 AM
Row 97 | Hi @praneeth.gayam@penske.com we are confirming that QA and QA2 is working fine. Please continue the change the instance name of production.Thanks! cc: @david.w.graf@penske.com | Sama | 10/16/23 8:32 PM
| Sure @bhagya.sama@penske.com | Gayam | 10/17/23 1:03 AM
| @bhagya.sama@penske.com , Prod plan instance value changed to external. | Gayam | 10/17/23 11:48 PM
Row 97 | @praneeth.gayam@penske.com I am checking on clex150ptlge(batch) server. | Sama | 10/06/23 8:06 PM
| @bhagya.sama@penske.com , What I know is above server is for batch apps. But usermgmt is a web app. | Gayam | 10/10/23 12:10 AM
| all artifacts are deployed to var/tmp on the batch server. I think that is what Laxmi is saying. | David Graf | 10/10/23 7:51 PM
| @david.w.graf@penske.com , this is a war application and tgz supposed to be pushed to apache server and war supposed to be deployed to QA was servers. Let us check on this and get back to you. | Gayam | 10/11/23 1:05 AM
| What you are describing is the step performed by Web Services to deploy the WAR into WebSphere. We are testing that the WAR and TGZ is available in the var/tmp and webcontent directory. And Laxmi and I have not seen the TGZ on the server with the recent build for QA2. Our test is to confirm the artifacts are available for the Web Services scripts. | David Graf | 10/11/23 5:26 PM
| @david.w.graf@penske.com / @bhagya.sama@penske.com , Instance name of QA and QA2 plans mentioned as internal. That was the reason it is not working. Now it is changed to 'external' and QA2 deployment is working fine. usermgmt2.tgz is deployed to /opt/webcontent/external/ location. Once you comfirm, we will change the instance name of production plan to 'external'. Thanks. | Gayam | 10/13/23 9:08 AM
Row 97 | @praneeth.gayam@penske.com I try deploying to QA2 and see that war file generating with out any issues but I don't see the tgz file under /opt/webcontent/external/usermgmt2. Can you please check on this? cc: @david.w.graf@penske.com | Sama | 10/05/23 10:56 PM
| @bhagya.sama@penske.com , Please let us know on which server you are checking. | Gayam | 10/06/23 12:54 AM
Row 97 | Still confirming if we can deploy to QA2 and Prod from the new Bamboo plan. | David Graf | 09/27/23 1:32 AM
| @david.w.graf@penske.com , We have modified the QA2 plan. Please check it. https://bamboo.penske.com/deploy/viewEnvironment.action?id=151912535 | Gayam | 09/28/23 12:59 AM
| I see that the variables for QA and QA2 do not match. The variables for QA2 seem to match Prod. Please confirm this is correct before we attempt to deploy. | David Graf | 10/02/23 11:40 PM
| @david.w.graf@penske.com , CICD team fixed the QA2 variables. COuld you please check now. | Gayam | 10/04/23 1:53 AM
Row 97 | I see the plan but running into issues with the intial deployment: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=147554384 | David Graf | 07/07/23 4:56 PM
| @david.w.graf@penske.com , We will check and get back to you. | Gayam | 07/10/23 11:29 PM
| @david.w.graf@penske.com issue is resolved. Please check. instancetype was missing initally. | Gayam | 07/12/23 1:44 AM
Row 97 | @praneeth.gayam@penske.com Please add a third deployment for QA 2 which will deploy an artifacts called usermgmt2.war and usermgmt2.tgz. | David Graf | 06/30/23 9:20 PM
| @david.w.graf@penske.com , I am not sure about the ask here. Build needs to be environment agnostic..right? One build and same war/tgz needs to be deployed to all environments. Could you please let me know whether I am missing anything. | Gayam | 07/01/23 1:34 AM
| it is the same agnostic artifact, the name of the artifact needs to change to usermgmt2 so that the QA server can host it using the usermgmt2 scripts. | David Graf | 07/03/23 4:39 PM
| I see there was an attempt to create a branch which alters the pom. I don't think that is the best way to proceed. The pom will support prod by default so it should be usermgmt. For usermgmt2, there should be a bamboo tasked added after the jar was pulled from artifactory which renames it with a 2 at the end (ex: usermgmt2) | David Graf | 07/05/23 7:30 PM
| @david.w.graf@penske.com , That is what I suggested to team. CICD team is looking into this. | Gayam | 07/06/23 3:11 AM
| @david.w.graf@penske.com , We have created another deploy plan 'qa2_was8-deploy' to satisfy the given requirement. Please check. Thanks. https://bamboo.penske.com/browse/USRMGMT-UMGMT/deployments | Gayam | 07/07/23 1:36 AM
Row 97 | @praneeth.gayam@penske.com Here are some details: User Management has the following Deployments: QA, QA2, Prod There is no DEV and QA2 deploys to the sam location as QA but the artifact is called usermgmt2.war. Currently the user-management build plan has two deployments and that should be fixed to only be one: https://bamboo.penske.com/browse/USRMGMT-UMGMT/deployments | David Graf | 06/29/23 1:30 AM
| @david.w.graf@penske.com We will delete the usermgmt-deploy plan and retain the user-management-deploy plan that has a matching name with the bitbucket project. | Gayam | 06/30/23 12:46 AM
| confirmed, looks good. Thanks. | David Graf | 06/30/23 6:57 PM
Row 97 | @praneeth.gayam@penske.com we have deployed changes succesfully to production on 05/09 so we can close this app. | Sama | 05/17/23 2:04 AM
| Thanks @bhagya.sama@penske.com . Changed the status to Done. | Gayam | 05/17/23 3:12 AM
| @bhagya.sama@penske.com , Do the log4j and maven changes are deployed to production? | Gayam | 06/06/23 9:51 AM
| @praneeth.gayam@penske.com log4j and maven changes are in production. However, we had to use the old bamboo build ALL_BUILD plan to deploy. We are starting the Bamboo effort back up. So that it can be completed. | David Graf | 06/29/23 1:15 AM
Row 97 | after that we will have to return to the bamboo plan. @hugo.scavino@penske.com @bhagya.sama@penske.com | David Graf | 04/11/23 12:16 AM
Row 97 | we have a deploy scheduled for 4/18 which contains all of the changes placed in develop_log4j. | David Graf | 04/11/23 12:14 AM
Row 97 | @bhagya.sama@penske.com - QA Deployment done on 16th Nov | Mathumala Nachiappan | 11/23/22 3:53 AM
Row 98 | WRP was successfully deployed last Thursday and the Oracle HR changes completed the deploy testing and signoff. Thanks for everyone's help. CC: @praneeth.gayam@penske.com | David Graf | 08/25/23 6:00 AM
| Thanks @david.w.graf@penske.com for the update. | Gayam | 08/26/23 12:57 AM
Row 98 | This app is scheduled to be deployed on 8/24 and by Friday we should have signoff that the application has completed modernization. | David Graf | 08/23/23 8:17 PM
Row 98 | @praneeth.gayam@penske.com Please ignore last message. I had a mistyped password during the last attempt. Just confirmed that the webrptportal.war is on the var/tmp in prod batch box. It is working. | David Graf | 08/16/23 10:52 PM
Row 98 | @praneeth.gayam@penske.com Still couldn't get the prod build to be successful: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151198338 although maybe it is a different issue. | David Graf | 08/16/23 9:45 PM
Row 98 | We ran into an issue when running the PROD deploy. Please investigate: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151197905 @praneeth.gayam@penske.com | David Graf | 08/12/23 2:18 AM
| @david.w.graf@penske.com , My team analyzed and compared with all other prod builds. They found that the branch which you used to create the snapshot version is missing in the bamboo. That is the reason prod build is failing. They onboarded that branch. Plese check now. Thanks. | Gayam | 08/16/23 6:51 PM
Row 98 | we confirm that QA deploy was successful. | David Graf | 04/06/23 5:21 PM
Row 98 | Confirming that artifact is in Artifactory and then announcing a QA deploy. | David Graf | 03/17/23 5:44 PM
Row 98 | Dev deploy is confirmed with develop_log4j branch | David Graf | 03/17/23 5:23 PM
Row 98 | yes please deploy to dev environment | David Graf | 03/09/23 6:23 PM
Row 98 | Maven and log4j changes have been confirmed. Moving this app to the next step which is Bamboo. | David Graf | 02/28/23 6:29 PM
| Thanks @david.w.graf@penske.com . We will let you know once we onbaord the app to Bamboo | Gayam | 02/28/23 11:45 PM
| @david.w.graf@penske.com , We onboarded the app to Bamboo. https://bamboo.penske.com/browse/WRP-WEBRP Can we deploy to Dev? | Gayam | 03/02/23 2:17 AM
Row 98 | I am assigning Amit, from WRP development team, to start the review. | David Graf | 02/22/23 7:25 PM
Row 98 | @david.w.graf@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:07 AM
Row 102 | Update from the DBA's is that the app will become obsolete around July-August 2023 but it is not confirmed yet. I am moving this app into retired status or whatever is equivalent. We can reevaluate in September. | David Graf | 02/28/23 10:08 PM
Row 102 | I agree. We shouldn't be doing any modernization work on this app as this will be retired soon. | Sherin | 02/28/23 1:10 AM
Row 102 | We just got notice that this app will be retired in the future. We may not want to go forward with modernization. I'll leave it to @sherin.basheer@penske.com to decide. | David Graf | 02/24/23 10:36 PM
Row 102 | Hi @yvette.urso@penske.com - Hope (AO) Final Testing would be correct. Once @sherin.basheer@penske.com is back from her PTO, she can look into this | Mathumala Nachiappan | 12/12/22 4:39 PM
Row 102 | @mathumala.nachiappan@penske.com - What was deployed? I do not think this is blocked. I picked a bucket - please work with @sherin.basheer@penske.com with specifically what you need. | Yvette Urso | 12/09/22 12:52 AM
Row 102 | @sherin.basheer@penske.com - Deployed in QA on 2nd Nov | Mathumala Nachiappan | 11/23/22 3:40 AM
Row 104 | This application has been retired | William | 08/25/23 8:33 PM
Row 104 | @praneeth.gayam@penske.com this application testing completed move this Deploy/Test | Mahipal | 05/17/23 12:00 AM
| @mahipal.podduturi@penske.com , Changed to QA Deploy/Test | Gayam | 05/17/23 1:56 AM
Row 104 | I deployed dev and qa and tested as well | Mahipal | 05/16/23 11:48 PM
Row 104 | I will check and let you know | Mahipal | 04/03/23 9:47 PM
Row 104 | @mahipal.podduturi@penske.com , this app is onboarded to Bamboo. Please review and let us know whether we can deploy to Dev. | Gayam | 03/23/23 11:06 PM
Row 104 | @praneeth.gayam@penske.com i am goof with PR you can star next steps | Mahipal | 03/22/23 9:15 AM
Row 104 | @praneeth.gayam@penske.com looks good to me the POM changes | Mahipal | 03/15/23 6:35 PM
| @mahipal.podduturi@penske.com , If you complete the review, can you merge the code to develop branch . https://bitbucket.penske.com/projects/ARPROJ/repos/shoptalkreg-web/pull-requests/4/overview | Gayam | 03/15/23 10:39 PM
Row 104 | @praneeth.gayam@penske.com updated the comments https://bitbucket.penske.com/projects/ARPROJ/repos/shoptalkreg-web/pull-requests/4/diff#pom.xml | Mahipal | 03/09/23 7:33 PM
| @mahipal.podduturi@penske.com , We have implemented the suggestions mentioned in the comment. Please check. | Gayam | 03/12/23 9:42 PM
Row 104 | @shane.myers@penske.com , Could you please review this app at https://bitbucket.penske.com/projects/ARPROJ/repos/shoptalkreg-web/pull-requests/4/overview | Gayam | 03/07/23 6:35 AM
Row 104 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:31 AM
Row 104 | @shane.myers@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 3:46 AM
Row 105 | This application is no longer needed and no modernization effort is required on this. | Sherin | 04/21/23 12:09 AM
Row 105 | @sherin.basheer@penske.com , There are no secrets found in this app. So we completed log4j/maven work. Please review at https://bitbucket.penske.com/projects/ARPROJ/repos/synchghdbc-batch/pull-requests/3/overview | Gayam | 03/02/23 3:11 AM
Row 105 | production source code is decompiled and checked in to svn. Branch prod should be used for new changes. | Sherin | 02/18/23 12:42 AM
| Thanks @sherin.basheer@penske.com . Changing the status to (Cap)Log4j | Gayam | 02/18/23 1:03 AM
| @sherin.basheer@penske.com , As discussed in the chat, we are are making SqlMapClientCallback empty args and this.val$emplist will be replaced with emplist. Also, we will provide this info in Reamdeme file. Thanks. | Gayam | 02/22/23 3:20 AM
Row 105 | I will get back to you on the question on which branch to work on. | Sherin | 02/14/23 12:47 AM
Row 105 | This application can go under Architecture commons. https://bitbucket.penske.com/projects/ARPROJ. Bamboo plan should match application name. | Sherin | 02/14/23 12:44 AM
Row 105 | @sherin.basheer@penske.com , Unable to find bamboo build plans. Bamboo build plans required for prod reference. Following are the Svn and respective branches info. https://svn.penske.com/svn/architecture/general/synchghdbc/ dev_gh/ offshore_pol/ (This is the Latest branch. Last modifications done in May-6-2014 ) qa/ @mathumala.nachiappan@penske.com | Gayam | 11/26/22 1:59 AM
| @sherin.basheer@penske.com , Adding to above question, as there is no existing bamboo build, under which project we need to create new bamboo specs? | Gayam | 01/11/23 9:25 AM
| Yes application is very old and there is no bamboo plan existing for this. Please create new one. | Sherin | 02/01/23 12:53 AM
| Question: @sherin.basheer@penske.com , We have 2 questions on this application. 1. There is no old bamboo build. So we are not sure what is the latest branch deployed to production. Could you please let us know on what branch we need start working on modernization. 2. For the new build plans in Bamboo, do you want to create a new project. If so please suggest the name. Or do you want us to create under any other Arch project? If so, under which project we need to create? Thanks. @haribabu.challa@penske.com @mathumala.nachiappan@penske.com | Gayam | 02/02/23 11:15 PM
Row 105 | @mathumala.nachiappan@penske.com moved to AO Bamboo Review. | Yvette Urso | 12/15/22 2:38 AM
Row 106 | This application has been retired. | William | 08/25/23 8:33 PM
Row 106 | @praneeth.gayam@penske.com it is already on boarded bambboo now is Faling build as well https://bamboo.penske.com/browse/TLMSBP-TLMS2-BLD-1 | Mahipal | 05/16/23 7:56 PM
| @mahipal.podduturi@penske.com , The PR is not yet merged. That is the reason it is failing. Please review and merge. https://bitbucket.penske.com/projects/ARPROJ/repos/telematicssvc-web/pull-requests/4/overview | Gayam | 05/17/23 2:10 AM
Row 106 | can you do | Mahipal | 05/16/23 7:48 PM
Row 106 | yes | Mahipal | 05/16/23 7:48 PM
Row 106 | @praneeth.gayam@penske.com can you mark this to complete | Mahipal | 05/04/23 7:13 PM
| @mahipal.podduturi@penske.com , Do you mean go to next step which is Bamboo onboarding? | Gayam | 05/05/23 6:15 AM
Row 106 | tested the application working as excepted. | Mahipal | 05/04/23 7:12 PM
Row 106 | @praneeth.gayam@penske.com can you deploy the devlop_log4j branch to dev | Mahipal | 04/03/23 10:02 PM
| @mahipal.podduturi@penske.com , telematicssvc.war - build & Deploy plan onboarding completed and dev deployment done from develop_log4j branch. Please verify. https://bamboo.penske.com/browse/TLMSBP-TLMS/deployments | Gayam | 04/04/23 11:19 PM
Row 106 | PR for this is https://bitbucket.penske.com/projects/ARPROJ/repos/telematicssvc-web/pull-requests/4/overview | Gayam | 04/03/23 9:41 PM
Row 106 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:31 AM
Row 106 | @shane.myers@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 3:50 AM
Row 107 | Confirmed by @sherin.basheer@penske.com | Mathumala Nachiappan | 11/23/22 4:02 AM
Row 112 | Mileage Reporting Web App Successfully deployed tonight 11/14/2023. Signing off. | Hernandez | 11/15/23 9:00 AM
| Thanks for the update @nicolas.hernandez@penske.com | Gayam | 11/15/23 11:45 PM
Row 112 | Completed testing in DEV, QA. Will be preparing plan to deploy on Tuesday, 11/14/2023. | Hernandez | 11/11/23 2:04 AM
Row 112 | @nicolas.hernandez@penske.com / @venkatesh.hossalinever@penske.com , We have onboarded the app to bamboo and dev deployment also completed. https://bamboo.penske.com/browse/WEBPROD-MLGRPTNG0/ | Gayam | 10/20/23 12:20 AM
Row 112 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/mileagereporting-web/pull-requests/3/overview | Gayam | 04/06/23 3:12 AM
Row 112 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/28/23 3:33 AM
| Thanks @venkatesh.hossalinever@penske.com . Changed the status to Cap Maven | Gayam | 02/28/23 11:51 PM
Row 112 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 112 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:55 AM
Row 113 | @praneeth.gayam@penske.com Tested in DEV, and QA. Waiting on Business User Sign-off.. | Hernandez | 11/11/23 2:00 AM
Row 113 | @nicolas.hernandez@penske.com , There is a small update in log4j2.xml. Please check and merge the PR. Thanks. https://bitbucket.penske.com/projects/PBTFUEL/repos/ssptktportal-web/pull-requests/13/overview | Gayam | 10/10/23 1:08 AM
| Merged. Looks Good. | Hernandez | 10/19/23 6:15 PM
| Thanks @nicolas.hernandez@penske.com . We will onboard to bamboo. | Gayam | 10/20/23 12:13 AM
| @nicolas.hernandez@penske.com , Onboarded to bamboo and deployment is completed. Please verify. Thanks. | Gayam | 10/21/23 4:16 AM
Row 113 | issue with code delivered after mavernizing. waiting on architect team to troubleshoot. | Rafiq Melath | 08/15/23 11:46 PM
Row 113 | @praneeth.gayam@penske.com There's an issue with the reuse jar or another dependencies when trying to access the dev application. I Have sent you some screens. | Hernandez | 08/15/23 1:13 AM
| @nicolas.hernandez@penske.com , We can't resolve the application specific run time issues as we don't have any idea about the application. Please let us know whether the application is missing any dependency. Usually, app will throw compilation issues if it misses any required dependencies. Thanks | Gayam | 08/15/23 2:13 AM
Row 113 | @praneeth.gayam@penske.com SSPTKTPORTAL seems to have some misconfiguration when running in DEV server and LOCAL. Could you verify? | Hernandez | 08/14/23 10:38 PM
| @nicolas.hernandez@penske.com , Could you please elaborate the issue. We are seeing the deployment in successful in bamboo. | Gayam | 08/15/23 1:03 AM
Row 113 | @praneeth.gayam@penske.com Can you please deploy suspended ticket portal on Dev | Venkatesh | 08/03/23 2:53 AM
| @venkatesh.hossalinever@penske.com , looks like dev deployment is completed yesterday. Please check. https://bamboo.penske.com/browse/SUSP-SSPT0/deployments | Gayam | 08/04/23 12:57 AM
Row 113 | Web Dev looking good with Log4j & Maven changes. We will proceed with QA deployment and keep you posted. | Nayum | 07/19/23 6:47 PM
Row 113 | @praneeth.gayam@penske.com @venkatesh.hossalinever@penske.com Retrofitted Recent PBT-567 (deployed) Changes to Develop_Log4J branch. I've submitted a pull request to push to develop branch. | Hernandez | 07/10/23 11:45 PM
| @nicolas.hernandez@penske.com , I believe changes are application specific and not related to modernization project. Do you want to deploy your changes and modernization changes to prod together? If yes, please review with your peer. Thanks. | Gayam | 07/11/23 11:37 PM
| @praneeth.gayam@penske.com Yes, we are intending to push the changes from PBT-567 with the modernization changes. | Hernandez | 07/13/23 1:44 AM
| Sure @nicolas.hernandez@penske.com . Please work with your team and merge the PR. | Gayam | 07/13/23 3:07 AM
Row 113 | @shilpaashok.rane@penske.com , Build plan and deploy plan of this app onboarded successfully. Also, deployment to dev is completed. Pelase verify. Thanks. | Gayam | 06/13/23 2:09 AM
Row 113 | Review: @shilpaashok.rane@penske.com This app is ready for AO review. Please check at https://bitbucket.penske.com/projects/ARPROJ/repos/ssptktportal-web/pull-requests/3/overview Thanks. | Gayam | 04/25/23 1:07 AM
| @praneeth.gayam@penske.com Code changes has been merged. Please deploy the application on dev. | Venkatesh | 06/08/23 8:02 PM
| We will onboard to Bamboo and will let you know. | Gayam | 06/09/23 1:38 AM
Row 113 | We have verified the secrets shared in the email, some are key events in jsp and js files. Some of the values used in UI. And they are not secret or confidential info. So no change required. | Rane | 04/10/23 6:06 PM
| Thanks @shilpaashok.rane@penske.com . We will work on the next step. | Gayam | 04/11/23 8:39 AM
Row 113 | Secrets: @dylan.price@penske.com / @william.spohn@penske.com , I have shared the secrets in the email. Please check and confirm. | Gayam | 03/24/23 12:05 AM
Row 113 | the bamboo build for this is https://bamboo.penske.com/browse/SUSP-SUSPPROD and the repo is https://svn.penske.com/svn/webprojects/admin/suspendedticketsportal/trunk/STP_Web | Dylan | 03/07/23 2:05 AM
| Thank you. Changed the app status to Cap Log4j | Gayam | 03/08/23 12:06 AM
Row 113 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 113 | Moved to AO Bamboo status | Yvette Urso | 12/15/22 2:49 AM
Row 113 | Hi @sam.skelding@penske.com - we couldnt trace the Bamboo key and the Repo url for this applicaiton. Pls. share those details. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 12:01 PM
Row 115 | After discussion with my manager, we will sort out the issue on DEV at a later time. We will proceed with PROD deployment once testing is complete in QA. Thanks! | Elliott | 11/09/23 6:22 PM
| @elliott.eames@penske.com , Thanks for the update. | Gayam | 11/10/23 10:51 PM
| @elliott.eames@penske.com , We disabled unit test case task in the bamboo build of this application. Are you in the plan to fix the unit test cases? Then we can enable the respective task in the build. Thank you. | Gayam | 11/15/23 11:53 PM
Row 115 | Changes seem to be working fine on QA. But on DEV it is still not working. I will talk to my team and figure out next steps. | Elliott | 11/07/23 6:19 PM
| Thanks @elliott.eames@penske.com | Gayam | 11/08/23 12:50 AM
Row 115 | @praneeth.gayam@penske.com I am not seeing those 2 jar files in the Develop branch. Your asking me to remove them but the jar files are not present. Also, the log file you attached is for cmsplus not fuel pricing | Elliott | 11/02/23 6:09 PM
| @elliott.eames@penske.com , Sorry. Downloaded and Provided a wrong server file. My team will rerun the develop branch and will get the new log file. It is strange that everything working fine on develop_log4j branch and not for develop branch. Only pom and other code changes are there when we compare both branches. I don't think code changes causing this issue. We believe pom changes are causing this issue. | Gayam | 11/02/23 10:07 PM
| @elliott.eames@penske.com , We extracted the 2 jars from the reuse dependency and deployment is getting successful. Please check and merge. https://bitbucket.penske.com/projects/PBTFUEL/repos/fuelpricing-web/pull-requests/8/overview | Gayam | 11/06/23 9:04 PM
Row 115 | After discussion with Divya Ganesan from web services, fuel-pricing-web is not getting deployed correctly out on the DEV server. Divya mentioned the issue... The bamboo logs is referring to gmt_1 but in the was console it's showing internal_1. Please change gmt_1 to internal_1. I have attached the bamboo log file. | Elliott | 10/31/23 8:11 PM
| @elliott.eames@penske.com , we will check on this issue. Thanks. | Gayam | 11/01/23 1:23 AM
| @elliott.eames@penske.com , develop_log4j branch is working perfectly fine with the deployment but not develop branch which has different dependencies. Develop branch contains 2 dependencies common-dbutils-1.1.jar and log4j-1.2.16 jar. These 2 jars are causing the deployment issues. Please check the attached logs from the server. Please remove those dependencies from develop branch and try. Thanks. | Gayam | 11/02/23 1:30 AM
Row 115 | @revathi.kandasamy@penske.com , This app is ready for your review. Please check. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelpricing-web/pull-requests/3/overview | Gayam | 04/05/23 2:43 AM
| @praneeth.gayam@penske.com Changes looks good and merged to dev branch. please deploy application on dev environment. | Venkatesh | 06/22/23 2:30 AM
| Thanks @venkatesh.hossalinever@penske.com | Gayam | 06/22/23 3:25 AM
| @venkatesh.hossalinever@penske.com , This app is onboarded to bamboo but test cases are failing. Currently, we disabled the test cases. So build got successful an deployed to dev. | Gayam | 06/23/23 11:49 PM
| @revathi.kandasamy@penske.com Can you review and if changes looks good than plan for Dev and QA deployment. | Venkatesh | 08/15/23 8:48 PM
Row 115 | PFA for the issue we get while executing application maven build. Architect team has recommended us to use a different version for below artifacts. <artifactId>security-author-filter</artifactId> <version>2.0.0-develop-20230220.233353-1</version> <artifactId>security-util</artifactId> <version>2.0.0-develop_log4j-20230202.213506-2</version> Kindly update the pom.xml with the above versions | Kandasamy | 03/29/23 6:19 PM
| @revathi.kandasamy@penske.com , Not sure for which app and which branch you are referring to. Log4j team is still working on this app and waiting for the response from AO to the question which we asked above. Question is regarding 'dassupport.jar'. Could you please check and provide your response. | Gayam | 03/29/23 9:02 PM
| I was referring to fuelpricing.war. While checking in local with svn code, dassupport.jar was not required. There was no compilation issue. Pls go ahead with your changes. | Kandasamy | 04/03/23 7:05 PM
Row 115 | @william.spohn@penske.com This app has dependency with 'dassupport.jar' is available. SVN repo is identified for this jar - https://svn.penske.com/svn/architecture/general/das_support/ Bamboo build is not available for this jar. So need confirmation on whether to upload this jar to artifactory or to consider for log4J modernization. If confirmed for Log4J changes, pls. share the reference folder/branch for log4J development. CC: @praneeth.gayam@penske.com , @rafiq.melath@penske.com | Mathumala Nachiappan | 01/10/23 10:54 AM
| @william.spohn@penske.com , Just want to update you, fuelpricing build is getting successful without using dassupport.jar. Do you want us to continue without including dassupport.jar. If not please let us know whether we can upload this jar to artifactory. | Gayam | 02/23/23 12:39 AM
Row 115 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 115 | Secrets Mitigation: @william.spohn@penske.com , Adding to above questions, we have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:44 AM
Row 115 | Let me know when fuelpricing.war is ready to test. | William Spohn | 01/10/23 10:18 PM
| @william.spohn@penske.com , Could you please check above question and provide your response. | Gayam | 01/11/23 8:58 AM
| I will update Venkatesh, then he/his team can assist you. | William Spohn | 01/17/23 7:20 PM
| @william.spohn@penske.com / @venkatesh.hossalinever@penske.com , Could you please provide the response to the question which i asked above. | Gayam | 01/27/23 11:55 PM
Row 132 | Flexbilling Web App Successfully deployed tonight 11/14/2023. Signing off. | Hernandez | 11/15/23 9:01 AM
| Thanks for the update @nicolas.hernandez@penske.com | Gayam | 11/15/23 11:45 PM
Row 132 | @praneeth.gayam@penske.com Log4j/Maven changes look complete. Tested in DEV/QA. Bamboo Plan ready. Planning to deploy flex-billing on Tuesday, 11/14/2023 | Hernandez | 11/11/23 2:09 AM
| Thanks for the update. | Gayam | 11/12/23 10:47 PM
Row 132 | @praneeth.gayam@penske.com Please bring these down and we will remediate these during our AO testing when the app status moves to 6.1 | Dylan | 08/24/23 9:43 PM
| @dylan.price@penske.com , We have completed the modernization of this app. Please chekc the PR. https://bitbucket.penske.com/projects/PBT/repos/flexbilling-web/pull-requests/3/overview | Gayam | 08/30/23 3:13 AM
Row 132 | Question: @dylan.price@penske.com , Targeted folder of this application contains different ApplicationProperties.properties files under different enviornment folders. 'DEFAULT_MACHINE' property value is different between different ApplicationProperties files. As we are going to do the environment agnostic build we should use only 1 file under resources. Could you please check and let us know which one we need to use. Thanks. | Gayam | 06/13/23 1:46 AM
Row 132 | Hi @praneeth.gayam@penske.com I am seeing "conf" and "conf_test". For the time being could you please bring both conf folders down and when I make the changes for the properties files I will consolidate them into 1 conf folder | Dylan | 06/07/23 6:17 PM
| Sure @dylan.price@penske.com | Gayam | 06/08/23 7:51 AM
Row 132 | HI @praneeth.gayam@penske.com secrets file looks great -- please start with log4j/maven changes | Dylan | 06/07/23 1:14 AM
| Thanks @dylan.price@penske.com . Also, could you please the question I posted above. | Gayam | 06/07/23 6:02 AM
Row 132 | Secrets: @elliott.eames@penske.com , Adding to above question, I sent secrets in the email. Please check and respond whether any changes required to remediate the secrets. | Gayam | 03/24/23 12:07 AM
Row 132 | Question: @elliott.eames@penske.com , In this application we have two conf folder one is under src folder and another one is outside the src folder so need confirmation which one we need to use? Thanks. | Gayam | 03/09/23 2:12 AM
Row 132 | As per @dylan.price@penske.com , the other 2 line items are Duplicates. This is the original one. Repo is https://svn.penske.com/svn/avolent/ptl_customization/billing/appserver/trunk | Gayam | 03/08/23 12:12 AM
Row 132 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 132 | @mark.weaver@penske.com and @elliott.eames@penske.com - Flex billing entries are replicated thrice. Ref. Row #97, #99 and #129. Pls. confirm and share the Repo details for these applications to consider for log4J Modernization CC: @rafiq.melath@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:10 AM
| @mark.weaver@penske.com Pls. ignore the row #s mentioned above. Applications under confusion are 1. flexbilling.war 2. flexbilling 3. Flex Billing CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com | Mathumala Nachiappan | 02/06/23 6:45 PM
Row 133 | @praneeth.gayam@penske.com @william.spohn@penske.com Application is deployed on QA. | Venkatesh | 11/10/23 8:15 PM
Row 133 | @praneeth.gayam@penske.com sys:srvname is not being substituted in QA logs, can you please resolve this [${sys:srvname}:clelx150ptlge.penske.com:qa] | Venkatesh | 10/27/23 1:49 AM
| @venkatesh.hossalinever@penske.com , we will check. | Gayam | 10/27/23 2:27 AM
| @venkatesh.hossalinever@penske.com , srvname should be configured in log4j2.xml with the value 'batch'. My team informed to @revathi.kandasamy@penske.com on this. | Gayam | 10/30/23 11:28 PM
Row 133 | This application is deployed to QA. cc: @praneeth.gayam@penske.com @william.spohn@penske.com | Venkatesh | 10/06/23 6:20 PM
Row 133 | @praneeth.gayam@penske.com : can you onboard the application for build and deployments. Regards, Revathi.K | Kandasamy | 09/16/23 2:08 AM
| Sure @revathi.kandasamy@penske.com | Gayam | 09/18/23 6:44 PM
| @revathi.kandasamy@penske.com , Onboarding of fuelbatch application build and deploy plans completed- https://bamboo.penske.com/browse/FBBP-FUELB/deployments | Gayam | 09/18/23 8:45 PM
Row 133 | @praneeth.gayam@penske.com Could you please change log4j version from 2.20.0 to 2.17.2, slf4j version from 2.0.6 to 1.7.36 | Nayum | 09/04/23 4:34 PM
| @pathan.nayum@penske.com , Changed are completed. Please check. | Gayam | 09/05/23 11:59 PM
Row 133 | @praneeth.gayam@penske.com : Gentle Reminder!!! Could you share the latest branch name to be validated | Kandasamy | 08/29/23 10:05 PM
| @revathi.kandasamy@penske.com , Team is busy several apps. We will try to provide the PR as soon as possible. | Gayam | 08/30/23 2:41 AM
| @revathi.kandasamy@penske.com , We have completed the modernization and code is in develop branch. Could you please check it and let us know if we need to do any modifications. Thanks. | Gayam | 08/31/23 10:50 PM
Row 133 | @praneeth.gayam@penske.com , Any update on the log4j/maven migrated code. Kindly share the branch to be validated. | Nayum | 08/24/23 12:34 PM
| @revathi.kandasamy@penske.com / @pathan.nayum@penske.com , we complated mavanization of this app but observed that @pathan.nayum@penske.com committed some changes recently. We need to accommodate those changes in the modernization branch. We will let you know once we compelte the changes. | Gayam | 08/25/23 12:00 AM
Row 133 | Praneeth, Any update on the log4j/maven migrated code. Kindly share the branch to be validated. Regards, Revathi.K | Kandasamy | 08/21/23 6:02 PM
| @revathi.kandasamy@penske.com , We will provide the app in a day. | Gayam | 08/21/23 9:43 PM
Row 133 | @praneeth.gayam@penske.com , wsdl files are configured inside conf folder. The wsdl file from targeted folder will not be used. Kindly, let us know once log4j/mavenization changes are done. | Nayum | 08/14/23 4:49 PM
| Thanks @pathan.nayum@penske.com . | Gayam | 08/14/23 11:44 PM
Row 133 | @praneeth.gayam@penske.com 1. dev folder might be used for local configuration. so we can have dev configuration folder. 2. MessageReceiverService.wsdl file has to be used from respective environment folder. 3. penske-service-security-framework.jar is not required, it can be removed. | Nayum | 07/19/23 7:02 PM
| @pathan.nayum@penske.com , In environment agnostic build there will be no separate builds for each environment. It should be handled in the code. Please check with Architecture team i.e @shane.myers@penske.com if you have any questions. | Gayam | 07/19/23 11:56 PM
Row 133 | @pathan.nayum@penske.com , While working on converting this app to mavenization we found following things. Please clarify them. 1.This application has dev environment in the targeted folder. But the batch apps don't have the dev enironment. Please confirm whether we can ignore the dev configurations. 2.App has MessageReceiverService.wsdl file in dev,prod and qa folders under targeted folder. But we need to use only 1 wsdl as this is a environment agnostic build. Could you please let us know which one we need to use. 3. This app is having penske-service-security-framework.jar. But build is successful without using this jar. Do we need to include the dependency or not? | Gayam | 05/24/23 1:25 AM
Row 133 | We have verified the secrets shared in the email, And they are not secret or confidential info. So no change required. | Nayum | 05/12/23 9:33 PM
| Thanks @pathan.nayum@penske.com . Changed the status to Cap Maven. | Gayam | 05/17/23 3:21 AM
Row 133 | @praneeth.gayam@penske.com The following is the complete url deployed in the prod https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_spring @william.spohn@penske.com please correct us if any concerns. Can I get the secret codes for this particular branch(fuelnetbatch_spring). | Nayum | 04/28/23 11:33 AM
| @praneeth.gayam@penske.com @pathan.nayum@penske.com Yes Its the correct Prod branch. https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_springPraneeth can you please share the secrets for production branch. | Venkatesh | 04/29/23 2:33 AM
| @venkatesh.hossalinever@penske.com / @pathan.nayum@penske.com , I will discuss with my team and will let you know. | Gayam | 05/02/23 1:21 AM
| @venkatesh.hossalinever@penske.com / @pathan.nayum@penske.com , The provided secrets file is from https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_spring only. Secrets scanning tool provides all commit history secrets too. | Gayam | 05/03/23 1:24 AM
| No Praneet, If it consider the commit history the svn path should be same and in the list we can find different path. Can you point the above svn url and share the new list of secret codes. The secrets you shared earlier was having duplicate entries. Hence requesting to share the secret codes for the above link alone. | Kandasamy | 05/03/23 5:51 PM
| @revathi.kandasamy@penske.com , we will do the secrets scanning one more time and will send the list. | Gayam | 05/04/23 12:15 AM
| @revathi.kandasamy@penske.com / @venkatesh.hossalinever@penske.com / @pathan.nayum@penske.com , I sent the secrets file which is produced from the scanning of https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_spring branch in the email. Scanning tool is scanning all the branches when we scan the bitbucket but scanning only the provided branch when we scan the svn. | Gayam | 05/05/23 6:46 AM
Row 133 | While analysing the secret codes in fuelbatch_secrets.xlsx, we could find the following different svn locations for fuelbatch application. Kindly, confirm appropriate svn location to be verified for secret codes. https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_spring https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet_batch_Spring_Migration https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet_batch https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet | Nayum | 04/27/23 3:29 PM
| @pathan.nayum@penske.com , You provided us the following URL for this repo. Please check above comments. Repository 1 name: FUELBATCH_PROD associated reposiory url: https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/ | Gayam | 04/28/23 1:59 AM
Row 133 | Secrets: @pathan.nayum@penske.com , We sent secrets file for this app in the email. Could you please verify. Thanks. | Gayam | 04/22/23 2:16 AM
Row 133 | Yes, we can refer it from the artifactory. | Nayum | 04/06/23 1:09 PM
Row 133 | Repository 1 name: FUELBATCH_PROD associated reposiory url: https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/ is the source code, the second repository is pointing to a jar. | Nayum | 04/05/23 4:47 PM
| @pathan.nayum@penske.com , that means can we add the jar which is pointing to repo2 as a dependency to repo1 app while mavanizing? | Gayam | 04/06/23 2:49 AM
Row 133 | @william.spohn@penske.com , Following is the old bamboo build. https://bamboo.penske.com/chain/viewChain.action?planKey=FBBP-FBPROD This Bamboo build have reference to 2 repositories. Repository 1 name: FUELBATCH_PROD associated reposiory url: https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/ Repository 2 name: SECURITYJAR_PROD associated reposiory url: https://svn.penske.com/svn/architecture/security/penske-service-security-framework Could you please check and clarify us which one is correct repo? | Gayam | 03/13/23 11:11 PM
Row 136 | Hi @mathumala.nachiappan@penske.com I cannot find this application in our application list. Could you please remove this from the smart sheet? This application will not need moved over. | Dylan | 06/06/23 11:43 PM
| @dylan.price@penske.com , we can't find the repo or bamboo build for this app. Can I change the status to Reitre? @yvette.urso@penske.com | Gayam | 06/09/23 1:58 AM
| @praneeth.gayam@penske.com yes we can retire this application | Dylan | 06/13/23 1:24 AM
| @yvette.urso@penske.com , As per above conversation, we are retiring this application. Thanks. | Gayam | 06/13/23 1:33 AM
Row 136 | @mathumala.nachiappan@penske.com This application does not have a bamboo build. We may need to create one for it. I need to see where the codebase is for this application then get back to you | Dylan | 03/07/23 12:40 AM
Row 136 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 136 | @sreenivasulu.mupparaju@penske.com - For this App, we referred the bamboo key of 'PBSBP'. Got the project name as 'cbos'. But doesnt look related to this application. Pls. help us to clarify this CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 12:09 PM
| @sreenivasulu.mupparaju@penske.com - Pls. ignore the previous comment. Actual issue is we couldnt find the Bamboo build for this app. Pls. help us with the bamboo reference and the branch/folder to refer for modernization changes CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 02/10/23 11:16 AM
Row 136 | @mathumala.nachiappan@penske.com moved to AO Bamboo Status | Yvette Urso | 12/15/22 2:44 AM
Row 137 | @praneeth.gayam@penske.com yes, this app is retired. | Venkatesh | 10/10/23 2:26 AM
| Thanks @venkatesh.hossalinever@penske.com . Changed the status to retired. | Gayam | 10/11/23 12:56 AM
Row 137 | @praneeth.gayam@penske.com edi_encryption application will get retired as new batch application is developed and its been tested on QA. | Venkatesh | 06/21/23 6:00 PM
| @venkatesh.hossalinever@penske.com , Do we need to change the status of this app to retired? @yvette.urso@penske.com / @shane.myers@penske.com | Gayam | 06/22/23 3:14 AM
Row 137 | @praneeth.gayam@penske.com We are not going to do log4j changes. Please close this request. We have redesigned this batch application. | Venkatesh | 05/16/23 6:26 PM
| @venkatesh.hossalinever@penske.com , Do you mean is this application retired or no need of log4j/maven changes and Bamboo onboarding? FYI: @yvette.urso@penske.com , @shane.myers@penske.com | Gayam | 05/18/23 12:51 AM
Row 137 | Review: @venkatesh.hossalinever@penske.com this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/edi-encryption-batch/pull-requests/3/overview | Gayam | 04/13/23 1:00 AM
Row 137 | Completed reviewing the log4j secrets, no code changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 2:06 AM
Row 137 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 137 | @praneeth.gayam@penske.com - True positives found on this application. To review once and share it to AO | Mathumala Nachiappan | 01/10/23 10:44 AM
Row 137 | Per Sam S. on 11/23/22 - I am not certain on the EDI_encryption… I think ITDS Operations actually owns the encryption routines. Sreenivasulu is my all in one EDI specialist. If Brian thinks it should be mine just insert my name. | Yvette Urso | 11/24/22 2:10 AM
Row 138 | Thanks @dylan.price@penske.com . Changing the status to Retired. @yvette.urso@penske.com , @shane.myers@penske.com | Gayam | 06/08/23 7:59 AM
Row 138 | Hi @praneeth.gayam@penske.com we have determined that this application is no longer being used. Could you please delete out the Bitbucket repo, as well as remove it from the smartsheet? | Dylan | 06/07/23 1:15 AM
Row 138 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/mileageforecast-web/pull-requests/3/overview | Gayam | 03/23/23 11:42 PM
Row 138 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/28/23 3:32 AM
| Thanks @venkatesh.hossalinever@penske.com . Changed the status to Cap Maven | Gayam | 02/28/23 11:50 PM
Row 138 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:54 AM
| @yvette.urso@penske.com Hello, this application should be assign to 'Billing' App group and AO Manager should change to Rafiq Melath. | Kalrav | 02/13/23 9:28 PM
| Thanks @kalrav.khamar@penske.com @praneeth.gayam@penske.com - For your note and to share the updates to the team, as this has the dependency with distribution management | Mathumala Nachiappan | 02/15/23 2:06 PM
Row 139 | Hi @praneeth.gayam@penske.com we are not finding any applications that rely on this jar file. Could you please retire this application? | Dylan | 06/13/23 5:12 PM
| Thanks @dylan.price@penske.com . As per your instructions, changing the status to retired. @yvette.urso@penske.com / @shane.myers@penske.com | Gayam | 06/14/23 2:41 AM
Row 139 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 139 | Question: @mark.weaver@penske.com , Is the modernization for this app going to take care by app team? From @rafeeq.ahamed@penske.com , we heard that, this app has big scope and changes are happening in this app. So want to make sure whether this is in CG scope for log4j/maven modernization changes. Thanks. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 02/03/23 12:43 AM
Row 139 | @rafiq.melath@penske.com - Is this App group correct for this application. CC: @yvette.urso@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/23/23 7:33 PM
Row 140 | @praneeth.gayam@penske.com added comment in bitbucket push request | Dylan | 05/03/23 9:18 PM
| @dylan.price@penske.com We will check and provide the response. | Gayam | 05/04/23 12:20 AM
| @dylan.price@penske.com , I responded in the PR. Please check. thanks. | Gayam | 05/06/23 2:58 AM
Row 140 | @venkatesh.hossalinever@penske.com , This app is ready for your review. Please verify in below PR. https://bitbucket.penske.com/projects/ARPROJ/repos/viewpdf-web/pull-requests/3/overview | Gayam | 03/30/23 11:33 PM
Row 140 | Completed reviewing the log4j secrets - there are no coding changes required. | Venkatesh | 02/27/23 10:09 PM
| Thanks @venkatesh.hossalinever@penske.com. Updated the status to (Cap)Maven | Gayam | 02/27/23 11:31 PM
Row 140 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 140 | @dylan.price@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:49 AM
Row 142 | @ravi.daram@penske.com / @krishna.tanga@penske.com , We sent a secret file to you for this app and it looks like all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:41 PM
Row 161 | Updated bamboo plan and I am seeing the bill-avobatch.jar file successfully deployed out in DEV. The user is not correct, so I have made the changes in the QA deploy and will test after the 5pm deploy window. If this works, I will do the same for all the "bill_" applications and start testing them in QA next week. | Dylan | 08/04/23 1:23 AM
Row 161 | @praneeth.gayam@penske.com this looks great! Can you please create this for a dev bamboo build off the develop branch? | Dylan | 06/01/23 10:30 PM
| Sure @dylan.price@penske.com . We will let you know once it is onboarded to Bamboo. | Gayam | 06/01/23 10:58 PM
| @dylan.price@penske.com , Do you have idea how this app is currently getting deployed to CBOS batch box? | Gayam | 06/02/23 11:37 PM
| Hi @praneeth.gayam@penske.com it gets packaged in the "CBOS_PROD_PACKAGE" and gets moved to /var/tmp on the CBOS servers | Dylan | 06/06/23 12:51 AM
| @dylan.price@penske.com , bill_apprunner is successfully deployed to Dev instance ghlx006ptlge. I believe ghlx006ptlge is a CBOS server. You mentioned bill_avobatch should be deployed to ghlx097ptlge server. But getting bamboo fails to connect to ghlx097ptlge server. Bamboo did not face this issue while connecting to ghlx006ptlge server. Could you please check and guide us whether the ghlx097ptlge server is correct or not. https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=141072739 | Gayam | 06/13/23 2:23 AM
| Hi @praneeth.gayam@penske.com I am sorry! you are correct -- ghlx006ptlge is the correct server. This will be the same for bill_xmlloader_mp | Dylan | 06/14/23 5:13 PM
| Sure @dylan.price@penske.com | Gayam | 06/15/23 12:44 AM
| @dylan.price@penske.com , Dev hostname changed to ghlx006 and deploy plan re onboarded. Dev deployment also successful. Please verify. | Gayam | 06/16/23 2:36 AM
Row 161 | @praneeth.gayam@penske.com I have merged my changes in with "develop_log4j". Could you please merge this into the "develop" branch and start with bamboo testing? | Dylan | 05/26/23 6:19 PM
Row 161 | Review: @dylan.price@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/bill-avo-batch/pull-requests/5/overview | Gayam | 04/15/23 1:13 AM
Row 161 | @praneeth.gayam@penske.com No issues with the database property passwords. It is being excluded in the build script. Please proceed with log4j changes | Dylan | 03/30/23 9:19 PM
Row 161 | @sam.skelding@penske.com / @dylan.price@penske.com , This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:57 AM
| This application is an internal CBOS batch application and deploys to ghlx097ptlge (our CBOS batch box). Not sure how you would mark this in your artifactory -- wondering if CBOS should have its own instance type. | Dylan | 03/06/23 6:45 PM
| @hugo.scavino@penske.com / @balu.mohan@penske.com , Could you please check @dylan.price@penske.com question above and provide your response. Thanks. | Gayam | 03/06/23 11:57 PM
Row 161 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 161 | @dylan.price@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:50 AM
Row 162 | @praneeth.gayam@penske.com thank you! we are deploying this out tonight. Will be closing out this application tomorrow | Dylan | 09/12/23 8:06 PM
Row 162 | @praneeth.gayam@penske.com bamboo build has failed when trying to deploy to PROD. Could you please look through the logs and fix the SSH task? | Dylan | 09/06/23 7:28 PM
| Sure @dylan.price@penske.com . Let me check with CICD team. | Gayam | 09/07/23 1:29 AM
| @dylan.price@penske.com , CICD team analyzed and found that the prod password is not setup. Please setup the password and try. | Gayam | 09/07/23 11:47 PM
Row 162 | Application has been tested and is ready to deploy. | Dylan | 09/05/23 5:00 PM
Row 162 | Deployed buzonebatch out to QA. Will start testing | Dylan | 08/22/23 6:08 PM
Row 162 | Hi @praneeth.gayam@penske.com develop_log4j branch has been merged with develop. Please start on the bamboo build for DEV. | Dylan | 06/06/23 11:47 PM
| Sure @dylan.price@penske.com | Gayam | 06/07/23 5:37 AM
| @dylan.price@penske.com ,Onboarded develop branch to Bamboo. Please deploy to QA. https://bamboo.penske.com/browse/BUZONEBBP-BUZBCH0 | Gayam | 06/09/23 2:03 AM
Row 162 | Review: @dylan.price@penske.com / @mark.weaver@penske.com , this app is ready for your review. Please verify in the below PR. https://bitbucket.penske.com/projects/ARPROJ/repos/buzone-batch/pull-requests/3/overview | Gayam | 04/03/23 2:52 AM
Row 162 | @praneeth.gayam@penske.com the MonetaryConversion.jar can be added to artifactory. We also have no code changes needed for the password file. | Dylan | 03/07/23 12:56 AM
Row 162 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 162 | @mark.weaver@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:52 AM
Row 162 | @rafiq.melath@penske.com / @mark.weaver@penske.com , For buzonebatch application, there is a dependency jar 'MonetaryConversion.jar' which is not available in artifactory. We need this in artifactory for mavanization. Could you please provide your approval to upload this jar to artifactory in the following location. Thanks. groupid : com.penske.util artifactid : MonetaryConversion version : Default @hugo.scavino@penske.com , @mathumala.nachiappan@penske.com , @swati.saxena@penske.com | Gayam | 01/20/23 12:53 AM
Row 163 | This application is deployed to QA and ready for UAT. cc: @praneeth.gayam@penske.com @sreenivasulu.mupparaju@penske.com | Venkatesh | 10/06/23 6:18 PM
| @venkatesh.hossalinever@penske.com , We are not seeing any deployments in bamboo. Could you please check and confirm. https://bamboo.penske.com/browse/EDIBBP-EBHALBD2/deployments | Gayam | 10/10/23 12:02 AM
Row 163 | @praneeth.gayam@penske.com Changes related to old log4j property file was removed and merged the code to Develop branch, Please wait, we will confirm on deployment to QA environment. | Venkatesh | 05/16/23 6:24 PM
| @venkatesh.hossalinever@penske.com , We just onboard and build the app for batch apps. AO needs to deploy to QA. If you are ok we will onboard to Bamboo. Please confirm. | Gayam | 05/18/23 12:52 AM
Row 163 | @praneeth.gayam@penske.com Do we have any updates on above comments. Apart from above comments we are good with log4j and maven changes review. | Kadu | 05/11/23 6:55 PM
| @dhanashree.kadu@penske.com , We did complete the changes and committed to develop_log4j branch. Please verify and merge the PR. https://bitbucket.penske.com/projects/ARPROJ/repos/edi-batch/pull-requests/4/overview | Gayam | 05/11/23 11:30 PM
Row 163 | We have found below findings while reviewing Log4j and Maven changes in edi-batch application. Maven: We need below dependencies in the application which are not available in pom.xml. Can you please add them. These jars are already available in svn lib folder as well. <dependency> <groupId>commons-httpclient</groupId> <artifactId>commons-httpclient</artifactId> <version>3.0.1</version> </dependency> <dependency> <groupId>commons-dbcp</groupId> <artifactId>commons-dbcp</artifactId> <version>1.4</version> </dependency> Log4j: Can you move log4j.properties file from 'src\main\resources\conf' to 'src\main\resources'. So that application can read it properly. Batch application is using penskebatch.jar/contextframework.jar to use connection framework. And these jars are using older log4j version, it requires older log4j and mail dependencies to be available in pom.xml. Please add below dependencies in pom.xml. <!-- Logging --> <dependency> <groupId>log4j</groupId> <artifactId>log4j</artifactId> <version>1.2.17</version> </dependency> <!--mail dependencies --> <dependency> <groupId>javax.activation</groupId> <artifactId>activation</artifactId> <version>1.1.1</version> </dependency> <dependency> <groupId>com.sun.mail</groupId> <artifactId>javax.mail</artifactId> <version>1.6.0</version> </dependency> | Kadu | 05/08/23 4:17 PM
| Sure @dhanashree.kadu@penske.com . We will check your comments and will make the changes. | Gayam | 05/08/23 10:26 PM
Row 163 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. Please check. https://bitbucket.penske.com/projects/ARPROJ/repos/edi-batch/pull-requests/4/overview | Gayam | 03/24/23 11:09 PM
Row 163 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/27/23 10:25 PM
| Thanks @venkatesh.hossalinever@penske.com . Updated the status to Cap Maven. | Gayam | 02/27/23 11:36 PM
Row 163 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 163 | @rafiq.melath@penske.com / @sreenivasulu.mupparaju@penske.com , We have completed the secrets scanning and analysis on this app and found that all are false positives. I will send the sheet in the email. Could you please check and confirm. Thanks. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/10/23 1:16 AM
Row 164 | @venkatesh.hossalinever@penske.com , App is onboarded to bamboo and deployed to dev successfully. Please verify. bamboo plan: https://bamboo.penske.com/browse/EDICBOSBP-EDBSALBD Dev deployment: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151195129 | Gayam | 07/27/23 10:43 PM
Row 164 | We have found below findings while reviewing Log4j and Maven changes in edicbos web application. Maven: We need below dependency in the application which is not available in pom.xml. Can you please add it. This jar is already available in svn lib folder. <dependency> <groupId>org.springframework</groupId> <artifactId>spring-webmvc-struts</artifactId> <version>2.5</version> </dependency> We need to remove below jars from pom.xml as its conflicting the version with spring-webmvc 4.3.30 dependency. <dependency> <groupId>com.trigonic</groupId> <artifactId>spring-utils</artifactId> <version>0.3</version> </dependency> <dependency> <groupId>org.springframework</groupId> <artifactId>spring-core</artifactId> <version>${spring.version}</version> </dependency> <dependency> <groupId>org.springframework</groupId> <artifactId>spring-web</artifactId> <version>${spring.version}</version> </dependency> Log4j: We need to remove log4j.properties and InitializeLoggingServlet from the web code. We will make the code changes and commit them in develop_log4J branch. | Rane | 05/12/23 6:49 PM
| @praneeth.gayam@penske.com : Any update on the pom.xml | Kandasamy | 05/15/23 6:46 PM
| @revathi.kandasamy@penske.com , We have completed the changes in develop_log4j branch. Could you please verify. Thanks. | Gayam | 05/18/23 12:46 AM
| @praneeth.gayam@penske.com Please create the pull request. we will review the changes. | Venkatesh | 06/22/23 2:31 AM
| @venkatesh.hossalinever@penske.com , Please review https://bitbucket.penske.com/projects/PBTED/repos/edicbos-web/pull-requests/3/overview | Gayam | 06/22/23 3:55 AM
| @praneeth.gayam@penske.com Changes are merged, please deploy on dev environment. | Venkatesh | 07/26/23 7:47 PM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 07/27/23 8:56 AM
Row 164 | @venkatesh.hossalinever@penske.com , this app is ready for your review. Please verify. https://bitbucket.penske.com/projects/ARPROJ/repos/edicbos-web/pull-requests/3/overview | Gayam | 03/24/23 11:10 PM
Row 164 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/27/23 10:26 PM
| Thanks @venkatesh.hossalinever@penske.com . Updated the status to Cap Maven. | Gayam | 02/27/23 11:36 PM
Row 164 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 164 | @sreenivasulu.mupparaju@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:46 AM
Row 165 | This application is deployed to QA and ready for UAT. cc: @praneeth.gayam@penske.com @sreenivasulu.mupparaju@penske.com | Venkatesh | 10/06/23 6:18 PM
| @venkatesh.hossalinever@penske.com , We are not seeing any deployments in bamboo. Could you please check and confirm. https://bamboo.penske.com/browse/EDIPOSTCLIENT-EPCTALBD1/deployments | Gayam | 10/10/23 12:04 AM
| @praneeth.gayam@penske.com Apps were deployed on QA, not sure why it was not showing on bamboo. We are seeing the builds on bamboo now. | Venkatesh | 10/19/23 6:37 PM
| Thanks @venkatesh.hossalinever@penske.com . Yes, I am seeing now. Is the prod deployment also completed? | Gayam | 10/20/23 12:16 AM
Row 165 | @praneeth.gayam@penske.com Could you please change log4j version from 2.20.0 to 2.17.2, slf4j version from 2.0.6 to 1.7.36 and add below dependencies for mailing : <dependency> <groupId>com.sun.mail</groupId> <artifactId>javax.mail</artifactId> <version>1.6.0</version> </dependency> <dependency> <groupId>javax.activation</groupId> <artifactId>activation</artifactId> <version>1.1.1</version> </dependency> | Nayum | 09/04/23 6:19 PM
| @pathan.nayum@penske.com , Changes are completed. Please verify. | Gayam | 09/06/23 12:17 AM
Row 165 | @praneeth.gayam@penske.com Reviewed the changes and merged the code to Develop branch, Please wait, we will confirm deployment to QA environment. | Venkatesh | 05/16/23 6:21 PM
Row 165 | @praneeth.gayam@penske.com Thanks for the updates. We are good for log4j and maven changes review. Please deploy the changes in further environment. | Kadu | 05/11/23 7:01 PM
| Sure @dhanashree.kadu@penske.com . But could you please merge the PR. So that we will onboard develop branch to Bamboo. | Gayam | 05/11/23 11:28 PM
| @dhanashree.kadu@penske.com , We onboarded the develop branch to Bamboo. But build is failing. Could you please merge the PR https://bitbucket.penske.com/projects/ARPROJ/repos/edipostclient-batch/pull-requests/3/overview So that build will be successful. | Gayam | 05/13/23 2:16 AM
Row 165 | @dhanashree.kadu@penske.com , Please check the below comment from @hugo.scavino@penske.com . "BATCH apps can count on log4j 1.2 (legacy) being in the ./ptlcommon_1 and that directory will load first. BATCH apps do not need to add log4j (legacy) as a dependency in their pom's. penskebatch.jar/contextframework.jar will load the log4j legacy as WebServices will add ptl_common_1 at the beginning " So we don't need to add log4j 1 dependency in the pom. Please check and let us know if you have any questions. | Gayam | 05/10/23 12:17 AM
Row 165 | @praneeth.gayam@penske.com : can we proceed to retain the log4j.properties along with log4j2.xml. Kindly update us with the discussion with Hugo. | Kandasamy | 05/03/23 6:16 PM
Row 165 | @praneeth.gayam@penske.com Please confirm for log4j from Hugo. The penskebatch jar is not available in svn lib folder as this jar will be available in shared lib path and application will point from there. Almost all batch applications are using this jar for connection framework. | Kadu | 04/28/23 11:28 AM
Row 165 | We have found below findings while reviewing Log4j and Maven changes in edi-postclient batch application. Log4j: Batch application is using penskebatch.jar/contextframework.jar to use connection framework. And these jars are using older log4j version, it requires older log4j and mail dependencies to be available in pom.xml. Please add below dependencies in pom.xml. <!-- Logging for Batchframework --> <dependency> <groupId>log4j</groupId> <artifactId>log4j</artifactId> <version>1.2.17</version> </dependency> <!--mail dependencies --> <dependency> <groupId>javax.activation</groupId> <artifactId>activation</artifactId> <version>1.1.1</version> </dependency> <dependency> <groupId>com.sun.mail</groupId> <artifactId>javax.mail</artifactId> <version>1.6.0</version> </dependency> Maven: We have observed that the .tgz file created after maven build does not contain .jar file in it. Please make necessary changes to include .jar file in the bin.xml file. | Kadu | 04/27/23 6:59 PM
| @dhanashree.kadu@penske.com , If we use the log4j 1 jar then the purpose of log4j migration deviated. We need to discuss about this with @hugo.scavino@penske.com . Also, we are not seeing the penskebatch dependency in the lib folder. That is the reason we did not add that dependency and app also compiled successfully. | Gayam | 04/28/23 2:04 AM
Row 165 | @dylan.price@penske.com / @sreenivasulu.mupparaju@penske.com , this app is ready for your review. Please check. https://bitbucket.penske.com/projects/ARPROJ/repos/edipostclient-batch/pull-requests/3/overview | Gayam | 03/24/23 10:43 PM
Row 165 | @praneeth.gayam@penske.com please add cxml.jar to artifactory. We also do not need any updates for the secret file. | Dylan | 03/07/23 12:46 AM
| Thanks @dylan.price@penske.com . Changing the status to Cap Maven | Gayam | 03/07/23 11:57 PM
Row 165 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 165 | @sreenivasulu.mupparaju@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:47 AM
Row 165 | @rafiq.melath@penske.com / @sreenivasulu.mupparaju@penske.com , This application is dependent on the jar cxml.jar but this jar is not available in artifactory. Could you please provide your approval to upload this jar to artifactory. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/11/23 9:19 AM
Row 166 | This application is deployed to production. cc: @praneeth.gayam@penske.com @william.spohn@penske.com | Venkatesh | 10/06/23 6:17 PM
| Thanks @venkatesh.hossalinever@penske.com . Changing the status to App Deployed. | Gayam | 10/10/23 12:00 AM
Row 166 | @praneeth.gayam@penske.com , could you please change the reuse jar version for efuel in develop branch as 1.1.3 as app is redirecting to dlinks, It might be issue with reuse jar version mismatch. there might be some discrepancy. it's just a work around. if it is working fine in dev, we can move the same changes in QA as well. | Nayum | 08/18/23 1:38 PM
| @pathan.nayum@penske.com , changed the code. Please check the develop branch. Thanks | Gayam | 08/18/23 9:08 PM
Row 166 | @praneeth.gayam@penske.com Could you please change slf4j version for efuel in develop branch from 2.0.6 to 1.7.36 as the logs are not printing in dev and qa. Dev deployment is not successful as the app name is not correct in bamboo deploy script. Requested Ritesh to check that. | Kandasamy | 08/16/23 2:46 PM
| @revathi.kandasamy@penske.com My team Changed and merged the code develop branch. Please verify. Thanks. | Gayam | 08/17/23 12:46 AM
Row 166 | @praneeth.gayam@penske.com , for efuel application, Dev changes looks good and logs also rolling correctly on Dev server. | Nayum | 06/12/23 8:24 PM
| Thanks @pathan.nayum@penske.com . Please deploy to QA and test it. | Gayam | 06/13/23 1:31 AM
Row 166 | @praneeth.gayam@penske.com Changes related to old log4j property file was removed and merged the code to Develop branch, Please deploy to Dev environment. | Venkatesh | 05/16/23 6:16 PM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 05/18/23 12:54 AM
| @venkatesh.hossalinever@penske.com , The develop branch for efuel.war has already been onboarded to Bamboo, and the dev deployment was successfully completed. Please verify. | Gayam | 05/18/23 10:43 PM
Row 166 | Created the pull request for Nayum's change. Pls approve and merge. | Kandasamy | 05/15/23 6:38 PM
Row 166 | Log4j/Maven Changes are looking good. Removed log4j.properties from the web code and committed to maven branch. Please deploy the changes to dev server. | Nayum | 05/11/23 7:00 PM
| @pathan.nayum@penske.com , Can you merge your changes to develop branch. So that we will onbaord develop branch to Bamboo. | Gayam | 05/11/23 11:33 PM
Row 166 | yes, working on changes to remove hardcoded changes to load old log4j file. | Venkatesh | 05/03/23 2:33 AM
Row 166 | @venkatesh.hossalinever@penske.com , bamboo build & deploy plan onboarding completed. Dev deployment done using develop_log4j branch. https://bamboo.penske.com/browse/EFUELBP-EFLALBD/ Also, please merge the code to develop branch. https://bitbucket.penske.com/projects/ARPROJ/repos/efuel-web/pull-requests/3/overview | Gayam | 04/19/23 3:09 AM
| @praneeth.gayam@penske.com Code has been merged. Currently we are working on code changes to remove loading of existing log4j property file from the code. | Venkatesh | 04/29/23 2:36 AM
| @venkatesh.hossalinever@penske.com , are you making the changes on top of develop_log4j branch? | Gayam | 05/02/23 1:06 AM
Row 166 | Yes, Please proceed with bamboo setup | Venkatesh | 04/17/23 8:25 PM
| Thanks @venkatesh.hossalinever@penske.com . We will let you know once it is onboarded to Bamboo. | Gayam | 04/18/23 3:14 AM
Row 166 | Log4j and Maven Changes are looking good. log4j.properties file location is hardcoded in the code, and hence required code fix to read the log4j2.xml and ensure the log files are created. | Nayum | 04/13/23 6:43 PM
| @pathan.nayum@penske.com , Can we onboard this app to Bamboo and deploy? | Gayam | 04/13/23 11:27 PM
Row 166 | @william.spohn@penske.com / @venkatesh.hossalinever@penske.com , Please review log4j/maven changes at https://bitbucket.penske.com/projects/ARPROJ/repos/efuel-web/pull-requests/3/overview | Gayam | 03/02/23 3:07 AM
Row 166 | Venkatesh has completed reviewing the log4j secrets - there are no coding changes required. | William Spohn | 02/23/23 3:03 AM
| Thanks @william.spohn@penske.com . Changing the status to (Cap)Maven | Gayam | 02/23/23 3:23 AM
Row 166 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 166 | @william.spohn@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:39 AM
Row 167 | @praneeth.gayam@penske.com Thanks praneeth, changes has been deployed to production successfully. | Venkatesh | 10/04/23 1:08 AM
| Thanks @venkatesh.hossalinever@penske.com | Gayam | 10/04/23 1:47 AM
Row 167 | @praneeth.gayam@penske.com : Could you please change slf4j version for efueladmin in develop branch from 2.0.6 to 1.7.36 as the logs are not printing in dev and qa. | Kandasamy | 08/16/23 12:45 PM
| @revathi.kandasamy@penske.com My team Changed and merged the code develop branch. Please verify. Thanks. | Gayam | 08/17/23 12:45 AM
Row 167 | @praneeth.gayam@penske.com , Logs are not rolling in dev as well as no mails were triggered, hence we need to add the attached Javamail dependencies in pom.xml. Kindly, update the pom.xml and deploy the same in dev. | Nayum | 06/16/23 6:49 PM
| @pathan.nayum@penske.com , we will add and get back to you. | Gayam | 06/16/23 10:27 PM
| @pathan.nayum@penske.com , We have updated the pom.xml with the mentioned dependencies. Please check and approve the PR. https://bitbucket.penske.com/projects/PBTFUEL/repos/efueladmin-web/pull-requests/7/overview | Gayam | 06/19/23 7:41 PM
| @praneeth.gayam@penske.com Merged the changes. Can you please deploy the changes on Dev. | Venkatesh | 07/26/23 8:00 PM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 07/27/23 8:58 AM
| @venkatesh.hossalinever@penske.com / @pathan.nayum@penske.com / @william.spohn@penske.com , App is deployed to dev. Please verify. | Gayam | 07/27/23 10:45 PM
Row 167 | @praneeth.gayam@penske.com , for efueladmin application, Dev URL is working correctly, but logs are not rolling in correct location in Dev log server. | Nayum | 06/12/23 8:25 PM
| @pathan.nayum@penske.com . Please provide where the logs are rolling out. Also provide the correct location where logs need to be rolled out. | Gayam | 06/13/23 1:32 AM
Row 167 | @praneeth.gayam@penske.com , efueladmin is working fine in local. But, In dev after deployment, Dev URL is not working. PFA for page loaded in dev. URL used for dev : https://web3dev.penske.com/efueladmin/entry/ApplicationEntry?LoginUserID=505025033 | Nayum | 06/08/23 8:33 PM
| @pathan.nayum@penske.com , Please debug the issue and check the logs. We don't know any information about the application other than mavanizing the application. | Gayam | 06/09/23 1:11 AM
Row 167 | @praneeth.gayam@penske.com Changes related to old log4j property file was removed and merged the code to Develop branch, Please deploy to Dev. | Venkatesh | 05/16/23 6:14 PM
| Sure @venkatesh.hossalinever@penske.com . We will onaboard the develop branhc to Bamboo and deploy to Dev. | Gayam | 05/18/23 12:48 AM
| @venkatesh.hossalinever@penske.com , The build plan and deploy plan for efueladmin.war have been successfully onboarded to Bamboo and completed the dev deployment through the develop branch. Please verify | Gayam | 05/18/23 10:42 PM
Row 167 | @praneeth.gayam@penske.com : Created Pull request for the changes. | Kandasamy | 05/15/23 6:42 PM
Row 167 | Log4j/Maven Changes are looking good. Removed log4j.properties from the web code and committed to maven branch. Please deploy the changes to dev server. | Nayum | 05/11/23 6:58 PM
| @pathan.nayum@penske.com Can you merge your changes to develop branch. | Gayam | 05/11/23 11:35 PM
Row 167 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. Please check. Thanks. https://bitbucket.penske.com/projects/ARPROJ/repos/efueladmin-web/pull-requests/3/overview | Gayam | 04/07/23 12:25 AM
Row 167 | Venkatesh has completed reviewing the log4j secrets - there are no coding changes required. | William Spohn | 02/23/23 3:03 AM
| Thanks @william.spohn@penske.com . Changing the status to (Cap)Maven | Gayam | 02/23/23 3:26 AM
Row 167 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 167 | @william.spohn@penske.com / @venkatesh.hossalinever@penske.com , @william.spohn@penske.com , Adding to Bamboo build question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:41 AM
Row 167 | Venkatesh Hossalinever provided me the following repo URL with folder and branch details for efueladmin.var Dev, QA, and Prod. Prod- https://svn.penske.com/svn/webprojects/admin/efueladmin/trunk/efueladmin7 Dev - https://svn.penske.com/svn/webprojects/admin/efueladmin/branches/dev_gh/efueladmin7 QA- https://svn.penske.com/svn/webprojects/admin/efueladmin/branches/qa/efueladmin7 | William Spohn | 12/09/22 11:15 PM
| Thanks @william.spohn@penske.com . Can we also get the Bamboo build for this project. @mathumala.nachiappan@penske.com | Gayam | 12/10/22 12:49 AM
| @william.spohn@penske.com / @venkatesh.hossalinever@penske.com, could you please provide the requested info when you get a chance. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 7:40 PM
Row 167 | Moved to AO Bamboo - Please move to CAP Bamboo when done @william.spohn@penske.com | Yvette Urso | 12/15/22 2:45 AM
Row 167 | Yes, we've made this request and are awaiting delivery. | William Spohn | 12/14/22 3:09 AM
Row 167 | Hi Praneeth, I will contact my GDC offshore web app contact for this information and get back to you. | William Spohn | 12/09/22 8:23 PM
Row 167 | @william.spohn@penske.com - Pls. share the Repo URL and confirm the folder/branch for log4J modernization CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 11:16 PM
Row 168 | UAT is completed and ready for production deployment . cc: @praneeth.gayam@penske.com @william.spohn@penske.com | Venkatesh | 10/06/23 6:20 PM
Row 168 | @william.spohn@penske.com UAT completed, ready for production deployment. cc: @praneeth.gayam@penske.com @revathi.kandasamy@penske.com | Venkatesh | 10/05/23 11:56 PM
| Thanks @venkatesh.hossalinever@penske.com . Please let us know once the deployment completes. | Gayam | 10/06/23 12:55 AM
Row 168 | @praneeth.gayam@penske.com : could you modify the following: 1. remove log4j.properties cofiguaration from web.xml <context-param> <param-name>log4jConfigLocation</param-name> <param-value>classpath:conf/log4j.properties</param-value> </context-param> 2. Remove the log4j.properties from the app 3. In log4j2.xml: artifact id should be without war. Kindly update as fuelcardsplit alone. <Property name="app_name">fuelcardsplit.war</Property> | Kandasamy | 08/22/23 1:56 PM
| @revathi.kandasamy@penske.com , My team said that they completed these changes. Could you please let us know the status of this pp. Thanks. | Gayam | 09/28/23 6:51 PM
Row 168 | @praneeth.gayam@penske.com : application is not deployed in dev as the artifactory id in pom.xml is not given correctly <artifactId>fuelcardsplit-web</artifactId> Kindly change as below: <artifactId>fuelcardsplit</artifactId> | Kandasamy | 08/16/23 3:51 PM
| Sure @revathi.kandasamy@penske.com . | Gayam | 08/17/23 1:22 AM
| we need to change the SLF4j and LOG4j version as well. Let follow up with log4j team for the changes | Kandasamy | 08/18/23 9:31 PM
| @revathi.kandasamy@penske.com , Team chagned the versions. Please check. | Gayam | 08/21/23 9:41 PM
Row 168 | @praneeth.gayam@penske.com , After deploying fuelcardsplit changes to QA, new logs are not created. Kindly, check if you have to restart the aplication. | Nayum | 07/19/23 6:49 PM
| @pathan.nayum@penske.com , will check. | Gayam | 07/19/23 11:50 PM
| @pathan.nayum@penske.com , Ritesh told me that he already updated you. Could you please run the application in local and check whether logs are getting generated. We can't run the application in our local. | Gayam | 07/24/23 11:58 PM
Row 168 | @praneeth.gayam@penske.com / @venkatesh.hossalinever@penske.com , for fuelcardsplit application, Dev URL is not working, while accessing the Dev URL it is redirecting to dlinks(https://logindev.penske.com/dlinks/app/dlinksMain?LoginUserID=null). | Nayum | 06/12/23 8:28 PM
Row 168 | @praneeth.gayam@penske.com Reviewed the changes and merged code to develop branch, Please deploy to Dev environment. | Venkatesh | 05/16/23 6:31 PM
| @venkatesh.hossalinever@penske.com , Onboarding develop branch to bamboo and deploying to dev completed. Please verify. | Gayam | 05/18/23 12:55 AM
| @venkatesh.hossalinever@penske.com , Because of recent architectural change from Hugo / @shane.myers@penske.com , we changed the scope of log4j jars from provided scope compile scope. Please verify and merge to develop branch. Thanks. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelcardsplit-web/pull-requests/6/overview | Gayam | 05/22/23 11:57 PM
Row 168 | @revathi.kandasamy@penske.com , Dev deployment is completed from develop_log4j. https://bamboo.penske.com/browse/FCARDBP-FCRDALBLD1/deployments Could you please verify. Also please merge the PR which is raised from develop_log4j to develop branch. | Gayam | 04/25/23 12:59 AM
Row 168 | @praneeth.gayam@penske.com : log4j and Maven changes looks good. Can you do dev deployment for testing. | Kandasamy | 04/20/23 6:49 PM
| Sure @revathi.kandasamy@penske.com . It looks like the PR is not yet merged. Could you please merge. | Gayam | 04/21/23 1:33 AM
Row 168 | Review: @venkatesh.hossalinever@penske.com , this is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelcardsplit-web/pull-requests/3/overview | Gayam | 03/08/23 2:35 AM
Row 168 | Venkatesh Hossalinever reports "No remediation is required for all False positives, these files are not using credentials. There are no code changes required to fuelcardsplit.var" | William Spohn | 02/24/23 9:16 PM
| Thank you. Changed the status to (Cap)Maven | Gayam | 02/25/23 12:51 AM
Row 168 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 168 | @william.spohn@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:42 AM
Row 168 | I am responsible for testing efuel.war, efueladmin.war, fuelbatch(UAT done), fuelcardsplit.war(UAT done), fuelnetsvc.war(UAT done), and fuelpricing.war. | William Spohn | 01/10/23 10:17 PM
Row 168 | @william.spohn@penske.com , we did not start the log4j/maven changes for this application. Could you please let us know whether you are providing sign off for any other changes. But this sheet is only for log4j/maven changes updates. @mathumala.nachiappan@penske.com | Gayam | 12/12/22 11:52 PM
Row 168 | Yes, Anju Nair emailed me on 11/24 that log4j2 changes to fuelcardsplit.var were ready for testing in QA. I completed my QA testing of this web app - all tests passed. Please consider this my QA testing signoff. | William Spohn | 12/08/22 7:44 PM
| Thanks @william.spohn@penske.com . Will take it forward. @praneeth.gayam@penske.com - Pls. ask Dev team to identify the rest other modernization changes requried | Mathumala Nachiappan | 12/12/22 4:53 PM
Row 168 | hi @william.spohn@penske.com - Is it related to Log4j modernization? | Mathumala Nachiappan | 12/08/22 3:53 PM
Row 168 | I tested "fuelcardsplit.war" in QA for Anju Nair and all tests passed. | William Spohn | 12/07/22 7:17 PM
Row 169 | @praneeth.gayam@penske.com Thanks praneeth, changes has been deployed to production. | Venkatesh | 10/04/23 1:06 AM
| Thanks @venkatesh.hossalinever@penske.com | Gayam | 10/04/23 1:48 AM
Row 169 | @praneeth.gayam@penske.com Could you please add the below dependency , for invarcsftpbatch in develop branch. <dependency> <groupId>com.penske.mis.common.customlib.oracle</groupId> <artifactId>ojdbc8</artifactId> <scope>${sharedLibScope}</scope> </dependency> scope :: <sharedLibScope>provided</sharedLibScope> | Nayum | 08/30/23 7:14 PM
| Sure @pathan.nayum@penske.com . We will modify and let you know. | Gayam | 08/30/23 10:44 PM
| @pathan.nayum@penske.com , Completed. Please verify the develop branch. | Gayam | 09/01/23 12:16 AM
Row 169 | @praneeth.gayam@penske.com Could you please change log4j version from 2.20.0 to 2.17.2, slf4j version from 2.0.6 to 1.7.36 and spring version 4.3.8.RELEASE to 4.3.30.RELEASE for invarcsftpbatch in develop branch. | Nayum | 08/24/23 12:41 PM
| @pathan.nayum@penske.com , Changes are compelted and merged to develop. Pelase check. | Gayam | 08/25/23 12:01 AM
Row 169 | @praneeth.gayam@penske.com High Radius application will not be retired. Please proceed with the log4j migration. CC: @rafiq.melath@penske.com @mark.weaver@penske.com @revathi.kandasamy@penske.com | Venkatesh | 08/17/23 8:29 PM
| @venkatesh.hossalinever@penske.com , alredy mavanization completed and deployed to QA. Plese verify. Thanks. https://bamboo.penske.com/browse/INVARCBATCHBP-INVSFTP/deployments | Gayam | 08/18/23 12:45 AM
Row 169 | Business has decided not to use this product. this app will be retired. | Rafiq Melath | 08/15/23 11:47 PM
Row 169 | @praneeth.gayam@penske.com : could you pls provide access to the project folder https://bitbucket.penske.com/projects/PA/repos/invarcsftpbatch/browse | Kandasamy | 08/14/23 8:22 PM
| I asked team to add you in RBAC group PTL-Billing-Development | Gayam | 08/15/23 1:02 AM
Row 169 | @venkatesh.hossalinever@penske.com , Deploy plan onboarded and deployed to QA. Please check and verify. Thanks. deploy plan: https://bamboo.penske.com/browse/INVARCBATCHBP-INVSFTP/deployments qa deployment: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151196298 | Gayam | 08/04/23 1:07 AM
Row 169 | Review: @venkatesh.hossalinever@penske.com , This app is ready for your review. Please validate and merge. https://bitbucket.penske.com/projects/PA/repos/invarcsftpbatch/pull-requests/3/overview | Gayam | 06/30/23 1:06 AM
| @praneeth.gayam@penske.com code has been merged. Please deploy changes on QA. As we don't have Dev box for batch application. | Venkatesh | 08/02/23 2:58 AM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 08/02/23 3:04 AM
Row 169 | @praneeth.gayam@penske.com Can you please share the secrets once again. | Venkatesh | 05/16/23 12:55 AM
| @venkatesh.hossalinever@penske.com , Sent secrets in email. | Gayam | 05/17/23 3:28 AM
| @praneeth.gayam@penske.com secrets has been reviewed there are no hardcoded values. Please proceed with the next step. | Venkatesh | 06/22/23 2:27 AM
| Thanks @venkatesh.hossalinever@penske.com . Changing the status to Cap Maven. | Gayam | 06/22/23 3:23 AM
Row 169 | @mark.weaver@penske.com , secrets of this app shared in the email. Please check. Thanks. | Gayam | 03/24/23 12:19 AM
Row 169 | Repo for this application is https://bitbucket.penske.com/projects/PBJB/repos/invarcsftpbatch/browse/src and bamboo link is https://bamboo.penske.com/browse/INVARCBATCHBP-INV | Dylan | 03/07/23 1:57 AM
Row 169 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 169 | Moved to AO Bamboo status | Yvette Urso | 12/15/22 2:45 AM
Row 169 | @mark.weaver@penske.com - Pls. share the Repo URL or the Bamboo project key for this applicaiton. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 12:00 PM
Row 170 | Print App deployed on 09/12 after log4j Mavernization caused an issue with Agent commission statements - having issues with data source and writeIFS procedure calls. Rollback of svn code is planned for 10/05. Log4j changes will be relooked to troubleshoot the issue and plan for deploy for future dates. | Rafiq Melath | 10/05/23 6:14 PM
Row 170 | @praneeth.gayam@penske.com thank you! we are deploying this out tonight. Will be closing out this application tomorrow | Dylan | 09/12/23 8:06 PM
Row 170 | @praneeth.gayam@penske.com Found batik-all jar is not the correct version. The maven repo for batik-all is not allowed by Penske's proxy however. Could you please add this jar into Artifactiory so we can grab it in our maven repos? https://mvnrepository.com/artifact/org.apache/batik-all/1.7.0 | Dylan | 09/05/23 10:13 PM
| Sure @dylan.price@penske.com . We will add above jar to artifactory. | Gayam | 09/07/23 1:32 AM
| @dylan.price@penske.com , batik-all uploaded in artifactory. <dependency> <groupId>org.apache.batik</groupId> <artifactId>batik-all</artifactId> <version>1.7</version> </dependency> | Gayam | 09/07/23 11:49 PM
Row 170 | Hi @praneeth.gayam@penske.com this application has been committed up to "Develop_Log4j" branch. Please setup Bamboo for this application. | Dylan | 08/22/23 2:42 AM
| Sure @dylan.price@penske.com . Do you want to onboard develop_log4j branch to bamboo because the code is not yet merged to develop? | Gayam | 08/22/23 9:39 PM
| yes please -- for now just use develop_log4j and I will merge my changes into develop when we have a working bamboo run | Dylan | 08/23/23 12:02 AM
| @dylan.price@penske.com , Build and deploy plan onboarded and develop_log4j branch onboarded to bamboo. https://bamboo.penske.com/browse/PRINTAPPBP-PRINTB1/deployments Please deploy. Thanks | Gayam | 08/24/23 12:44 AM
Row 170 | @Review: @venkatesh.hossalinever@penske.com , This app is ready for your review. Please check. Thanks. https://bitbucket.penske.com/projects/PBJB/repos/printapplication/pull-requests/3/overview | Gayam | 03/30/23 11:37 PM
Row 170 | Completed reviewing the log4j secrets there is no code changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 3:42 AM
| Thank you. Changed the status to Cap Maven. | Gayam | 03/02/23 1:22 AM
Row 170 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 170 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:52 AM
Row 171 | We have prepared documents to deploy this on 08/03/2023 | Dylan | 08/02/23 7:10 PM
| Thanks @dylan.price@penske.com . Please let me know once it is deployed. i will change the status to Done. | Gayam | 08/03/23 12:42 AM
Row 171 | Hi @praneeth.gayam@penske.com Nicolas will be deploying his changes for StopBilling with Maven/log4j2. There is no other work for Capgemini team that needs completed. Thank you! | Dylan | 07/10/23 8:22 PM
Row 171 | @praneeth.gayam@penske.com I pushed my changes to dev. everything in develop looks good on my end. Are you able to build develop? | Hernandez | 05/22/23 6:43 PM
| @nicolas.hernandez@penske.com , Develop branch build is successful and it is deployed to dev environment. https://bamboo.penske.com/browse/STOPBILLINGBP-STOPBILL0/deployments Please verify in Dev. | Gayam | 05/22/23 10:03 PM
| @praneeth.gayam@penske.com I am not seeing the changes made from old log4j in dev. I made changes and merged to 'develop' branch. | Hernandez | 05/22/23 10:51 PM
| @nicolas.hernandez@penske.com , Could you please verify now. We changed the artifactid to stopbilling. Hope it works now. Thanks. | Gayam | 05/24/23 1:28 AM
| @praneeth.gayam@penske.com I've verified the changes are now on dev. Thank you. Is QA bamboo plan ready? | Hernandez | 05/24/23 2:17 AM
| @nicolas.hernandez@penske.com , QA deploy plan is already ready. | Gayam | 05/25/23 2:42 AM
Row 171 | @praneeth.gayam@penske.com , There are two changes I made to the XML file to get log4j2 running: 1. Added a <Loggers> tag and added <Root> tag inside (Error in console gone) 2. SMTP Apender syntax error (Error in console) Also noticed that log4j2 is creating a new log file after each mvn clean build. Is that happening on your end? We can setup a discussion for further details. I made code changes to the application to remove old log4j properties and configuration. Please Review | Hernandez | 05/18/23 6:54 PM
Row 171 | @praneeth.gayam@penske.com Thanks. Nicolas validated changes in his local and he is not able to see the logs getting generated in his local. Also on dev server the logs are not rolling when he tested the changes. Error from his local system: [5/15/23 15:13:25:015 EDT] 0000004f SystemOut O 2023-05-15 15:13:25,015 server.startup : 0 ERROR Unknown object "Root" of type org.apache.logging.log4j.core.config.LoggerConfig is ignored: try nesting it inside one of: ["Appenders", "Loggers", "Properties", "Scripts", "CustomLevels"]. [5/15/23 15:13:25:017 EDT] 0000004f SystemOut O 2023-05-15 15:13:25,016 server.startup : 0 WARN No Loggers were configured, using default. Is the Loggers element missing? | Venkatesh | 05/16/23 12:45 AM
| @venkatesh.hossalinever@penske.com , As discussed in the call, one of the log4j team member able to build the app successfully in local using billing settings. | Gayam | 05/18/23 1:02 AM
Row 171 | @praneeth.gayam@penske.com We will using ARPROJ repo. Please deploy develop_log4j changes on dev environment. | Venkatesh | 05/10/23 1:06 AM
| @venkatesh.hossalinever@penske.com We will do that and will let you know. | Gayam | 05/11/23 6:41 AM
| @venkatesh.hossalinever@penske.com , Onboarded develop_log4j to bamboo and deployed to Dev. Please verify https://bamboo.penske.com/browse/STOPBILLINGBP-STOPBILL1/deployments | Gayam | 05/11/23 11:23 PM
Row 171 | @venkatesh.hossalinever@penske.com / @mark.weaver@penske.com , We observed there is a new repo created for stopbilling recently. Following is the repo details. https://bitbucket.penske.com/projects/PBJB/repos/stopbilling-web/browse?at=refs%2Fheads%2Ffeature%2FPBT-141-Cancel-Code-Feature But we already create a repo for this application and mavanized. Repo which we created is https://bitbucket.penske.com/projects/ARPROJ/repos/stopbilling-web/browse?at=refs%2Fheads%2FDevelop_Log4j Do you know why there is a new repo created? | Gayam | 04/07/23 12:02 AM
Row 171 | Review: @venkatesh.hossalinever@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/stopbilling-web/pull-requests/3/overview | Gayam | 03/18/23 1:08 AM
Row 171 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 2:02 AM
| Thank you. Changed the status to Cap Maven | Gayam | 03/02/23 2:02 AM
Row 171 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 171 | @rafiq.melath@penske.com / @mark.weaver@penske.com , We completed the secrets scanning on this application and found that all are false positives. I will send the sheet to you in the email. Could you please check and confirm. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/10/23 12:39 AM
Row 172 | @praneeth.gayam@penske.com We see some pull request today, But log4j changes has been already deployed to production successfully. cc: @mark.weaver@penske.com | Venkatesh | 10/04/23 9:57 PM
| @venkatesh.hossalinever@penske.com , it is deployed from develop_log4j branch. Because still the above PR is open and code is not merged to develop branch. | Gayam | 10/05/23 1:23 AM
Row 172 | @praneeth.gayam@penske.com Any update on log4j changes, can you please share it soon. | Venkatesh | 09/14/23 8:37 PM
| @venkatesh.hossalinever@penske.com , Please review the PR https://bitbucket.penske.com/projects/PB/repos/webmileagesvc/pull-requests/3/overview | Gayam | 09/15/23 7:25 AM
Row 172 | @praneeth.gayam@penske.com Can you please start the log4j migration. Use the following SVN code base. https://svn.penske.com/svn/webprojects/admin/webmileagesvc/branches/dev_gh_log4j2 cc: @mark.weaver@penske.com | Venkatesh | 08/24/23 1:45 AM
| Thanks @venkatesh.hossalinever@penske.com | Gayam | 08/24/23 4:02 AM
Row 172 | please modernize this jar, and add it into artifactory. thank you! also, i do not see any secrets files that need updated. | Dylan | 03/07/23 2:12 AM
| @dylan.price@penske.com Thanks for your response on secrets. Could you please also provide the response for the question asked above. | Gayam | 03/07/23 6:19 AM
| We are working on the changes on this application, please wait for sometime. | Venkatesh | 03/24/23 8:56 PM
Row 172 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 172 | @mark.weaver@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:56 AM
Row 172 | Question: @rafiq.melath@penske.com / @mark.weaver@penske.com , Following things are we observed in this application. Please check and provide your response. The lib folder contains following jars. servicenetsvc-client.jar serviceRequestUtility.jar. While mavanizing it build is getting successful with out adding these dependencies into pom. Let us know whether we need add these dependencies. If yes, serviceRequestUtility.jar is available in artifactory. So, we can add this dependency. But servicenetsvc-client.jar is not available in artifactory. Please let us know whether we can upload this jar into artifactory. Also we found the bamboo build plan for this jar. The link for this jar is https://bamboo.penske.com/browse/SVCN-SNSVCPROD . Please check it and let us know whether we need to modernize and upload to artifactory. Thanks. @mathumala.nachiappan@penske.com | Gayam | 12/17/22 2:15 AM
Row 173 | @rajesh.haravde@penske.com , We disabled unit test case task in the bamboo build. Are you in the plan to fix the unit test cases? Then we can enable the respective task in the build. Thank you. | Gayam | 11/15/23 11:49 PM
Row 173 | Ready to Deploy | Rajesh | 09/11/23 5:29 PM
Row 173 | Please provide access | Narsimhamurthy | 08/17/23 8:26 PM
| @narsimhamurthy.peddoju@penske.com , You are already in the RBAC group PTL-Development and this group already have the access to bbupload bamboo build. Please check now. | Gayam | 08/18/23 7:18 PM
Row 173 | Access denied Sorry, you have insufficient permissions to view the page. Please contact an administrator if you believe this is an error. Go to... | Narsimhamurthy | 08/17/23 8:25 PM
Row 173 | Praneeth, getting below error while trying to access above url | Narsimhamurthy | 08/17/23 8:25 PM
Row 173 | @praneeth.gayam@penske.com After disabling the test cases & jtest results. we are getting following issue while executing bamboo build as requested. 12-Jun-2023 14:04:45 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:04:45 [INFO] BUILD FAILURE 12-Jun-2023 14:04:45 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:04:45 [INFO] Total time: 9.394 s 12-Jun-2023 14:04:45 [INFO] Finished at: 2023-06-12T14:04:45-04:00 12-Jun-2023 14:04:45 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:04:45 [ERROR] Failed to execute goal org.apache.maven.plugins:maven-surefire-plugin:3.0.0-M4:test (unit-tests) on project bbupload: There are test failures. 12-Jun-2023 14:04:45 [ERROR] | Rajesh | 06/12/23 11:43 PM
| @rajesh.haravde@penske.com , Still seeing test failures. Let me check with my CICD team on this. | Gayam | 06/13/23 1:36 AM
| @rajesh.haravde@penske.com , unit tests are disabled and build got success https://bamboo.penske.com/browse/BBUPLOADBP-BBULD0 | Gayam | 06/14/23 3:45 AM
Row 173 | Please confirm if we can validate the bamboo script for this project and which branch | Rajesh | 06/08/23 11:16 PM
| @rajesh.haravde@penske.com , This app is already onboarded to Bamboo. Please check. https://bamboo.penske.com/browse/BBUPLOADBP-BBULD0/ | Gayam | 06/09/23 1:22 AM
Row 173 | PR been executed please take it forward. Thanks for guidance on process Praneeth appreciated. | Rajesh | 05/18/23 1:50 AM
| Sure @rajesh.haravde@penske.com . We will let you know once we deploy to dev. | Gayam | 05/18/23 10:47 PM
| @rajesh.haravde@penske.com , Test cases are failing in this application. Please check the build at https://bamboo.penske.com/browse/BBUPLOADBP-BBULD1-UTEST-3 Could you please work with your team to fix them. Thanks. | Gayam | 05/22/23 9:27 PM
Row 173 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/bbupload-web/pull-requests/3/overview Thanks. | Gayam | 02/16/23 11:01 PM
Row 173 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:44 PM
Row 173 | WAR is building now | Hugo Scavino | 01/19/23 3:14 AM
Row 173 | I moved the XML files from source and test source to the appropriate resources folder to follow maven conventions. XML files should not be the src/main/java directory. Added simple console log4j into test resources. Please see the below comment I added in one of the tests. Application Owner should review. Test was failing and I made a more generic test but would prefer their test if possible. // TODO This test was failing because the recordset1 was not the same argument. Should be resolved. | Hugo Scavino | 01/19/23 3:14 AM
Row 173 | @rajesh.haravde@penske.com , I provided the response above. Please check. | Gayam | 01/18/23 9:13 PM
Row 173 | We updated Praneeth and waiting on response. | Rajesh | 01/18/23 8:20 PM
Row 173 | BBUpload failed its maven build, so I couldn’t test it. These are the main errors that came up. | Rajesh | 01/18/23 8:20 PM
Row 173 | @rajesh.haravde@penske.com , This is ragarding the issues you posted in the email. Maven build is failing when we run the tests but without tests it is getting successful. @hugo.scavino@penske.com | Gayam | 01/14/23 12:29 AM
Row 173 | @krishna.tanga@penske.com / @yogesh.sinha@penske.com , Please review the log4j/maven changes in below MR and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/bbupload-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 11/28/22 9:02 AM
Row 174 | In the build log. | Rajesh | 06/13/23 11:32 PM
| @rajesh.haravde@penske.com , Narsimha able to build from feature/maven branch and deployed to dev. | Gayam | 06/14/23 3:09 AM
Row 174 | @praneeth.gayam@penske.com please guide. Error 2-Jun-2023 14:19:17 Finished publishing of artifact Non required shared artifact: [Source], pattern: [src/**] in 19.73 ms 12-Jun-2023 14:19:17 Publishing an artifact: target 12-Jun-2023 14:19:17 Unable to publish artifact [target]: 12-Jun-2023 14:19:17 The artifact is required for down stream Stages and Jobs, build will now fail. 12-Jun-2023 14:19:17 The artifact hasn't been successfully published after 4.918 ms 12-Jun-2023 14:19:17 Publishing an artifact: XML 12-Jun-2023 14:19:17 Unable to publish artifact [XML]: 12-Jun-2023 14:19:17 The artifact is required for down stream Stages and Jobs, build will now fail. 12-Jun-2023 14:19:17 The artifact hasn't been successfully published after 5.120 ms 12-Jun-2023 14:19:17 Running post build plugin 'Artifactory Release Management Staging' 12-Jun-2023 14:19:17 Running post build plugin 'Artifactory Build Info Copier' 12-Jun-2023 14:19:17 Running post build plugin 'Artifactory Gradle Properties Info Copier' 12-Jun-2023 14:19:17 Running post build plugin 'npm Cache Cleanup' 12-Jun-2023 14:19:17 Running post build plugin 'NCover Results Collector' | Rajesh | 06/12/23 11:54 PM
| @rajesh.haravde@penske.com , where are you getting above error? | Gayam | 06/13/23 1:35 AM
Row 174 | @praneeth.gayam@penske.com can we proceed with "develop_log4j" branch for maven validation? | Rajesh | 05/30/23 10:46 PM
| Sure @rajesh.haravde@penske.com | Gayam | 05/31/23 1:01 AM
| @rajesh.haravde@penske.com , Onboard develop_log4j to bamboo and deploy to dev is completed. https://bamboo.penske.com/deploy/viewEnvironment.action?id=142802957 | Gayam | 06/01/23 12:08 AM
Row 174 | @rajesh.haravde@penske.com , Bamboo build for this app is https://bamboo.penske.com/browse/CCMS-CCMSSVVC | Gayam | 03/07/23 12:22 AM
Row 174 | GIT URL info: https://bitbucket.penske.com/scm/ptlcorp/ccmsservice-web.gitBranch :develop_log4J | Rajesh | 03/04/23 1:16 AM
Row 174 | Please build bamboo deployment script for development environment. | Rajesh | 03/04/23 1:11 AM
Row 174 | Thanks @rajesh.haravde@penske.com . Please review the below PR when you get a chance. https://bitbucket.penske.com/projects/PTLCORP/repos/ccmsservice-web/pull-requests/3/overview | Gayam | 02/16/23 10:44 PM
Row 174 | Its false positive please do the needful. no action needed at this time. | Rajesh | 02/16/23 3:43 AM
Row 174 | we do not want to address secrete mitigation at this movement. please move forward with project upgrade with respect to bitbucket, maven and log4j | Rajesh | 02/16/23 3:41 AM
Row 174 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:46 PM
Row 174 | validation work in progress. | Rajesh | 01/18/23 8:23 PM
Row 174 | @rajesh.haravde@penske.com / @krishna.tanga@penske.com , Log4j team completed log4j/maven changes on this app. Please review them in below MR and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/ccmsservice-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/10/22 3:29 AM
| We will do the needful as requested and get back to you the build result as early as possible. | Rajesh | 12/12/22 10:14 PM
Row 175 | @praneeth.gayam@penske.com Application is failing to run on QA environment. Immediate attention needed as we are getting ready to push for next step. | Rajesh | 08/29/23 12:32 AM
| @rajesh.haravde@penske.com , as discussed in the email, the error related to dlinks auth filter. AOs are discussing with Architecture tema on this issue. | Gayam | 08/30/23 2:21 AM
Row 175 | We are seeing only master and develop branch in bamboo. what happens to rest of bitbucket branches. | Rajesh | 06/14/23 12:12 AM
| @rajesh.haravde@penske.com , As part of the process when we onboard to bamboo only master and develop will be onboarded. If you want any other branch, please let us know. we will add. | Gayam | 06/15/23 12:50 AM
Row 175 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:08 AM
| @rajesh.haravde@penske.com , this app is deployed to dev using develop branch - https://bamboo.penske.com/browse/CVIBP-CVIW2/deployments | Gayam | 06/10/23 1:40 AM
Row 175 | Its merged. please take it forward. | Rajesh | 04/26/23 8:24 PM
| @rajesh.haravde@penske.com , this app is deployed to dev using develop_log4j branch - https://bamboo.penske.com/browse/CVIBP-CVIW1/deployments Please verify and merge the code to develop branch. | Gayam | 04/27/23 1:34 AM
Row 175 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 175 | Bitbucket and maven validation completed. awaiting on development environment configuration to move forward. | Rajesh | 04/25/23 5:58 PM
| Thanks @rajesh.haravde@penske.com . PR is still in open status. Could you please merge. In the mean time we will onboard to bamboo. | Gayam | 04/26/23 1:20 AM
Row 175 | @rajesh.haravde@penske.com / @venkata.bobba@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/PTLCORP/repos/cvi-web/pull-requests/5/overview | Gayam | 03/03/23 1:36 AM
Row 175 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So changing the status to (Cap) Maven | Gayam | 02/16/23 11:26 PM
Row 175 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:47 PM
Row 175 | Validation work in progress | Rajesh | 01/18/23 8:21 PM
Row 175 | @rajesh.haravde@penske.com , log4j and maven changes are completed for this application. Could you please review them in the below PR and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/cvi-web/pull-requests/5/overview @mathumala.nachiappan@penske.com | Gayam | 12/14/22 10:36 AM
Row 175 | Need to determine who will work this app. Was notified by @hugo.scavino@penske.com we may not have an resource. | Yvette Urso | 11/22/22 2:43 AM
| we are the owner of the application. please let us know if you need any information on source URL. but we do want to move to maven and bitbucket. | Rajesh | 12/12/22 10:16 PM
Row 176 | Ready to Deploy | Rajesh | 09/11/23 5:29 PM
Row 176 | @rajesh.haravde@penske.com , Build and deployment completed in Dev. Please verify the application in dev. https://bamboo.penske.com/browse/FIXEDASSETBP-FXDAT1/deployments | Gayam | 05/22/23 9:29 PM
Row 176 | PR been executed please take it forward. Thanks for guidance on process Praneeth appreciated. | Rajesh | 05/18/23 1:48 AM
Row 176 | @rajesh.haravde@penske.com , If you are able to verify the develop_log4j branch, could you please merge the PR. https://bitbucket.penske.com/projects/PTLCORP/repos/fixedasset-web/pull-requests/3/overview | Gayam | 05/17/23 3:14 AM
| @rajesh.haravde@penske.com Onboarding both develop_log4j and develop branches to bamboo is completed. Running the develop branch failed as pom.xml is not in develop. Also, deployment in dev from develop_log4j is successful. Please merge abiove PR. | Gayam | 05/18/23 12:59 AM
Row 176 | I am not able to change App Status using my login can anyone please reset my profile, as i was able to update it last week. Thanks. | Rajesh | 05/16/23 6:50 PM
Row 176 | We able to build project using maven. please change status "(AO) Maven completed. | Rajesh | 05/16/23 6:49 PM
Row 176 | Thanks @rajesh.haravde@penske.com . We have completed log4j/maven changes for this application. Please review in below PR. https://bitbucket.penske.com/projects/PTLCORP/repos/fixedasset-web/pull-requests/3/overview | Gayam | 02/16/23 11:33 PM
Row 176 | we do not want to address secrete mitigation at this movement. please move forward with project upgrade with respect to bitbucket, maven and log4j | Rajesh | 02/16/23 3:41 AM
Row 176 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:49 PM
Row 176 | @april.ottey@penske.com / @yogesh.sinha@penske.com ,Please review the PR and provide your approval. https://bitbucket.penske.com/projects/PTLCORP/repos/fixedasset-web/pull-requests/3/overview FYI: @mathumala.nachiappan@penske.com | Gayam | 11/24/22 3:46 AM
Row 177 | App deployed to PROD on 10/12/2023 | Sreekanth | 10/12/23 10:27 PM
Row 177 | @praneeth.gayam@penske.com this app depends on irs.jar and irs.jar is built with xsd folder. We thought the xsd folder is not being used in hvutefile explicitly but we are wrong. This app requires both irs.jar & xsd also to be part of the source in order to run. So, we've placed the xsd folder also in hvutefile source. Latest code is available in "develop" branch. If possible, can we generate the java source from xsd in hvutefile application itself & generate hvutefilebatch.jar file with both hvutefile (com.penske.apps.hvut) & irs (gov.irs.efile) packages. If this works, we can completely remove the irs repo in bitbucket & corresponding bamboo plans & irs artifactory dependency. All the source can be maintained in single repo i.e. hvutefilebatch. | Sreekanth | 10/05/23 1:04 AM
| Sue @sreekanth.kancharla@penske.com . We will check and get back to you. | Gayam | 10/05/23 1:11 AM
| I could see a PR is created to develop branch. Posted a comment in Bitbucket. Please check. We are also going live without combining both the applications. If we've the source ready with combined logic, then we'll use that next time when we make any changes to the application. | Sreekanth | 10/10/23 9:04 PM
Row 177 | Review: @sreekanth.kancharla@penske.com , This app is ready for youe review. https://bitbucket.penske.com/projects/PTLCORP/repos/hvutefile-batch/pull-requests/3/overview | Gayam | 07/09/23 11:50 PM
| @praneeth.gayam@penske.com Thank you! Merged the PR. We'll start testing this app. Please change the App Status accordingly. | Sreekanth | 07/10/23 7:09 PM
| @sreekanth.kancharla@penske.com , Do we need to onboard to bamboo? | Gayam | 07/10/23 11:27 PM
| @praneeth.gayam@penske.com Yes, please! | Sreekanth | 07/11/23 12:02 AM
| @praneeth.gayam@penske.com In develop branch, the version "2.0.0-feature-irs_Maven_XSD-to-java--20230628.124813-3" is provided. Do we need to have the version hard coded. We'll place the irs source in the irs repo and execute the build plan which should placed the jar in artifactory & this latest jar should be loaded in hvutefile batch app. Hope in this case, hard coded version would not work. | Sreekanth | 07/11/23 12:05 AM
| @sreekanth.kancharla@penske.com , I think if we remove the version, it always brings the latest version. But when you execute the build of irs, you should build the hvute also to get the latest irs files to hvute. | Gayam | 07/11/23 11:47 PM
| @praneeth.gayam@penske.com Yes, that is how the hvutefile app works. We always build the irs jar with latest source code and then once that build is successful, we'll initiate the build for hvutefile app, so latest irs will be used in the build. So getting the latest version of irs.jar is expected. | Sreekanth | 07/12/23 2:08 AM
| @sreekanth.kancharla@penske.com , Changed the version from specific number to 'RELEASE'. It is taking whatever latest IRS release from artifactory. | Gayam | 07/25/23 12:00 AM
| @praneeth.gayam@penske.com Perfect! We'll work on testing the app, once the issue with irs.jar is resolved. | Sreekanth | 07/25/23 5:35 PM
| irs issue is resolved. Please check this application. Thanks. | Gayam | 08/02/23 2:47 AM
| @praneeth.gayam@penske.com Great, we'll continue testing this application as well. Thank you! | Sreekanth | 08/03/23 9:20 PM
| @sreekanth.kancharla@penske.com , Release version of irs jar is available in artifactory and build of develop_log4j branch of hvute is working fine. Please verify. | Gayam | 08/18/23 12:24 AM
| @praneeth.gayam@penske.com Please create PR to develop branch. | Sreekanth | 08/18/23 7:43 AM
| @sreekanth.kancharla@penske.com Following is the PR. https://bitbucket.penske.com/projects/PTLCORP/repos/hvutefile-batch/pull-requests/6/overview | Gayam | 08/18/23 8:03 PM
| @praneeth.gayam@penske.com PR merged. Thank you! We'll continue testing. | Sreekanth | 08/18/23 8:37 PM
| @praneeth.gayam@penske.com We are getting below warning with IRS jar with version as RELEASE in local maven build. Is there anything we need to do? Some problems were encountered while building the effective model for com.penske.corp:hvutefilebatch:jar:2.0.0-SNAPSHOT 'dependencies.dependency.version' for com.penske.corp:irs:jar is either LATEST or RELEASE (both of them are being deprecated) @ line 79, column 13 It is highly recommended to fix these problems because they threaten the stability of your build. For this reason, future Maven versions might no longer support building such malformed projects. | Sreekanth | 09/06/23 7:40 PM
| Yes @sreekanth.kancharla@penske.com . They are recommending to maintain the version numbers. But if we want always the latest then we have to use RELEASE which is not recommended. | Gayam | 09/07/23 1:31 AM
| @praneeth.gayam@penske.com As suggested, used 1.0.0-SNAPSHOT in hvutefile but getting below error in local build. Could not resolve dependencies for project com.penske.corp:hvutefilebatch:jar:2.0.0-SNAPSHOT: Could not find artifact com.penske.corp:irs:jar:1.0.0-SNAPSHOT in corp-mvn-virtual (https://artifactory.penske.com/artifactory/corp-mvn-virtual) | Sreekanth | 09/09/23 12:17 AM
Row 177 | Query: @veronique.labeille@penske.com , Adding to above secrets validation, there is one more query. This app depends on irs.jar but it is not available in artifactory. Could you please provide your approval to upload this jar into artifactory at below location. Groupid: gov.irs.efile Artifactid: irs Thanks. | Gayam | 04/07/23 10:55 PM
| @praneeth.gayam@penske.com irs.jar file is not static dependency. Every 6 months, we get latest files from IRS and with those files the irs.jar file be created via existing bamboo plan (https://bamboo.penske.com/browse/HVUTBP-HVUTFDEV) used for the application jar creation as well. The current bamboo plan generates, both irs.jar and hvutefile.jar which is app specific jar. Post testing the irs.jar file in SUPPORT by users, the same will be pushed to QA & PROD. In this case, please suggest how the irs.jar file can be moved to artifactory. @veronique.labeille@penske.com | Sreekanth | 04/12/23 12:27 AM
| @sreekanth.kancharla@penske.com , what is the repo of irs.jar? If the repo exist, we can mavanize IRS and create a new bamboo plan which uploads the jar to artifactory. Update that dependency in hvutefile pom and rebuild and deploy the hvutefile app. I hope it resolves our issue. Let me know whether I did not understand the requirement correctly. | Gayam | 04/12/23 1:00 AM
| @praneeth.gayam@penske.com The repo for irs.jar also resides in same location of hvutefile i.e. "https://svn.penske.com/svn/webprojects/corp/hvutefile/branches/support/production_latest/xsd" Every time we get the files from IRS, we replace them under xsd folder. We are not sure how the existing bamboo plan generating the 2 jar files. Hope analyzing the bamboo script should help us how the irs.jar is being generated. | Sreekanth | 04/12/23 7:13 AM
| @sreekanth.kancharla@penske.com I extracted the irs.jar and it looks like it has the files from the folder https://bitbucket.penske.com/projects/PTLCORP/repos/hvutefile-batch/browse/irs%20java%20files?at=refs%2Fheads%2Fdevelop In my opinion, we have to segregate hvutefile and irs files into 2 separate projects in bitbucket and 2 separate bamboo builds. We can setup a call with @hugo.scavino@penske.com to discuss on this further. thanks. | Gayam | 04/13/23 12:50 AM
| @praneeth.gayam@penske.com Thank for the details. So are those irs java files not depending on the files from below folder which we need to replace yearly twice? https://bitbucket.penske.com/projects/PTLCORP/repos/hvutefile-batch/browse/xsd?at=refs%2Fheads%2Fdevelop Sure, we can connect with Hugo. Please proceed with scheduling the meeting. | Sreekanth | 04/13/23 1:14 AM
| @sreekanth.kancharla@penske.com , it doesn't seem like that jar has those xsd files. But I am not sure. Could you please check whether there is any relation. | Gayam | 04/13/23 11:25 PM
| @praneeth.gayam@penske.com FP ticket# 1834638 is created to architect team for clarification on irs.jar generation. | Sreekanth | 04/19/23 9:16 PM
| @praneeth.gayam@penske.com We received clarification from Architect team with FP# 1834638. The irs.jar is completely dependent on source/xsd/ETEC/2290/Return2290.xsd folder & source/lib/jaxb-xjc.jar With this the xsd folder is required to build the irs.jar file and these will be changed twice per year. If this can be built as a separate bamboo plan and add this jar as dependency in artifactory, we are ok with that. If so, please have this new plan under the existing bamboo project itself. We can connect with @hugo.scavino@penske.com on this for any further guidance if needed. | Sreekanth | 04/24/23 8:35 PM
| Thanks @sreekanth.kancharla@penske.com . So we need to create separate bitbucket repository for the irs files. Is that correct? @hugo.scavino@penske.com | Gayam | 04/26/23 1:15 AM
| @praneeth.gayam@penske.com Yes, if that needs to be maintained as a separate dependency. | Sreekanth | 04/26/23 6:15 PM
| Sure @sreekanth.kancharla@penske.com . Sent an email to Yvette to add one more line item irs.jar in smartsheets. We will start working on it. Thanks | Gayam | 04/28/23 2:19 AM
| @sreekanth.kancharla@penske.com , Yvette create a separate line item for irs.jar. We will complete that and add that dependency to this project and will let you know. Thanks | Gayam | 05/02/23 1:14 AM
| @sreekanth.kancharla@penske.com , Could you please confirm what are the folders from hvutefile repo need to move to irs repo. I know following. 1. You said source/xsd/ETEC/2290/Return2290.xsd folder. Do you mean total xsd folder source/xsd? 2. source/lib/jaxb-xjc.jar Any other folders are files need to move to irs repo? | Gayam | 05/03/23 2:05 AM
| @praneeth.gayam@penske.com Replied the answer in the irs.jar item. | Sreekanth | 05/03/23 7:46 PM
| @sreekanth.kancharla@penske.com , We are getting compilation issues because of irs.jar doesn't have required java classes. 1.import gov.irs.efile.ObjectFactory; 2.import gov.irs.efile.Return; I believe we need to add 'irs java files' fold r under hvutefile to irs.jar. Could you please check and confirm. Thanks. | Gayam | 05/25/23 3:09 AM
| @praneeth.gayam@penske.com These imports are part of irs.jar file only. Is that dependency added to hvutefile pom, if so we shouldn't get these compiler errors. | Sreekanth | 05/25/23 8:19 PM
| @sreekanth.kancharla@penske.com But irs.jar file doesn't have these java classes. Only schema files. | Gayam | 05/25/23 11:54 PM
| @praneeth.gayam@penske.com The irs.jar file should be generated with the xsd files available under xsd folder. Once the irs.jar file is generated, that needs to be uploaded to artifactory every time, so that hvutefile app used that as dependency. | Sreekanth | 06/01/23 12:14 AM
| @sreekanth.kancharla@penske.com , We are working on it. | Gayam | 06/01/23 10:48 PM
Row 177 | @veronique.labeille@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:28 AM
| @praneeth.gayam@penske.com Except the "conf/as400server.prop" file, no other file required any mitigation. "conf/as400server.prop" - To remove the dependency, we need to implement the connection framework which required some analysis. Either we'll implement the connection framework OR we'll continue with the prop file itself. Please proceed with the log4j changes. @veronique.labeille@penske.com | Sreekanth | 04/12/23 12:22 AM
| Sure @sreekanth.kancharla@penske.com . We will continue with the current code as you suggested. | Gayam | 04/12/23 1:21 AM
Row 177 | @praneeth.gayam@penske.com - SVN to BB migration issue | Mathumala Nachiappan | 02/02/23 10:28 AM
Row 177 | Sure @veronique.labeille@penske.com . Thanks for the confirmation | Mathumala Nachiappan | 02/01/23 8:12 PM
Row 177 | @mathumala.nachiappan@penske.com , would you please add this app to your plan? Thank you | Veronique Labeille | 01/27/23 10:38 PM
Row 177 | @mathumala.nachiappan@penske.com please share that information to me via email with the Fleet Service Team, hugo and Don included. I am not aware of any change to assignment for these. | Yvette Urso | 01/11/23 2:09 AM
Row 177 | @yvette.urso@penske.com - To confirm this application to be taken by CAP for Modernization activity. CC: @brian.hug@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:40 AM
Row 177 | hi @yvette.urso@penske.com - as per the previous communication, modernization will be taken care by the Fleet services team. from the latest update of yours, is it moved under CAP scope for modernization? | Mathumala Nachiappan | 12/08/22 3:51 PM
Row 177 | @mathumala.nachiappan@penske.com this will remain where it it per @veronique.labeille@penske.com - I moved to (Cap) Analysis. Please move to the correct status per your work. | Yvette Urso | 12/02/22 12:15 AM
Row 177 | @veronique.labeille@penske.com @mathumala.nachiappan@penske.com @praneeth.gayam@penske.com - Veronique, can you please confirm this application is no longer a part of Corp App Group and it should be moved to fall under the Fleet Services Team? Thank you | Yvette Urso | 12/01/22 8:39 PM
| @yvette.urso@penske.com , It is part of Fleet Services which is under CORP systems | Veronique Labeille | 12/01/22 9:22 PM
Row 177 | Scope is moved to Fleet services Team. CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com and @april.ottey@penske.com | Mathumala Nachiappan | 12/01/22 8:10 PM
Row 178 | <groupId>com.penske.websphere8.lib</groupId> <artifactId>mail</artifactId> <version>1.0.0</version> </dependency> | Narsimhamurthy | 08/30/23 8:22 AM
| From where did you take this jar and added to pom.xml | Narsimhamurthy | 08/30/23 8:22 AM
Row 178 | @praneeth.gayam@penske.com can you clarify below 1. is bamboo script triggering .sh files to start this batch same like old job 2.logs not generated after scheduled deployment in QA.does this job in scheduled deployment list? 3. can you provide the details which script is using to start this batch from bamboo | Narsimhamurthy | 08/18/23 10:44 PM
| @narsimhamurthy.peddoju@penske.com , As far as we know, ant scripts are used for creating the package only. After that, webservices scripts will trigger the batch apps in the respective server. Please verify the app and let us know if we miss anything. | Gayam | 08/21/23 9:48 PM
Row 178 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:09 AM
| @rajesh.haravde@penske.com , this is already onboarded to Bamboo. Please deploy to QA and verify. https://bamboo.penske.com/browse/IRMBUILD-IRMBACH1/ | Gayam | 06/09/23 1:50 AM
| provide access to above url | Narsimhamurthy | 08/18/23 10:39 PM
Row 178 | PR been executed please take it forward. Thanks for guidance on process Praneeth appreciated. | Rajesh | 05/18/23 1:48 AM
| @rajesh.haravde@penske.com , build on develop branch is successful. Please deploy to QA. | Gayam | 05/18/23 10:49 PM
Row 178 | @praneeth.gayam@penske.com We able to build project JAR FILE using maven. please change the status to next step. Thanks. | Rajesh | 05/17/23 1:32 AM
| @rajesh.haravde@penske.com , could you please merge the PR. https://bitbucket.penske.com/projects/PTLCORP/repos/irm-batch/pull-requests/3/overview | Gayam | 05/17/23 3:10 AM
| @rajesh.haravde@penske.com , Onboarding both develop_log4j and develop branches to bamboo are completed. Please merge the above PR. So that build on develop branch will be successful. | Gayam | 05/18/23 12:57 AM
Row 178 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/irm-batch/pull-requests/3/overview | Gayam | 02/16/23 11:41 PM
Row 178 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:49 PM
Row 178 | Work in progress. | Rajesh | 01/18/23 8:22 PM
Row 178 | @rajesh.haravde@penske.com - Pls. approve the PR after your review and confirmation. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:21 PM
Row 179 | App deployed to PROD on 10/12/2023 as part of hvutefile batch application. | Sreekanth | 10/12/23 10:28 PM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 10/13/23 6:35 AM
Row 179 | @praneeth.gayam@penske.com You are correct. Even we've to use RELEASE version, shouldn't we've version? So should we use the dependency as below with no version at all? <dependency> <groupId>com.penske.corp</groupId> <artifactId>irs</artifactId> </dependency> OR as below <dependency> <groupId>com.penske.corp</groupId> <artifactId>irs</artifactId> <version>RELEASE</version> </dependency> | Sreekanth | 08/14/23 6:29 PM
| @sreekanth.kancharla@penske.com , we will create a release version and will let you know. thanks | Gayam | 08/15/23 1:02 AM
Row 179 | @sreekanth.kancharla@penske.com , Following question already asked in hvutefile line item. Just moving the conversation from hvutefile line item to irs.jar line item. Could you please confirm what are the folders from hvutefile repo need to move to irs repo. I know following. 1. You said source/xsd/ETEC/2290/Return2290.xsd folder. Do you mean total xsd folder source/xsd? 2. source/lib/jaxb-xjc.jar Any other folders are files need to move to irs repo? | Gayam | 05/03/23 2:08 AM
| @praneeth.gayam@penske.com Those are the only files needed to build the jar. We can check on any other dependency when we have the bamboo build issues. | Sreekanth | 05/03/23 7:45 PM
| @praneeth.gayam@penske.com The status is "Waiting on AO". Please let us know in case any other details required from us. | Sreekanth | 05/08/23 9:32 PM
| @sreekanth.kancharla@penske.com , Changed to Cap. | Gayam | 05/08/23 10:21 PM
| @sreekanth.kancharla@penske.com , Completed the changes for irs.jar. Please check https://bitbucket.penske.com/projects/PTLCORP/repos/irs/pull-requests/2/overview | Gayam | 05/13/23 2:44 AM
| @praneeth.gayam@penske.com Added review comment. | Sreekanth | 05/17/23 2:39 AM
| @sreekanth.kancharla@penske.com , Modified the folder name. Please verify. | Gayam | 05/18/23 1:44 AM
| @praneeth.gayam@penske.com Merged the PR. | Sreekanth | 05/18/23 2:02 AM
| We are wokring on XSD to java files binding on this jar. | Gayam | 06/01/23 10:49 PM
| @sreekanth.kancharla@penske.com , This utility app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/irs/pull-requests/4/overview | Gayam | 06/24/23 12:28 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 06/26/23 6:34 PM
| @sreekanth.kancharla@penske.com , This app is onboarded to Bamboo and jar is deployed to artifactory. Please verify. thanks. | Gayam | 06/28/23 12:57 AM
| @praneeth.gayam@penske.com We'll validate this once hvutefile app completed as the irs.jar is the dependency for another app. | Sreekanth | 06/28/23 2:46 AM
| @sreekanth.kancharla@penske.com , We created a release version of this jar and used in hvutefile. But we observed recently that build of irs is failing after the creation of release version. Team is checking on this. Thanks. | Gayam | 07/25/23 12:01 AM
| @praneeth.gayam@penske.com Ok, thank you! | Sreekanth | 07/25/23 5:33 PM
| @praneeth.gayam@penske.com Please let us know in case any update on above mentioned issue fix. | Sreekanth | 07/31/23 11:22 PM
| @sreekanth.kancharla@penske.com , Log4j CICD team is working with Architecture team to resolve the issue. Hopefully we will get some solution in a day. Thanks. | Gayam | 08/01/23 12:39 AM
| @sreekanth.kancharla@penske.com , issue got resolved and created a release version. Please check bitbucket and bamboo. Thanks. | Gayam | 08/02/23 2:46 AM
| @praneeth.gayam@penske.com We are using irs dependency in hvut as below which is giving error. Please provide the version value for the release version which you created. <dependency> <groupId>com.penske.corp</groupId> <artifactId>irs</artifactId> <version>2.0.0-develop_log4j-20230628.200202-3</version> </dependency> | Sreekanth | 08/11/23 6:25 PM
| @sreekanth.kancharla@penske.com , you said that you don't want to provide the version number..right? Instead you can provide RELEASE which brings the latest release version. | Gayam | 08/13/23 3:26 AM
Row 180 | Awaiting on Singoff | Rajesh | 09/11/23 5:29 PM
Row 180 | @praneeth.gayam@penske.com Application is failing to run on QA environment. Immediate attention needed as we are getting ready to push for next step. | Rajesh | 08/29/23 12:31 AM
| @rajesh.haravde@penske.com , as discussed in the email, the error related to dlinks auth filter. AOs are discussing with Architecture tema on this issue. | Gayam | 08/30/23 2:21 AM
Row 180 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:09 AM
| @rajesh.haravde@penske.com , This is already onbaorded to bamboo and deployed to Dev. https://bamboo.penske.com/browse/RSIBP-RSIB2/deployments | Gayam | 06/09/23 1:48 AM
Row 180 | Done. Please take it forward. | Rajesh | 04/26/23 8:28 PM
| @rajesh.haravde@penske.com , this app is deployed to dev using develop_log4j branch - https://bamboo.penske.com/browse/RSIBP-RSIB1/deployments Please verify and merge the code to develop branch. | Gayam | 04/27/23 2:07 AM
Row 180 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 180 | Validation with bitbucket & Maven done. we are awaiting on development environment configuration and validation. | Rajesh | 04/25/23 5:57 PM
| Thanks @rajesh.haravde@penske.com . PR is still in open status. Could you please merge. In the mean time we will onboard to bamboo. | Gayam | 04/26/23 1:19 AM
Row 180 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/rsi-web/pull-requests/3/overview | Gayam | 02/16/23 11:45 PM
Row 180 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:49 PM
Row 180 | Work in progress. | Rajesh | 01/18/23 8:22 PM
Row 180 | @rajesh.haravde@penske.com , We have completed the log4j/maven changes. Please review them and merge in below MR. https://bitbucket.penske.com/projects/PTLCORP/repos/rsi-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/09/22 6:43 AM
| We will do the needful as requested and get back to you on build results. Thanks. Please do the same thing as requested earlier for CVI project too. | Rajesh | 12/12/22 10:21 PM
Row 181 | @rajesh.haravde@penske.com , the status modified as App Deployed. But looking at above comments it is still in Maven review. Also, no bamboo deployments happened. Please check and let us know whether the updated status correct or not. @yvette.urso@penske.com | Gayam | 10/06/23 5:51 PM
Row 181 | Web.xml file was not configured properly. Please take prod version and check other conf files as well | Narsimhamurthy | 08/30/23 7:36 AM
| @narsimhamurthy.peddoju@penske.com , Do you mean copy web.xml and other conf files from trageted/prod folder? | Gayam | 08/30/23 10:52 PM
Row 181 | Bamboo build job has to create | Narsimhamurthy | 08/17/23 9:10 PM
| @narsimhamurthy.peddoju@penske.com , once the review completes and you merge the code, you can provide a comment to onboard to bamboo. Is the review completed? | Gayam | 08/18/23 12:56 AM
Row 181 | @rajesh.haravde@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/PTLCORP/repos/safetydata-web/pull-requests/3/overview | Gayam | 06/16/23 4:02 AM
Row 181 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 181 | On Secrete with respect to Safety data, we are not implementing any code change at this time. please take forward as it is. | Rajesh | 04/26/23 8:02 PM
Row 181 | Secrets: @rajesh.haravde@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:34 AM
Row 181 | @rajesh.haravde@penske.com confirmed following URL for web application. Web project URL : https://svn.penske.com/svn/webprojects/corp/safety/ branches/dev_gh/ | Gayam | 02/10/23 3:10 AM
Row 181 | @rajesh.haravde@penske.com , Both web and Batch bamboo plan is connecting to same repo. Not sure whether that is correct or are we missing nay info. Usually web and batch projects should be separate..right? @mathumala.nachiappan@penske.com | Gayam | 12/09/22 1:57 AM
| Safetydata and safetydata.war are same project. here the info as requested. Please find details of repo and bamboo build for QA environment. Repo: https://svn.penske.com/svn/webprojects/corp/safety/ Branch : branches/dev_gh/ Bamboo Build : https://bamboo.penske.com/browse/SAF-SAFQA | Rajesh | 12/12/22 10:26 PM
| @hugo.scavino@penske.com , Both web and batch projects related to this app have same repository. Not sure how it is going as we have to have separate bamboo builds and repos in mavanization. Could you please suggest. Thanks. @rajesh.haravde@penske.com | Gayam | 01/26/23 12:03 AM
Row 181 | Changed status to AO Bamboo | Yvette Urso | 12/15/22 2:54 AM
Row 181 | @rajesh.haravde@penske.com - Issue with Folder structure. Pls. share the folder reference to start the log4J changes. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:12 PM
| what do you mean by folder reference ?please schedule team call to take it forward thanks. | Rajesh | 12/01/22 9:52 PM
| @rajesh.haravde@penske.com , Web and Batch both source code, configuration files commit in single SVN repo....So they are used same repo to both WEB and Batch build plan... It is required to separate the source code, configuration files for Web and Batch. https://svn.penske.com/svn/webprojects/corp/safety/ and same branch "branches/dev_gh/ " but artifact generation is different for both @mathumala.nachiappan@penske.com | Gayam | 12/08/22 3:10 AM
| SafetyData QA : https://bamboo.penske.com/browse/SAF-SAFQA SafetyData PROD: | Rajesh | 12/09/22 1:36 AM
| https://bamboo.penske.com/browse/SAF-SAFPROD | Rajesh | 12/09/22 1:36 AM
Row 182 | App deployed to PROD on 08/22/2023 | Sreekanth | 08/23/23 7:35 PM
Row 182 | @veronique.labeille@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:29 AM
| @praneeth.gayam@penske.com I've provided the source as https://bitbucket.penske.com/projects/PTLCORP/repos/hvut-web/browse The shared secrets looks something different and the excel file doesn't has the source path. We don't have the below file in the bitbucket source "src/main/liberty/config/server.xml" which is part of the secret. Please clarify. @veronique.labeille@penske.com | Sreekanth | 02/25/23 2:34 AM
| @sreekanth.kancharla@penske.com , In the file we have inserted 2 columns Columns B & C. These 2 columns are from the Log4j team's review. Column B gives the info about whether it is a True/False positive. Column C gives the info about why it is a False or True positive. For the current issue, we provided the reason 'The file is not available,It is from the commit history'. Secrets scanning tool gives the secrets even if the commit history contains any secrets. Please check and let us know if you have any more questions. | Gayam | 02/27/23 11:43 PM
| @praneeth.gayam@penske.com Thank you for the clarification. We've made small change in this application and yet to be deployed to PROD. The code is not yet merged to master branch and still available in develop only. I'll have the code merged to master branch, so your team can work on log4j migration. | Sreekanth | 03/04/23 3:02 AM
| Thanks @sreekanth.kancharla@penske.com . Are these changes as part of secrets mitigation or something else? Also, please let us know once you merge your chagnes to develop branch. | Gayam | 03/07/23 12:17 AM
| @praneeth.gayam@penske.com These changes are not part of secrets. We are making changes as part of ongoing projects. The changes are merged to develop branch and yet to merge with master. | Sreekanth | 03/07/23 12:37 AM
| @sreekanth.kancharla@penske.com once your changes are deployed to production, are you planning to merge the develop_log4j to develop branch? develop_log4j contains the log4j team's changes | Gayam | 03/08/23 12:03 AM
| @praneeth.gayam@penske.com Sure, we'll take care of merging the log4j changes from develop_log4j to develop post prod deployment of current changes. | Sreekanth | 03/08/23 3:02 AM
| @praneeth.gayam@penske.com FYI, we've scheduled the PROD deployment with our changes today 04/11/2023. All the code is merged to master branch and develop branch. Could you please create PR from develop_log4j to develop branch tomorrow? | Sreekanth | 04/11/23 11:42 PM
| Sure @sreekanth.kancharla@penske.com | Gayam | 04/12/23 1:11 AM
| @praneeth.gayam@penske.com FYI, the deployment to PROD is completed. You are good to create PR for log4j changes to develop branch. | Sreekanth | 04/12/23 8:26 PM
| @sreekanth.kancharla@penske.com , Created PR https://bitbucket.penske.com/projects/PTLCORP/repos/hvut-web/pull-requests/41/overview | Gayam | 04/13/23 12:26 AM
| @praneeth.gayam@penske.com The PR has conflict. Could you please resolve and push the changes. | Sreekanth | 04/13/23 12:47 AM
| @praneeth.gayam@penske.com I've merged both the PR. We are good now. We'll continue testing the changes in local and use the existing Bamboo plan https://bamboo.penske.com/browse/HVUTBP-HVUTW itself to deploy to DEV and test once we are good with local testing. @veronique.labeille@penske.com | Sreekanth | 04/14/23 8:03 PM
| @praneeth.gayam@penske.com We've started testing this application in local & DEV. Please change the "App Status" accordingly. | Sreekanth | 04/19/23 9:17 PM
| @praneeth.gayam@penske.com We've tested this app in QA & got signoff from Users as well. Please update the "App Status". | Sreekanth | 05/22/23 8:50 PM
| @sreekanth.kancharla@penske.com , Changed the status. | Gayam | 05/22/23 10:13 PM
Row 182 | @veronique.labeille@penske.com , We couldn't find the SVN location and Bamboo build for this application. Could you please provide the requested info. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/18/23 2:09 AM
| @praneeth.gayam@penske.com This application is redesigned with a new name and the artifact name is "hvutirsforms.war". hvutirsforms is already in bitbcket. https://bitbucket.penske.com/projects/PTLCORP/repos/hvut-web/browse @mathumala.nachiappan@penske.com @veronique.labeille@penske.com | Sreekanth | 01/27/23 10:06 PM
| Thanks @sreekanth.kancharla@penske.com . From which branch you want us to create log4j branch. Also, please provide the bamboo location. | Gayam | 01/27/23 10:11 PM
| @praneeth.gayam@penske.com master branch is good to use for migration. Bamboo: https://bamboo.penske.com/browse/HVUTBP-HVUTW | Sreekanth | 01/27/23 10:17 PM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (Cap)Log4j | Gayam | 02/01/23 12:35 AM
Row 182 | @veronique.labeille@penske.com Testing Email | Yvette Urso | 01/25/23 1:25 AM
Row 182 | @yvette.urso@penske.com - To confirm this application to be taken by CAP for Modernization activity. CC: @brian.hug@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:40 AM
Row 182 | hi @yvette.urso@penske.com - as per the previous communication, modernization will be taken care by the Fleet services team. from the latest update of yours, is it moved under CAP scope for modernization? | Mathumala Nachiappan | 12/08/22 3:50 PM
Row 182 | @mathumala.nachiappan@penske.com this will remain where it it per @veronique.labeille@penske.com - I moved to (Cap) Analysis. Please move to the correct status per your work. | Yvette Urso | 12/02/22 12:15 AM
Row 182 | @veronique.labeille@penske.com @mathumala.nachiappan@penske.com @praneeth.gayam@penske.com - Veronique, can you please confirm this application is no longer a part of Corp App Group and it should be moved to fall under the Fleet Services Team? Thank you | Yvette Urso | 12/01/22 8:39 PM
| @yvette.urso@penske.com , It is part of Fleet Services which is under CORP systems | Veronique Labeille | 12/01/22 9:20 PM
Row 182 | Scope is moved to Fleet services Team. CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com and @april.ottey@penske.com | Mathumala Nachiappan | 12/01/22 8:10 PM
Row 183 | App deployed to PROD on 09/14/2023 | Sreekanth | 09/15/23 6:41 PM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 09/16/23 12:19 AM
Row 183 | Review: @sreekanth.kancharla@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/PTLCORP/repos/scorecard-batch/pull-requests/3/overview | Gayam | 05/03/23 2:13 AM
| @praneeth.gayam@penske.com Added review comment to the PR. please check and do the need. | Sreekanth | 05/08/23 10:58 PM
| @praneeth.gayam@penske.com I could the review comment is taken care. I've merged the PR. Please proceed with further process. | Sreekanth | 05/09/23 7:12 PM
| @sreekanth.kancharla@penske.com , Onboarded develop branch to Bamboo--------https://bamboo.penske.com/browse/CBP-CEFLEETB0 Please deploy to QA. | Gayam | 05/11/23 11:22 PM
| @praneeth.gayam@penske.com We've started validating the changes in our local environment, post that we'll deploy this to QA. Hope the "App Status" needs to be changed to AO team. | Sreekanth | 05/22/23 8:42 PM
| Yes @sreekanth.kancharla@penske.com . I already kept this app in (AO)Bamboo Review status. | Gayam | 05/22/23 10:09 PM
Row 183 | @veronique.labeille@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:29 AM
| @praneeth.gayam@penske.com Apart from 1 secret related to "src/conf/DB.properties" no other required any mitigation. For "src/conf/DB.properties", as per my analysis, this file seems unused. Please proceed with log4j changes. While testing this application, we'll remove the "src/conf/DB.properties" and test. Post testing, we'll remove this file and corresponding changes in the code. | Sreekanth | 04/12/23 12:02 AM
| Sure @sreekanth.kancharla@penske.com . Thanks | Gayam | 04/12/23 1:18 AM
Row 183 | Thanks @yvette.urso@penske.com . Following is the repo and bamboo details for this project. Batch: - https://svn.penske.com/svn/webprojects/corp/cefleetBatch/trunk/cefleetBatch Bamboo: https://bamboo.penske.com/browse/CBP | Gayam | 02/01/23 2:54 AM
Row 183 | @praneeth.gayam@penske.com I created a Batch and Web for Scorecard. Moved the status to (Cap) Analysis - please update the status to the right one from here. Thank you | Yvette Urso | 02/01/23 2:24 AM
Row 184 | App deployed to PROD on 09/14/2023 | Sreekanth | 09/15/23 6:41 PM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 09/16/23 12:19 AM
Row 184 | @praneeth.gayam@penske.com We've received confirmation from Manager that we'll continue with "scorecard" name. With this, we'll have to change the artifact name to "cefleetservices" in pom.xml as that is the context root of the application. We'll make this code change from our end. The other change should be in bamboo deploy plan(s) variable "appname" should also be as "cefleetservices" along with this, please delete the old deploy plan https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=140509192 | Sreekanth | 05/09/23 7:17 PM
| @sreekanth.kancharla@penske.com , Changed variable Appname from 'scorecard' to 'cefleetservices' in the deploy spec. Also, deleted the old deploy plans and run feature branch according to deleted deploy plans. https://bamboo.penske.com/browse/CBP-CEFLEETW/deployments https://bamboo.penske.com/deploy/config/configureEnvironmentVariables.action?environmentId=142802994 | Gayam | 05/11/23 11:21 PM
| @praneeth.gayam@penske.com Seems still the app is not deploying fine and I could see somewhere the name of the war is still scorecard.war & scorecard.tgz but we've changed that to cefleetservices.war and the same is available in target folder of artifact in bamboo. Please check below deployment logs and do the need. https://bamboo.penske.com/deployment-download/142802994/build_logs/142737427-142802994-141069075.log | Sreekanth | 05/12/23 6:49 PM
| @sreekanth.kancharla@penske.com , We observed following things. Changes for artifact id has done in "feature/FS-132-Log4j2-Testing" .But recently 2 more branches were created and artifact id is still "scorecard" . So need to make changes in those 2 branches pom file . https://bamboo.penske.com/deployment-download/142802994/build_logs/142737427-142802994-141068843.log - Deployment with "feature/FS-132-Log4j2-Testing" https://bamboo.penske.com/deployment-download/142802994/build_logs/142737427-142802994-141069010.log - Deployment with "develop-log4j-ao-testing" Could you please check. | Gayam | 05/15/23 11:33 PM
| @praneeth.gayam@penske.com We kept the artifact id as "scorecard" to have no change artifactory folder path but we've changed the final-name to "cefleetservices". Even then the artifact name is creating as scorecard-2.0.0-feature-sree-peer-review-20230515.190735-7.war Is that based on the artifactId attribute from pom file, if so then we've no choice other than making the artifactId to "scorecard" so the path in artifactory also would be as com/penske/cefleetservices instead of com/penske/scorecard Since the correct app name is scorecard we wanted to have the same everywhere except the artifact name as "cefleetservices" Hope you understand, please suggest on this. | Sreekanth | 05/16/23 2:19 AM
| @sreekanth.kancharla@penske.com , Theoretically it is possible but this has to be discussed with the broad team as environment has multiple steps to deploy to the server like build, deployment to artifactory, deployment to /opt location and a websphere script deploys to desire websphere server. | Gayam | 05/17/23 3:06 AM
| We've changed the artifact id in pom file to "cefleetservices" only so artifact name also will be the same. | Sreekanth | 05/22/23 8:41 PM
Row 184 | Review: @sreekanth.kancharla@penske.com , this app is ready for review. https://bitbucket.penske.com/projects/PTLCORP/repos/scorecard-web/pull-requests/3/overview | Gayam | 03/18/23 1:11 AM
| @praneeth.gayam@penske.com Added review comments. Please check. | Sreekanth | 04/11/23 11:53 PM
| @sreekanth.kancharla@penske.com , As discussed we implemented the review comments. Please check and merge. Thanks | Gayam | 04/15/23 12:44 AM
| @praneeth.gayam@penske.com The PR is merged. Please proceed with further steps. | Sreekanth | 04/15/23 12:55 AM
| Thanks @sreekanth.kancharla@penske.com . We will onboard to bamboo and deploy to Dev | Gayam | 04/19/23 3:26 AM
| @sreekanth.kancharla@penske.com , Bamboo build onboarding completed. Dev deployment done using develop branch. Please verify. Thanks. https://bamboo.penske.com/browse/CBP-CEFLEETW | Gayam | 04/20/23 2:05 AM
| @praneeth.gayam@penske.com Thank you for the update. We'll start testing this app in DEV. | Sreekanth | 04/24/23 8:35 PM
| @praneeth.gayam@penske.com If possible, please change the name of the plan in Bamboo from "scorecard-Web" to "scorecard-web" to maintain the consistency between Bamboo & Bitbucket. | Sreekanth | 04/24/23 11:41 PM
| Sure @sreekanth.kancharla@penske.com . we will let you know once the change implemented. | Gayam | 04/25/23 1:11 AM
| @sreekanth.kancharla@penske.com , changes are completed. Please verify. | Gayam | 04/27/23 2:12 AM
| @praneeth.gayam@penske.com Thank you for making the naming corrections as same as bitbucket repo name for both build & deploy plans. Started using new deploy plan. Please delete old deploy plan. | Sreekanth | 04/27/23 7:01 PM
Row 184 | @praneeth.gayam@penske.com No remediation required for the shared secrets. @veronique.labeille@penske.com | Sreekanth | 02/25/23 2:36 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to Cap Maven | Gayam | 02/27/23 11:45 PM
Row 184 | @praneeth.gayam@penske.com The status is as (AO). Please remind us in case you are waiting on something from us. CC: @veronique.labeille@penske.com | Sreekanth | 02/22/23 8:40 PM
| @sreekanth.kancharla@penske.com , Secrets need to be confirmed. I will share all the secrets of new corp apps. Thanks. | Gayam | 02/23/23 3:29 AM
| @veronique.labeille@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:29 AM
Row 184 | @praneeth.gayam@penske.com I created a Batch and Web for Scorecard. Moved the status to (Cap) Analysis - please update the status to the right one from here. Thank you | Yvette Urso | 02/01/23 2:24 AM
Row 184 | @veronique.labeille@penske.com , We couldn't find the SVN location and Bamboo build for this application. Could you please provide the requested info. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/18/23 2:08 AM
| @praneeth.gayam@penske.com This application has 2 projects. Web - https://svn.penske.com/svn/webprojects/corp/cefleet/trunk/cefleetservices Batch: - https://svn.penske.com/svn/webprojects/corp/cefleetBatch/trunk/cefleetBatch Bamboo: https://bamboo.penske.com/browse/CBP Not sure why we've only 1 application in this file. @mathumala.nachiappan@penske.com @veronique.labeille@penske.com | Sreekanth | 01/27/23 10:09 PM
| @sreekanth.kancharla@penske.com , Please let us know whether we need to modernize both batch and war applicaitons for this app. If yes, @yvette.urso@penske.com please insert 1 more column for batch app. @mathumala.nachiappan@penske.com | Gayam | 01/27/23 10:17 PM
Row 184 | @yvette.urso@penske.com - To confirm this application to be taken by CAP for Modernization activity. CC: @brian.hug@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:40 AM
Row 184 | hi @yvette.urso@penske.com - as per the previous communication, modernization will be taken care by the Fleet services team. from the latest update of yours, is it moved under CAP scope for modernization? | Mathumala Nachiappan | 12/08/22 3:51 PM
Row 184 | @mathumala.nachiappan@penske.com this will remain where it it per @veronique.labeille@penske.com - I moved to (Cap) Analysis. Please move to the correct status per your work. | Yvette Urso | 12/02/22 12:15 AM
Row 184 | @veronique.labeille@penske.com @mathumala.nachiappan@penske.com @praneeth.gayam@penske.com - Veronique, can you please confirm this application is no longer a part of Corp App Group and it should be moved to fall under the Fleet Services Team? Thank you | Yvette Urso | 12/01/22 8:39 PM
| @yvette.urso@penske.com , It is part of Fleet Services which is under CORP systems | Veronique Labeille | 12/01/22 9:24 PM
Row 184 | Scope is moved to Fleet services Team. CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com and @april.ottey@penske.com | Mathumala Nachiappan | 12/01/22 8:11 PM
Row 187 | @praneeth.gayam@penske.com @jeremiah.ashway@penske.com After meeting with the business team, a decision has been made to retire this application. You may cease all modernization activity on this application . Please mark it as Retired as soon as you see this message. | Gianfranco | 10/03/23 12:55 AM
| Sure @frank.d'angelo@penske.com . Thaks for the update. | Gayam | 10/03/23 1:27 AM
Row 187 | @praneeth.gayam@penske.com All items found are validated as false positive. Please proceed. | Gianfranco | 08/24/23 1:49 AM
| Thanks @frank.d'angelo@penske.com | Gayam | 08/24/23 4:11 AM
Row 187 | @jeremiah.ashway@penske.com , I sent the secrets file of this app in email. Could you please check it and let su know whether it requires any code changes. Thanks. | Gayam | 08/22/23 2:20 AM
Row 188 | @praneeth.gayam@penske.com I changed the status. It was "Waiting on AO". Note the AO start date of 8/14. | Gianfranco | 08/15/23 10:22 PM
| Thanks @frank.d'angelo@penske.com | Gayam | 08/17/23 1:04 AM
Row 188 | @praneeth.gayam@penske.com FedEx Rental is not in scope for CapGemini, it is a retired application. Can we remove? | Gianfranco | 08/15/23 8:20 PM
| @frank.d'angelo@penske.com , status mentioned as 'Retire App'. So we are not working on this app. | Gayam | 08/15/23 9:04 PM
Row 188 | @frank.d'angelo@penske.com , Could you please let us know whether this application is going away. If not could you please provide the production branch. We are unable to find from bamboo as the prod deploy never ran on this application. Thanks. | Gayam | 02/15/23 12:36 AM
Row 188 | @frank.d'angelo@penske.com - Per Frank please get with him prior to starting - this app may go away. | Yvette Urso | 01/25/23 2:54 AM
Row 189 | Thanks @frank.d'angelo@penske.com | Gayam | 08/18/23 1:02 AM
Row 189 | @praneeth.gayam@penske.com That is fine. We will work to retire, but for your team you can mark it as retired. | Gianfranco | 08/17/23 1:46 AM
Row 189 | @praneeth.gayam@penske.com FI Migration batch is going to be retired by Penske team. We can consider this app completed at this time. | Gianfranco | 08/17/23 12:01 AM
| @frank.d'angelo@penske.com , Can I change the status as Retired? | Gayam | 08/17/23 1:13 AM
Row 189 | @praneeth.gayam@penske.com RETIREMENT? - there is a chance this app can just be retired and I have a task to research this. Please hold off for the time being on this application and focus on others. | Gianfranco | 08/14/23 11:38 PM
Row 189 | Query: @jeremiah.ashway@penske.com , We are able to find the bitbucket repo for this app but not bamboo build. Without bamboo build we couldn't figure out the production branch. Could you please let us know the latest branch which is deployed to production. BB Repo: https://bitbucket.penske.com/projects/EBCE/repos/fimigration/browse | Gayam | 07/27/23 8:50 AM
Row 190 | Application will be retired. No longer needed due to recent upgrades with automating fuel price data feed. I have marked application as App Status = Retired | Gianfranco | 08/21/23 9:42 PM
Row 190 | @praneeth.gayam@penske.com , yes Please hold. Will have an answer tomorrow | Gianfranco | 08/17/23 2:13 AM
Row 190 | @praneeth.gayam@penske.com , this application may be able to be retired. Checking with the business. Fuel prices are now automatically populated, so this may not be needed. | Gianfranco | 08/17/23 1:16 AM
| @frank.d'angelo@penske.com , Do you want us to hold this applicaton for now? | Gayam | 08/17/23 1:19 AM
Row 190 | @praneeth.gayam@penske.com We have reviewed the assessment and agree that these are false positives. Please proceed to the next step. | Gianfranco | 08/16/23 1:49 AM
| Thanks @frank.d'angelo@penske.com . Changing the status to Cap Maven. | Gayam | 08/17/23 12:58 AM
Row 190 | @sree.gopal@penske.com , I sent secrets in an email. Could you please verify it. Thanks. | Gayam | 08/05/23 12:33 AM
Row 191 | @praneeth.gayam@penske.com @shweta.gupta@penske.com We have done some additional research and found that this application is obsolete. We are flagging this for retirement. You may stop working on modernizing it. | Gianfranco | 08/31/23 2:37 AM
| Thanks @frank.d'angelo@penske.com for the update. | Gayam | 08/31/23 11:28 PM
Row 191 | @praneeth.gayam@penske.com All items found are validated as false positive. Please proceed. | Gianfranco | 08/24/23 1:44 AM
| Thanks @frank.d'angelo@penske.com . Changing the stauts to Cap Maven. | Gayam | 08/24/23 3:59 AM
Row 191 | @shweta.gupta@penske.com , I sent the secrets file of this app in email. Could you please check it and let su know whether it requires any code changes. Thanks. | Gayam | 08/22/23 2:24 AM
Row 192 | @praneeth.gayam@penske.com The team completed their analysis of this batch. It has not processed any transactions since 2018. The application that initiated JMS queue transactions was sunset in 2018. This must have accidentally been left behind. We are going to shut down in QA and monitor, but we are 99.999% sure this is going to be retired. I am going to change the status to Retire App. Can you do me a favor and change the Current AO status dates to blank for any app that is marked as "retire app". Thanks. | Gianfranco | 08/24/23 3:07 AM
| @frank.d'angelo@penske.com , Current AO status is populating automatically. @yvette.urso@penske.com , Can you help on this please | Gayam | 08/24/23 4:22 AM
Row 192 | For our reference, ticket to shut down batch in QA submitted: https://jira.penske.com/browse/ITDSW-2647 | Gianfranco | 08/24/23 3:18 AM
Row 192 | @jeremiah.ashway@penske.com , I sent secrets in an email. Could you please verify it. Thanks. | Gayam | 08/05/23 12:35 AM
Row 193 | @praneeth.gayam@penske.com Please do not proceed with working on this application. We have a partner org who is going to be completely rewriting this application, so we want to hold off on modernizing presently. I am going to mark it as Retire App for now to get it off the list. If something changes, I will let you know. | Gianfranco | 08/22/23 7:05 PM
Row 194 | @praneeth.gayam@penske.com , we have confirmed that SSO Service is not used. We are going to mark it for retirement | Gianfranco | 08/28/23 9:47 PM
Row 194 | @praneeth.gayam@penske.com , we are not seeing any usage. We are going to turn this off in QA and see if there is any impact to applications. We will keep this as Waiting on AO, but we may be retiring this application. | Gianfranco | 08/23/23 2:07 AM
| @frank.d'angelo@penske.com , thanks for the update. | Gayam | 08/23/23 8:06 AM
Row 194 | @praneeth.gayam@penske.com NEEDS RESEARCH - Multiple configuration files (for each env) a lot of our applications use this approach. I will need to check, but maybe architecture has a solution for this as this style of setup is used by many Penske apps. Is the expectation that the Penske team needs to remediate existing builds that are not environment agnostic? | Gianfranco | 08/14/23 11:39 PM
| @frank.d'angelo@penske.com , Cap Log4j team will create a new bamboo build and deploy plan. But to go that step, application needs to be written in a way that one build version can be deployed to all environments. | Gayam | 08/14/23 11:48 PM
Row 194 | @jeremiah.ashway@penske.com / @frank.d'angelo@penske.com , This application's resources folder has different xml files for each environment and virtual-host name variable is different in prod, qa ibm-web-bnd.xml files. As modernization involves environment agnostic build which means 1 build needs to be deployed to different environments. In this case, we can't use different xml files for diff environments. Could you please check how to resolve this issue. Thanks. | Gayam | 08/01/23 1:08 AM
Row 208 | Per Pramod - This application will be retired by Q2 2024. | Yvette Urso | 05/12/23 12:46 AM
Row 208 | Question: @pete.macmahon@penske.com , Could you please provide the response to above question. Thanks. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 03/24/23 10:53 PM
Row 208 | Peter - Currently off SVN. Will be moving Savion platform but not until 2024. We want to go ahead and upgrade this app by end of JSM project. | Yvette Urso | 03/24/23 7:10 PM
Row 208 | @pete.macmahon@penske.com , For this application both SVN and Bamboo are not available. Could you please let us know the SVN and Bamboo details. Thanks. | Gayam | 01/14/23 1:05 AM
Row 209 | Kalrav is not familiar with this app but will ask his offshore team. | Yvette Urso | 05/11/23 12:59 AM
Row 209 | Per Kathy Marko - As indicated in my previous email, this application can be retired. I believe this would fall under Steve McMullen and/or Kalrav to retire the application as I am just the business process owner. Thank you, Kathy | Yvette Urso | 05/11/23 12:14 AM
Row 209 | Changing owner of this application and need to work with April to determine who to work with for this application. | Yvette Urso | 05/01/23 9:12 PM
Row 209 | @scott.bortzel@penske.com , For this application SVN repo available https://svn.penske.com/svn/webprojects/admin/SEM/. But Bamboo plan is not available. We need production branch confirmation for log4j-Migration and without existing bamboo build we could not find this. Could you please let us know what is the latest production branch. Thanks. | Gayam | 01/14/23 1:03 AM
| @scott.bortzel@penske.com , Could you please provide the response to above question. Thanks. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 03/24/23 10:53 PM
Row 211 | Decision is to retire these applications | Yvette Urso | 05/01/23 9:17 PM
Row 211 | smvendors feeds cyclops.war. So dependent to this app. | Yvette Urso | 05/01/23 9:13 PM
Row 211 | @scott.bortzel@penske.com / @scott.pemrick@penske.com , For this application both SVN and Bamboo are not available. Could you please let us know the SVN and Bamboo details. Thanks. | Gayam | 01/14/23 1:06 AM
| @scott.bortzel@penske.com / @scott.pemrick@penske.com , Could you please provide the response to above question. Thanks. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 03/24/23 10:54 PM
Row 212 | Decision is to retire these applications | Yvette Urso | 05/01/23 9:17 PM
Row 212 | @scott.bortzel@penske.com / @scott.pemrick@penske.com , For this application both SVN and Bamboo are not available. Could you please let us know the SVN and Bamboo details. Thanks. | Gayam | 01/14/23 1:06 AM
| @scott.bortzel@penske.com / @scott.pemrick@penske.com , Could you please provide the response to above question. Thanks. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 03/24/23 10:51 PM
Row 215 | @praneeth.gayam@penske.com Unitjkt has been made platform agnostic in the "feature/unitjkt_PlatformAgnosticChanges" branch on bitbucket, and is ready for a bamboo build plan. | Mikos | 11/04/23 1:42 AM
| Sure @kenneth.mikos@penske.com . We will let you know once the deployment completes. | Gayam | 11/07/23 2:06 AM
| @kenneth.mikos@penske.com , Onboarded branch 'feature/unitjkt_PlatformAgnosticChanges' to bamboo and deployment to dev is completed. Please verify. build plan: https://bamboo.penske.com/browse/UJBP-UJW dev deployment: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=157913211 | Gayam | 11/07/23 11:31 PM
| @praneeth.gayam@penske.com The new Unitjkt bamboo plan is building and deploying correctly to Dev and QA environments. The app has also been tested and is working correctly on both environments. Thanks! | Mikos | 11/09/23 8:16 PM
| Thanks for the update @kenneth.mikos@penske.com | Gayam | 11/09/23 8:17 PM
Row 215 | Thanks @praneeth.gayam@penske.com - we will make platform agnostic changes and let you know. @david.long@penske.com , @kenneth.mikos@penske.com | Patel | 11/02/23 1:22 AM
Row 215 | Review & Query: We have completed the modernization of this app with an open query. Please review it. PR: https://bitbucket.penske.com/projects/MAIN/repos/unitjkt-web/pull-requests/3/overview Query: This application has environment based header.jsp and web.xml files. It looks like build depends on environment. But in environment agnostic build, one build can be deployed to different environments. So code needs to satisfy in that way. Could you please check and rectify this. | Gayam | 11/01/23 2:38 AM
Row 215 | @praneeth.gayam@penske.com - I discussed this with @david.long@penske.com . Yes, we would like you to manually upload the coversheet jar to artifactory. We do not want to change any existing logic \ dependencies. | Patel | 08/15/23 2:32 AM
| Thanks @falgun.patel@penske.com . Changing the status to Cap Maven | Gayam | 08/15/23 8:43 PM
Row 215 | @praneeth.gayam@penske.com , As the jar is currently being referenced by existing application, let's keep that jar in the build for now. | Patel | 07/28/23 12:47 AM
| @falgun.patel@penske.com , That mean do you want us to maually upload the coversheet jar to artifactory? | Gayam | 07/31/23 2:24 AM
Row 215 | Question: @david.long@penske.com , There is a coversheet jar in the lib folder of this app but without that jar also build is getting successful. Do you want us to upload this jar to artifactory and include that dependency in pom? | Gayam | 07/19/23 3:31 AM
Row 215 | Query: @david.long@penske.com , This application dependent on attachservice-client.jar(shared jar) latest version but the latest version is not available in artifactory. Old version is available in artifactory which is used by several other apps. The latest jar build is done by you from the below branch. SVN-URL: https://svn.penske.com/svn/fieldsys/other/attachment-service/ tags/qa/_T_QA-2022-06-16 Can we upload latest version to artifactory? | Gayam | 07/06/23 4:27 AM
| That may be a question for @stella.george@penske.com and @subramanian.vennimalayan@penske.com as they work with attachment service more than I do. I built that last year, but I'm sure some things have been changed since then | David | 07/06/23 7:27 PM
| @stella.george@penske.com / @subramanian.vennimalayan@penske.com , Could you please check the above comment and provide your response. Thanks. | Gayam | 07/07/23 12:16 AM
| @praneeth.gayam@penske.com please use the latest jar for attachment artifactory. | David | 07/11/23 1:28 AM
Row 215 | @praneeth.gayam@penske.com Emailed you back. no code changes are required as all secrets found were false positives. | David | 07/03/23 11:21 PM
| Thanks @david.long@penske.com . Chaning the status to Cap Maven. | Gayam | 07/03/23 11:23 PM
Row 215 | @david.long@penske.com / @falgun.patel@penske.com , I sent the secrets to you in the email. Please analyze and let me know wether this requires any code changes. Thanks. | Gayam | 07/03/23 11:14 PM
Row 215 | @praneeth.gayam@penske.com This is still in the "waiting on AO" status. Is there something I need to address? yea the attach svc client jar may already be in artifactory. | David | 06/09/23 6:21 PM
| @david.long@penske.com , Do we need to modernize the UnitJacket_ATTACHSVCCLIENT_JAR (Jar repo)- https://svn.penske.com/svn/fieldsys/other/attachment-service/Jar/prod too? | Gayam | 06/10/23 2:06 AM
| I don't think you need to. To my knowledge the attachment svc client jar is already on artifactory which means it should be running on maven, but I'm not totally sure. If it's not, then yes the attach svc client jar would need to be modernized | David | 06/15/23 1:33 AM
| Sure @david.long@penske.com . We will check and come back to you. | Gayam | 06/15/23 1:50 AM
| @david.long@penske.com , We found the dependency in artifactory. We will use this dependency in unitjkt. <dependency> <groupId>com.penske.mis.common.sharedlib</groupId> <artifactId>attachservice-client</artifactId> <version>1.0.0-20210310.061729-1</version> </dependency> | Gayam | 06/16/23 1:06 AM
| @david.long@penske.com , As indicated in the comment of 'servicereqweb.war' app, the penske team is doing the modernization of attachservice-client jar. So, we will be including the following dependency in the unitjkt.war. <dependency> <groupId>com.penske.mis.common.sharedlib</groupId> <artifactId>attachservice-client</artifactId> <version>1.0.0-20210310.061729-1</version> </dependency> | Gayam | 06/19/23 7:59 PM
| Sounds good thank you @praneeth.gayam@penske.com | David | 06/21/23 7:55 PM
Row 215 | @yojando.drullard@penske.com , Log4j team started working on modernizing this application. When we verified the old production bamboo build we are seeing following 2 repositories mentioned in the build. UnitJacket_PROD - https://svn.penske.com/svn/fieldsys/maintenance/unit-jacket/tags/prod/20220623/unitjkt UnitJacket_ATTACHSVCCLIENT_JAR (Jar repo)- https://svn.penske.com/svn/fieldsys/other/attachment-service/Jar/prod I am expecting 2nd one is a dependency jar for the first repo. Is that correct? If yes, we need to do the log4j and mavanization for the dependency jar also. Could you please check and confirm. Thanks. FYI: @shane.myers@penske.com | Gayam | 05/18/23 1:16 AM
| @praneeth.gayam@penske.com Yojando is no longer an employee at Penske. You are correct that the 2nd one is the dependency jar. The jar supports attachments in unit jacket. The attach svc client jar is already in artifactory i believe. I am not sure on the status of log4j for attach service | David | 06/06/23 10:30 PM
| @david.long@penske.com . Thanks for the info. we need to modernize the attach svc client jar also. @yvette.urso@penske.com , Could you please add one line in smartsheets for UnitJacket_ATTACHSVCCLIENT_JAR. | Gayam | 06/07/23 3:37 AM
Row 216 | Hi @praneeth.gayam@penske.com , The application is working good. We are deploying it into production next week. Thanks, Sai Kothapalli. | Kothapalli | 09/09/23 12:48 AM
| @saisatyakrishna.kothapalli@penske.com Thanks for the update. | Gayam | 09/09/23 2:41 AM
Row 216 | @praneeth.gayam@penske.com The app deployed to qa | Kothapalli | 09/08/23 7:34 PM
Row 216 | @praneeth.gayam@penske.com Sure, Thanks | Kothapalli | 09/06/23 6:10 PM
| @saisatyakrishna.kothapalli@penske.com , onboarded to bamboo successfully. build plan: https://bamboo.penske.com/browse/PARTSPO-PRTSPBH0/ deploy plan: https://bamboo.penske.com/browse/PARTSPO-PRTSPBH0/deployments Please deploy to QA and test. Thanks | Gayam | 09/07/23 12:49 AM
Row 216 | @praneeth.gayam@penske.com , we have merged the changes to the develop branch. May I know whether the pipeline is configured for this to deploy in QA?? | Kothapalli | 09/05/23 10:59 PM
| @saisatyakrishna.kothapalli@penske.com , we need to onboard the app to bamboo. We will let you know once we complete that task. | Gayam | 09/06/23 1:02 AM
Row 216 | In above attached document. In Jee resources.xml we are seeing the JDBC was changed GHDBC1 from support may I know the reason? | Kothapalli | 08/31/23 8:41 PM
| @saisatyakrishna.kothapalli@penske.com , Check the targeted/prod/jee-resources.xml | Gayam | 09/01/23 12:10 AM
Row 216 | @praneeth.gayam@penske.com @karthikeyan.srinivasan@penske.com We have made changes in pom.xml we have fixed the spring version issue and have modified the log4j2.Please have a look on Develop_Log4j branch.. I request please go through the pom and we are seeing lot of spring dependencies we are thinking that some of them are not required can you please validate pom and remove the unused dependencies.. | Kothapalli | 08/30/23 2:22 AM
| @saisatyakrishna.kothapalli@penske.com , We added the dependencies by checking into lib folder of master branch. it contains all the spring ones. | Gayam | 08/30/23 10:57 PM
Row 216 | @praneeth.gayam@penske.com @saisatyakrishna.kothapalli@penske.com The partspo-batch app is set in Sai's machine and it is running. Mavenization is complete. Yet log4j2 configuration is not printing log messages. I have asked Sai to look in to that. The application set up with mavenization is done. We have modified the pom.xml with version modifications and dependency additions for mavenization. | Karthikeyan | 08/30/23 12:06 AM
Row 216 | The code (PropertiesFilesManager.PROPERTIES_FILE_NAME) refers the location of the file as "/conf/init_propfiles.properties" which seems logically correct. But upon execution, the file could not be found. @praneeth.gayam@penske.com | Karthikeyan | 08/23/23 1:22 AM
| I tried giving the absolute path as well. That failed too. | Karthikeyan | 08/23/23 1:22 AM
| @karthikeyan.srinivasan@penske.com , all the files under resources folders will be added to classpath as per maven. I am seeing init_propfiles.properties file under resournces/conf folder. That means this file is in classpath. | Gayam | 08/23/23 8:06 AM
Row 216 | The properties files are not being read when I checked them recently when I have pulled the code from this branch (https://bitbucket.penske.com/projects/MAIN/repos/partspo-batch/browse?at=refs%2Fheads%2Fdevelop_Log4j). @praneeth.gayam@penske.com | Karthikeyan | 08/21/23 11:35 PM
| @karthikeyan.srinivasan@penske.com , Please explain what properties files you are refrring to. We copied all the resource files to src/main/resources. Let us know whether we missed anything. | Gayam | 08/22/23 9:33 PM
Row 216 | @praneeth.gayam@penske.com I pulled the latest code. I still see the following spring-jms-5.1.18.RELEASE - 6.0.0 spring-messaging - 5.3.15 spring-orm - 5.3.14 spring-oxm - 5.3.15 Is the same branch used? The branch shows that the latest commit was on 10th August. https://bitbucket.penske.com/projects/MAIN/repos/partspo-batch/pull-requests/3/commits Am I missig something? | Karthikeyan | 08/19/23 12:02 AM
| @karthikeyan.srinivasan@penske.com , Yes the develop_log4j branch is correct. | Gayam | 08/21/23 9:37 PM
Row 216 | Let me check. | Karthikeyan | 08/18/23 11:03 PM
Row 216 | @praneeth.gayam@penske.com The pom uses Spring 4.3 while the application context uses 3.1 | Karthikeyan | 08/18/23 2:57 AM
| @karthikeyan.srinivasan@penske.com , We followed the confluence and changed the versions. Please check and let us know the issue. | Gayam | 08/18/23 8:22 PM
Row 216 | I am unable to run the main method. | Karthikeyan | 08/18/23 2:46 AM
Row 216 | @praneeth.gayam@penske.com The application is not running after log4j2 conversion. | Karthikeyan | 08/18/23 2:46 AM
Row 216 | @praneeth.gayam@penske.com the project compiles successfully. However, I have to check the configuration and execution of the code. | Karthikeyan | 08/17/23 2:39 AM
Row 216 | @praneeth.gayam@penske.com I am currently checking the local build and deploy for this application. Will provide an update by EOD | Karthikeyan | 08/16/23 5:56 PM
Row 216 | Review: @karthikeyan.srinivasan@penske.com / @stella.george@penske.com , This app is ready for your review. Please validate and merge. Thanks. https://bitbucket.penske.com/projects/MAIN/repos/partspo-batch/pull-requests/3/overview | Gayam | 06/30/23 1:01 AM
| @praneeth.gayam@penske.com Karthik is working on it. | Stella george | 08/15/23 2:59 AM
Row 216 | Secrets: @stella.george@penske.com I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:56 AM
| @praneeth.gayam@penske.com There is no secrets in this application. | Stella george | 06/14/23 1:38 AM
| Thanks @stella.george@penske.com . We will do the mavanization. | Gayam | 06/14/23 3:10 AM
Row 217 | Looks good. | Vaddi Mani | 08/21/23 9:15 PM
| Thanks @sarath.mani@penske.com . | Gayam | 08/22/23 9:48 PM
Row 217 | @dale.porter@penske.com , build plan onboarded and deployment to artifactory is also successful. Please verify. Build plan: https://bamboo.penske.com/browse/PNSKESPLNGBP-PENSKESPLNGCLT0 | Gayam | 08/03/23 12:50 AM
Row 217 | @dale.porter@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/penske_spelling_client/pull-requests/3/overview | Gayam | 07/27/23 2:26 AM
| I reviewed and merged the code. Thank you. | Dale Porter | 07/28/23 1:50 AM
| Will onbaoard to bamboo. | Gayam | 07/31/23 2:33 AM
Row 217 | I approve and please move forward with uploading the needed jars. | Dale Porter | 07/10/23 11:58 PM
| Thanks @dale.porter@penske.com | Gayam | 07/11/23 6:55 AM
Row 217 | @dale.porter@penske.com , This app depends on RapidSpellMDict.jar and RapidSpellWeb.jar jars. They are not available in artifactory. Please provide your approval to upload to artifactory in below location@dale.porter@penske.com , This app depends on RapidSpellMDict.jar and RapidSpellWeb.jar jars. They are not available in artifactory. Please provide your approval to upload to artifactory in below lcoation. Thanks. groupid - com.keyoti.rapidSpell | Gayam | 07/06/23 4:18 AM
Row 217 | No secrets found on this app. So changing the status to Cap Maven. | Gayam | 07/03/23 11:02 PM
Row 218 | Yes, Thx! | Vaddi Mani | 08/23/23 9:00 PM
Row 218 | Looks good. | Vaddi Mani | 08/18/23 10:10 PM
| Thanks @sarath.mani@penske.com . Can I change the status to Done as this is just a dependency doesn't have to go to any server. | Gayam | 08/21/23 9:49 PM
Row 218 | @dale.porter@penske.com , onboarded to bamboo and deployed to artifactory. https://bamboo.penske.com/browse/PNSKESPLNGBP-PSUJ | Gayam | 07/12/23 1:40 AM
Row 218 | Sarath has approved and merged this back on June 28th in bitbucket. Thank you. | Dale Porter | 07/11/23 12:02 AM
Row 218 | Review: @stella.george@penske.com / @dave.kost@penske.com , This utility app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/penske_spellingutility/pull-requests/2/overview | Gayam | 06/24/23 12:25 AM
Row 218 | There are no secrets exist for this application. So changing the status of this app to Cap Maven. | Gayam | 06/23/23 12:13 AM
Row 219 | @praneeth.gayam@penske.com , I don't have access to the specified bamboo path hence took help from @sarath.mani@penske.com did the bamboo build and verified the artifact. Everything looks good with the jar. | Subramanian | 09/06/23 1:35 AM
| Thanks @subramanian.vennimalayan@penske.com | Gayam | 09/07/23 1:27 AM
Row 219 | @praneeth.gayam@penske.com we have verified the changes and merged the PR | Subramanian | 08/31/23 8:13 PM
| Thanks @subramanian.vennimalayan@penske.com . We will onboard to Bamboo and upload the jar to artifactory. | Gayam | 08/31/23 11:42 PM
| @subramanian.vennimalayan@penske.com , we have onboarded the app to bamboo and deploy to artifactory. Please verify. https://bamboo.penske.com/browse/SVCRQ-SVCREQUTIL0 | Gayam | 09/02/23 4:15 AM
Row 219 | @praneeth.gayam@penske.com I have verified the pull request and it looks like the source has been taken from https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/tags/prod/PROD_2023-04-06 we did two more prod deploy after that tag. Could you please use the below tag and add the changes. https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/tags/prod/PROD_2023-06-27 | Subramanian | 07/28/23 2:35 AM
| @subramanian.vennimalayan@penske.com , Are there any changed made in the servicerequestutility folder? Also, are you planning any more prod deployments or code changes? | Gayam | 07/31/23 2:48 AM
| @praneeth.gayam@penske.com We are good with 2023-04-06 tag. please move forward. | Stella george | 08/19/23 12:12 AM
| Thanks @stella.george@penske.com . In that case, please review the PR and merge. https://bitbucket.penske.com/projects/MAIN/repos/servicerequestutility/pull-requests/2/overview | Gayam | 08/21/23 9:50 PM
Row 219 | @stella.george@penske.com , This app is ready for review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/servicerequestutility/pull-requests/2/overview | Gayam | 07/07/23 1:08 AM
Row 219 | Secrets: @stella.george@penske.com , I sent the secrets in the email. Please verify and let us know whether this app requires code changes. | Gayam | 06/28/23 12:45 AM
| @stella.george@penske.com confirmed there are no code chagnes required for this app. | Gayam | 07/06/23 3:36 AM
Row 220 | @praneeth.gayam@penske.com PR has been reviewed and merged. | Shawn | 09/05/23 9:10 PM
| Thanks @shawn.mcmurtry@penske.com . we will onboard to bamboo and deploy to artifactory. | Gayam | 09/06/23 12:58 AM
| @shawn.mcmurtry@penske.com , smsserviceutility is successfully uploaded in artifactory through bamboo. Maven dependency: <groupId>com.penske.maintenance</groupId> <artifactId>smsserviceutility</artifactId> <version>2.0.0-develop-20230906.072026-1</version> | Gayam | 09/07/23 12:48 AM
Row 220 | @shawn.mcmurtry@penske.com , Modernization completed and following is the PR. Please review and merge. https://bitbucket.penske.com/projects/MAIN/repos/smsserviceutility/pull-requests/2/overview | Gayam | 08/30/23 9:58 PM
Row 221 | Just to not it's not DONE as in deployed to PROD, but DONE as in it's working and now Penske needs to promote to PROD. Thanks, | David | 08/25/23 12:36 AM
Row 221 | @praneeth.gayam@penske.com I found the Bitbucket build, but I don't have access to it, so I'm getting access and then will confirm that it's up on artifactory | David | 07/11/23 1:31 AM
| @david.long@penske.com , We referred a different source repo for this app. We are reworking on this app as each application's prod reference have different sosutility folders. Trying to compare all these and we will ask the question if there are any differences. Thanks. Changing the status of the app to Cap. | Gayam | 07/11/23 6:53 AM
| Thanks for the update @praneeth.gayam@penske.com Keep me posted if there are any questions | David | 07/11/23 7:30 PM
| @david.long@penske.com , All the changes are completed and deployed to artifactory. Following is the bamboo build. https://bamboo.penske.com/chain/viewChain.action?planKey=SOSSBP-SOSUTIL | Gayam | 07/13/23 2:12 AM
| Hey @praneeth.gayam@penske.com my apologies for the big delay. I am still unable to view the plan and I need to contact qa team in order to give me access. no update on this at this time. | David | 08/15/23 6:11 PM
| @david.long@penske.com , as per configuration you should see view and build. | Gayam | 08/17/23 1:37 AM
| @praneeth.gayam@penske.com Hey there! I was able to validate that the build is working and deploying to artifactory | David | 08/23/23 8:34 PM
| @david.long@penske.com , Thank you. Can i change the status to Done as this is just a dependency jar and not going to be deployed into production. | Gayam | 08/24/23 3:45 AM
| @praneeth.gayam@penske.com yes you can mark as Done | David | 08/24/23 6:54 PM
Row 221 | @david.long@penske.com , This is onboarded to Bamboo and deployed to artifactory. Please check and confirm. Thanks. | Gayam | 07/07/23 1:34 AM
| Sorry for the delay. What's the bamboo build URL? I can't seem to find it @praneeth.gayam@penske.com | David | 07/11/23 1:26 AM
Row 221 | Review: @david.long@penske.com / @falgun.patel@penske.com , This app is ready for your review. Please check and merge. https://bitbucket.penske.com/projects/MAIN/repos/sosutility/pull-requests/2/overview | Gayam | 06/28/23 2:53 AM
| @praneeth.gayam@penske.com I reviewed the PR and merged it into the develop branch! Thanks! | David | 07/04/23 2:51 AM
| Thanks @david.long@penske.com . We will onboard to bamboo and let you know. | Gayam | 07/06/23 3:10 AM
Row 221 | No secrets found on this jar. So changing the status to Cap Maven | Gayam | 06/23/23 12:16 AM
Row 221 | Hi Yvette, I wanted to bring to your attention that the shared jar "sosutility" requires a new repository and a bamboo build. This jar is utlized by three Maintenance apps: 24x7custnotif, sosservice and sos.war. David has confirmed the need to create a separate repository and Bamboo build for "sosutility" and it also requires to implement all modernization steps. Therefore I kindly request you to include a new line item "sosutility" in the smartsheet. Thanks, Praneeth | Yvette Urso | 06/12/23 9:11 PM
Row 222 | @dale.porter@penske.com , You just need to verify whether the bamboo built correctly and jar is deployed to artifactory. This is just a dependency jar and not going to deployed to any server. Thanks. | Gayam | 08/10/23 1:00 AM
| I ran a build and see in Jfrog artifactory the new artifacts "vehicleinformationutility" added. Look good, thank you | Dale Porter | 08/26/23 2:53 AM
| Thanks @dale.porter@penske.com . Closing the app. | Gayam | 08/28/23 10:16 PM
Row 222 | Thanks @dale.porter@penske.com . We will onboard to Bamboo. | Gayam | 07/07/23 10:42 PM
| The jar is onboarded to bamboo and uploaded to artifactory. Following is the dependency. <dependency> <groupId>com.penske.maintenance</groupId> <artifactId>vehicleinformationutility</artifactId> <version>2.0.0-develop-20230710.062023-1</version> </dependency> | Gayam | 07/10/23 11:12 PM
| Hi @praneeth.gayam@penske.com , please let me know if you are waiting on me for update as I am not sure what to do next. thanks | Dale Porter | 08/10/23 12:02 AM
Row 222 | thank you | Dale Porter | 07/17/23 10:58 PM
Row 222 | Review: @stella.george@penske.com / @dave.kost@penske.com , This utility app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/vehicleinformationutility/pull-requests/3/overview | Gayam | 06/24/23 12:22 AM
Row 222 | Review: @Stell | Gayam | 06/24/23 12:22 AM
Row 222 | There are no secrets exist for this application. So changing the status of this app to Cap Maven. | Gayam | 06/23/23 12:14 AM
Row 223 | @praneeth.gayam@penske.com @stella.george@penske.com This is being deployed to PROD tomorrow night (October 3rd, 2023) | David | 10/03/23 3:32 AM
Row 223 | @praneeth.gayam@penske.com so the vendor dvir batch isn't logging and doesn't seem to actually be running after it's deployed. Need to contact architecture or webservices. | David | 08/29/23 2:45 AM
| @david.long@penske.com , i think it is not daemon application which runs always. You may need to trigger manually. | Gayam | 08/30/23 2:31 AM
| @praneeth.gayam@penske.com We are seeing below error when i start batch. same error happens for ServiceNet batch also. [600114230@clelx150ptlge ~]$ sudo -u apps /apps/vendordvir/vendordvir.sh [sudo] password for 600114230: stopping vendordvir [600114230@clelx150ptlge ~]$ log4j:WARN No appenders could be found for logger (com.penske.architecture.batchframework.config.PropertiesConfigurator). log4j:WARN Please initialize the log4j system properly. log4j:WARN See http://logging.apache.org/log4j/1.2/faq.html#noconfig for more info. | Stella george | 09/06/23 1:46 AM
| @stella.george@penske.com , We added a file batchconfig-qa.prop file. Please deploy and check again. | Gayam | 09/07/23 11:58 PM
| @praneeth.gayam@penske.com @stella.george@penske.com When I go to run the batch I still don't see any logs and have no indicator that the batch is actually running... | David | 09/13/23 1:33 AM
Row 223 | @praneeth.gayam@penske.com the logging is incorrect so I just did a quick fix on develop. Testing it out after 5pm qa deploy | David | 08/29/23 1:47 AM
Row 223 | @praneeth.gayam@penske.com build is working and running deploy scripts now. Everything looks good from a build perspective. Will test if the batch works at 5pm. | David | 08/18/23 1:42 AM
| @praneeth.gayam@penske.com I need to build the project again since the threads in the batch need to be turned on individually. I did notice however, that the logs are going to the wrong folder. It looks like there is an extra directory lower than where it should log... I'm seeing for example the path is /apps/logs/vendordvir/vendordvir/rootlog. when it should be /apps/logs/vendordvir/rootlog | David | 08/23/23 8:40 PM
| @praneeth.gayam@penske.com I can confirm the build is working though :) | David | 08/23/23 8:41 PM
Row 223 | Review: @david.long@penske.com / @payel.ganguly@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/MAIN/repos/vendordvir-batch/pull-requests/3/overview | Gayam | 07/21/23 10:55 PM
| @praneeth.gayam@penske.com reviewed and merged :) | David | 08/15/23 6:19 PM
| Thanks @david.long@penske.com . Changed to Cap Bamboo | Gayam | 08/17/23 1:56 AM
| @david.long@penske.com , Bamboo onboarding completed. Please verify https://bamboo.penske.com/browse/VDBP-VENDV0 | Gayam | 08/18/23 12:19 AM
Row 223 | @david.long@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:53 AM
| AO confirmed no changes required for secrets. | Gayam | 06/16/23 10:32 PM
| Thank you for the update @praneeth.gayam@penske.com I am included on this app as one of it's contacts, but as you saw in our email chain for secrets, Stella and her team will be taking care of this mostly. Thanks again :) | David | 06/21/23 7:56 PM
Row 223 | @praneeth.gayam@penske.com Is there any update on this batch? | David | 06/13/23 7:54 PM
| @david.long@penske.com , We have started working on this applciation. | Gayam | 06/14/23 2:50 AM
Row 224 | @david.long@penske.com , I see that you have already merged the code to develop branch. But we have an open query in this application. In the ant build, application.properties file is replaced by application.properties.build .This file contains app.version=@DEPLOYMENT_INSTANCE@ and this variable value is injected based on environment. This needs to be corrected to satisfy the environment agnostic build. Please check. Thanks. | Gayam | 09/27/23 1:40 AM
| So Virtual Pay already has been pushed to PROD. I was able to fix this build issue. The app doesn't need the property files anymore, as it's able to get the server environment through a websphere variable. Based on this value, the app is able to set the environment and handle if the user should go through the local test filter or the dlink filter. | David | 10/03/23 3:32 AM
| Thanks @david.long@penske.com | Gayam | 10/04/23 1:49 AM
Row 224 | @shane.myers@penske.com | Yvette Urso | 09/25/23 10:51 PM
| @praneeth.gayam@penske.com please verify the mavenization was completed successfully - once you confirm, I will investigate further. | William | 09/25/23 10:57 PM
Row 224 | @yvette.urso@penske.com @praneeth.gayam@penske.com I'm currently running into issues with Virtual Pay. It seems whenever someone tries to access it, it goes to the test auth filter instead of the dlinks filter. I compared the project to sos-web and other web apps and virtual pay doesn't have any configurations like them when starting up the app...this was "mavenized" but I still see ant build things in the app, so I question if this is actually done. | David | 09/25/23 10:39 PM
| Hi David. Shane and Praneeth should be able to direct you technically. | Yvette Urso | 09/25/23 10:51 PM
Row 224 | @david.long@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/virtualpay-web/pull-requests/3/overview | Gayam | 07/07/23 1:16 AM
| @praneeth.gayam@penske.com merged! :) | David | 07/11/23 1:29 AM
| @david.long@penske.com , onboarded to bamboo and deployed to dev. Please verify. Deployment link: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151192149 build & Deploy plan: https://bamboo.penske.com/browse/VIR-VIRPW | Gayam | 07/13/23 1:04 AM
| @praneeth.gayam@penske.com my apologies on this. Will try to validate that today. | David | 08/23/23 8:41 PM
| @praneeth.gayam@penske.com I am building qa for the 2pm deploy window. However I think I'm not in the correct group to update the build plan, because I can't seem to be able to configure the virtual pay build plan and look at values | David | 08/23/23 9:00 PM
| @praneeth.gayam@penske.com Virtual Pay is working on QA | David | 08/24/23 1:35 AM
| Thanks @david.long@penske.com | Gayam | 08/24/23 3:54 AM
Row 224 | @david.long@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:53 AM
| AO confirmed that all secrets are false positives. No code changes required. | Gayam | 06/16/23 1:14 AM
Row 224 | @praneeth.gayam@penske.com I believe that wsdl can be removed from the project. | David | 06/06/23 10:31 PM
| @david.long@penske.com , We will remove that wsdl and let you know whether we are facing any problems. Thanks. | Gayam | 06/07/23 3:39 AM
Row 224 | @david.long@penske.com , We are facing following issue in this app. Could you please check. Thank you. The application having error in one file under conf folder - AccessOnlineWebServices.wsdl . Its look like application error. Error message : - The part 'userNameToken' has an invalid value 'userNameToken' defined for its element. Element declarations must refer to valid values defined in a schema. | Gayam | 05/25/23 3:26 AM
Row 224 | @David | Gayam | 05/25/23 3:25 AM
Row 228 | @dale.porter@penske.com , Bamboo build is completed. Please deploy to QA and verify. https://bamboo.penske.com/browse/OROSBBP-OROSSUMM | Gayam | 07/20/23 12:06 AM
| Hi, I am seeing errors in the Bamboo build for the final Archive stage and included link to bamboo for showing the error. Also, I did not see a war file created on ghlx008ptlge. Can you take a look. Thank you https://bamboo.penske.com/download/OROSBBP-OROSSUMM0-DTA/build_logs/OROSBBP-OROSSUMM0-DTA-2.log | Dale Porter | 07/28/23 1:41 AM
| @dale.porter@penske.com , we will check. | Gayam | 07/31/23 2:30 AM
| @dale.porter@penske.com , This is a batch application. So it doesn't have war package. Also, whatever the errors you are seeing are not causing@dale.porter@penske.com , This is a batch application. So it doesn't have war package. Also, whatever the errors you are seeing are not causing any issues. Jars are pushed to artifactory successfully and tgz file is pushed to targeted location correctly. Please check. | Gayam | 08/01/23 12:43 AM
| Hi all, I ran the deploy to QA but it did not place the tgz file of the build in the /var/tmp of the qa deploymanager (clelx150ptlge). I included url of qa build log, thank you https://bamboo.penske.com/browse/OROSBBP-OROSSUMM0-DTA-3/log | Dale Porter | 08/05/23 1:15 AM
| We will check and get back to you. | Gayam | 08/08/23 1:11 AM
| @dale.porter@penske.com , we have completed the QA deployment and tgz file also generated. Please verify and let us know if you have any questions. Thanks. | Gayam | 08/10/23 12:46 AM
| Hi, I ran the open repair order summary batch deplioy but afterwards, I do not see the tgz file on /var/tmp of clelx150ptlge. I have included reference to bamboo log below, thank you https://bamboo.penske.com/browse/OROSBBP-OROSSUMM0-DTA-4/log | Dale Porter | 08/17/23 6:32 PM
| @dale.porter@penske.com , will check and get back to you. Thanks | Gayam | 08/18/23 12:31 AM
| @dale.porter@penske.com , It looks like you only run the build but you need to run the deploy plan also. If you want to deploy to QA, you need to run the QA deploy plan and for prod need to run the prod deploy plan. | Gayam | 08/18/23 8:01 PM
| I ran the QA build and it did create a TGZ file on /var/tmp of deploy manager. However, upon inspecting the file, the internal code base for the openrepairsumm-batch.jar is dated 8/4/2023 not the current date of build 8/25/2023. Can someone take a look? thank you. Build log https://bamboo.penske.com/deployment-download/151912538/build_logs/151814164-151912538-151200192.log | Dale Porter | 08/26/23 7:47 AM
| @dale.porter@penske.com , we will check and get back to you. | Gayam | 08/28/23 10:40 PM
| I made a small code change without affecting code, "verbiage in log comment" and upon doing the qa build, I did get class files built for current build which is good. However, when I tried to run the application, no logs where showing in the /logs/apps/openrepairsumm folder on the qa batch box and also I did not see any emails generated to the ebs mailer in QA so it appears to not be running when I start it. | Dale Porter | 08/30/23 8:46 AM
| @dale.porter@penske.com , We will check and get back to you. | Gayam | 08/30/23 10:33 PM
| @dale.porter@penske.com , My team ran the build and deployed to QA and it is also moved to targeted location correctly. Please check. | Gayam | 09/02/23 4:18 AM
| @praneeth.gayam@penske.com , I ran a qa deploy and did see the tgz file get built and placed in /var/tmp of qa batch machine. However, when I tried to run it, the process did not run and there is no logging in the /logs/apps/openrepairsumm I do not know if logging is working. But the process is not working either. I did not see a log4j warning on starting the process like I do with ServiceNet batch. | Dale Porter | 09/08/23 7:30 PM
| @praneeth.gayam@penske.com its same issue we faced with other batch applications too. Please address this ASAP and let us know. | Stella george | 09/08/23 8:10 PM
| @stella.george@penske.com / @dale.porter@penske.com , Can your un the application in local and check the issue. Log4j team does not have knowledge to run the application. We only mavanize and compile the application as per defined process. | Gayam | 09/09/23 2:29 AM
Row 228 | I have reviewed and merged pull request. Thank you. | Dale Porter | 07/17/23 7:30 PM
Row 228 | Review: @dale.porter@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/MAIN/repos/openrepairsumm-batch/pull-requests/3/overview | Gayam | 07/16/23 9:21 PM
Row 228 | Thanks @dale.porter@penske.com | Gayam | 06/14/23 4:18 AM
Row 228 | I approve of adding velocity-1.7 to artifactory as needed for the application. Thank you. | Dale Porter | 06/14/23 2:20 AM
Row 228 | Regarding Secrets: I went ahead to analyze this and see this appears to be the guest user id and password for SVN repository access. I removed these on all of the property files as Bamboo does not use this. I believe this was from prior to using Bamboo back in the day. After removing the id and password references, I made a new qa tag and run a qa build in Bamboo without any issue. This should be fine now. | Dale Porter | 06/06/23 6:25 AM
| Thanks @dale.porter@penske.com . Could you please check the query mentioned above regarding the dependency jar and provide your response | Gayam | 06/06/23 8:36 AM
Row 228 | Secrets: @shawn.mcmurtry@penske.com , adding to above question, I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:53 AM
Row 228 | Query: @shawn.mcmurtry@penske.com , This app depends on velocity-1.7-dep.jar which is not availabe in artifactory. Could you please provide your approval to uplaod to artifactory in the following location. <groupid>org.apache.velocity</groupid> <artifactid>velocity-1.7-dep</artifactid> <version>Default</version> | Gayam | 06/01/23 1:59 AM
Row 230 | I made corrections proper property files names, placement of configuration of xml files as well as pom spring setting updates. I was able to get the servicenet batch application to run in QA environment and logging is working too. | Dale Porter | 09/25/23 7:15 PM
| Thanks @dale.porter@penske.com | Gayam | 09/26/23 1:00 AM
Row 230 | @praneeth.gayam@penske.com Please check this and let us know. We are having same issues with all of our batch. I think you have addressed for Parts PO. Can you please address this issue ASAP. This is impacting our testing | Stella george | 09/08/23 8:15 PM
| @stella.george@penske.com , we followed the same process for all the batch apps and it is difficult to debug the issue without running the app in local. Please run in local and check. Thanks. | Gayam | 09/09/23 2:41 AM
| @praneeth.gayam@penske.com It is not working let us know how we can proceed? | Stella george | 09/21/23 10:39 PM
| @stella.george@penske.com , After including batchconfig-qa.properties there was no build and deployment happened. We built and deployed. It is working fine. Please check. | Gayam | 09/23/23 2:09 AM
Row 230 | I see a build was run on Sept. 6th around 3:07 pm by Sireesha. The tgz was deployed to QA but when it then ran, it did not start up correctly and is not processing like it should. When I stopped it and restarted it, I saw the same log4j errors warning as noted above. Because QA team needs this to be running in QA for testing, I had to deploy the SVN version of the app so it can run again in qa. This is not resolved, can the log4j issue be resolved for the modernized version? Thank you. | Dale Porter | 09/08/23 7:07 PM
Row 230 | @dale.porter@penske.com , build plan onboarded and deployment to artifactory is successful. Deploy plan onboarding is also successful. Please deploy to QA and test it. Thanks. Build plan: https://bamboo.penske.com/browse/SERVICENETBATCH-SVCNETB0 Deploy Plan: https://bamboo.penske.com/browse/SERVICENETBATCH-SVCNETB/deployments | Gayam | 08/03/23 12:49 AM
| HI all, I ran the deploy to QA but it did not place the tgz file of the build in the /var/tmp of the qa deploymanager (clelx150ptlge). I included url of qa build log, thank you https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151196764 | Dale Porter | 08/05/23 1:07 AM
| @dale.porter@penske.com , we will check and get back to you. | Gayam | 08/08/23 1:05 AM
| @dale.porter@penske.com , issue got fixed. Qa deployment done and tgz file generated in clelx150ptlge. Thank you | Gayam | 08/11/23 12:18 AM
| I just ran QA build for develop branch and it shows completed. However, I am not finding the servicenetbatch.tgz file in /var/tmp of the qa deployment/batch manager (clelx150ptlge). I included the url to the build log for the deployment. https://bamboo.penske.com/download/SERVICENETBATCH-SVCNETB0-DTA/build_logs/SERVICENETBATCH-SVCNETB0-DTA-5.log | Dale Porter | 08/16/23 2:08 AM
| @dale.porter@penske.com , I have verified the /apps/servicenetbatch location of QA server and jar is deployed yesterday. Please check. | Gayam | 08/17/23 1:29 AM
| That build is one I did with the old QA build using SVN for getting a change we had to test. I just ran the develop branch build and after it "completed", I do not see the servicenetbatch.tgz file in /var/tmp. Included build log reference. https://bamboo.penske.com/browse/SERVICENETBATCH-SVCNETB0-DTA-6/log | Dale Porter | 08/17/23 9:10 AM
| @dale.porter@penske.com , It looks like you only run the build but you need to run the deploy plan also. If you want to deploy to QA, you need to run the QA deploy plan and for prod need to run the prod deploy plan. | Gayam | 08/18/23 8:00 PM
| I ran the build and it did place a servicenetbatch.tgz file on /var/tmp However, when it deployed I see that the servicenetbatch.jar file is dated 8/9 not the date 8/24 of the bamboo build so the compiled code is not included. Before looking into the log4 j issue noted next, Can someone please take a look at reason for why old code from days prior is only being packaged. Thank you. Build log https://bamboo.penske.com/deployment-download/151912586/build_logs/151814174-151912586-151200180.log | Dale Porter | 08/26/23 7:36 AM
| @dale.porter@penske.com , QA webservices deploy job runs every hour which copies the jar from var/tmp to targeted location. I am seeing the servicenetbatch.jar in the targeted location with the 08/25 date. Please check. | Gayam | 08/28/23 10:35 PM
| Made a small java code change in the logger comment (do not effect application) however, the packaged tgz file did not include a recently built class files. Including the "UnitAttachment.java" that I changed in develop branch. The bamboo build can be found at https://bamboo.penske.com/browse/SERVICENETBATCH-SVCNETB0-7/log | Dale Porter | 08/30/23 8:35 AM
| I ran the full deploy to pickup the new build and it included the updated class files. However, issue is that application does not run in QA. Is not processing data. Also there is no logger and I see an immediate error message when starting the program as follows: [600013879@clelx150ptlge servicenetbatch]$ log4j:WARN No appenders could be found for logger (com.penske.architecture.batchframework.config.PropertiesConfigurator). log4j:WARN Please initialize the log4j system properly. log4j:WARN See http://logging.apache.org/log4j/1.2/faq.html#noconfig for more info. | Dale Porter | 09/06/23 2:24 AM
Row 230 | Review: @dale.porter@penske.com , this app is ready for your review. Please check and merge the PR. https://bitbucket.penske.com/projects/MAIN/repos/servicenet-batch/pull-requests/3/overview | Gayam | 07/27/23 11:50 PM
| I reviewed and merged the code. Thank you. | Dale Porter | 07/28/23 1:48 AM
| will onboard to bamboo. | Gayam | 07/31/23 2:32 AM
Row 230 | @stella.george@penske.com / @dale.porter@penske.com , This application dependent on servicenet-models.jar. This jar is not available in artifactory Could you please provide your approval to upload it to artifactory in the below location. GroupId: com.penske.apps ArtifactId: servicenet-models Version:default Location: common-mvn-development-local | Gayam | 06/30/23 12:56 AM
| Yes, please upload the servcienet-models.jar to the Penske artifactory. | Dale Porter | 07/07/23 12:54 AM
| Thanks @dale.porter@penske.com . We have uploaded the dependency jar to artifactory. | Gayam | 07/10/23 11:36 PM
Row 230 | Had a discussion with @dale.porter@penske.com and confirmed that we need to use the latest prod reference branch as base brach for modernization changes. | Gayam | 06/29/23 3:11 AM
Row 230 | Query: @stella.george@penske.com , Adding to secrets, we have a query on this app. This application dependent on servicenet-models.jar. This jar is not available in artifactory Could you please provide your approval to upload it to artifactory in the below location. GroupId: com.penske.apps ArtifactId: servicenet-models Version:default Location: common-mvn-development-local | Gayam | 06/15/23 2:02 AM
| @dale.porter@penske.com , Please provide your response for above query. Thanks. | Gayam | 06/21/23 1:06 AM
| @dale.porter@penske.com , Could you please respond to above query. | Gayam | 06/27/23 3:31 AM
Row 230 | It will be deploy later for production, please use the branch as instructed. Thank you. | Dale Porter | 06/24/23 12:44 AM
| Thanks @dale.porter@penske.com . We will use the following as base branch as instructed. https://svn.penske.com/svn/fieldsys/maintenance/batch/servicenetbatch/branches/servicenetbatch_Log4jChanges | Gayam | 06/27/23 3:28 AM
Row 230 | I have merged prior code changes we have in QA that are planned to deploy in future and do not want to lose in the bit bucket migration to the branch https://svn.penske.com/svn/fieldsys/maintenance/batch/servicenetbatch/branches/servicenetbatch_Log4jChanges | Dale Porter | 06/23/23 12:41 AM
| @dale.porter@penske.com , Do we need wait until you confirm your changes goes to production? or let us know what is the step we need to take? | Gayam | 06/23/23 11:46 PM
Row 230 | I have removed the test user User name and secret for the iBMI connection in the applicationContext.xml file and checked in the change in SVN. The other files were not senstive data (just false positives). Thank you. | Dale Porter | 06/16/23 3:02 AM
| @dale.porter@penske.com , We are seeing your changes in the dev_gh branch. Also, we are seeing latest commits in this branch. https://svn.penske.com/svn/fieldsys/maintenance/batch/servicenetbatch/branches/dev_gh But we took the https://svn.penske.com/svn/fieldsys/maintenance/batch/servicenetbatch/tags/prod/20230309 as base branch. Bamboo prod build is pointing to this branch. Which one we need to consider as base branch and start doing log4j changes? | Gayam | 06/21/23 1:05 AM
Row 230 | Secrets: @stella.george@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:52 AM
Row 231 | @praneeth.gayam@penske.com we deployed into production and no issues found as of now | Sreenivasa | 11/07/23 8:21 PM
| Thanks for the update. | Gayam | 11/08/23 12:46 AM
Row 231 | . | Sreenivasa | 10/16/23 8:57 PM
Row 231 | I verified in QA, will plan for prod deployment | Sreenivasa | 10/11/23 1:33 AM
Row 231 | changes looks good. we can deploy into QA and test | Sreenivasa | 09/25/23 8:41 PM
| Sure @sreenivasa.papannagari@penske.com | Gayam | 09/26/23 12:59 AM
| @sreenivasa.papannagari@penske.com , This app is deployed to QA. Please verify. | Gayam | 09/27/23 12:45 AM
Row 231 | @sreenivasa.papannagari@penske.com , Onboarded to bamboo and deployed to dev. Pelase check. https://bamboo.penske.com/browse/SOSSBP-SOSW1/deployments | Gayam | 09/22/23 12:09 AM
Row 231 | Reviewed and merged. | Sreenivasa | 09/20/23 12:00 AM
| Thanks @sreenivasa.papannagari@penske.com . We will onboard to Bamboo. | Gayam | 09/20/23 12:34 AM
Row 231 | looks good for me.. please go ahead with further steps | Sreenivasa | 09/16/23 1:42 AM
| @sreenivasa.papannagari@penske.com , We completed all the changes in develop_log4j branch. Can you merge the chagnes to develop branch. https://bitbucket.penske.com/projects/MAIN/repos/sos-web/pull-requests/3/overview So that we can onboard the develop branch to bamboo. Thanks | Gayam | 09/19/23 12:50 AM
Row 231 | reviewed and gave one comment ... please check and confirm | Sreenivasa | 09/14/23 8:36 PM
| Thanks @sreenivasa.papannagari@penske.com . We will check on this. | Gayam | 09/15/23 7:24 AM
| @sreenivasa.papannagari@penske.com , Narendra modified the configuration as recommended in confluence documentation. Please verify. Thanks | Gayam | 09/16/23 12:43 AM
Row 231 | @praneeth.gayam@penske.com , I made the changes to align with environment agnostic. Please review and approve the pull request- https://bitbucket.penske.com/projects/MAIN/repos/sos-web/pull-requests/4/overview | Sreenivasa | 08/25/23 5:25 PM
| @sreenivasa.papannagari@penske.com , I merged the code to develop_log4j branch. We continue the next set of work and will provide for your review. Thanks. | Gayam | 08/26/23 1:05 AM
| Review: @sreenivasa.papannagari@penske.com , Please review the total modernization changes in below PR. https://bitbucket.penske.com/projects/MAIN/repos/sos-web/pull-requests/3/overview | Gayam | 09/13/23 11:09 PM
Row 231 | Working on code changes to align with environment agnostic. will update you by this Wednesday. | Sreenivasa | 08/21/23 7:32 PM
Row 231 | Query: @sreenivasa.papannagari@penske.com , In this application build folder having sos_specificbuild.xml. The build is including dispatcher-servlet.xml on environment basis. how to implement this in environment agnostic build as we don't have separate builds for each environment. | Gayam | 07/25/23 12:06 AM
Row 231 | @shawn.mcmurtry@penske.com , This app depends on the sosutility.jar . Sosutility having the svn repo . Can we continue to migrate sosutility also ? https://svn.penske.com/svn/fieldsys/other/sos-service/tags/prod/2023-05-04/SosUtility/ There are other apps soservice.war and 24*7custnotify also depend on Sosutility jar. | Gayam | 05/18/23 10:57 PM
| @david.long@penske.com confirmed to create a separate repo and Bamboo plan for sosutility. We will take up this app for migration once Sosutiloity work completed. Thanks. | Gayam | 06/12/23 7:42 AM
Row 231 | I have validated the secretes , looks good for me ... except these 3 build_script/prod.properties build_script/dev.properties build_script/qa.properties. Remaining all are not secrets. | Sreenivasa | 06/09/23 7:30 PM
| Thanks @sreenivasa.papannagari@penske.com . We will remove build_script folder while doing the mavanization. | Gayam | 06/12/23 7:37 AM
Row 231 | Secrets: @shawn.mcmurtry@penske.com , adding to above question, I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:53 AM
Row 232 | @praneeth.gayam@penske.com we deployed into production and no issues found as of now | Sreenivasa | 11/07/23 8:21 PM
| Thanks for the update. | Gayam | 11/08/23 12:45 AM
Row 232 | @praneeth.gayam@penske.com @falgun.patel@penske.com Able to see static content now and verified logs too.. we are good to go for production | Sreenivasa | 10/26/23 7:59 PM
| Thanks @sreenivasa.papannagari@penske.com | Gayam | 10/26/23 11:59 PM
Row 232 | @praneeth.gayam@penske.com ,please refer sos application and make changes accordingly | Sreenivasa | 10/26/23 12:31 AM
| @sreenivasa.papannagari@penske.com , As discussed changes are completed and deployed to QA. Please verify | Gayam | 10/26/23 10:20 AM
Row 232 | @praneeth.gayam@penske.com , Static content is not loading properly in the browser.. like images..js files. please check ibm-web-bnd and ibm-web-ext files configurations. | Sreenivasa | 10/26/23 12:03 AM
| @sreenivasa.papannagari@penske.com , Not sure what we need to check in those 2 files. We just copied those 2 files to WEB-INF folder. Just changed the file type from xmi to xml as mentioned in one of the modernzation confluence page. | Gayam | 10/26/23 12:13 AM
Row 232 | @sreenivasa.papannagari@penske.com , Sospcard successfully deployed to QA , war and tgz placed in targeted location and logs are also generating. Please verify. Thanks | Gayam | 10/25/23 11:33 PM
Row 232 | can you deploy in QA? I will validate in QA directly | Sreenivasa | 10/23/23 6:44 PM
| Sure @sreenivasa.papannagari@penske.com | Gayam | 10/25/23 1:34 AM
Row 232 | @praneeth.gayam@penske.com - tagging you to make sure you can see Sreeni's response. | Patel | 10/24/23 11:45 PM
Row 232 | yes I am able to see logs in local | Sreenivasa | 10/17/23 6:37 PM
| @sreenivasa.papannagari@penske.com , Can you check the changes which you have completed to satisfy the environment agnostic build. It looks like you have deleted several xmi files and also environment dependent files. Could you please check. https://bitbucket.penske.com/projects/MAIN/repos/sospcard-web/pull-requests/2/diff Because we have completed all the things on our side and not seeing any difference compare other apps except the changes which you have completed. Please check. Thanks, | Gayam | 10/20/23 12:39 AM
Row 232 | application is not up in DEV, even I don't see any logs in the dev. | Sreenivasa | 10/11/23 1:57 AM
| @praneeth.gayam@penske.com - tagging you to make sure you saw Sreeni's response. | Patel | 10/11/23 2:02 AM
| @sreenivasa.papannagari@penske.com / @falgun.patel@penske.com , We will check whether anything missed in the modernization process. Also, @sreenivasa.papannagari@penske.com is this app genrated logs in local? | Gayam | 10/12/23 7:13 AM
Row 232 | @praneeth.gayam@penske.com - just making sure you received the confirmation from @sreenivasa.papannagari@penske.com to move forward. | Patel | 10/06/23 6:30 PM
| @sreenivasa.papannagari@penske.com / @falgun.patel@penske.com , Dev deployment is completed. Please verify. Thanks. | Gayam | 10/10/23 12:08 AM
Row 232 | looking good .. please proceed with next steps | Sreenivasa | 10/04/23 7:31 PM
Row 232 | changes looks good, please go ahead with further steps | Sreenivasa | 09/27/23 7:00 PM
| Sure @sreenivasa.papannagari@penske.com | Gayam | 09/28/23 12:45 AM
| @sreenivasa.papannagari@penske.com , Onboarded develop_log4j branch to bamboo - https://bamboo.penske.com/browse/SOSP-SOSPCW1/ Please check. | Gayam | 10/03/23 1:38 AM
Row 232 | Please make log4j changes as like sos.war | Sreenivasa | 09/16/23 1:49 AM
| Sure @sreenivasa.papannagari@penske.com | Gayam | 09/19/23 12:51 AM
| @sreenivasa.papannagari@penske.com , Changes are completed. Pelase verify the PR. | Gayam | 09/21/23 12:54 AM
Row 232 | yes all changes completed .. please go ahead with further steps | Sreenivasa | 09/09/23 1:18 AM
| Sure @sreenivasa.papannagari@penske.com | Gayam | 09/11/23 10:31 PM
| Review: @sreenivasa.papannagari@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/MAIN/repos/sospcard-web/pull-requests/4/overview | Gayam | 09/15/23 7:38 AM
Row 232 | Hi Praneeth, I made the changes to align with environment agnostic and created a pull request to your branch - https://bitbucket.penske.com/projects/MAIN/repos/sospcard-web/pull-requests/2/overview. Please review and merge the changes | Sreenivasa | 09/08/23 7:12 PM
| Thanks @sreenivasa.papannagari@penske.com . Are your changes completed? If yes, we will take it forward. | Gayam | 09/09/23 12:36 AM
Row 232 | Need to do code changes, will update you on this by Friday. | Sreenivasa | 08/21/23 7:43 PM
Row 232 | Query: @sreenivasa.papannagari@penske.com / @stella.george@penske.com , We have following queries in this application. 1.Targeted folder contains different sosProperties.properties files for different environments. These properties are referred in web.xml and InitializationServlet. The main difference is upload path Production UploadPath = \\GRNHILLS/ROOT/applications/pcard/ Qa UploadPath = \\QAGH/ROOT/applications/pcard/) 2.Targeted folder contains different web.xml files for different environments. In environment agnostic build there will be no separate builds for each environment. But it seems above files are environement specific. Could you please check and resolve this issue. Thanks. | Gayam | 07/25/23 12:16 AM
Row 232 | Verified the secrets, I don't see any PI data hardcoded in the code.. most of them are getting from back end(DB). So we should be ok with it. | Sreenivasa | 06/15/23 10:56 PM
| Thank you. | Gayam | 06/16/23 1:13 AM
Row 232 | @stella.george@penske.com / @sreenivasa.papannagari@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:52 AM
Row 242 | @praneeth.gayam@penske.com we are going to retire this app | Shawn | 08/31/23 6:37 PM
| @shawn.mcmurtry@penske.com , Thanks for the update. | Gayam | 08/31/23 11:35 PM
Row 242 | @shawn.mcmurtry@penske.com - tagging you for test | Patel | 07/28/23 10:23 PM
Row 242 | Testing Shawn's email notification | Patel | 07/28/23 9:39 PM
Row 242 | Question: @shawn.mcmurtry@penske.com / @dave.kost@penske.com , cns_application.properties.ant file contains a variable 'version' having value @DEPLOYMENT_INSTANCE@. It looks like this value comes from the bamboo build for each environment. But after modernization, it is going to be environment agnostic build. So it needs to be rectified if this variable used in code. Please check. Thanks. | Gayam | 07/19/23 3:23 AM
Row 242 | AO confirmed that all secrets are false positives. No code changes required. | Gayam | 06/16/23 1:12 AM
Row 242 | @shawn.mcmurtry@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:51 AM
Row 243 | I did a deploy to QA environment but I do not see any logging in the /logs/apps folder for the etimservice application in any of the three qa app servers. I think the code is running as I do get a certificate error message back when it tries to communicate with ADP. However, without the loging I am not sure what is the direct cause. Can the logging be fixed? thank you. | Dale Porter | 09/22/23 8:42 PM
| @dale.porter@penske.com , We will check and update you. | Gayam | 09/26/23 1:11 AM
| @dale.porter@penske.com , we changed the log4j configuration in web.xml and deployed to Dev. Logs are getting generated in dev. Please check. Thanks. | Gayam | 09/29/23 1:32 AM
Row 243 | Did another test and I do see the latest files being packaged in the war file for the Dev build. thank you. | Dale Porter | 08/30/23 7:45 AM
Row 243 | Sure @dale.porter@penske.com . We will check and get back to you. | Gayam | 07/31/23 2:26 AM
| @dale.porter@penske.com CICD team checked build log of deployment to artifactory(archive) stage report and found that error statement is coming, but those errors are coming for all the applications and those are not causing any issues. https://bamboo.penske.com/download/ETSBP-ETSW0-DTA/build_logs/ETSBP-ETSW0-DTA-2.log. Then team verified whether the war is getting deployed to artifactory or not and found that it is deploying. Also verified in ghlx008 server and found that etimeservice.war is deploying in server also. So please validate the app. Thanks. | Gayam | 08/01/23 12:46 AM
| Hi all, I ran the buld again for develop branch and I do see the war file for etimeservice is being put to ghlx008 as noted. However, it is not running the ssh app deployment process as I check the application installed in websphere at /opt/websphere/profiles/wsv/installedApps/ghlx006ptlgeNetwork-remoting/etservice.ear and it is still dated as 7/18/2023. I also included a reference to the bamboo build log with errors. https://bamboo.penske.com/download/ETSBP-ETSW0-DTA/build_logs/ETSBP-ETSW0-DTA-3.log | Dale Porter | 08/01/23 8:20 PM
| @dale.porter@penske.com , dev server was down for the past couple of days. That is the reason deployment is failing. Now the server is up and deployment is successful. Please check. https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151196087. | Gayam | 08/04/23 1:04 AM
| Hi I ran a dev build and see that the deployment is being executed (the file folders at and under the below directory are dated today's deploy date 8/9/2023 I ran but the class object files were dated 8/1/2023. I do not think the build is working correctly as the class compiled files should also be dated with current build date. Please take a look. thank you. /opt/websphere/profiles/wsv/installedApps/ghlx006ptlgeNetwork-remoting/etservice.ear | Dale Porter | 08/09/23 11:50 PM
| @dale.porter@penske.com , I don't think there is any issue in the build. If you see the log4j2.xml file it is dated as 8/1. Not sure why the server dated them as 8/1 but total package is correctly built by bamboo. | Gayam | 08/10/23 12:57 AM
| I ran another develop deploy for etimeservice to Dev, this time I do see the class files with the correct tiemstamps. However, I am not seeing any logging to the log on ghlx008ptlge in directory /logs/apps/etimeservice. Can someone check the logging for the application. Thank you. | Dale Porter | 08/16/23 8:49 AM
| @dale.porter@penske.com , Is that application creating logs in local? | Gayam | 08/17/23 1:26 AM
| not sure what you mean by local, prior modernization, it was logging in dev to /logs/apps/etimeservice, now I do not see logging occurring there. | Dale Porter | 08/17/23 9:03 AM
| @dale.porter@penske.com , The application needs to run in local and verify whether logs are creating in local. Cap Log4j team only compiles the applicaition once mavanization completes. We don't know the information about running the application. So AOs are running the apps in local and checking whether things are working fine. If you want to verify in server, I heard that dev is not a good environment to check for most of the apps. QA is best. Please deploy to QA and check. | Gayam | 08/18/23 12:41 AM
| Hi, I ran the Dev deployed on 8/26 and the class files deployed on "" are dated 8/15 not the correct build ones for 8/26. Folder I checked on dev app server ghlx008ptlge /opt/websphere/profiles/wsv/installedApps/ghlx006ptlgeNetwork-remoting/etimeservice.ear/etimeservice.war/WEB-INF/classes/com/penske/apps/etimeservice/domain The build log in bamboo is https://bamboo.penske.com/deployment-download/151912485/build_logs/151814151-151912485-151200197.log Also, I tested the QA build and saw same issue when inspected the WAR file placed in /var/tmp of QA deploy manager clelx150ptlge I saw class file dates of 8/15 and not 8/26 for current build date. The bamboo build log for qa is https://bamboo.penske.com/deployment-download/151912486/build_logs/151814151-151912486-151200196.log | Dale Porter | 08/27/23 3:16 AM
| @dale.porter@penske.com , If you see that all the folder dates are 08/26 and log4j2.xml files also available in the server. I am not sure why the file dates are 08/15 but I can say that latest build is deployed to dev. Please verify the application and check whether all the things are working fine. | Gayam | 08/28/23 10:55 PM
Row 243 | hi All, I am getting access denied error when clicking on the link above from Bamboo. Can I be given access to the above project in bamboo for the link. Thank you. | Dale Porter | 07/17/23 7:37 PM
| @dale.porter@penske.com , you have all the required access. Please check again. https://bamboo.penske.com/browse/ETSBP-ETSW/deployments | Gayam | 07/20/23 12:14 AM
| Hi, I am seeing errors in the Bamboo build for the final Archive stage and included link to bamboo for showing the error. Also, I did not see a war file created on ghlx008ptlge. Can you take a look. Thank you https://bamboo.penske.com/download/ETSBP-ETSW0-DTA/build_logs/ETSBP-ETSW0-DTA-2.log | Dale Porter | 07/28/23 1:35 AM
Row 243 | @dale.porter@penske.com , onboarded to bamboo and dev deployment is successful. Please verify. Thanks. https://bamboo.penske.com/browse/ETSBP-ETSW/deployments | Gayam | 07/12/23 1:39 AM
Row 243 | I have verified and merged. thank you | Dale Porter | 07/07/23 1:03 AM
| Thanks @dale.porter@penske.com . We will onboard to bamboo. | Gayam | 07/10/23 11:31 PM
Row 243 | Review: @dale.porter@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/etimeservice/pull-requests/4/overview | Gayam | 06/24/23 12:46 AM
Row 243 | The xml file in question “EncryptionKeyStoreDao” is a mybatis sql call to procedure GETENCRYPTIONKEY from EK_MASTER library. It does not have a specific key id or key password stored, it is just the variable placeholder for receiving the password when returned from the procedure call to be using in the application. This should not be an issue. | Dale Porter | 06/06/23 6:18 AM
| Thanks @dale.porter@penske.com . Changed the status to Cap Maven | Gayam | 06/06/23 8:30 AM
Row 243 | @dale.porter@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:48 AM
Row 244 | @kenneth.mikos@penske.com , Onboarded to bamboo and dev deployment is completed with develop branch - https://bamboo.penske.com/browse/MCBP-MAINTCW0/deployments Please verify. | Gayam | 10/17/23 11:50 PM
Row 244 | @kenneth.mikos@penske.com , All the modernization chagnes are completed. Please review the PR and merge. https://bitbucket.penske.com/projects/MAIN/repos/maintconfig-web/pull-requests/4/overview | Gayam | 10/12/23 8:01 AM
| @praneeth.gayam@penske.com The PR has been reviewed and merged. Thanks! | Mikos | 10/12/23 5:52 PM
| Thanks @kenneth.mikos@penske.com . We will onbaord to Bamboo. | Gayam | 10/13/23 6:33 AM
Row 244 | @praneeth.gayam@penske.com We had the same in servicenet application except the .build file in src/conf. I recommend following the same way how it is implemented in servicenet application. | Vaddi Mani | 08/18/23 10:08 PM
| @sarath.mani@penske.com , It doesn't look like both apps are same. Please check and provide the solution which is best for maintconfig app. | Gayam | 08/21/23 10:01 PM
| @praneeth.gayam@penske.com Platform agnostic changes are complete for maint-config and can be found in the "mainconfig_PlatformAgnosticChanges" feature branch. | Mikos | 10/06/23 3:26 AM
| Thanks @kenneth.mikos@penske.com . We will check and will include all the remaining mavanization steps if anything missed. | Gayam | 10/09/23 11:58 PM
Row 244 | Those should be the variables which have to defined in bamboo plan for each environment. | Vaddi Mani | 08/04/23 7:26 PM
| @sarath.mani@penske.com , there will be no separate builds for each environment after modernization. Please check the files below and provide your decision what to do for the next step. Thanks. build_script/maintconfig_specificBuild.xml src/conf/maintconfig.properties.build | Gayam | 08/08/23 1:23 AM
Row 244 | Query: @sarath.mani@penske.com / @falgun.patel@penske.com , In this application build folder having maintconfig_specificBuild.xml. The build is including maintconfig.properties on environment basis. how to implement this in environment agnostic build as we don't have separate builds for each environment. | Gayam | 07/25/23 9:15 PM
| Can you tell which variables from maintconfig_specificBuild.xml & maintconfig.properties? | Vaddi Mani | 07/28/23 2:07 AM
| @sarath.mani@penske.com , check the 39th to 45 line. | Gayam | 07/31/23 2:40 AM
Row 244 | Sarath already replied to the email on 6/27 that this application does not require any code changes related to secret. Please proceed. | Patel | 06/29/23 1:46 AM
| Thanks. Changed the status to Cap Maven. | Gayam | 06/29/23 2:37 AM
Row 244 | Secrets: @sarath.mani@penske.com / @falgun.patel@penske.com , I sent the secrets in the email. Please verify and let us know whether this app requires code changes. | Gayam | 06/28/23 12:47 AM
Row 244 | @sarath.mani@penske.com - may you please assist Gayam with the question? | Patel | 06/08/23 11:09 PM
| @praneeth.gayam@penske.com that was very old tag. you should use https://svn.penske.com/svn/fieldsys/maintenance/maint-config/tags/prod/maint-config20230605 | Stella george | 06/14/23 2:08 AM
| Thanks @stella.george@penske.com | Gayam | 06/14/23 3:39 AM
Row 244 | @david.long@penske.com , In the current bamboo build the prod reference mentioned as complete "https://svn.penske.com/svn/fieldsys/maintenance/maint-config/tags/prod/maint-config20201215". But this path doesn't exist in svn. Could you please help us to find the prod reference branch. Thanks. | Gayam | 05/09/23 2:42 AM
Row 246 | @praneeth.gayam@penske.com , @yvette.urso@penske.com , @shawn.mcmurtry@penske.com - as I have mentioned in my email, the application is not loading on Dev and it looks like Maven issue. Can you please look into this? | Patel | 09/08/23 5:52 PM
Row 246 | @praneeth.gayam@penske.com , @shawn.mcmurtry@penske.com - PR has been reviewed and merged to Dev. | Patel | 08/19/23 1:25 AM
| Thanks @falgun.patel@penske.com . We will onabord to bamboo and deploy to dev. | Gayam | 08/21/23 9:52 PM
| @falgun.patel@penske.com , We onboarded to bamboo and deployed to Dev. Please verify. | Gayam | 08/24/23 11:09 PM
Row 246 | @praneeth.gayam@penske.com - is there any update on this? | Patel | 08/16/23 5:28 PM
| Yes @falgun.patel@penske.com . Pelase review https://bitbucket.penske.com/projects/MAIN/repos/pmscheduling-web/pull-requests/3/overview | Gayam | 08/17/23 1:21 AM
Row 246 | @falgun.patel@penske.com @shawn.mcmurtry@penske.com - test 2 | Patel | 07/28/23 10:30 PM
Row 246 | Test email two..... | Patel | 07/28/23 10:23 PM
Row 246 | @shawn.mcmurtry@penske.com / @falgun.patel@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:52 AM
| AO confirmed that all secrets are false positives. No code changes required. | Gayam | 06/16/23 1:13 AM
Sheet | @praneeth.gayam@penske.com Please use the folder with bodyshop6 | Subramanian | 06/15/23 1:25 AM

## Summary
Capgemini App Summary | Capgemini Migration
Field 2 | 2023-02-01
Total Apps Not Started | 0
Total Apps Capgemini is Working on | 29
Total Apps AO is Working on | 96
Grand Total of All Apps/All Status Levels | 250
Total Apps Done | 81
Total Apps Retire/Duplicate | 44
Billing - Not Started | 0
Billing - Total In Progress | 24
Billing - Done | 17
Billing - Retire/Duplicate | 11
Finance & Biz Auto - Not Started | 0
Finance & Biz Auto - Total In Progress | 1
Finance & Biz Auto - Done | 21
Finance & Biz Auto - Retire/Duplicate | 4
Architect - Not Started | 0
Architect - Total In Progress | 39
Architect - Done | 13
Architect - Retire/Duplicate | 9
Fleet Services - Not Started | 0
Fleet Services - Total In Progress | 9
Fleet Services - Done | 13
Fleet Services - Retire/Duplicate | 3
Cust Digital Engineer - Not Started | 0
Cust Digital Engineer - Total In Progress | 21
Cust Digital Engineer - Done | 0
Cust Digital Engineer - Retire/Duplicate | 10
HR - Not Started | 0
HR - Total In Progress | 12
HR - Done | 0
HR - Retire/Duplicate | 0
Web - Not Started | 0
Web - Total In Progress | 1
Web - Done | 0
Web - Retire/Duplicate | 2
Maintenance - Not Started | 0
Maintenance - Total In Progress | 18
Maintenance - Done | 17
Maintenance - Retire/Duplicate | 3
Savvion - Retire/Duplicate | 1
Security - Retire/Duplicate | 1
Oldest AO Waiting Date | 56
Blank | \
Total In Progress | 125