## Capgemini Migration - Java Sec
Redeploy w/log4j2 Complete? | Original Scope | Redeploy Needed? | Dependency | Pending Secrets Mitigation? | Application | App Group | Pending AO Review of Log4J | App Status | Health | Planned Month to be in Step 6.2? | Planned Month to Deploy to Prod (i.e. Done)? | Tshirt Size | Current (AO) Status - Start Date | Duration of Current Status (weeks) | Department Directors | AO Manager | AO Assigned | AO Assigned Email | File Total Count | Bamboo JDK8 Compliant? | Log4j? | Secrets? | Bamboo Plan is Java v1.8? REQUIRED (AO) | Bamboo? | BitBucket? | Maven? | Module (Not Confirmed) | Cap Contacts | Project Completion Date | CAP Migration (y/n) | Start Date for Major Blocker | Refresh Helper | Start Date for Waiting On AO | Start Date for (AO) Need Dev Envir Built | Start Date for (AO) Log4J | Start Date of (AO) Secrets Mitigation | Start Date for (AO) BitBucket | Start Date for (AO) Maven | Start Date for (AO) Bamboo | Start Date for (AO) QA Deploy | Start Date for (AO) App Deployed
| No |  |  |  | 24x7custnotif | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Oct 2023 | Nov 2023 | XL | 2023-10-13 | 1.2 | David Kost | Patel-Falgun | Long-David, Patel-Falgun | David, Mikos, Patel | [13 empty] | 2023-10-19 | 2023-09-06 |  |  |  |  | 2023-09-18 | 2023-09-26 | 2023-10-13
| Yes | No |  |  | ach.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-14 | 13.2 | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 131 |  | Needed | Not Needed |  | Needed | Needed | Needed | Customer File | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [6 empty] | 2023-03-30 |  | 2023-08-14
| Yes | No |  |  | achbatch | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-14 | 13.2 | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 44 |  | Needed | Not Needed |  | Needed | Needed | Needed | Cash Application | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-02-06 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-03-01 | 2023-03-29 |  | 2023-08-14
| Yes | No |  |  | achsvc.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-14 | 13.2 | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 26 |  | Needed | Not Needed |  | Needed | Needed | Needed | Customer File | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [8 empty] | 2023-08-14
| Yes | No |  |  | b2busercreation.war | Architect | TRUE | 4.2 (AO)Maven | Green | Nov 2023 | Jan 2024 | Small | 2023-10-18 | 0.2 | Victor Chelladurai | Don Kichline | Sama Bhagya - Mahendra | David Graf, Kalyan, Sama |  |  | Needed |  | Yes | Needed | Needed | Needed | B2B User Creation | Kalyan, Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-04-17 |  |  | 2023-02-24 |  | 2023-10-18
| Yes | No |  |  | bbupload.war | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done |  |  | 2023-09-22 | 5.4 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 120 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Blue Book Upload | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-02-15 | 2023-06-08 | 2023-09-11 | 2023-09-22
| Yes | No |  |  | bill_apprunner | Billing |  | 6.2 (AO)QA Deploy/Test | Green |  |  |  | 2023-09-15 | 6.8 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | 15 |  |  | Needed |  |  |  |  | PBS - CBOS - Invoice Job | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-05-18 |  |  |  |  | 2023-04-17 |  | 2023-09-15
| Yes | No |  |  | bill_avobatch | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-10 | 1.8 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | 20 |  |  | Needed |  |  |  |  | PBS - CBOS - Avo Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-06-02 |  |  |  |  | 2023-04-14 | 2023-06-15 | 2023-08-03 | 2023-10-10
| Yes | No |  |  | bill_rpginvoker | Billing |  | 6.2 (AO)QA Deploy/Test | Green |  |  |  | 2023-09-15 | 6.8 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | 12 |  |  | Needed |  |  |  |  | PBS - CBOS - RPG Invoker | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2022-12-20 |  |  | 2023-05-12 |  | 2023-08-24 | 2023-09-12 | 2023-09-15
| Yes | No |  |  | bill_xmlloader_mp | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-08-24 | 11.2 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  |  | Needed |  |  |  |  | PBS - CBOS - Invoice XML Generator | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-06-13 |  |  |  |  | 2023-05-10 | 2023-08-24
| Yes | No |  |  | bill_xmlloader_st | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-09-12 | 7.4 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | PBS - CBOS - Invoice XML Generator | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  | 2023-04-18 |  | 2023-07-13 | 2023-09-12
| Yes | No |  |  | billingcommons.jar | Customer Digital Engineer (eBusiness) |  | Dup App | Green | Done | Done | Done | 2023-03-24 | 41.8 | Michael Hintenach | D'Angelo-Frank | Shweta Gupta | shweta.gupta@penske.com | [8 empty] | Billing Commons | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-08-14
| Yes | No |  |  | billingservice.war | Billing | TRUE | 4.2 (AO)Maven | Green |  |  | Medium | 2023-09-15 | 6.8 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed |  |  | Needed | Needed | Needed | WSV - Billing Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-08-25 |  |  |  |  | 2023-09-15
| No |  | cmns, cnsmailer, wambea, billingservice depends on this utility |  | billingutility.jar | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-08-28 | 10.4 | Stephen McMullen |  | Dylan Price | [14 empty] | 2023-10-19 | [5 empty] | 2023-06-27 | 2023-08-28
| No |  |  |  | bodyshop.war | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Oct 2023 | Large | 2023-10-10 | 1.8 | David Kost | Patel-Falgun | Vennimalayan-Subramanian, Patel-Falgun,Papannagari-Sreenivasa | Patel, Sreenivasa, Subramanian | [13 empty] | 2023-10-19 | 2023-05-10 |  |  |  |  | 2023-09-21 | 2023-09-25 | 2023-10-10
| Yes | No |  |  | bos.war | HR Systems | TRUE | 3.1 (Cap)Bitbucket Migrate | Green | Nov 2023 | Jan 2024 | Medium | 2023-03-09 | 44.8 | David Kost | Tim Fox | Satish Polubothu | Satish, Shabeer |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | BOS - Breach of Security | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  | 2023-03-09
| Yes | No |  |  | buzonebatch | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-09-15 | 6.8 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  | Needed | Not Needed |  | Needed | Needed | Needed | PBS - LBS - Buzone Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-01-19 |  |  |  |  | 2023-04-02 | 2023-06-08 | 2023-09-07 | 2023-09-15
| No |  |  |  | captchabatchjob | Customer Digital Engineer (eBusiness) |  | 2.1 (Cap)Secrets Scan | Yellow |  |  | Large | 2023-09-19 | 6 | Michael Hintenach | Gopal-Sree | Joseph-Brian | Brian | [13 empty] | 2023-10-19 | 2023-08-14 |  | 2023-09-19
| No |  | PR Pending |  | captchaservice.war | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-10-04 | 3 | Michael Hintenach | Gopal-Sree | Joseph-Brian | Brian | [13 empty] | 2023-10-19 | [5 empty] | 2023-10-04
| Yes | No |  |  | cbosdbmonitor | Billing |  | Retire App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Sreenivasulu Mupparaju | Sreenivasulu | [8 empty] | CCMS | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-06-07 |  |  | 2023-05-12
| Yes | No |  |  | ccms.war | Fleet Services & Asset Mngmt (Corp) |  | Dup App | Green | Done | Done | Done |  | 0 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh |  |  | Not Needed | Not Needed | Yes | Not Needed | Not Needed | Not Needed | CCMS - Arch Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| Yes | Yes |  |  | ccms.war (Web Application) | Fleet Services & Asset Mngmt (Corp) | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-08-16 | 12.8 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 152 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | CCMS | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-08-16 | 2023-08-16
| Yes | No |  |  | ccmsservice.war | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-09-11 | 7.6 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 35 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | CCMSSERVICE | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-02-15 | 2023-05-31 |  | 2023-09-11
| Yes | Yes |  |  | ccmsxservice.war | Fleet Services & Asset Mngmt (Corp) |  | 6.1 (Cap/AO)Dev Deploy/Test | Green |  |  |  |  | 0 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 50 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | CCMS - Extranet Services | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-02-15 | 2023-06-09
| Yes | No |  |  | cds.war | HR Systems | TRUE | 4.2 (AO)Maven | Green | Nov 2023 | Jan 2024 | Medium | 2023-10-04 | 3 | David Kost | Tim Fox | Satish Polubothu | Satish, Shabeer |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | CDS E-Learning | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  | 2023-03-09 |  | 2023-10-04
| No |  |  |  | cedabatchjob | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  |  | Medium | 2023-10-18 | 0.2 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-10-19 | 2023-08-14 |  |  | 2023-09-13 |  | 2023-10-18
| No |  | PR Pending |  | cedanotifybatch | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-09-13 | 7.2 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-10-19 |  |  |  | 2023-08-21 |  | 2023-09-13
| Yes | No | billingutility.jar | TRUE | cmns.war | Billing | TRUE | 4.1 (Cap)Maven | Yellow |  |  | Medium | 2023-09-27 | 4.4 | Stephen McMullen | Rafiq Melath | Mark Weaver | manish sisodiya |  |  | Needed |  |  | Needed | Needed | Needed | CE - Customer Maintenance Notification System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-06-09 |  |  | 2023-09-27
| No |  |  |  | cmns.war | Maintenance |  | Dup App | Green | Done | Done | Done |  | 0 | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-10-19 | 2023-05-09
| Yes | No |  |  | cmsplus.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-30 | 10 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Mark Weaver | 310 |  | Needed | Not Needed |  | Needed | Needed | Needed | Collection Management Systems Enhanced | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | 2023-02-15 | 2023-10-19 | 2023-05-11 |  |  |  |  | 2023-07-19 | 2023-07-24 | 2023-08-22 | 2023-08-30
| No |  |  |  | cns.war | Maintenance |  | Retire App | Green | Done | Done | Done | 2023-07-18 | 18.6 | David Kost | McMurtry-Shawn | McMurtry-Shawn | Shawn | [13 empty] | 2023-10-19 | 2023-08-14 |  |  | 2023-06-14
| Yes | No | BillingUtility.jar | TRUE | cnsmailer | Billing | TRUE | 4.2 (AO)Maven | Yellow |  |  | Small | 2023-09-28 | 4.2 | Stephen McMullen | Rafiq Melath | Mark Weaver | manish sisodiya |  |  | Needed | Needed |  | Needed | Needed | Needed | CMNS - CNSMAILER | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-06-09 |  |  |  |  | 2023-09-28
| Yes | No |  |  | cntxfrmwrk | Architect |  | Dup App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Not Needed | Not Needed | Yes | Not Needed | Not Needed | Not Needed | Connection Mangement Framework | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed |  | Yes - Capgemini |  | 2023-10-19
| Yes | No |  |  | connectionmaint.war | Architect |  | 5.2 (AO)Bamboo Review | Green | Nov 2023 | Jan 2024 | Medium | 2023-02-09 | 50.4 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Needed | Yes | Needed | Needed | Needed | Connection Maintenance | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [6 empty] | 2023-02-09
| Yes | No |  |  | contextframework | Architect |  | 5.2 (AO)Bamboo Review | Green | Nov 2023 | Jan 2024 | Small | 2023-07-09 | 20.4 | Victor Chelladurai | Don Kichline | David Graf - Amit | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Connection Mangement Framework | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [6 empty] | 2023-07-09
| Yes | No |  |  | contribreport | Architect | TRUE | 4.2 (AO)Maven | Green | Sept 2023 | Sept 2023 | Medium | 2023-09-28 | 4.2 | Victor Chelladurai | Shane Myers | Mahipal Podduturi | David Graf, Shane Myers | 50 |  | Needed |  | Yes | Needed | Needed | Needed | Contribution Reports | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-02-16 |  |  |  |  | 2023-09-28 |  | 2023-05-04
| No |  | Blocked - No Source, Working with WAR from WebServices |  | cookie.war | Customer Digital Engineer (eBusiness) |  | Waiting on AO | Yellow |  |  | Large | 2023-08-28 | 10.4 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-10-19 | 2023-08-28
| Yes | No |  |  | csar.war | Architect |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Oct 2023 | Nov 2023 | Large |  | 0 | Victor Chelladurai | Don Kichline | David Graf | David Graf | [8 empty] | CSAR - Computer Security Access Request | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| Yes | No |  |  | csb.war | Billing | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-08-24 | 11.2 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  |  | Not Needed |  |  |  |  | PBS - Contract Support Billing (Lease) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-03-24 |  |  |  |  | 2023-08-24
| Yes | Yes |  |  | cvi.war | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done |  |  | 2023-09-22 | 5.4 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 179 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | IT Docs Lease/Cmaint Vehicle Installation | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-03-02 | 2023-06-09 | 2023-09-11 | 2023-09-22
| Yes | No |  |  | cyclops.war | Web Services |  | Retire App | Green | Done | Done | Done |  | 0 | Scott Pemrick | Scott Bortzel | Scott Pemrick | Scott Pemrick | [8 empty] | 3rd Party SSO Utility | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-03-24
| Yes | No |  |  | da.war | Architect |  | Dup App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Not Needed | Not Needed | Yes | Not Needed | Not Needed | Not Needed | Delegated Admin | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| Yes | No |  |  | darptbatch | Architect | TRUE | 2.2 (AO)Secrets Mitigate | Green | Oct 2023 | Jan 2024 | Medium | 2023-07-16 | 19 | Victor Chelladurai | Don Kichline | Elan Arulsamy | ARULSAMY, David Graf |  |  | Needed | Needed | Yes | Needed | Needed | Needed | Delegated Admin - Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  | 2023-07-16
| Yes | No |  |  | dasservice.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Nov 2023 | Small | 2023-09-12 | 7.4 | Victor Chelladurai | Don Kichline | Sarvesh Sharma | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Document Archive | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [7 empty] | 2023-09-12
| Yes | No |  |  | dasservice.war | Architect |  | Dup App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| No |  |  |  | digitech.war | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green |  |  |  | 2023-10-05 | 2.8 |  | George-Stella | Obst Gregg | [14 empty] | 2023-10-19 | 2023-08-14 |  |  | 2023-06-01 |  | 2023-09-07 | 2023-09-25 | 2023-10-05
| Yes | No |  |  | dlinkappremoval | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Oct 2023 | Small | 2023-05-24 | 29.6 | Victor Chelladurai | Don Kichline | Chokshi, Maitri | Chokshi, Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Not Needed | Dlinks Application Removal | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-05-22 |  | 2023-05-24
| Yes | No |  |  | dlinks.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Dec 2023 | Small | 2023-05-16 | 31.2 | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf, Sama |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | Dlinks | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-05-01 | 2023-04-12 | 2023-05-16
| Yes | No |  |  | dlinks_filter.jar | Architect |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Sept 2023 | Nov 2023 | Small |  | 0 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed |  | Yes | Needed | Not Needed | Needed | DLinks Authentication Filter | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| No |  |  |  | docserviceclient.jar | Architect | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-07-20 | 18.2 | Victor Chelladurai | Don Kichline | Sarvesh Sharma | David Graf | [13 empty] | 2023-10-19 | [5 empty] | 2023-07-20
| No |  |  |  | domicileservice.jar | Fleet Services & Asset Mngmt (Corp) | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-04-24 | 35.6 | Krishna Tanga |  | Rajesh Harvade | Rajesh | [13 empty] | 2023-10-19 |  |  |  | 2023-04-14 |  | 2023-04-24
| Yes | No |  |  | domservice.war | Fleet Services & Asset Mngmt (Corp) |  | 6.1 (Cap/AO)Dev Deploy/Test | Green |  |  |  |  | 0 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 46 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Domicile Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  |  | 2023-02-15 | 2023-02-16 | 2023-06-08
| Yes | No |  |  | ebill | Finance & Business Process Automation (Admin) |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth |  |  | Needed |  |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-06-05
| Yes | No |  |  | ebs.war | Architect | TRUE | 4.2 (AO)Maven | Green | Sept 2023 | Nov 2023 | Medium | 2023-09-06 | 8.6 | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf, Sama |  |  | Needed |  | Yes | Needed | Needed | Needed | EBS - Email Broadcast System | ankita.tiwary@penske.com, Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-09-06 |  |  |  |  | 2023-09-06
| Yes | No |  |  | ebsadmin.war | Architect |  | 5.2 (AO)Bamboo Review | Green | Sept 2023 | Nov 2023 | Small | 2023-09-28 | 4.2 | Victor Chelladurai | Don Kichline | Sama Bhagya, Tiwary, Ankita | David Graf, Sama |  |  | Needed |  | Yes | Needed | Needed | Needed | EBS - Admin | ankita.tiwary@penske.com, Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-09-06 |  |  |  |  | 2023-09-06 | 2023-09-28
| Yes | No |  |  | ebsservice.war | Architect |  | 5.2 (AO)Bamboo Review | Green | Oct 2023 | Dec 2023 | Small | 2023-10-02 | 3.4 | Victor Chelladurai | Don Kichline | David Graf - Amit | David Graf, Sama |  |  | Needed |  | Yes | Needed | Not Needed | Needed | WSV - EBSservice | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  | 2023-02-22 |  | 2023-03-03 | 2023-10-02
| No |  |  |  | ebsserviceclient.jar | Architect |  | 5.2 (AO)Bamboo Review | Green | Oct 2023 | Dec 2023 | Small | 2023-09-27 | 4.4 | Victor Chelladurai | Don Kichline | David Graf - Amit | David Graf, Sama | [13 empty] | 2023-10-19 | [5 empty] | 2023-06-13 | 2023-09-27
| No | No |  |  | ebsworkerbatch | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-03-20 | 42.6 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed |  | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [8 empty] | 2023-03-20
| Yes | No |  |  | ecm.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-23 | 11.4 | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 180 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | e-Credit Memo | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [7 empty] | 2023-05-16 | 2023-08-23
| Yes | No |  |  | edi_encryption | Billing | TRUE | Retire App | Green |  |  |  | 2023-04-12 | 38 | Stephen McMullen | Brian Hug | Sreenivasulu Mupparaju | Sreenivasulu |  |  | Needed | Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-04-12
| Yes | No |  |  | edibatch | Billing | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-05-12 | 32 | Stephen McMullen | Rafiq Melath | Sreenivasulu Mupparaju | Sreenivasulu |  |  |  | Not Needed |  |  |  |  | EDI Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-05-12
| Yes | No |  |  | edicbos.war | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-07-27 | 16.8 | Stephen McMullen | Rafiq Melath | Sreenivasulu Mupparaju | Sreenivasulu |  |  |  | Not Needed |  |  |  |  | EDI/CBOS | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-05-17 | 2023-07-27
| Yes | No |  |  | edipostclient | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-05-17 | 31 | Stephen McMullen | Rafiq Melath | Sreenivasulu Mupparaju | Sreenivasulu |  |  |  | Not Needed |  |  |  |  | EDI Post Client Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-01-10 |  |  |  |  | 2023-05-09 | 2023-05-17
| No |  |  |  | edvir.war | Maintenance | TRUE | 4.1 (Cap)Maven | Green | Sept 2023 | Oct 2023 | Medium |  | 0 | David Kost | George-Stella | Payel | Stella george, Vaddi Mani | [13 empty] | 2023-10-19 | 2023-05-17 |  |  | 2023-06-27
| Yes | No |  |  | efuel.war | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-09 | 2 | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn |  |  |  | Not Needed |  |  |  |  | eFuel | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-04-18 | 2023-04-18 | 2023-06-12 | 2023-10-09
| Yes | No |  |  | efueladmin.war | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-03 | 3.2 | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn |  |  |  | Not Needed |  |  |  |  | eFuel Admin | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2022-12-08 |  |  |  |  | 2023-06-19 |  |  | 2023-10-03
| No |  |  |  | emetrics.war | Customer Digital Engineer (eBusiness) |  | Retire App | Green |  |  |  | 2023-08-21 | 11.8 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-10-19 |  |  |  | 2023-08-21
| No |  |  |  | employeemasterbatch | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-21 | 11.8 | Stephen McMullen | Kalrav Khamar | [15 empty] | 2023-10-19 | 2023-06-06 |  |  |  |  | 2023-06-27 |  | 2023-06-29 | 2023-08-21
| Yes | No |  |  | eram.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA |  | 0 | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 50 |  | Needed |  | Yes | Needed | Needed | Needed | eRam | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-02-28 | 2023-03-10
| Yes | No |  |  | esr.war | Finance & Business Process Automation (Admin) |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Sept 2023 |  | 2023-08-23 | 11.4 | Stephen McMullen | Steve McMullen | Charles Csoky | Charles Csoky | 72 |  | Needed | Not Needed |  | Needed | Needed | Needed | Environmental Self Review | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-01-31 | [5 empty] | 2023-06-12 | 2023-08-23
| Yes | Yes |  |  | esrbatch | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Sept 2023 | Sept 2023 | Large | 2023-09-29 | 4 | Stephen McMullen | Steve McMullen | Charles Csoky | Charles Csoky | 31 |  | Needed | Needed |  | Needed | Needed | Needed | Environmental Self Review - Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-02-16 | 2023-03-29 | 2023-05-24 | 2023-09-29
| No |  |  |  | etimeservice.war | Maintenance |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Sept 2023 | Oct 2023 | Medium |  | 0 | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-10-19 |  |  |  | 2023-06-01 |  | 2023-06-23
| No |  | Blocked - Secrets Remediation |  | etservice.war | Customer Digital Engineer (eBusiness) | TRUE | 2.2 (AO)Secrets Mitigate | Yellow |  |  | Large | 2023-08-28 | 10.4 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth | [13 empty] | 2023-10-19 |  |  |  | 2023-08-28
| Yes | No |  |  | fbwatermark | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-09-20 | 5.8 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - CBOS - Watermark | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2022-12-20 |  |  | 2023-03-23 |  | 2023-08-24 | 2023-09-20
| Yes | No |  |  | fbwatermark.jar | Billing |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - CBOS - Watermark | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| No |  |  |  | fcservice.war | Customer Digital Engineer (eBusiness) | TRUE | 4.1 (Cap)Maven | Green |  |  | Small |  | 0 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth | [13 empty] | 2023-10-19
| No |  | PR Sent Back |  | fdtypes | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-10-18 | 0.2 | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | shweta.gupta@penske.com | [13 empty] | 2023-10-19 |  |  |  | 2023-08-09 |  | 2023-10-18
| Yes | No |  |  | fedexrental.war | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done | 2023-02-14 | 49.4 | Michael Hintenach | D'Angelo-Frank | Frank D'Angelo | Frank D'Angelo | [8 empty] | Federated SSO | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-08-14
| No |  |  |  | fimigration | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done | 2023-07-26 | 17 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-10-19 | 2023-08-14
| Yes | No |  |  | fixedasset.war | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done |  |  | 2023-09-15 | 6.8 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 14 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Fixed Assets (Web) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-06-08 | 2023-05-17 | 2023-09-11 | 2023-09-15
| Yes | No |  |  | Flex Billing | Billing |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - CBOS - Invoice and Profile Control | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-01-09
| Yes | No |  |  | flex_billing_acl.jar | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-08-29 | 10.2 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Flex Billing Account Context Loader (not in PC2) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-04-17 |  |  |  |  | 2023-08-24 | 2023-08-29
| Yes | No |  |  | flexbilling | Billing |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Elliott Eames | Elliott | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-01-09
| Yes | No |  |  | flexbilling.war | Billing | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-08-29 | 10.2 | Stephen McMullen | Rafiq Melath | Elliott Eames | Elliott | [8 empty] | PBS - CBOS - Profile Maintenance | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-08-24 |  |  | 2023-05-12 |  | 2023-08-29
| Yes | No |  |  | fmea.war | Web Services | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-08-18 | 12.4 | Gary Galyas | Gary Galyas | Gary Galyas | [9 empty] | FMEA | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-06-12 |  |  | 2023-06-01 |  | 2023-08-18
| No |  |  |  | football.war | Maintenance | TRUE | 4.1 (Cap)Maven | Green | Sept 2023 | Oct 2023 | Medium | 2023-06-22 | 23.8 | David Kost | George-Stella | Obst-Gregg | Gregg, Vaddi Mani | [13 empty] | 2023-10-19 | 2023-08-14 |  |  | 2023-06-01
| Yes | No |  |  | fuelbatch | Billing | TRUE | 6.2 (AO)QA Deploy/Test | Green |  |  |  | 2023-10-09 | 2 | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn | [8 empty] | FuelNet - Fuel Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-05-23 |  |  | 2023-05-04 |  | 2023-08-31 |  | 2023-10-09
| No |  | PR Pending w/ questions |  | fuelcalc.war | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-09-25 | 4.8 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth | [13 empty] | 2023-10-19 |  |  |  | 2023-08-09 |  | 2023-09-25
| No |  |  |  | fuelcalcadmin.war | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done | 2023-08-17 | 12.6 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth | [13 empty] | 2023-10-19 | 2023-08-17 |  |  | 2023-08-04
| Yes | No |  |  | fuelcardsplit.war | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-17 | 0.4 | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Truckstop Fuel | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-09-28 | 2023-08-21 | 2023-10-05 | 2023-10-17
| Yes | No |  |  | fuelnet | Billing |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-05-03 |  |  | 2023-05-12
| Yes | No |  |  | fuelnetsvc.war | Billing | TRUE | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-10-17 | 0.4 | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn |  |  | Needed | Not Needed |  | Needed | Needed | Not Needed | FuelNet - Web Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-08-21 | 2023-10-17
| Yes | No |  |  | fuelpricing.war | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-06-23 | 23.6 | Stephen McMullen | Rafiq Melath | Bill Spohn | Elliott |  |  | Needed | Needed |  | Needed | Needed | Needed | Fuel Purchasing - Fuel Pricing | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-01-10 |  |  |  |  | 2023-04-04 | 2023-06-23
| Yes | Yes |  |  | fuelpromos.war | Billing | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-09-01 | 9.6 | Stephen McMullen | Rafiq Melath | Elliott Eames | Elliott | [8 empty] | Fuel Promotion Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-01-09 |  |  | 2023-07-17 |  | 2023-09-01
| Yes | No |  |  | fuelrecptbatch | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-05-16 | 31.2 | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | CE - Fuel Receipt Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  |  | 2023-08-14
| No | No |  |  | fuelrecptbatch | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| Yes | No |  |  | gewebcash | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | Oct 2023 |  | 2023-09-26 | 4.6 | Stephen McMullen | Kalrav Khamar | Srinivasan Narayanan | Sreekanth, Srinivasan Narayanan |  |  | Needed | Not Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [6 empty] | 2023-03-23 | 2023-09-05 | 2023-09-26
| Yes | No |  |  | High Radius | Billing |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-03 | 3.2 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | invarcbatch-sftp | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2022-12-07 |  |  | 2023-03-23 |  | 2023-06-29 |  | 2023-08-03 | 2023-10-03
| No |  | football.war |  | highavail | Architect |  | 1.2 (AO)Log4i Review | Green |  |  | Large | 2023-09-06 | 8.6 | Victor Chelladurai | Don Kichline | Shane Myers | [15 empty] | 2023-08-24 |  | 2023-09-06
| Yes | No |  |  | hrcc.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-30 | 10 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 83 |  | Needed | Not Needed |  | Needed | Not Needed | Needed | HRCC Highradius Collection Cloud | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-04-18 |  | 2023-05-24 | 2023-08-30
| Yes | No |  |  | hrldapcomparision | Architect |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Oct 2023 | Nov 2023 | Small |  | 0 | Victor Chelladurai | Don Kichline | Chokshi, Maitri | Chokshi, David Graf, Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | HRLDAP Comparison | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| Yes | No |  |  | hvutefile | Fleet Services & Asset Mngmt (Corp) | TRUE | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-12 | 1.4 | Krishna Tanga | Veronique Labeille | Veronique Labeille | Sreekanth, Veronique Labeille |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-05-24 |  |  | 2023-02-24 |  | 2023-07-09 |  |  | 2023-10-12
| Yes | No |  |  | ias-broker | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-09-13 | 7.2 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | IASBATCHBROKER (not in PC2) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2022-12-13 |  |  | 2023-06-27 |  | 2023-09-06 | 2023-09-13
| Yes | No |  |  | ias-invoiceimage | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-09-12 | 7.4 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | invoiceimagebatch (not in PC2) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | 2023-06-29 | 2023-10-19 | 2023-08-14 |  |  | 2023-05-12 |  | 2023-08-29 | 2023-09-12
| Yes | No |  |  | ias-lbs | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-09-12 | 7.4 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - LBS - Logistics Billing System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-08-14 |  |  | 2023-03-23 |  | 2023-08-30 | 2023-09-12
| Yes | No |  |  | ias.war | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-09-12 | 7.4 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Invoice Archive System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-08-24 | 2023-09-12
| Yes | No |  |  | iasarchiver | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-09-12 | 7.4 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | IASARCHIVER (not in PC2) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2022-12-13 |  |  | 2023-05-12 |  | 2023-08-29 | 2023-09-12
| Yes | No |  |  | iasinvservice.war | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-09-12 | 7.4 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  | Needed | Not Needed |  | Needed | Needed | Needed | WSV - IASInvService | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-08-24 | 2023-09-12
| Yes | No |  |  | international.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Dec 2023 | Small | 2023-05-09 | 32.6 | Victor Chelladurai | Don Kichline | David Graf - Ankita | David Graf, Sama |  |  | Needed | Needed | Yes | Needed | Needed | Needed | ASP - International Link (eLearning) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-04-11 |  |  |  |  | 2023-02-22 |  | 2023-05-09
| No |  | PR Pending |  | intsecuritysvc.war | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-10-12 | 1.4 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-10-19 | [5 empty] | 2023-10-12
| Yes | No |  |  | invarcbatch | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-09-12 | 7.4 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | PBS - Invoice Archive Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2022-12-15 |  |  | 2023-04-18 |  | 2023-08-24 | 2023-09-12
| Yes | No |  |  | invarcbatch | Billing |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - Invoice Archive Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2022-12-15 |  |  | 2023-05-12
| Yes | Yes |  |  | irm.war | Fleet Services & Asset Mngmt (Corp) | TRUE | 2.2 (AO)Secrets Mitigate | Green |  |  |  | 2023-09-15 | 6.8 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 208 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | IRM Prism / Web Application | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-08-14 |  |  | 2023-09-15 |  |  | 2023-04-17
| Yes | No |  |  | irmbatch | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-09-22 | 5.4 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 110 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | IRM Prism / Savvion Transfer | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-02-16 | 2023-06-08 |  | 2023-09-22
| No |  |  |  | IRS Dependency Jar Here | Fleet Services & Asset Mngmt (Corp) |  | Dup App | Green | Done | Done | Done |  | 0 | Krishna Tanga | Veronique Labeille | Sreekanth Kancharla | Kancharla, Sreekanth (Penske, Capgemini) <Sreekanth.Kancharla@penske.com> | [13 empty] | 2023-10-19
| Yes |  |  |  | irs.jar | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-10-12 | 1.4 | Krishna Tanga | Veronique Labeille | Sreekanth Kancharla | Kancharla, Sreekanth (Penske, Capgemini) <Sreekanth.Kancharla@penske.com> | [13 empty] | 2023-10-19 | 2023-05-02 |  |  |  |  | 2023-06-23 | 2023-08-01 |  | 2023-10-12
| Yes | No |  |  | iseriessavvionwebserviceclient | Savvion |  | Retire App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Peter MacMahon | Peter MacMahon | Peter | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-03-24
| Yes | No |  |  | itcontact.war | HR Systems | TRUE | 4.1 (Cap)Maven | Yellow | Dec 2023 | Jan 2024 | Large | 2023-03-09 | 44.8 | David Kost | Tim Fox | Satish Polubothu | Satish, Shabeer |  |  | Needed |  | Yes | Needed | Needed | Needed | IT Contact Information | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  | 2023-03-09
| Yes | No |  |  | javapostop | Architect |  | 5.2 (AO)Bamboo Review | Green | Oct 2023 | Dec 2023 | Medium | 2023-10-04 | 3 | Victor Chelladurai | Don Kichline | Maitri Chokshi | Chokshi, Sherin |  |  | Needed | Needed | Yes | Needed | Needed | Needed | JAVAPOSTOP | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-04-05 |  |  |  |  | 2023-07-13 | 2023-10-04
| Yes | No |  |  | lbs.war | Billing |  | 6.1 (Cap/AO)Dev Deploy/Test | Green |  |  |  |  | 0 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | PBS - LBS - Logistics Billing System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-06-05
| No |  | PR Pending w/ questions |  | ldapcompanybatch | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-09-20 | 5.8 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-10-19 |  |  |  | 2023-08-09 |  | 2023-09-20
| Yes | No |  |  | ldapismgr | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | Sherin |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | ldapismgr | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-04-06
| No |  |  |  | locationfinder.war | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done | 2023-08-21 | 11.8 | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | shweta.gupta@penske.com | [13 empty] | 2023-10-19 |  |  |  | 2023-08-21
| No |  | Secrets Review Pending |  | locationsearch | Customer Digital Engineer (eBusiness) | TRUE | 2.2 (AO)Secrets Mitigate | Yellow |  |  | XL | 2023-09-13 | 7.2 | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | shweta.gupta@penske.com | [13 empty] | 2023-10-19 | 2023-09-07 |  |  | 2023-09-13
| No |  | Blocked - Mult Environ Folder |  | locrulesrv.war | Customer Digital Engineer (eBusiness) | TRUE | 4.1 (Cap)Maven | Green |  |  |  | 2023-09-13 | 7.2 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth | [13 empty] | 2023-10-19 | 2023-08-14 |  |  | 2023-08-21 |  | 2023-09-13
| Yes | No |  |  | mailreader_1_0 | Finance & Business Process Automation (Admin) |  | Dup App | Green | Done | Done | Done | 2023-08-03 | 15.4 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth |  |  | Needed |  |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-08-14
| Yes | No |  |  | mailreader_2_0 | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Sept 2023 | Oct 2023 | XL | 2023-10-12 | 1.4 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth |  |  | Needed | Not Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-05-01 | 2023-05-09 | 2023-09-05 | 2023-10-12
| No |  |  |  | maintconfig.war | Maintenance | TRUE | 6.1 (Cap/AO)Dev Deploy/Test | Green | Oct 2023 | Nov 2023 | XL | 2023-10-11 | 1.6 | David Kost | Patel-Falgun | Mani-Sarath, Patel-Falgun | Mikos, Patel, Vaddi Mani | [13 empty] | 2023-10-19 | 2023-09-06 |  |  | 2023-06-27 |  | 2023-10-11
| No |  |  |  | mapadmin.war | Customer Digital Engineer (eBusiness) | TRUE | 4.1 (Cap)Maven | Green |  |  |  | 2023-08-21 | 11.8 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth | [13 empty] | 2023-10-19 |  |  |  | 2023-08-21
| No |  | Blocked - Secrets Remediation |  | mapservice.war | Customer Digital Engineer (eBusiness) | TRUE | 2.2 (AO)Secrets Mitigate | Yellow |  |  | Large | 2023-08-04 | 15.2 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth | [13 empty] | 2023-10-19 |  |  |  | 2023-08-04
| No |  | PR Pending |  | mfaservice | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  |  | Large | 2023-09-18 | 6.2 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth | [13 empty] | 2023-10-19 | 2023-08-14 |  |  | 2023-09-13 |  | 2023-09-18
| Yes | No |  |  | mileageforecast.war | Billing |  | Retire App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Dylan Price |  |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Iron Mountain Excel upload (Mileage Forecast) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-03-23
| Yes | No |  |  | mileagereporting.war | Billing | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-08-24 | 11.2 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Web Mileage Entry | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-08-24
| No |  |  |  | modifyuserdaemon | Customer Digital Engineer (eBusiness) | TRUE | 4.1 (Cap)Maven | Green |  |  |  | 2023-08-04 | 15.2 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-10-19 |  |  |  | 2023-08-04
| No |  | PR Pending, Blocked - Mult Environ Folder |  | notificationbatch | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-10-10 | 1.8 | Michael Hintenach | D'Angelo-Frank | Ashway, Jeremiah | Jeremiah Ashway | [13 empty] | 2023-10-19 | 2023-08-17 |  |  |  |  | 2023-10-10
| No |  |  |  | openrepairsumm | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Oct 2023 | Medium | 2023-09-01 | 9.6 | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-10-19 | 2023-05-31 |  |  |  |  | 2023-07-16 | 2023-07-19 | 2023-09-01
| Yes | No |  |  | oracle2ldap | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Nov 2023 | Small | 2023-06-23 | 23.6 | Victor Chelladurai | Don Kichline | Chokshi, Maitri | David Graf |  |  | Needed | Needed | Yes | Needed | Needed | Needed | Oracle2LDAP | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-04-19 | 2023-04-13 | 2023-06-23
| Yes | No |  |  | oraemail | Architect |  | Retire App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | OraEmail | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| No |  |  |  | partspo | Maintenance |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-09-12 | 7.4 | David Kost | George-Stella | Karthik | Karthikeyan, Vaddi Mani | [13 empty] | 2023-10-19 |  |  |  | 2023-06-01 |  | 2023-06-29 |  | 2023-09-06 | 2023-09-12
| Yes | No |  |  | pcc | HR Systems | TRUE | 4.1 (Cap)Maven | Yellow | Dec 2023 | Jan 2024 | Large | 2023-10-03 | 3.2 | David Kost | Tim Fox | Satish Polubothu | Satish, Shabeer |  |  | Needed |  | Yes | Needed | Needed | Needed | PC2- Penske Change Control Batch App | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-08-14 |  |  | 2023-10-03
| Yes | No |  |  | pcc.war | HR Systems | TRUE | 4.1 (Cap)Maven | Yellow | Dec 2023 | Jan 2024 | Large | 2023-10-03 | 3.2 | David Kost | Tim Fox | Satish Polubothu | Satish, Shabeer |  |  | Needed |  | Yes | Needed | Needed | Needed | PCÂ² - Penske Change Control | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-08-14 |  |  | 2023-10-03
| No | No |  |  | penske-secure-logger-1.0.0.jar | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-04-14 | 37.6 | Victor Chelladurai | Don Kichline | David Graf | Don Kichline |  |  | Needed |  | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [8 empty] | 2023-04-14
| No | No |  |  | penske-watchlist-client jar | Architect | TRUE | 4.1 (Cap)Maven | Green | Oct 2023 | Nov 2023 | Small | 2023-07-05 | 21.2 | Victor Chelladurai | Don Kichline | Mahipal Podduturi | David Graf |  |  | Not Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-07-05
| No |  | spellingservice.war |  | penske_spelling_Client | Maintenance |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-22 | 11.6 | David Kost | George-Stella | Mani-Sarath | Dale Porter | [13 empty] | 2023-10-19 | 2023-07-05 |  |  |  |  | 2023-07-26 | 2023-08-02 |  | 2023-08-22
| No |  | spellingservice.war depends on this utility. |  | penske_spellingutility.jar | Maintenance |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-24 | 11.2 | David Kost | George-Stella | Mani-Sarath | Dale Porter, Vaddi Mani | [13 empty] | 2023-10-19 | [5 empty] | 2023-06-23 | 2023-07-11 |  | 2023-08-24
| Yes | No |  |  | penskesso-ws-client.jar | Architect | TRUE | 4.2 (AO)Maven | Green | Oct 2023 | Dec 2023 | Small | 2023-09-06 | 8.6 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Not Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-09-06 |  |  |  |  | 2023-09-06
| No | No |  |  | penskesso.jar | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-04-14 | 37.6 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [8 empty] | 2023-04-14
| No |  |  |  | peoplenetbatch | Maintenance |  | Dup App | Green | Oct 2023 | Oct 2023 | Medium | 2023-07-19 | 18.4 | David Kost | George-Stella | Payel | Ganguly, Stella george, Vaddi Mani | [13 empty] | 2023-10-19 |  |  |  | 2023-06-01 |  | 2023-07-19
| Yes | No |  |  | pettycash.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA |  | 0 | Stephen McMullen | Kalrav Khamar | Srinivasan Narayanan | Sreekanth, Srinivasan Narayanan | 72 |  | Needed | Needed |  | Needed | Needed | Needed | AP Petty Cash | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  | 2023-02-24 |  |  | 2023-03-10
| Yes | No |  |  | pextfl | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | Sept 2023 | Medium | 2023-09-15 | 6.8 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 9 |  | Needed | Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-07-26 |  | 2023-08-21 | 2023-09-15
| No |  |  |  | phonesvc.war | Maintenance |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Sept 2023 | Oct 2023 | Medium |  | 0 | David Kost | Patel-Falgun | Long-David, Patel-Falgun | David, Patel | [13 empty] | 2023-10-19 |  |  |  | 2023-06-01 |  | 2023-07-11
| No |  |  |  | pmmailer | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Oct 2023 | XL | 2023-10-13 | 1.2 | David Kost | Patel-Falgun | Kenneth Mikos | Mikos | [13 empty] | 2023-10-19 | 2023-09-06 |  |  | 2023-06-01 |  | 2023-09-15 | 2023-09-26 | 2023-10-13
| No |  |  |  | pmscheduling.war | Maintenance |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Oct 2023 | Nov 2023 | XL | 2023-08-16 | 12.8 | David Kost | Patel-Falgun | McMurtry-Shawn, Patel-Falgun | Mikos, Patel, Shawn | [13 empty] | 2023-10-19 |  |  |  | 2023-06-14 |  | 2023-08-16
| Yes | No |  |  | pops.war | Finance & Business Process Automation (Admin) |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Oct 2023 |  | 2023-09-15 | 6.8 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 300 |  | Needed |  |  | Needed | Needed | Needed | POPS - Penske On-Line Payment System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-02-24 |  |  |  |  | 2023-03-16 |  | 2023-09-15
| Yes | No |  |  | pops_batch | Finance & Business Process Automation (Admin) |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Oct 2023 | XL | 2023-03-28 | 41 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 85 |  | Needed |  |  | Needed | Needed | Needed | POPS - Batch Process | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-02-27 |  |  |  |  | 2023-03-15 |  | 2023-03-28
| Yes | No |  |  | printapp | Billing |  | 6.2 (AO)QA Deploy/Test | Green |  |  |  | 2023-10-05 | 2.8 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  | Needed | Needed |  | Needed | Needed | Needed | PRINTAPP | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-03-30 | 2023-08-23 | 2023-10-05 | 2023-09-15
| No | No |  |  | psndmail | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Sept 2023 | Oct 2023 | Large | 2023-10-05 | 2.8 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | [13 empty] | 2023-10-19 |  |  |  | 2023-02-23 |  | 2023-03-01 | 2023-03-20 | 2023-08-21 | 2023-10-05
| Yes | No |  |  | ptldao.jar | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA |  | 0 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Was Needed - AO Done | Was Needed - AO Done | Yes | Not Needed | Was Needed - AO Done | Was Needed - AO Done | PTL DAO | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| Yes | No |  |  | queryrunner | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA |  | 0 | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed |  | Yes | Needed | Needed | Needed | need to create one | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed |  |  |  | 2023-10-19 |  |  |  |  | 2023-02-22 |  |  |  | 2023-05-16
| No |  |  |  | reconcilebatch | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done | 2023-08-04 | 15.2 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-10-19 |  |  |  | 2023-08-04
| No |  |  |  | rentaladmin.war | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done |  | 0 | Michael Hintenach | Gopal-Sree | French-Kenneth | Kenneth | [13 empty] | 2023-10-19
| Yes | No |  |  | rentalnet.war | Billing |  | Retire App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | 1050 |  | Needed |  |  | Needed | Needed | Needed | PBS - Contract Support Billing (RentalNet/VAR) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-01-23 |  |  | 2023-05-12
| Yes | No |  |  | restfilter.jar | Architect |  | 5.2 (AO)Bamboo Review | Green | Nov 2023 | Jan 2024 | Small | 2023-09-27 | 4.4 | Victor Chelladurai | Don Kichline | Sama Bhagya | Sama |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-01-24 | 2023-09-27
| Yes | No |  |  | reuse-changemode | Architect |  | Retire App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Not Needed | Not Needed | Yes | Not Needed | Not Needed | Not Needed | Reusable Web Code | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed |  |  |  | 2023-10-19
| Yes | No |  |  | reuse.jar | Architect |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Jan 2024 | Jan 2024 | XL |  | 0 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Needed | Yes | Needed | Needed | Needed | Reusable Web Code | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| Yes | No |  |  | roforms.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Oct 2023 | Medium | 2023-04-05 | 39.4 | Victor Chelladurai | Don Kichline | Chokshi, Maitri | Chokshi |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | ASP - RO Forms | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [7 empty] | 2023-04-05
| No |  |  |  | rsareviewloop.war | Maintenance | TRUE | 4.2 (AO)Maven | Green | Sept 2023 | Nov 2023 | Medium | 2023-09-22 | 5.4 | David Kost | Patel-Falgun | Long-David, Patel-Falgun | David, Patel | [13 empty] | 2023-10-19 |  |  |  | 2023-06-27 |  | 2023-09-22
| Yes | Yes |  |  | rsi.war | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done |  |  | 2023-09-22 | 5.4 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 84 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | IT DOCS Rental Vehicle Installation | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-02-15 | 2023-06-08 | 2023-09-11 | 2023-09-22
| Yes | No |  |  | safetydata | Fleet Services & Asset Mngmt (Corp) |  | Dup App | Green | Done | Done | Done |  | 0 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Non-Critical | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-02-16 |  |  |  |  | 2023-02-15
| Yes | Yes |  |  | safetydata.war | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-09-22 | 5.4 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh |  | No | Needed | Not Needed | Yes | Needed | Needed | Needed | Insurance Safety Data | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2022-12-26 |  |  | 2023-02-24 |  | 2023-06-15 |  |  | 2023-09-22
| Yes | No |  |  | schedule1reprint | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-23 | 11.4 | Krishna Tanga | Veronique Labeille | Veronique Labeille | Sreekanth, Veronique Labeille |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  | 2023-02-24 |  | 2023-04-14 |  | 2023-05-22 | 2023-08-23
| No | No |  |  | scorecard - Batch | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-09-15 | 6.8 | Krishna Tanga | Veronique Labeille | Veronique Labeille | Sreekanth, Veronique Labeille | [13 empty] | 2023-10-19 |  |  |  | 2023-02-24 |  | 2023-05-02 | 2023-05-11 | 2023-05-22 | 2023-09-15
| Yes | No |  |  | scorecard - Web | Fleet Services & Asset Mngmt (Corp) |  | DONE - (AO)App Deployed | Green |  |  |  | 2023-09-15 | 6.8 | Krishna Tanga | Veronique Labeille | Veronique Labeille | Sreekanth, Veronique Labeille |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  | 2023-02-19 |  | 2023-03-17 |  | 2023-05-22 | 2023-09-15
| No | No |  |  | security_author_filter.jar | Architect |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-02-13 | 49.6 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  | 2023-02-08 |  |  | 2023-02-13
| No | No |  |  | security_util.jar | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-02-15 | 49.2 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [8 empty] | 2023-02-15
| Yes | No |  |  | sellsheet | Fleet Services & Asset Mngmt (Corp) | TRUE | 4.2 (AO)Maven | Green |  |  | XL | 2023-10-18 | 0.2 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 26 |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | 2023-04-13 | 2023-10-19 | 2023-08-14 |  |  |  |  | 2023-10-18
| Yes | No |  |  | sem.war (aka Security Exception Maintenance) | Security |  | Retire App | Green | Done | Done | Done |  | 0 | Scott Bortzel | Scott Bortzel <scott.bortzel@penske.com> | [10 empty] | Security Exception Maintenance | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-03-24
| No |  |  |  | servicenetbatch | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Oct 2023 | Medium | 2023-08-11 | 13.8 | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-10-19 | 2023-06-20 |  |  | 2023-06-14 |  | 2023-07-27 |  | 2023-08-11
| No |  |  |  | servicereqbatch | Maintenance | TRUE | 4.1 (Cap)Maven | Green | Sept 2023 | Oct 2023 | Medium | 2023-08-04 | 15.2 | David Kost | George-Stella | Vennimalayan-Subramanian | Subramanian, Vaddi Mani | [13 empty] | 2023-10-19 | 2023-05-17 |  |  | 2023-08-04
| No |  | serviceRequestUtility.jar |  | servicereqsvc.war | Maintenance | TRUE | 4.2 (AO)Maven | Green | Sept 2023 | Oct 2023 | Medium | 2023-09-20 | 5.8 | David Kost | George-Stella | Vennimalayan-Subramanian | Subramanian, Vaddi Mani | [13 empty] | 2023-10-19 | 2023-05-31 |  |  | 2023-09-13 |  | 2023-09-20
| No |  | Servicereqsvc,war, edvir.war, servicereqbatch, servicereqweb, webmileagesvc.war and unitjkt.war are depends on this utility |  | serviceRequestUtility.jar | Maintenance |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-09-06 | 8.6 | David Kost | George-Stella | Vennimalayan-Subramanian | Stella george, Subramanian | [13 empty] | 2023-10-19 |  |  |  | 2023-06-27 |  | 2023-07-06 | 2023-09-01 |  | 2023-09-06
| No |  |  |  | servicereqweb.war | Maintenance |  | 6.1 (Cap/AO)Dev Deploy/Test | Yellow | Sept 2023 | Oct 2023 | Medium | 2023-09-20 | 5.8 | David Kost | George-Stella | Vennimalayan-Subramanian | Subramanian, Vaddi Mani | [13 empty] | 2023-10-19 | 2023-08-14 |  |  | 2023-09-13 |  | 2023-09-20
| Yes | Yes |  |  | sessionmgmtsvc.war | Architect |  | DONE - (AO)App Deployed | Green | Sept 2023 |  | Small | 2023-09-27 | 4.4 | Victor Chelladurai | Don Kichline | Sivagamasundari Suresh | David Graf |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | Session Management Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [7 empty] | 2023-09-12 | 2023-09-27
| Yes | No |  |  | shoptalkreg.war | Architect |  | Retire App | Green | Done | Done | Done | 2023-05-16 | 31.2 | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Shop Talk Registration | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [6 empty] | 2023-03-23 | 2023-05-16
| No |  | PR Pending |  | shorturlservice | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  |  | Medium | 2023-10-10 | 1.8 | Michael Hintenach | Gopal, Sree | French-Kenneth | Kenneth | [13 empty] | 2023-10-19 |  |  |  | 2023-09-13 |  | 2023-10-10
| Yes | No |  |  | sics | Finance & Business Process Automation (Admin) |  | Retire App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | NA |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed |  |  |  | 2023-10-19
| Yes | No |  |  | sics.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-17 | 12.6 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 204 |  | Needed | Not Needed |  | Needed | Needed | Needed | SICS - Sales Incentives Commission System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [7 empty] | 2023-07-05 | 2023-08-17
| Yes | No |  |  | sicsbatch | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-17 | 12.6 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 108 |  | Needed | Not Needed |  | Needed | Needed | Needed | SICS Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [7 empty] | 2023-07-05 | 2023-08-17
| Yes | No |  |  | sicssvc.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-17 | 12.6 | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 83 |  | Needed | Not Needed |  | Needed | Needed | Needed | SICS Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [7 empty] | 2023-07-05 | 2023-08-17
| No |  |  |  | smsbatch | Maintenance | TRUE | 4.2 (AO)Maven | Yellow |  | Nov 2023 | Small | 2023-10-12 | 1.4 | David Kost | McMurtry-Shawn | McMurtry-Shawn | Shawn | [13 empty] | 2023-10-19 | 2023-07-30 |  |  | 2023-09-13 |  | 2023-10-12
| No |  |  |  | smsservice.war | Maintenance | TRUE | 4.1 (Cap)Maven | Yellow |  | Nov 2023 | Small | 2023-09-13 | 7.2 | David Kost | McMurtry-Shawn | McMurtry-Shawn | Shawn | [13 empty] | 2023-10-19 | 2023-07-30 |  |  | 2023-09-13
| No |  |  |  | smsserviceutility | Maintenance |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-09-06 | 8.6 | David Kost | George-Stella | Shawn Mcmurtry | Shawn | [19 empty] | 2023-08-30 |  |  | 2023-09-06
| Yes | No |  |  | smvendors | Web Services |  | Retire App | Green | Done | Done | Done |  | 0 | Scott Pemrick | Scott Bortzel | Scott Pemrick | Scott Pemrick | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-03-24
| No |  |  |  | sos.war | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Oct 2023 | Oct 2023 | XL | 2023-09-25 | 4.8 | David Kost | Patel-Falgun | Papannagari-Sreenivasa, George-Stella | Patel, Sreenivasa | [13 empty] | 2023-10-19 | 2023-08-14 |  |  | 2023-06-01 |  | 2023-09-18 |  | 2023-09-25
| No |  |  |  | sospcard.war | Maintenance |  | 6.1 (Cap/AO)Dev Deploy/Test | Green | Oct 2023 | Oct 2023 | XL | 2023-10-02 | 3.4 | David Kost | Patel-Falgun | Papannagari-Sreenivasa, George-Stella | Patel, Sreenivasa | [13 empty] | 2023-10-19 | 2023-09-06 |  |  | 2023-06-14 |  | 2023-09-20 | 2023-10-02
| No |  | sosutility.jar |  | sosservice.war | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Done | Oct 2023 | Medium | 2023-08-23 | 11.4 | David Kost | Patel-Falgun | Long-David | David, Patel | [13 empty] | 2023-10-19 | 2023-05-10 |  |  | 2023-07-17 |  | 2023-08-08 | 2023-08-17 | 2023-08-23
| No |  | sosservice,sos.war,24x7custnotif depend on this utlity. |  | sosutility | Maintenance |  | DONE - (AO)App Deployed | Green | Done | Sept 2023 | Small | 2023-08-24 | 11.2 | David Kost | Patel-Falgun | Long-David, Patel-Falgun | David, Patel, Sreenivasa | [13 empty] | 2023-10-19 | [5 empty] | 2023-06-27 | 2023-07-12 |  | 2023-08-24
| No |  | penske_spelling_Client |  | spellingservice.war | Maintenance | TRUE | 4.2 (AO)Maven | Green | Sept 2023 | Oct 2023 | Medium | 2023-10-17 | 0.4 | David Kost | George-Stella | Mani-Sarath | Dale Porter, Vaddi Mani | [13 empty] | 2023-10-19 | 2023-06-20 |  |  | 2023-07-21 |  | 2023-10-17
| No |  |  |  | ssoservice.war | Customer Digital Engineer (eBusiness) |  | Retire App | Green | Done | Done | Done | 2023-07-31 | 16 | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Jeremiah Ashway | [13 empty] | 2023-10-19 | 2023-08-14
| Yes | No |  |  | ssptktportal.war | Billing |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-08-16 | 12.8 | Stephen McMullen | Rafiq Melath | Spohn-Bill | William Spohn | [8 empty] | Fuel Reconciliation-Suspended Tkts Portal | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2022-12-07 |  |  | 2023-03-23 |  | 2023-04-24 | 2023-08-16 | 2023-08-03
| Yes | No |  |  | stopbilling.war | Billing |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-15 | 13 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | IT Docs - Stop Billing | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-05-11 |  | 2023-08-02 | 2023-08-15
| Yes | No |  |  | synchghdbc | Architect |  | Retire App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed |  | Yes | Needed | Needed | Needed | SynchGHDBC | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2022-12-15 |  |  |  |  | 2023-03-01
| Yes | No |  |  | taebatch | Fleet Services & Asset Mngmt (Corp) | TRUE | 2.2 (AO)Secrets Mitigate | Green |  |  | Medium |  | 0 | Krishna Tanga | Krishna Tanga | Ravi Daram | Ravi | 60 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | T&E Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| Yes | No |  |  | techchallenge.war | Architect | TRUE | 4.2 (AO)Maven | Green | Sept 2023 | Nov 2023 | Small | 2023-09-06 | 8.6 | Victor Chelladurai | Don Kichline | Sarvesh Sharma | David Graf, Sama |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | ASP - Tech Challenge | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-09-06 |  |  |  |  | 2023-09-06
| Yes | No |  |  | telematicssvc.war | Architect |  | Retire App | Green | Done | Done | Done | 2023-05-15 | 31.4 | Victor Chelladurai | Don Kichline | Myers-Shane | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Telematics Service (eDTR) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-05-15
| Yes | No |  |  | tririga_integrations | Finance & Business Process Automation (Admin) |  | 5.2 (AO)Bamboo Review | Green | Sept 2023 | Oct 2023 |  | 2023-07-14 | 19.4 | Stephen McMullen | Steve McMullen | Charles Csoky | Charles Csoky | 30 |  | Needed |  |  | Needed | Needed | Needed | Tririga- Integrations | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-06-15 |  |  |  |  | 2023-07-12 | 2023-07-14
| Yes | No |  |  | trs_extract | Billing |  | Dup App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Rafiq Melath | Manish Sisodiya | manish sisodiya | [8 empty] | Trust Extract | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19
| Yes | No |  |  | trs_extract.jar | Billing |  | 6.2 (AO)QA Deploy/Test | Green |  |  |  | 2023-09-15 | 6.8 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | Trust Extract | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2022-12-14 |  |  | 2023-03-23 |  | 2023-08-24 | 2023-09-12 | 2023-09-15
| No |  |  |  | unitjkt.war | Maintenance | TRUE | 4.1 (Cap)Maven | Green | Sept 2023 | Oct 2023 | Medium | 2023-07-18 | 18.6 | David Kost | Patel-Falgun | Long-David | David, Patel | [13 empty] | 2023-10-19 | 2023-08-14 |  |  | 2023-07-03
| No |  | Blocked - Secrets, Mult Environ Folder |  | updlatlong | Customer Digital Engineer (eBusiness) | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-10-17 | 0.4 | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | shweta.gupta@penske.com | [13 empty] | 2023-10-19 | 2023-09-06 |  |  |  |  | 2023-10-17
| No |  |  |  | updtimezon | Customer Digital Engineer (eBusiness) |  | Dup App | Green | Done | Done | Done | 2023-07-27 | 16.8 | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | shweta.gupta@penske.com | [13 empty] | 2023-10-19 | 2023-08-14
| No |  | PR Pending |  | usedtrucksadmin.war | Customer Digital Engineer (eBusiness) | TRUE | 4.1 (Cap)Maven | Green |  |  |  | 2023-10-12 | 1.4 | Michael Hintenach | Gopal-Sree | Joseph-Brian | Brian | [13 empty] | 2023-10-19 |  |  |  | 2023-08-04 |  | 2023-10-12
| Yes | No |  |  | userlookup.war | Architect |  | DONE - (AO)App Deployed | Green | Sept 2023 | Nov 2023 | Small | 2023-09-29 | 4 | Victor Chelladurai | Don Kichline | David Graf - Ankita | David Graf, Sherin |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | User Lookup Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-06-19 | 2023-06-30 | 2023-07-05 | 2023-09-29
| No |  |  |  | usermaint.war | Maintenance |  | 6.1 (Cap/AO)Dev Deploy/Test | Yellow | Sept 2023 | Oct 2023 | Medium | 2023-09-19 | 6 | David Kost | George-Stella | Srinivasan-Karthikeyan | Karthikeyan, Vaddi Mani | [13 empty] | 2023-10-19 | 2023-08-14 |  |  | 2023-09-13 |  | 2023-09-19
| Yes | No |  |  | usermgmt.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Oct 2023 | Oct 2023 | Medium | 2023-10-17 | 0.4 | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf, Sama |  |  | Needed | Was Needed - AO Done | Yes | Needed | Not Needed | Needed | User Management | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [6 empty] | 2023-09-11 | 2023-10-17 | 2023-09-11
| Yes | Yes |  |  | usermgmtsvc.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Oct 2023 | Oct 2023 | Medium | 2023-09-26 | 4.6 | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | User Management Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 |  |  |  | 2023-02-08 |  |  |  | 2023-09-26
| Yes | No |  |  | userstoreclient_rest.jar | Architect | TRUE | 4.2 (AO)Maven | Green | Jan 2024 | Jan 2024 | Small | 2023-02-15 | 49.2 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | User Store Client - Rest | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-02-15
| Yes | No |  |  | userstoresvcjws.war | Architect | TRUE | 4.2 (AO)Maven | Green | Jan 2024 | Jan 2024 | Small | 2023-09-06 | 8.6 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Userstore Service - jax-ws | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-09-06 |  |  |  |  | 2023-09-06
| No |  |  |  | usrcreationsvc-client.jar | Architect |  | 5.2 (AO)Bamboo Review | Green | Oct 2023 | Dec 2023 | Small | 2023-06-09 | 26.4 | Victor Chelladurai | Don Kichline | David Graf - Mahendra | David Graf | [13 empty] | 2023-10-19 | 2023-04-18 |  |  | 2023-04-25 |  | 2023-05-24 | 2023-06-09
| Yes | No |  |  | usrcreationsvc.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Dec 2023 | Small | 2023-06-19 | 24.4 | Victor Chelladurai | Don Kichline | David Graf - Mahendra | David Graf |  |  | Needed | Needed | Yes | Needed | Not Needed | Needed | User Creation Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-04-11 |  | 2023-06-19
| No |  |  |  | utimageservice.jar | Fleet Services & Asset Mngmt (Corp) |  | Waiting on AO | Yellow |  |  | Large | 2023-03-30 | 40.6 | Krishna Tanga |  | Brain Joseph | [14 empty] | 2023-10-19 | 2023-08-14
| Yes | No |  |  | vdrfilebatch | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Dec 2023 | Small | 2023-06-26 | 23 | Victor Chelladurai | Don Kichline | Sarvesh Sharma | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | VDR File Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [7 empty] | 2023-06-26
| Yes | No |  |  | vdrfilesvc.war | Architect |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Dec 2023 | Small | 2023-08-11 | 13.8 | Victor Chelladurai | Don Kichline | Sarvesh Sharma | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | VDR File SVC | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [7 empty] | 2023-08-11
| Yes | No |  |  | vehicledatarepo | Architect |  | Retire App | Green | Done | Done | Done |  | 0 | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed |  | Yes | Needed | Needed | Needed | Vehicle Data Repository Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed |  |  |  | 2023-10-19
| Yes | No |  |  | vehicleimageupdate | Fleet Services & Asset Mngmt (Corp) |  | 6.2 (AO)QA Deploy/Test | Green |  |  |  | 2023-09-11 | 7.6 | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 13 |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-02-16 |  |  | 2023-02-24 |  | 2023-05-01 | 2023-07-10 | 2023-09-11
| No |  | vehicleinfosvc,football.war depend on this utility. |  | vehicleInformationUtility.jar | Maintenance |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-28 | 10.4 | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-10-19 | [5 empty] | 2023-06-23 | 2023-07-10 |  | 2023-08-28
| No |  |  |  | vehicleinfosvc.war | Maintenance | TRUE | 4.1 (Cap)Maven | Green | Sept 2023 | Oct 2023 | Medium |  | 0 | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-10-19 | 2023-07-11 |  |  | 2023-07-25
| No |  |  |  | vendordvir | Maintenance |  | DONE - (AO)App Deployed | Green | Sept 2023 | Sept 2023 | Small | 2023-10-09 | 2 | David Kost | George-Stella | Long-David, Ganguli-Payel | David, Ganguly, Vaddi Mani | [13 empty] | 2023-10-19 |  |  |  | 2023-06-14 |  | 2023-07-21 | 2023-08-17 | 2023-08-23 | 2023-10-09
| Yes | No |  |  | vendorinfo.war | Finance & Business Process Automation (Admin) |  | Retire App | Green | Done | Done | Done |  | 0 | Stephen McMullen | Kalrav Khamar | Narayanan-Srinivasan | Srinivasan Narayanan |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed | [5 empty] | 2023-10-19
| Yes | No |  |  | vendorreg.war | Architect | TRUE | 4.2 (AO)Maven | Green | Nov 2023 | Dec 2023 | Small | 2023-05-30 | 28.4 | Victor Chelladurai | Don Kichline | Mahipal Podduturi | Mahipal, Sherin |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | vendorregistration | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-05-30
| Yes | No |  |  | vfjexcel | Fleet Services & Asset Mngmt (Corp) |  | 5.2 (AO)Bamboo Review | Green |  |  |  | 2023-09-25 | 4.8 | Krishna Tanga | Krishna Tanga | Krishna Tanga | Rajesh |  |  | Needed |  |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-08-14 |  |  | 2023-08-30 |  | 2023-09-06 | 2023-09-25
| Yes | No |  |  | viewpdf.war | Billing |  | Retire App | Green |  |  |  | 2023-08-24 | 11.2 | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  | Needed | Not Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-08-24
| No |  |  |  | virtualpay.war | Maintenance |  | DONE - (AO)App Deployed | Green | Sept 2023 | Oct 2023 | Medium | 2023-10-03 | 3.2 | David Kost | Patel-Falgun | Long-David | David, Patel | [13 empty] | 2023-10-19 | 2023-05-24 |  |  | 2023-06-14 |  | 2023-07-06 |  |  | 2023-10-03
| No |  |  |  | voicepmsvc.war | Maintenance |  | 6.2 (AO)QA Deploy/Test | Green | Sept 2023 | Oct 2023 | Medium | 2023-09-26 | 4.6 | David Kost | George-Stella | Mani-Sarath | Vaddi Mani | [13 empty] | 2023-10-19 |  |  |  | 2023-06-14 |  | 2023-07-20 |  | 2023-09-26
| Yes | No | BillingUtility.jar |  | wambea | Billing | TRUE | 4.2 (AO)Maven | Green |  |  | Small | 2023-09-11 | 7.6 | Stephen McMullen | Rafiq Melath | Manish Sisodiya | manish sisodiya |  |  | Needed |  |  | Needed | Needed | Needed | CMNS - WAMBEA | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-06-13 |  |  | 2023-05-12 |  | 2023-09-11
| Yes | No |  |  | watchlistbatch | Architect | TRUE | 4.2 (AO)Maven | Green | Oct 2023 | Nov 2023 | Medium | 2023-09-28 | 4.2 | Victor Chelladurai | Don Kichline | Mahipal Podduturi | David Graf, Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | Watch List Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-11-29 | Yes - Capgemini |  | 2023-10-19 | 2023-09-06 |  |  |  |  | 2023-09-28
| Yes | Yes |  |  | watchlistsvc.war | Architect | TRUE | 4.2 (AO)Maven | Green | Oct 2023 | Nov 2023 | Small | 2023-09-06 | 8.6 | Victor Chelladurai | Don Kichline | Mahipal Podduturi | Sama |  |  | Needed | Needed | Yes | Needed | Not Needed | Needed | Watch List Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-09-06 |  |  |  |  | 2023-09-06
| Yes | No |  |  | wbmusernotifier | Billing | TRUE | 4.2 (AO)Maven | Green |  |  |  | 2023-09-26 | 4.6 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  |  | Not Needed |  |  |  |  | WSV - wbmuserservice | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-09-26
| Yes | No |  |  | webmileagesvc.war | Billing | TRUE | 5.2 (AO)Bamboo Review | Green |  |  | Medium | 2023-10-17 | 0.4 | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed |  |  | Needed | Needed | Needed | Web Mileage Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-08-14 |  |  |  |  | 2023-09-14 | 2023-10-17
| Yes | No |  |  | webrptportal.war | Architect |  | DONE - (AO)App Deployed | Green | Done | NA | NA | 2023-08-24 | 11.2 | Victor Chelladurai | Don Kichline | David Graf - Amit | David Graf, Sama |  |  | Needed | Needed | Yes | Needed | Not Needed | Not Needed | Web Report Portal | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [6 empty] | 2023-03-01 | 2023-08-11 | 2023-08-24
| Yes | No |  |  | wje.war | Finance & Business Process Automation (Admin) |  | DONE - (AO)App Deployed | Green | Done | Sept 2023 | Large | 2023-09-20 | 5.8 | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 67 |  | Needed |  |  | Needed | Needed | Needed | Web Journal Entry | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | 2023-02-13 |  |  | 2023-02-23 |  | 2023-03-08 |  | 2023-08-24 | 2023-09-20
| Yes | No |  |  | wlstandalone.war | Architect |  | 5.2 (AO)Bamboo Review | Green | Oct 2023 | Nov 2023 | Small | 2023-09-05 | 8.8 | Victor Chelladurai | Don Kichline | Mahipal Podduturi | David Graf, Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Not Needed | FBI Watch List (Web) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-10-19 | [5 empty] | 2023-05-22 | 2023-09-05
| Yes | No |  |  | ws_authorizationfilter.jar | Architect | TRUE | 4.2 (AO)Maven | Green | Dec 2023 | Jan 2024 | Small | 2023-09-06 | 8.6 | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | 2023-06-05 | 2023-10-19 | 2023-09-06 |  |  |  |  | 2023-09-06 | 2023-03-01

## Comments
Row 1 | @kenneth.mikos@penske.com , This app is onboarded to bamboo - https://bamboo.penske.com/browse/CUSTNF-CUSTB0/deployments Please check. Thanks | Gayam | 09/27/23 12:35 AM
| @praneeth.gayam@penske.com 24x7custnotif has been deployed to QA and has been tested and is working without any apparent issues. @david.long@penske.com has confirmed this as well. | Mikos | 10/13/23 10:17 PM
| Great. Thanks @kenneth.mikos@penske.com / @david.long@penske.com | Gayam | 10/14/23 1:52 AM
Row 1 | @praneeth.gayam@penske.com The 24x7custnotif project is now updated to be platform agnostic using Connection Framework. The changes can be found in the "feature/PlatformAgnosticChanges" branch on bitbucket. | Mikos | 09/13/23 8:11 PM
| Review: @kenneth.mikos@penske.com , Further changes are completed and raised a PR to develop branch. Please review and merge. Thanks. https://bitbucket.penske.com/projects/MAIN/repos/24x7custnotif-batch/pull-requests/4/overview | Gayam | 09/19/23 1:05 AM
| @praneeth.gayam@penske.com The PR has been merged into develop. Thanks! | Mikos | 09/23/23 1:43 AM
| Thanks @kenneth.mikos@penske.com . We will onboard to bamboo. | Gayam | 09/26/23 1:25 AM
Row 1 | @praneeth.gayam@penske.com I'm still working and investigating on this | David | 08/18/23 2:28 AM
Row 1 | @david.long@penske.com , The jdbc configuration is configured in applicationcontext.xml file and depends on the environment the respective configuration loaded from different properties files. But when we modernize the app, the build is going to be environment agnostic. Means one build should be deployed to all environments. So, the current way of implementation doesn't work for jdbc configuration. Same issue exist in pmmailer app also. Could you please check with Architecture team to resolve this issue. Thanks. | Gayam | 07/20/23 11:08 PM
Row 1 | @praneeth.gayam@penske.com I checked out the secrets in the 24x7 cust notif batch and there are none. All secrets are stored in the encrypted table. Yes you may move the velocity jar to artifactory! Thanks! | David | 06/09/23 6:19 PM
| Thanks @david.long@penske.com . Regarding an email you sent about the branches, we took the base reference branch https://svn.penske.com/svn/fieldsys/other/24x7-customer-notifications/tags/PROD/2023-02-02/24x7CustomerNotifications for log4j/maven changes. This branch corresponds to the latest prod deployment in Bamboo. Kindly inform us whether we should utilize the dev_24x7_threads branch instead of the above branch? Thanks. | Gayam | 06/10/23 1:43 AM
| @praneeth.gayam@penske.com Please use the PROD tag, as the dev threads branch is current on dev and qa, but that will not be pushed to PROD for some time. Best to do what's on PROD vs what's on dev | David | 06/13/23 2:25 AM
| Sure @david.long@penske.com . Thanks | Gayam | 06/14/23 2:05 AM
Row 1 | Thanks @praneeth.gayam@penske.com | Yvette Urso | 06/08/23 8:05 PM
Row 1 | @yvette.urso@penske.com I now have access to the smart sheet. What's the item waiting on AO? Is there someone actively working on this migration? | David | 06/06/23 8:06 PM
| @david.long@penske.com we are waiting for following 2 things. 1. Secrets confirmation 2. This app depends on the velocity-dep jar but this is not available in artifactory. Could you please provide your approval to upload to artifactory in the below provided location. <groupid>org.apache.velocity</groupid> <artifactid>velocity-1.7-dep</artifactid> <version>Default</version> | Gayam | 06/08/23 2:47 AM
Row 1 | This is my reply @falgun.patel@penske.com | Yvette Urso | 06/03/23 1:47 AM
Row 1 | @david.long@penske.com @falgun.patel@penske.com @yvette.urso@penske.com testing | Yvette Urso | 06/03/23 1:43 AM
Row 1 | @falgun.patel@penske.com - test comment | Patel | 06/02/23 8:34 PM
Row 1 | Secrets: @shawn.mcmurtry@penske.com , adding to above question, I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:53 AM
Row 1 | @shawn.mcmurtry@penske.com , This app depends on the velocity-dep jar but this is not available in artifactory. Could you please provide your approval to upload to artifactory in the below provided location. <groupid>org.apache.velocity</groupid> <artifactid>velocity-1.7-dep</artifactid> <version>Default</version> | Gayam | 05/13/23 2:58 AM
Row 2 | Deployed app to PROD on 08/08/2023 | Sreekanth | 08/16/23 7:52 PM
| @sreekanth.kancharla@penske.com , Thanks for the update. | Gayam | 08/18/23 1:01 AM
Row 2 | Ready to be tested in QA. | Sreekanth | 07/05/23 7:35 PM
| @sreekanth.kancharla@penske.com , QA deployment needs to complete by AO only. Please deploy and test. Thanks. | Gayam | 07/06/23 3:16 AM
Row 2 | @sreekanth.kancharla@penske.com : this app is deployed to dev. https://bamboo.penske.com/browse/ACH-ACHW/deployments | Gayam | 04/13/23 11:43 PM
Row 2 | @james.minisce@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @sreekanth.kancharla@penske.com | Gayam | 01/24/23 10:19 AM
| @praneeth.gayam@penske.com No remediations required for the shared secrets as all are valid. CC: @james.minisce@penske.com | Sreekanth | 01/26/23 1:29 AM
| Thanks @sreekanth.kancharla@penske.com. Changing back to (AO)Maven status. Please review the MR when you get a chance. MR provide above. | Gayam | 01/26/23 2:03 AM
| @praneeth.gayam@penske.com The PR is not yet merged. I've added comments. Please provide clarification. https://bitbucket.penske.com/projects/ITFIS/repos/ach-web/pull-requests/3/overview | Sreekanth | 02/16/23 8:46 PM
| @sreekanth.kancharla@penske.com , I have responnded in the PR. Please check. | Gayam | 02/17/23 1:22 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 03/24/23 5:50 PM
| Thanks @sreekanth.kancharla@penske.com . We will let you know once onboarding to Bamboo and deploymnet to Dev completed. | Gayam | 03/24/23 11:06 PM
| @sreekanth.kancharla@penske.com , this app is onboarded to Bamboo. But the build was failing. For that reason we had to change version of one dependency. Could you please approve and merge the below PR for this change. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/ach-web/pull-requests/5/overview | Gayam | 03/30/23 11:29 PM
| @praneeth.gayam@penske.com The latest PR was merged on 03/30/2023 | Sreekanth | 04/12/23 7:18 AM
Row 2 | @rafiq.melath@penske.com / @james.minisce@penske.com / @sreekanth.kancharla@penske.com , Log4j, Mavne changes are completed for this app. Please review in the below PR and merge. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/ach-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/13/22 2:58 AM
| @praneeth.gayam@penske.com I've added comment to PR. Please check and reply back to take further action. @mathumala.nachiappan@penske.com @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 3:00 AM
Row 2 | @praneeth.gayam@penske.com What is the plan once the changes are reviewed and merged ? Hope we may've to have a new Bamboo plan with latest CICD approach to deploy this app in DEV/QA for testing. | Sreekanth | 12/20/22 4:33 AM
| Yes @sreekanth.kancharla@penske.com . We will build and deploy the application to dev/qa with the new build plan. | Gayam | 12/20/22 4:54 AM
Row 3 | @sreekanth.kancharla@penske.com , Thanks for the update. | Gayam | 08/18/23 1:01 AM
Row 3 | Deployed app to PROD on 08/08/2023 | Sreekanth | 08/16/23 7:53 PM
Row 3 | Ready to be tested in QA. | Sreekanth | 07/05/23 7:35 PM
| @sreekanth.kancharla@penske.com , QA deployment needs to complete by AO only. Please deploy and test. Thanks. | Gayam | 07/06/23 3:16 AM
Row 3 | @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: achbatch-deploy New deployment project name: ach-batch-deploy Thank you. | Gayam | 05/14/23 9:15 PM
| @praneeth.gayam@penske.com Perfect! Thank you! | Sreekanth | 05/24/23 9:07 PM
Row 3 | @sreekanth.kancharla@penske.com , This app is onboarded to bamboo. Please deploy to QA and test. Thanks. https://bamboo.penske.com/browse/ACH-ACHBAP1/deployments | Gayam | 03/30/23 12:40 AM
Row 3 | @rafiq.melath@penske.com / @james.minisce@penske.com / @sreekanth.kancharla@penske.com , We have completed the secrets scanning on this application and found that there is 1 true positive and all others are false positives. I will share the excel report in the email. Could you please check and remediate the secrets. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/06/23 1:01 AM
| @sreekanth.kancharla@penske.com , Is there a standard process/practice already in place to remediate these finding(s)? | James | 01/06/23 2:06 AM
| @praneeth.gayam@penske.com No remediation is required for all False positives as those are Connection Framework setup related files as per the Penske standard. The 1 True positive seems in offshore branch only and not in DEV/QA/Trunk branches. We are not sure whether offshore branch has latest code. To make any changes, we always refer the trunk branch and then either create a new branch from trunk (OR) work with DEV branch if the source is in sync with Trunk branch. With this, hope we don't need to make any remediation for the shared secrets. Please let us know in case any further clarifications required. CC: @mathumala.nachiappan@penske.com @james.minisce@penske.com | Sreekanth | 01/06/23 2:41 AM
| Thanks @sreekanth.kancharla@penske.com . We will do the next step which is Mavanizing the application. @james.minisce@penske.com | Gayam | 01/07/23 12:50 AM
| @sreekanth.kancharla@penske.com , As discussed PR is already merged to develop branch. Could you please check and provide your approval for the Bamboo stage. | Gayam | 03/02/23 2:49 AM
| @praneeth.gayam@penske.com Please proceed with further steps. @james.minisce@penske.com | Sreekanth | 03/04/23 2:54 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to Cap Bamboo | Gayam | 03/07/23 12:19 AM
Row 4 | @sreekanth.kancharla@penske.com , Thanks for the update. | Gayam | 08/18/23 1:01 AM
Row 4 | Deployed app to PROD on 08/08/2023 | Sreekanth | 08/16/23 7:53 PM
Row 4 | Ready to be tested in QA. | Sreekanth | 07/05/23 7:35 PM
| @sreekanth.kancharla@penske.com , QA deployment needs to complete by AO only. Please deploy and test. Thanks. | Gayam | 07/06/23 3:16 AM
| @praneeth.gayam@penske.com Yes. Just updated the status for information. | Sreekanth | 07/06/23 7:50 PM
Row 4 | @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: achsvc-deploy New deployment project name: ach-service-deploy Thank you. | Gayam | 05/14/23 9:15 PM
| @praneeth.gayam@penske.com Thank you! | Sreekanth | 05/24/23 9:07 PM
Row 4 | @sreekanth.kancharla@penske.com , Dev deployment of this app is completed. Please check. Thank you. | Gayam | 03/23/23 11:45 PM
Row 4 | @james.minisce@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @sreekanth.kancharla@penske.com | Gayam | 01/24/23 10:20 AM
| @praneeth.gayam@penske.com No remediations required for the shared secrets as all are valid. CC: @james.minisce@penske.com | Sreekanth | 01/26/23 1:30 AM
| Thanks @sreekanth.kancharla@penske.com. Changing back to (AO)Maven status. Please review the MR when you get a chance. MR provide above. | Gayam | 01/26/23 2:05 AM
| @praneeth.gayam@penske.com - Still i see the status is (Cap) Bamboo.. Missing anything here? And is that PR? | Mathumala Nachiappan | 01/27/23 10:51 AM
| @mathumala.nachiappan@penske.com , Sreekanth already merged the code and provided the update above. I changed the status to Cap Bamboo. Please check | Gayam | 01/27/23 7:30 PM
Row 4 | @rafiq.melath@penske.com / @james.minisce@penske.com / @sreekanth.kancharla@penske.com , Log4j team completed log4j and maven changes. Please review them in below PR and merge. https://bitbucket.penske.com/projects/ITFIS/repos/ach-service/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/09/22 6:48 AM
| @sreekanth.kancharla@penske.com Please review the log4j changes in the link above and merge if there are no issues. Thank you. | James | 12/09/22 5:54 PM
| @praneeth.gayam@penske.com PR is merged. @mathumala.nachiappan@penske.com @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 3:12 AM
| Thanks @sreekanth.kancharla@penske.com . We will create the Bamboo for this and will deploy to Dev and let you know. Please confirm whether you are ok for Dev deployment. Thanks. Changed the status to (AO)Bamboo. | Gayam | 01/26/23 8:59 PM
Row 5 | Hi @praneeth.gayam@penske.com As discussed over the teams we are seeing issues with while upgrading to spring4 so I am working on that.Thanks! | Sama | 05/19/23 7:56 PM
Row 5 | Hi @praneeth.gayam@penske.com As discussed I found the issue that spring jar dependency is missing: org.springframework.remoting.httpinvoker.CommonsHttpInvokerRequestExecutor so please let us know if this is happening because of the upgrade or something else so that we will check our side. | Sama | 05/15/23 11:00 PM
| @bhagya.sama@penske.com , we will check this issue. Also, as per @hugo.scavino@penske.com 's suggestions we are changing the log4j2 scope to compile from provided. So changed this and merged to develop branch. Thank you. | Gayam | 05/16/23 12:20 AM
| @bhagya.sama@penske.com , we added the dependency and raised the PR. https://bitbucket.penske.com/projects/ARPROJ/repos/b2busercreation-web/pull-requests/10/overview Please check. | Gayam | 05/18/23 1:48 AM
Row 5 | Hi @praneeth.gayam@penske.com dev deployment looks good so please proceed to deploy to QA. | Sama | 05/09/23 8:05 PM
| @bhagya.sama@penske.com , Log4j team is not supposed to do the QA deployments per instructions from management. AO need to take care of it. | Gayam | 05/09/23 10:29 PM
Row 5 | Hi @praneeth.gayam@penske.com I merged the code to develop branch. | Sama | 05/03/23 6:46 PM
| @bhagya.sama@penske.com Develop branch is deployed to Dev. Please verify. Thanks | Gayam | 05/05/23 6:13 AM
Row 5 | @bhagya.sama@penske.com , this app is deployed to dev using develop_log4j branch - https://bamboo.penske.com/browse/BBUC-BBUCT1/deployments Please check and also please merge the code to develop branch. https://bitbucket.penske.com/projects/ARPROJ/repos/b2busercreation-web/pull-requests/6/overview | Gayam | 04/28/23 12:20 AM
Row 5 | @praneeth.gayam@penske.com I have done the changes and committed to develop_log4j branch. Please deploy to the DEV. | Sama | 04/10/23 11:09 PM
| Thanks @bhagya.sama@penske.com . We will take up the next step. | Gayam | 04/11/23 8:34 AM
| @bhagya.sama@penske.com , When we check the old bamboo builds, this app doesn't have dev environment. Could you please check and let us know whether it needs to be deployed to Dev. If so, can we deploy to ghlx008ptlge server and also we need instance type. Could you please check and update us. Thanks. | Gayam | 04/18/23 3:02 AM
| @bhagya.sama@penske.com confirmed that the instanceType is external as per documentation https://confluence.penske.com/display/ATSD/B2B+User+Creation | Gayam | 04/27/23 1:29 AM
Row 5 | Hi @praneeth.gayam@penske.com I am working on it and will update once I am done with it.Thanks! | Sama | 03/30/23 8:21 PM
Row 5 | Question: @sherin.basheer@penske.com , Adding to above secrets question, there is a header.jspf file which is different for both prod and qa exist under targeted folder. Could you please check and let us know whether we can use prod one. Thanks. | Gayam | 03/03/23 1:09 AM
| Hi @praneeth.gayam@penske.com I have checked the files in both qa and prod, we have to pick the file based on the environment. | Sama | 03/20/23 7:34 AM
| Hi @bhagya.sama@penske.com , Are you making the code changes to pick the file depends on environment? Thanks. | Gayam | 03/20/23 11:46 PM
| Hi @praneeth.gayam@penske.com Can you use env variable in the file like ${sys:srvenv}] ,this should give you the environment QA/PROD | Sama | 03/25/23 12:28 AM
| @bhagya.sama@penske.com , As per instructions we are not supposed to do any code changes other than log4j and maven changes. Also, to verify the changes we don't know how to run the app in local. So could you please complete the changes on top of log4j branch. Thanks. @hugo.scavino@penske.com | Gayam | 03/27/23 11:36 PM
Row 5 | Secrets: @sherin.basheer@penske.com , adding to above question we sent the secret file of this app to you in the email. Could you please check whether this app requires any code changes on secrets part. Thanks | Gayam | 02/24/23 1:51 AM
| Hi @praneeth.gayam@penske.com I have taken the secret file from Sherin and verified, it's does not require code changes. | Sama | 03/20/23 7:35 AM
Row 5 | @sherin.basheer@penske.com , As per @hugo.scavino@penske.com penske-secure-logger is not getting migrated to log4j2 and there is no modernization for that jar. But b2busercreation.war using loggers from penske-seucre-logger jar which is using log4j1. Do you want us to replace the loggers from penske-secure jar with log4j2 loggers in b2busercreation app? | Gayam | 02/23/23 12:28 AM
| Yes you can replace with log4j2 loggers. Thank you. | Sherin | 02/24/23 9:37 PM
| Thank you. Changing the status (AO)Secrets Mitigation | Gayam | 02/25/23 12:59 AM
Row 5 | Blocker: penske-secure-logger-1.0.0.jar | Yvette Urso | 02/01/23 8:29 PM
Row 5 | @sherin.basheer@penske.com Can you assist @mathumala.nachiappan@penske.com with this blocker? | Yvette Urso | 12/09/22 12:46 AM
Row 5 | Hi @yvette.urso@penske.com - Once this dependent jar modernization is complete, this parent application can be progressed. | Mathumala Nachiappan | 12/02/22 5:24 PM
Row 5 | @mathumala.nachiappan@penske.com Can you clarify this blocker? | Yvette Urso | 11/30/22 12:36 AM
Row 5 | <Mathu> Dependent with penske-secure-logger-1.0.0.jar | Mathumala Nachiappan | 11/23/22 3:11 AM
Row 6 | Ready to Deploy | Rajesh | 09/11/23 5:29 PM
Row 6 | Please provide access | Narsimhamurthy | 08/17/23 8:26 PM
| @narsimhamurthy.peddoju@penske.com , You are already in the RBAC group PTL-Development and this group already have the access to bbupload bamboo build. Please check now. | Gayam | 08/18/23 7:18 PM
Row 6 | Access denied Sorry, you have insufficient permissions to view the page. Please contact an administrator if you believe this is an error. Go to... | Narsimhamurthy | 08/17/23 8:25 PM
Row 6 | Praneeth, getting below error while trying to access above url | Narsimhamurthy | 08/17/23 8:25 PM
Row 6 | @praneeth.gayam@penske.com After disabling the test cases & jtest results. we are getting following issue while executing bamboo build as requested. 12-Jun-2023 14:04:45 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:04:45 [INFO] BUILD FAILURE 12-Jun-2023 14:04:45 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:04:45 [INFO] Total time: 9.394 s 12-Jun-2023 14:04:45 [INFO] Finished at: 2023-06-12T14:04:45-04:00 12-Jun-2023 14:04:45 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:04:45 [ERROR] Failed to execute goal org.apache.maven.plugins:maven-surefire-plugin:3.0.0-M4:test (unit-tests) on project bbupload: There are test failures. 12-Jun-2023 14:04:45 [ERROR] | Rajesh | 06/12/23 11:43 PM
| @rajesh.haravde@penske.com , Still seeing test failures. Let me check with my CICD team on this. | Gayam | 06/13/23 1:36 AM
| @rajesh.haravde@penske.com , unit tests are disabled and build got success https://bamboo.penske.com/browse/BBUPLOADBP-BBULD0 | Gayam | 06/14/23 3:45 AM
Row 6 | Please confirm if we can validate the bamboo script for this project and which branch | Rajesh | 06/08/23 11:16 PM
| @rajesh.haravde@penske.com , This app is already onboarded to Bamboo. Please check. https://bamboo.penske.com/browse/BBUPLOADBP-BBULD0/ | Gayam | 06/09/23 1:22 AM
Row 6 | PR been executed please take it forward. Thanks for guidance on process Praneeth appreciated. | Rajesh | 05/18/23 1:50 AM
| Sure @rajesh.haravde@penske.com . We will let you know once we deploy to dev. | Gayam | 05/18/23 10:47 PM
| @rajesh.haravde@penske.com , Test cases are failing in this application. Please check the build at https://bamboo.penske.com/browse/BBUPLOADBP-BBULD1-UTEST-3 Could you please work with your team to fix them. Thanks. | Gayam | 05/22/23 9:27 PM
Row 6 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/bbupload-web/pull-requests/3/overview Thanks. | Gayam | 02/16/23 11:01 PM
Row 6 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:44 PM
Row 6 | WAR is building now | Hugo Scavino | 01/19/23 3:14 AM
Row 6 | I moved the XML files from source and test source to the appropriate resources folder to follow maven conventions. XML files should not be the src/main/java directory. Added simple console log4j into test resources. Please see the below comment I added in one of the tests. Application Owner should review. Test was failing and I made a more generic test but would prefer their test if possible. // TODO This test was failing because the recordset1 was not the same argument. Should be resolved. | Hugo Scavino | 01/19/23 3:14 AM
Row 6 | @rajesh.haravde@penske.com , I provided the response above. Please check. | Gayam | 01/18/23 9:13 PM
Row 6 | We updated Praneeth and waiting on response. | Rajesh | 01/18/23 8:20 PM
Row 6 | BBUpload failed its maven build, so I couldn’t test it. These are the main errors that came up. | Rajesh | 01/18/23 8:20 PM
Row 6 | @rajesh.haravde@penske.com , This is ragarding the issues you posted in the email. Maven build is failing when we run the tests but without tests it is getting successful. @hugo.scavino@penske.com | Gayam | 01/14/23 12:29 AM
Row 6 | @krishna.tanga@penske.com / @yogesh.sinha@penske.com , Please review the log4j/maven changes in below MR and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/bbupload-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 11/28/22 9:02 AM
Row 7 | Hi @praneeth.gayam@penske.com looks like I am not able to publish the local version of my bill-apprunner to artifactory. Getting 403 error. [ERROR] Failed to execute goal org.apache.maven.plugins:maven-deploy-plugin:2.8.2:deploy (default-deploy) on project bill-apprunner: Failed to deploy artifacts: Could not transfer artifact com.penske.billing:bill-apprunner:jar:2.0.0-20230601.150206-1 from/to billing-development (https://artifactory.penske.com/artifactory/billing-mvn-development-local): Access denied to https://artifactory.penske.com/artifactory/billing-mvn-development-local/com/penske/billing/bill-apprunner/2.0.0-SNAPSHOT/bill-apprunner-2.0.0-20230601.150206-1.jar. Error code 403, Forbidden -> [Help 1] | Dylan | 06/01/23 8:34 PM
| looks like it should only deploy when we run bamboo. Going to move the code from develop_log4j to develop | Dylan | 06/01/23 8:46 PM
| Thanks @dylan.price@penske.com . Build is successfully completed and as mentioned deployed to Dev server ghlx006ptlge. Could you please check and let us know whether it is working without any issues. Thanks. | Gayam | 06/01/23 10:55 PM
Row 7 | Hi @praneeth.gayam@penske.com I have created a generic unit test to satisfy bamboo. Could you please try again? | Dylan | 05/26/23 1:48 AM
| Hi @dylan.price@penske.com , develop_log4j build is successful. Could you please merge the code develop branch. https://bitbucket.penske.com/projects/ARPROJ/repos/bill-apprunner-batch/pull-requests/8/overview | Gayam | 05/31/23 12:50 AM
| Hi @praneeth.gayam@penske.com looks like the repos are being built for our team. I no longer have access to bill-apprunner-batch path on bitbucket. I will let you know as soon as the repo is moved to a billing repo and I can merge the develop_log4j changes into develop branch. | Dylan | 05/31/23 5:19 PM
| Sure @dylan.price@penske.com . Thanks | Gayam | 05/31/23 11:52 PM
Row 7 | @praneeth.gayam@penske.com thank you! I have merged the pull request into develop branch. Can you please move onto bamboo for this application? | Dylan | 05/17/23 5:33 PM
| Sure @dylan.price@penske.com . We will let you know once it is onboarded to Bamboo. | Gayam | 05/18/23 12:39 AM
| @dylan.price@penske.com , The following question we asked above but didn't get the response. Could you please check it and provide your response. "This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application." | Gayam | 05/18/23 10:40 PM
| Hi @praneeth.gayam@penske.com this application is an internal application. It will deploy to a separate server though outside of the original batch box. It will deploy as an internal batch application to ghlx006ptlge.penske.com | Dylan | 05/24/23 11:52 PM
| @dylan.price@penske.com , We onboarded this app to Bamboo but unit tests are getting failed. Could you please check. https://bamboo.penske.com/browse/PBSBP-BILAP2 | Gayam | 05/25/23 8:41 PM
| Hi @praneeth.gayam@penske.com yes there are no test cases so the check is failing. Let me create a feature and fix this issue. I will merge it into the develop branch. I will let you know here when that is completed. | Dylan | 05/25/23 10:32 PM
Row 7 | @praneeth.gayam@penske.com is there a way we could move this application off of the architecture repo and into https://bitbucket.penske.com/projects/PBJB ? | Dylan | 05/24/23 11:53 PM
| Yes @dylan.price@penske.com . We can do that. There is an email going on between billing team and Yvette to decide on Billing project. Is it decided to move all billing repos under PBJB or only this bill_apprunner needs to be moved under PBJB? | Gayam | 05/25/23 2:35 AM
Row 7 | @praneeth.gayam@penske.com Hi Praneeth I have created a pull request to move some code into your develop_log4j branch. Once you confirm, I will accept the pull request you have out there for me. | Dylan | 05/16/23 11:47 PM
| @dylan.price@penske.com , You can merge as you are the AO. | Gayam | 05/17/23 2:09 AM
Row 7 | @praneeth.gayam@penske.com added comment in bitbucket push request | Dylan | 05/03/23 9:18 PM
| @dylan.price@penske.com , I just replied to your questions. Please check and let me know if you have any other question. Thanks. | Gayam | 05/04/23 12:09 AM
Row 7 | Hi @praneeth.gayam@penske.com getting following error when I try to run through my local: [INFO] Scanning for projects... [ERROR] [ERROR] Some problems were encountered while processing the POMs: [FATAL] Non-resolvable parent POM for com.penske.billing:bill-apprunner:2.0.0-SNAPSHOT: com.penske.mis.common:batch-parent:pom:1.0.0-DJ-BAT-18-04d91b2 was not found in https://repo.maven.apache.org/maven2 during a previous attempt. This failure was cached in the local repository and resolution is not reattempted until the update interval of central has elapsed or updates are forced and 'parent.relativePath' points at wrong local POM @ line 10, column 10 @ [ERROR] The build could not read 1 project -> [Help 1] [ERROR] [ERROR] The project com.penske.billing:bill-apprunner:2.0.0-SNAPSHOT (C:\ptl_mis\AvolentSource\bill-apprunner\pom.xml) has 1 error [ERROR] Non-resolvable parent POM for com.penske.billing:bill-apprunner:2.0.0-SNAPSHOT: com.penske.mis.common:batch-parent:pom:1.0.0-DJ-BAT-18-04d91b2 was not found in https://repo.maven.apache.org/maven2 during a previous attempt. This failure was cached in the local repository and resolution is not reattempted until the update interval of central has elapsed or updates are forced and 'parent.relativePath' points at wrong local POM @ line 10, column 10 -> [Help 2] [ERROR] [ERROR] To see the full stack trace of the errors, re-run Maven with the -e switch. [ERROR] Re-run Maven using the -X switch to enable full debug logging. [ERROR] [ERROR] For more information about the errors and possible solutions, please read the following articles: [ERROR] [Help 1] http://cwiki.apache.org/confluence/display/MAVEN/ProjectBuildingException [ERROR] [Help 2] http://cwiki.apache.org/confluence/display/MAVEN/UnresolvableModelException | Dylan | 04/11/23 8:36 PM
| @dylan.price@penske.com , You need to use the Billing groups settings.xml in your .m2 location. Please check and let me know whether you are facing same issue. | Gayam | 04/12/23 1:05 AM
Row 7 | Hi @praneeth.gayam@penske.com looks like I do not have the correct privileges to merge your pull request. I will work with Architecture to get this access. In the meantime I will clone the repo down to my local machine and start testing the maven changes. | Dylan | 04/06/23 11:30 PM
Row 7 | @praneeth.gayam@penske.com we are scheduling this to be tested in April 2023 | Dylan | 03/30/23 9:20 PM
Row 7 | @venkatesh.hossalinever@penske.com , Maven changes are completed. Please review the app at https://bitbucket.penske.com/projects/ARPROJ/repos/bill-apprunner-batch/pull-requests/3/overview | Gayam | 03/02/23 3:01 AM
Row 7 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 2:07 AM
| Thank you @venkatesh.hossalinever@penske.com . Could you please provide the response which I asked above. | Gayam | 03/02/23 1:31 AM
Row 7 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:26 AM
Row 7 | @dylan.price@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:50 AM
Row 7 | @sam.skelding@penske.com / @dylan.price@penske.com , This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:57 AM
Row 8 | Updated bamboo plan and I am seeing the bill-avobatch.jar file successfully deployed out in DEV. The user is not correct, so I have made the changes in the QA deploy and will test after the 5pm deploy window. If this works, I will do the same for all the "bill_" applications and start testing them in QA next week. | Dylan | 08/04/23 1:23 AM
Row 8 | @praneeth.gayam@penske.com this looks great! Can you please create this for a dev bamboo build off the develop branch? | Dylan | 06/01/23 10:30 PM
| Sure @dylan.price@penske.com . We will let you know once it is onboarded to Bamboo. | Gayam | 06/01/23 10:58 PM
| @dylan.price@penske.com , Do you have idea how this app is currently getting deployed to CBOS batch box? | Gayam | 06/02/23 11:37 PM
| Hi @praneeth.gayam@penske.com it gets packaged in the "CBOS_PROD_PACKAGE" and gets moved to /var/tmp on the CBOS servers | Dylan | 06/06/23 12:51 AM
| @dylan.price@penske.com , bill_apprunner is successfully deployed to Dev instance ghlx006ptlge. I believe ghlx006ptlge is a CBOS server. You mentioned bill_avobatch should be deployed to ghlx097ptlge server. But getting bamboo fails to connect to ghlx097ptlge server. Bamboo did not face this issue while connecting to ghlx006ptlge server. Could you please check and guide us whether the ghlx097ptlge server is correct or not. https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=141072739 | Gayam | 06/13/23 2:23 AM
| Hi @praneeth.gayam@penske.com I am sorry! you are correct -- ghlx006ptlge is the correct server. This will be the same for bill_xmlloader_mp | Dylan | 06/14/23 5:13 PM
| Sure @dylan.price@penske.com | Gayam | 06/15/23 12:44 AM
| @dylan.price@penske.com , Dev hostname changed to ghlx006 and deploy plan re onboarded. Dev deployment also successful. Please verify. | Gayam | 06/16/23 2:36 AM
Row 8 | @praneeth.gayam@penske.com I have merged my changes in with "develop_log4j". Could you please merge this into the "develop" branch and start with bamboo testing? | Dylan | 05/26/23 6:19 PM
Row 8 | Review: @dylan.price@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/bill-avo-batch/pull-requests/5/overview | Gayam | 04/15/23 1:13 AM
Row 8 | @praneeth.gayam@penske.com No issues with the database property passwords. It is being excluded in the build script. Please proceed with log4j changes | Dylan | 03/30/23 9:19 PM
Row 8 | @sam.skelding@penske.com / @dylan.price@penske.com , This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:57 AM
| This application is an internal CBOS batch application and deploys to ghlx097ptlge (our CBOS batch box). Not sure how you would mark this in your artifactory -- wondering if CBOS should have its own instance type. | Dylan | 03/06/23 6:45 PM
| @hugo.scavino@penske.com / @balu.mohan@penske.com , Could you please check @dylan.price@penske.com question above and provide your response. Thanks. | Gayam | 03/06/23 11:57 PM
Row 8 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 8 | @dylan.price@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:50 AM
Row 9 | @praneeth.gayam@penske.com please create bamboo plan the same as bill_avobatch | Dylan | 09/12/23 1:24 AM
| Sure @dylan.price@penske.com | Gayam | 09/12/23 2:35 AM
| @dylan.price@penske.com , develop_log4j branch onboarded to bamboo and tasks are modified as like bill_avobatch. https://bamboo.penske.com/browse/PBSBP-BILLRPG/deployments | Gayam | 09/13/23 12:51 AM
Row 9 | Review: @dylan.price@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/PBTCBOS/repos/bill-rpginvoker-batch/pull-requests/3/overview | Gayam | 06/30/23 1:19 AM
Row 9 | Hi @praneeth.gayam@penske.com we will remove the properties file and have it moved to /apps/conf on the server. Could you please continue with your log4j/maven changes? As soon as develop_log4j is up to date with both changes I will pull down and take care of the property files | Dylan | 05/26/23 6:36 PM
| Sure @dylan.price@penske.com . We will let you know once we complete the mavanization. | Gayam | 05/30/23 9:41 AM
Row 9 | @sam.skelding@penske.com / @mark.weaver@penske.com , This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:55 AM
| This application is an internal CBOS batch application and deploys to ghlx097ptlge (our CBOS batch box). Not sure how you would mark this in your artifactory -- wondering if CBOS should have its own instance type. | Dylan | 03/06/23 6:45 PM
| @hugo.scavino@penske.com , Could you please check @dylan.price@penske.com question above and provide your response. Thanks. @balu.mohan@penske.com | Gayam | 03/06/23 11:56 PM
Row 9 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 9 | @mark.weaver@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:52 AM
Row 10 | Hi @praneeth.gayam@penske.com this application has been merged into "develop" branch. Please create the bamboo plan for DEV | Dylan | 06/02/23 12:44 AM
| Thanks @dylan.price@penske.com . We will let you know once we onboard to Bamboo. | Gayam | 06/02/23 11:40 PM
| @dylan.price@penske.com , Onboarded the build and deploy plan successfully but dev deployment to cbos server ghlx097ptlge getting failed. It's look like that deployment is failing because it can't connect to host server(ghlx097ptlge@penske.com). Same issue we are facing in bill-avo-batch. Could you please check and guide us whether the ghlx097ptlge server is correct or not. | Gayam | 06/14/23 3:50 AM
| Hi @praneeth.gayam@penske.com I am sorry! you are correct -- ghlx006ptlge is the correct server. This will be the same for bill_avobatch | Dylan | 06/14/23 5:14 PM
| @dylan.price@penske.com , Dev hostname changed to ghlx006 and deploy plan re onboarded. Dev deployment also successful. Please verify. | Gayam | 06/16/23 2:35 AM
Row 10 | Review: @dylan.price@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/ARPROJ/repos/bill-xmlloader-mp-batch/pull-requests/4/overview | Gayam | 05/10/23 11:32 PM
Row 10 | @praneeth.gayam@penske.com No issues with the database property passwords. It is being excluded in the build script. Please proceed with log4j changes | Dylan | 03/30/23 9:22 PM
Row 10 | @sam.skelding@penske.com / @dylan.price@penske.com , This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:56 AM
| This application is an internal CBOS batch application and deploys to ghlx097ptlge (our CBOS batch box). Not sure how you would mark this in your artifactory -- wondering if CBOS should have its own instance type. | Dylan | 03/06/23 6:45 PM
| @hugo.scavino@penske.com , Could you please check @dylan.price@penske.com question above and provide your response. Thanks. @balu.mohan@penske.com | Gayam | 03/06/23 11:55 PM
Row 10 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 10 | @dylan.price@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:50 AM
Row 11 | @praneeth.gayam@penske.com please create bamboo plan the same as bill_avobatch | Dylan | 09/12/23 1:25 AM
| @dylan.price@penske.com , develop_log4j branch onboarded to bamboo and tasks are modified as like bill_avobatch. https://bamboo.penske.com/browse/PBSBP-BLXMLST | Gayam | 09/13/23 12:52 AM
Row 11 | Review: This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/PBTCBOS/repos/bill-xmlloader-st-batch/pull-requests/3/overview | Gayam | 07/14/23 6:40 AM
Row 11 | Hi @praneeth.gayam@penske.com the secrets file on this application is fine. it will be hidden behind a configuration file that only webmasters have access to. Could you please start maven/log4j changes? | Dylan | 06/02/23 12:50 AM
| Thanks @dylan.price@penske.com . we will do the changes and will let you know. | Gayam | 06/02/23 11:44 PM
Row 11 | Secrets: @dylan.price@penske.com , secrets are shared in the email. Please check and confirm. Thanks. | Gayam | 02/21/23 5:49 AM
Row 11 | @sam.skelding@penske.com / @dylan.price@penske.com , This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:57 AM
| Adding to above question, @hugo.scavino@penske.com , While doing the svn to bb migration we are facing the issue "Software caused connection abort: Error running context: ". I believe this is because of timeout issue. Could you please increase the timeout in svn server. Thanks. | Gayam | 01/20/23 1:13 AM
| @praneeth.gayam@penske.com please share the SVN branch name. I can try from local PC and in the alternative from an onprem linux server like the Arch Server | Hugo Scavino | 01/26/23 8:36 PM
| @hugo.scavino@penske.com , My team is working with CICD team to resolve this issue. I will let you know incase if we need help from you. @haribabu.challa@penske.com | Gayam | 01/26/23 8:54 PM
| @hugo.scavino@penske.com , CICD team also unable to resolve the issue. Could you please look into it. Following are the details. https://svn.penske.com/svn/avolent/ptl_customization/billing/standalone/bill_xmlloader_st/ Branch: trunk | Gayam | 02/01/23 3:40 AM
| @hugo.scavino@penske.com , I just want to update you that we are able to resolve the issue. | Gayam | 02/08/23 12:22 AM
Row 12 | I marked it as Retire app so it clears off the dashboard. Leadership team was reviewing pending work. This is something we will handle as part of a Billing project. | Gianfranco | 08/16/23 1:13 AM
| Thank you | Gayam | 08/17/23 2:05 AM
Row 12 | @praneeth.gayam@penske.com BillingCommons is being handled by Penske, please remove from the list | Gianfranco | 08/15/23 8:42 PM
Row 12 | @frank.d'angelo@penske.com - Per Frank please get with him prior to starting - this app may go away. | Yvette Urso | 01/25/23 2:54 AM
Row 12 | @frank.d'angelo@penske.com / @shweta.gupta@penske.com, For this application SVN repo available https://svn.penske.com/svn/ebusiness/extranet/billingcommons/. But Bamboo plan is not available. We need production branch confirmation for log4j-Migration and without existing bamboo build we could not find this. Could you please let us know what is the latest production branch. Thanks. @hugo.scavino@penske.com / @mathumala.nachiappan@penske.com | Gayam | 01/14/23 12:50 AM
Row 13 | @praneeth.gayam@penske.com I tried to deploy latest build on bamboo, build is showing deployed successful, but on dev box artifacts are not deployed. Can you please deploy and confirm. | Venkatesh | 09/30/23 12:45 AM
| @venkatesh.hossalinever@penske.com , Sure We will check. | Gayam | 10/02/23 7:09 PM
| @venkatesh.hossalinever@penske.com , Issue is fixed and now the deployment is completed successfully and the file placed in the targeted location. | Gayam | 10/06/23 7:36 AM
Row 13 | Review & Question: @venkatesh.hossalinever@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/PB/repos/billingservice/pull-requests/3/overview Question: The jee:jndi-lookup properties are configured in applicationcontext.xml file are based on the environment and the respective configuration loaded from different properties files. But when we modernize the app, the build is going to be environment agnostic. Means 1 build should be deployed to all environments. So, the current way of implementation should be changed to satisfy the enviornment agnostic build. Could you please check. | Gayam | 09/16/23 12:36 AM
| @praneeth.gayam@penske.com It was working with Ant previously, now it should work with maven changes. Let me know if any property values are missing. | Venkatesh | 09/30/23 12:47 AM
Row 13 | @praneeth.gayam@penske.com Please deploy the maven/log4j changes on dev and let us know. we will validate and confirm. | Venkatesh | 09/25/23 10:59 PM
| @venkatesh.hossalinever@penske.com , Did you handle the above query? Otherwise application will not run properly. | Gayam | 09/26/23 12:55 AM
| @venkatesh.hossalinever@penske.com , Bamboo onboarding is completed. we have disabled the test cases as these are failing. https://bamboo.penske.com/browse/BILL-BLSVC1 Please check the open question which I asked above. Thanks. | Gayam | 09/27/23 12:33 AM
Row 13 | @praneeth.gayam@penske.com Any update on log4j changes, can you please share it soon. | Venkatesh | 09/14/23 8:37 PM
| @venkatesh.hossalinever@penske.com , We are working on it and will share asap. | Gayam | 09/15/23 7:21 AM
Row 13 | @praneeth.gayam@penske.com Sorry about that. Please use the below production branch code and implement the log4j changes. 'https://svn.penske.com/svn/fieldsys/other/billing-service/tags/prod/1.0.3_20220926' | Venkatesh | 08/29/23 1:58 AM
| Sure @venkatesh.hossalinever@penske.com . We will start working on provided branch | Gayam | 08/30/23 2:23 AM
Row 13 | @praneeth.gayam@penske.com Please keep this application on hold. We wanted to go with prod branch as there is a delay in deploying active development code to prod. I will confirm production branch on monday. | Venkatesh | 08/25/23 11:53 PM
| @venkatesh.hossalinever@penske.com , We started working on the app already and we are doing the rework on same application. Could you please sign off on production branch when you are really sure about it. Thank you. | Gayam | 08/26/23 12:46 AM
Row 13 | @praneeth.gayam@penske.com There was active development going on and associate added latest commits by mistake. Please use the following new branch which is freezed and will not get updated until log4j migration is done. https://svn.penske.com/svn/fieldsys/other/billing-service/branches/dev_gh_log4j2 cc: @prashant.prabhakar@penske.com | Venkatesh | 08/24/23 2:30 AM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 08/24/23 4:08 AM
Row 13 | @venkatesh.hossalinever@penske.com , We are seeing latest commits on master branch of this application in bitbucket. Do you want us to modernize the app on top of the master branch? | Gayam | 08/22/23 2:37 AM
Row 13 | Sure @venkatesh.hossalinever@penske.com | Gayam | 08/15/23 10:34 PM
Row 13 | @praneeth.gayam@penske.com Can you please start working on log4j migration for billingservice. Refer following path: https://svn.penske.com/svn/fieldsys/other/billing-service/trunk | Venkatesh | 08/15/23 10:02 PM
Row 13 | @praneeth.gayam@penske.com Please proceed with log4j migration for billing service. you can use the source code from following location https://svn.penske.com/svn/fieldsys/other/billing-service/trunk/billing-service | Venkatesh | 08/03/23 12:48 AM
| @praneeth.gayam@penske.com Billing service we have active development, please keep log4j migration on hold. | Venkatesh | 08/03/23 9:27 PM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 08/04/23 12:53 AM
Row 13 | I am working on some of the changes, please wait for log4j and maven changes implementation. | Venkatesh | 03/17/23 7:51 PM
Row 13 | @sam.skelding@penske.com / @manish.sisodiya@penske.com , This application in SVN contains multiple src folders. Ideally each application should have only 1 src folder. Could you please check and clarify us. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 1:33 AM
| The src that should be used is https://svn.penske.com/svn/fieldsys/other/billing-service/trunk/billing-service/src/ | Dylan | 03/07/23 12:32 AM
| Thanks @dylan.price@penske.com . Is there any active development going on this app? Because we are seeing latest commits in the given src folder. | Gayam | 03/07/23 7:59 PM
Row 14 | hi @praneeth.gayam@penske.com merged the changes. Please utilize bamboo for this | Dylan | 08/24/23 9:42 PM
| Thanks @dylan.price@penske.com | Gayam | 08/25/23 12:10 AM
| @dylan.price@penske.com , it is onboarded to bamboo and jar is uploaded to artifactory. Please check and confirm. I will close this app once you confirm. Thanks. | Gayam | 08/28/23 10:13 PM
Row 14 | Review: @dylan.price@penske.com , This app is ready for your review. Please check and merge. Thanks. https://bitbucket.penske.com/projects/PB/repos/billingutility/pull-requests/3/overview | Gayam | 06/28/23 3:00 AM
| @dylan.price@penske.com , Could you please review and merge. There are several other applications depend on this dependency. Thnaks. | Gayam | 08/18/23 12:21 AM
Row 14 | there are no secrets in this utility jar. So changing the status to Cap maven | Gayam | 06/23/23 12:09 AM
Row 15 | @praneeth.gayam@penske.com we have verified the application in dev and logs are getting added to the Log file. | Subramanian | 10/10/23 2:41 AM
| Thanks @subramanian.vennimalayan@penske.com . Please deploy to QA and test. | Gayam | 10/11/23 12:57 AM
Row 15 | @subramanian.vennimalayan@penske.com , Onboarded to bamboo and dev deployment is completed. build plan: https://bamboo.penske.com/browse/BODYSHOPBP-BDSP deploy plan: https://bamboo.penske.com/browse/BODYSHOPBP-BDSP/deployments | Gayam | 09/26/23 1:35 AM
Row 15 | @praneeth.gayam@penske.com I have verified the changes and merged the PR. Everything looks good with the changes. | Subramanian | 09/22/23 1:57 AM
| Thanks @subramanian.vennimalayan@penske.com . We will onboard to Bamboo. | Gayam | 09/22/23 11:27 PM
Row 15 | @subramanian.vennimalayan@penske.com , This app is ready for your review. Pelase verify. Thanks. https://bitbucket.penske.com/projects/MAIN/repos/bodyshop-web/pull-requests/3/overview | Gayam | 09/22/23 1:07 AM
Row 15 | @praneeth.gayam@penske.com I have verified the code and it looks like you have taken the base code from https://svn.penske.com/svn/fieldsys/other/bodyshop/tags/_T_Prod_Build_2018-09-05, but we did one more deploy in November 2020 https://svn.penske.com/svn/fieldsys/other/bodyshop/tags/_T_Prod_Build_2020-11-22 and somehow bamboo is not showing this in the plan. I have merged the pull request to develop branch and while going through the history only I could able to find this issue in bamboo. Could you please take the base source code from https://svn.penske.com/svn/fieldsys/other/bodyshop/tags/_T_Prod_Build_2020-11-22 and create the pull request again. | Subramanian | 07/28/23 1:59 AM
| @subramanian.vennimalayan@penske.com , We need to rework on this app. Because I don't think pull from 2023-11-22 branch to mavanization branch may cause lot of problems as both have different folder structures. We will rework on this app. | Gayam | 08/01/23 1:21 AM
Row 15 | @falgun.patel@penske.com / @subramanian.vennimalayan@penske.com , This app is ready for your review. Please verify and merge. Thanks https://bitbucket.penske.com/projects/MAIN/repos/bodyshop-web/pull-requests/3/overview | Gayam | 07/20/23 11:15 PM
Row 15 | There are no secrets exist for this application. So changing the status of this app to Cap Maven. | Gayam | 06/23/23 12:11 AM
Row 15 | Copied Subramanian's comments @praneeth.gayam@penske.com Please use the folder with bodyshop6 | Patel | 06/15/23 1:35 AM
| Thanks | Gayam | 06/15/23 1:44 AM
Row 15 | @praneeth.gayam@penske.com the status is saying Waiting on AO. we did not see any comment or emails. | Stella george | 06/14/23 2:06 AM
| @stella.george@penske.com , Not sure what happened to the question I asked. But let me give you the question again. For this application prod reference in Bamboo build is pointed to https://svn.penske.com/svn/fieldsys/other/bodyshop/tags/_T_Prod_Build_2018-09-05 But this reference have two folders and both the folders have java source and webcontent folder in it. Need clarification which folder is correct. Following are the folders info. https://svn.penske.com/svn/fieldsys/other/bodyshop/tags/_T_Prod_Build_2018-09-05/bodyshop/ https://svn.penske.com/svn/fieldsys/other/bodyshop/tags/_T_Prod_Build_2018-09-05/bodyshop6/ | Gayam | 06/14/23 3:38 AM
Row 16 | @praneeth.gayam@penske.com yes please | Shabeer | 09/15/23 5:31 PM
| Thanks @shabeer.shaik@penske.com | Gayam | 09/16/23 12:27 AM
Row 16 | Current SVN Branch Details for BOS : DEV: https://svn.penske.com/svn/ecomm/hr/bos/branches/dev_gh QA: https://svn.penske.com/svn/ecomm/hr/bos/branches/qa PROD: https://svn.penske.com/svn/ecomm/hr/bos/branches/branches/tags/CC_52847_09FEB2017 We have analyzed the secretsCurrent SVN Branch Details for BOS: We have analyzed the secrets in the application with refrence of provided secrets file most of them are from old branches which we don't use. Please initiate the next steps from your side for this Application and let us know. | Shabeer | 09/13/23 12:31 AM
| @shabeer.shaik@penske.com , Can we take the PROD one as base branch for migration? | Gayam | 09/15/23 7:47 AM
Row 16 | @vinay.ramanand@penske.com , I sent the secrets in the email. Could you please verify them. | Gayam | 03/10/23 2:00 AM
Row 16 | Bamboo Project Setup 2/1/23 - Yvette sent Tim Fox the below question via email: Tim, We are submitting a request for a Bamboo Project and would like to know who to add from the HR team as the Admin of that Project? That person can then create what ever they need for other access and repositories, etc. | Yvette Urso | 02/01/23 8:53 PM
Row 16 | @hugo.scavino@penske.com , This is regarding log file size which needs to be mentioned in log4j2.xml for file appenders. You mentioned that it has to be maximum 1MB in confluence page. But for bos.war application's log4j.properties has the file size of 4096kb. In this case do we need to mention 4MB in log4j2.xml or 1MB only? | Gayam | 01/18/23 3:02 AM
| We should keep what they have had in the past. Let them know they are exceeding the recommendation but we should keep what they have when deploying to DEV. | Hugo Scavino | 01/18/23 9:38 PM
Row 17 | @praneeth.gayam@penske.com thank you! we are deploying this out tonight. Will be closing out this application tomorrow | Dylan | 09/12/23 8:06 PM
Row 17 | @praneeth.gayam@penske.com bamboo build has failed when trying to deploy to PROD. Could you please look through the logs and fix the SSH task? | Dylan | 09/06/23 7:28 PM
| Sure @dylan.price@penske.com . Let me check with CICD team. | Gayam | 09/07/23 1:29 AM
| @dylan.price@penske.com , CICD team analyzed and found that the prod password is not setup. Please setup the password and try. | Gayam | 09/07/23 11:47 PM
Row 17 | Application has been tested and is ready to deploy. | Dylan | 09/05/23 5:00 PM
Row 17 | Deployed buzonebatch out to QA. Will start testing | Dylan | 08/22/23 6:08 PM
Row 17 | Hi @praneeth.gayam@penske.com develop_log4j branch has been merged with develop. Please start on the bamboo build for DEV. | Dylan | 06/06/23 11:47 PM
| Sure @dylan.price@penske.com | Gayam | 06/07/23 5:37 AM
| @dylan.price@penske.com ,Onboarded develop branch to Bamboo. Please deploy to QA. https://bamboo.penske.com/browse/BUZONEBBP-BUZBCH0 | Gayam | 06/09/23 2:03 AM
Row 17 | Review: @dylan.price@penske.com / @mark.weaver@penske.com , this app is ready for your review. Please verify in the below PR. https://bitbucket.penske.com/projects/ARPROJ/repos/buzone-batch/pull-requests/3/overview | Gayam | 04/03/23 2:52 AM
Row 17 | @praneeth.gayam@penske.com the MonetaryConversion.jar can be added to artifactory. We also have no code changes needed for the password file. | Dylan | 03/07/23 12:56 AM
Row 17 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 17 | @mark.weaver@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:52 AM
Row 17 | @rafiq.melath@penske.com / @mark.weaver@penske.com , For buzonebatch application, there is a dependency jar 'MonetaryConversion.jar' which is not available in artifactory. We need this in artifactory for mavanization. Could you please provide your approval to upload this jar to artifactory in the following location. Thanks. groupid : com.penske.util artifactid : MonetaryConversion version : Default @hugo.scavino@penske.com , @mathumala.nachiappan@penske.com , @swati.saxena@penske.com | Gayam | 01/20/23 12:53 AM
Row 18 | Log4j changes are completed for this application and pushing the status to Cap Secrets. | Gayam | 10/10/23 1:03 AM
Row 18 | This is the jar in the Lib Folder in prod.. | Brian | 10/04/23 6:46 AM
Row 18 | There is only 1 version. | Brian | 10/03/23 6:43 PM
| Thanks @brian.joseph@penske.com . | Gayam | 10/04/23 1:46 AM
Row 18 | Hi @praneeth.gayam@penske.com <!-- https://mvnrepository.com/artifact/com.google.code.kaptcha/kaptcha --> <dependency> <groupId>com.google.code.kaptcha</groupId> <artifactId>kaptcha</artifactId> <version>2.3</version> </dependency> | Brian | 10/03/23 6:42 PM
Row 18 | Hi isnt kaptchacode a google dependency ? I dont see why we would need this in a penske repo. I am going to attach the decompiled jar in prod. If you need this let me know I will send you the jar via teams. | Brian | 10/01/23 1:01 AM
| @brian.joseph@penske.com , Could you please provide the correct maven dependecy for the kaptchacode jar whcih we can use in captchabatchjob pom. I think if we use that dependency, no need of including trunk/kaptchacode/src folder in captchabatchjob. Please confirm. | Gayam | 10/03/23 1:35 AM
Row 18 | Query: @frank.d'angelo@penske.com , We have following queries while upgrading log4j on the gicen source code. Could you please check them. Thanks. 1.This application have multiple src folders (trunk/src and trunk/kaptchacode/src). I Believe trunk/src is the original source code for this app and trunk/kaptchacode/src is a dependency folder. We noticed that there is a kaptcha.jar in lib folder which is built from trunk/kaptchacode/src . Do you want us to create two separate repos for trunk/src and trunk/kaptchacode/src and modernize them? or any other solution. 2. We are facing compilation issues in one class under trunk/kaptchacode/src for below import statements . We couldn't find the dependency jar for these imports. Could you please let us know what is the dependency jar. import com.penske.apps.captchaimages.models.CaptchaImageBean; import com.penske.apps.captchaimages.services.ICaptchaImagesService; | Gayam | 09/20/23 12:42 AM
Row 18 | @praneeth.gayam@penske.com , I assume your team will handle BitBucket migration? | Gianfranco | 08/24/23 3:10 AM
| Yes @frank.d'angelo@penske.com | Gayam | 08/24/23 4:19 AM
Row 18 | This repo is in SVN located at https://svn.penske.com/svn/ebusiness/intranet/captchabatchjob/trunk/ There is no Bamboo build, it will need to be created after migration to bitbucket. | Brian | 08/24/23 2:46 AM
Row 18 | @yvette.urso@penske.com | Yvette Urso | 08/15/23 10:42 PM
Row 18 | @brian.joseph@penske.com / @sree.gopal@penske.com , We couldn't find Bamboo and code repo for this app. Could you please help us to find them. Thanks. | Gayam | 07/27/23 11:20 PM
Row 19 | will review today.. | Brian | 10/13/23 7:51 PM
Row 19 | Review: @brian.joseph@penske.com , This app is ready for your review. Please check and merge. https://bitbucket.penske.com/projects/EBCS/repos/captcha-service/pull-requests/3/overview | Gayam | 10/05/23 1:37 AM
Row 19 | No secrets found for this application. | Gayam | 10/04/23 2:49 AM
Row 20 | Hi @mathumala.nachiappan@penske.com I cannot find this application in our application list. Could you please remove this from the smart sheet? This application will not need moved over. | Dylan | 06/06/23 11:43 PM
| @dylan.price@penske.com , we can't find the repo or bamboo build for this app. Can I change the status to Reitre? @yvette.urso@penske.com | Gayam | 06/09/23 1:58 AM
| @praneeth.gayam@penske.com yes we can retire this application | Dylan | 06/13/23 1:24 AM
| @yvette.urso@penske.com , As per above conversation, we are retiring this application. Thanks. | Gayam | 06/13/23 1:33 AM
Row 20 | @mathumala.nachiappan@penske.com This application does not have a bamboo build. We may need to create one for it. I need to see where the codebase is for this application then get back to you | Dylan | 03/07/23 12:40 AM
Row 20 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 20 | @sreenivasulu.mupparaju@penske.com - For this App, we referred the bamboo key of 'PBSBP'. Got the project name as 'cbos'. But doesnt look related to this application. Pls. help us to clarify this CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 12:09 PM
| @sreenivasulu.mupparaju@penske.com - Pls. ignore the previous comment. Actual issue is we couldnt find the Bamboo build for this app. Pls. help us with the bamboo reference and the branch/folder to refer for modernization changes CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 02/10/23 11:16 AM
Row 20 | @mathumala.nachiappan@penske.com moved to AO Bamboo Status | Yvette Urso | 12/15/22 2:44 AM
Row 21 | @praneeth.gayam@penske.com can you please remove dupp apps. | Rajesh | 04/26/23 8:53 PM
| @yvette.urso@penske.com can help on removing dup apps. I am not authorized too delete them. @rajesh.haravde@penske.com | Gayam | 04/27/23 3:13 AM
Row 21 | validation work in progress. | Rajesh | 01/18/23 8:23 PM
Row 22 | 15-Aug-2023 15:20:24 [INFO] BUILD FAILURE 15-Aug-2023 15:20:24 [INFO] ------------------------------------------------------------------------ 15-Aug-2023 15:20:24 [INFO] Total time: 2.247 s 15-Aug-2023 15:20:24 [INFO] Finished at: 2023-08-15T15:20:24-04:00 15-Aug-2023 15:20:24 [INFO] ------------------------------------------------------------------------ 15-Aug-2023 15:20:24 [ERROR] Failed to execute goal org.codehaus.mojo:versions-maven-plugin:2.16.0:set (default-cli): Goal requires a project to execute but there is no POM in this directory (/apps/bamboows/build-dir/CCMS-CCMSW-BLD). Please verify you invoked Maven from the correct directory. -> [Help 1] 15-Aug-2023 15:20:24 [ERROR] 15-Aug-2023 15:20:24 [ERROR] To see the full stack trace of the errors, re-run Maven with the -e switch. 15-Aug-2023 15:20:24 [ERROR] Re-run Maven using the -X switch to enable full debug logging. 15-Aug-2023 15:20:24 [ERROR] | Narsimhamurthy | 08/16/23 1:12 AM
| @narsimhamurthy.peddoju@penske.com , Provide the details like which branch you are building. Without the details it is difficult to debug. | Gayam | 08/17/23 2:01 AM
| I tried master and develop as well | Narsimhamurthy | 08/17/23 9:15 PM
| @narsimhamurthy.peddoju@penske.com , Hope you got the calrification from our call. Please let us know if you need any other info. | Gayam | 08/18/23 12:46 AM
| Getting below exception . Look like we missed proper conf files based on env . ERROR :Error 500: javax.servlet.ServletException: SRVE0207E: Uncaught initialization exception created by servlet | Narsimhamurthy | 08/30/23 7:11 PM
| @narsimhamurthy.peddoju@penske.com , Please check the master branch and develop branch. Master branch have only one conf folder which we copied to resources folder. Please check. | Gayam | 08/30/23 10:55 PM
Row 22 | Hi Praneeth, we are seeing building errors. Please check and let us know. | Narsimhamurthy | 08/16/23 1:12 AM
Row 22 | Project got build issue while dev deployment with following Error: 13-Jun-2023 14:18:46 Connecting to ghlx008ptlge.penske.com on port: 22 13-Jun-2023 14:18:46 Uploading '/apps/bamboows/build-dir/142737482-142803182/ccms.tgz' to '${bamboo.static_ftpdir_service}/ccms'... 13-Jun-2023 14:18:46 Failed to upload file '/apps/bamboows/build-dir/142737482-142803182/ccms.tgz' 13-Jun-2023 14:18:46 net.schmizz.sshj.xfer.scp.SCPRemoteException: Remote SCP command had error: scp: ${bamboo.static_ftpdir_service}/ccms: No such file or directory 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPEngine.check(SCPEngine.java:73) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPEngine.sendMessage(SCPEngine.java:133) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPUploadClient.sendFile(SCPUploadClient.java:105) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPUploadClient.process(SCPUploadClient.java:84) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPUploadClient.startCopy(SCPUploadClient.java:76) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPUploadClient.copy(SCPUploadClient.java:54) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPUploadClient.copy(SCPUploadClient.java:47) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPUploadClient.copy(SCPUploadClient.java:43) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPFileTransfer.upload(SCPFileTransfer.java:55) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.plugins.scp.ScpTransport.transferFiles(ScpTransport.java:131) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.plugins.scp.ScpTask.execute(ScpTask.java:189) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.plugins.scp.ScpTask.run(ScpTask.java:62) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.plugins.scp.ScpTask.execute(ScpTask.java:49) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.task.TaskExecutorImpl.lambda$executeTasks$1(TaskExecutorImpl.java:319) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.task.TaskExecutorImpl.executeTaskWithPrePostActions(TaskExecutorImpl.java:258) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.task.TaskExecutorImpl.executeTasks(TaskExecutorImpl.java:319) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.task.TaskExecutorImpl.execute(TaskExecutorImpl.java:118) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.build.pipeline.tasks.ExecuteBuildTask.call(ExecuteBuildTask.java:73) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.v2.build.agent.DefaultBuildAgent.executeBuildPhase(DefaultBuildAgent.java:205) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.v2.build.agent.DefaultBuildAgent.build(DefaultBuildAgent.java:177) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.v2.build.agent.BuildAgentControllerImpl.lambda$waitAndPerformBuild$0(BuildAgentControllerImpl.java:169) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.variable.CustomVariableContextImpl.withVariableSubstitutor(CustomVariableContextImpl.java:118) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.v2.build.agent.BuildAgentControllerImpl.waitAndPerformBuild(BuildAgentControllerImpl.java:162) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.v2.build.agent.DefaultBuildAgent.lambda$start$0(DefaultBuildAgent.java:122) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.utils.BambooRunnables$1.run(BambooRunnables.java:48) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.security.ImpersonationHelper.runWith(ImpersonationHelper.java:26) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.security.ImpersonationHelper.runWithSystemAuthority(ImpersonationHelper.java:17) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.security.ImpersonationHelper$1.run(ImpersonationHelper.java:41) 13-Jun-2023 14:18:46 at java.lang.Thread.run(Thread.java:748) 13-Jun-2023 14:18:46 Copy Failed. Some files were not uploaded successfully. 13-Jun-2023 14:18:46 '/apps/bamboows/build-dir/142737482-142803182/ccms.tgz' was not uploaded. 13-Jun-2023 14:18:46 Finished task 'SCP tgz' with result: Error 13-Jun-2023 14:18:46 Finalising the build... 13-Jun-2023 14:18:46 Stopping timer. 13-Jun-2023 14:18:46 Build 142737482-142803182-141073425 completed. 13-Jun-2023 14:18:46 Finished processing deployment result Deployment of '2.0.0-develop_log4j-SNAPSHOT-4' on 'dev_was8-deploy' | Rajesh | 06/13/23 11:50 PM
| We will check | Gayam | 06/14/23 3:06 AM
| @rajesh.haravde@penske.com , Issue got fixed. Please check. | Gayam | 06/15/23 12:54 AM
Row 22 | while executing build after disabling test cases requirement, though the project getting build successfully, but failing on missing pom.xml ARE WE MISSIGN ANY STEP HERE? PLEASE GUIDE. 12-Jun-2023 14:16:30 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:16:30 [INFO] BUILD FAILURE 12-Jun-2023 14:16:30 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:16:30 [INFO] Total time: 2.143 s 12-Jun-2023 14:16:30 [INFO] Finished at: 2023-06-12T14:16:30-04:00 12-Jun-2023 14:16:30 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:16:30 [ERROR] Failed to execute goal org.codehaus.mojo:versions-maven-plugin:2.16.0:set (default-cli): Goal requires a project to execute but there is no POM in this directory (/apps/bamboows/build-dir/CCMS-CCMSW-BLD). Please verify you invoked Maven from the correct directory. -> [Help 1] 12-Jun-2023 14:16:30 [ERROR] | Rajesh | 06/12/23 11:47 PM
| @rajesh.haravde@penske.com , I am seeing that you ran the build on master branch. But the code is not yet merged to develop or master branch. You need to run the build on develop_log4j branch. | Gayam | 06/13/23 1:39 AM
Row 22 | Please confirm if we can validate the bamboo script for this project and which branch | Rajesh | 06/09/23 12:07 AM
| @rajesh.haravde@penske.com , this is also already onboarded . https://bamboo.penske.com/browse/CCMS-CCMSW0 | Gayam | 06/09/23 1:23 AM
Row 22 | We are getting maven build issue. following is the error messages: [4:37 PM] Peddoju, Narsimhamurthy (Penske) Error1: [ERROR] com.penske.ccms.service.impl.DefaultClientServiceTest.shouldUpdateContact Time elapsed: 0 s <<< ERROR! java.lang.IllegalStateException: Failed to load ApplicationContext Caused by: org.springframework.beans.factory.BeanDefinitionStoreException: Failed to parse configuration class [com.penske.ccms.configuration.ApplicationConfiguration]; nested exception is java.lang.NoSuchMethodError: org.slf4j.spi.LocationAwareLogger.log(Lorg/slf4j/Marker;Ljava/lang/String;ILjava/lang/String;Ljava/lang/Throwable;)V Caused by: java.lang.NoSuchMethodError: org.slf4j.spi.LocationAwareLogger.log(Lorg/slf4j/Marker;Ljava/lang/String;ILjava/lang/String;Ljava/lang/Throwable;)V error 2: [5/30/23 16:32:41:618 EDT] 0000005a webapp I com.ibm.ws.webcontainer.webapp.WebApp log SRVE0292I: Servlet Message - [ccms-web-git#ccms-web-git.war]:.Initializing Spring FrameworkServlet 'Dispatcher' @praneeth.gayam@penske.com [5/30/23 16:32:42:021 EDT] 0000005a ServletWrappe E com.ibm.ws.webcontainer.servlet.ServletWrapper init SRVE0271E: Uncaught init() exception created by servlet [Dispatcher] in application [ccms-web-git]: java.lang.NoSuchMethodError: org/slf4j/spi/LocationAwareLogger.log(Lorg/slf4j/Marker;Ljava/lang/String;ILjava/lang/String;Ljava/lang/Throwable;)V at org.apache.commons.logging.impl.SLF4JLocationAwareLog.debug(SLF4JLocationAwareLog.java:99) | Rajesh | 05/31/23 2:11 AM
| @rajesh.haravde@penske.com , Test cases are getting failed. Please check. | Gayam | 05/31/23 11:51 PM
Row 22 | @praneeth.gayam@penske.com can we proceed with "develop_log4j" branch for maven validation? | Rajesh | 05/30/23 10:45 PM
| Sure @rajesh.haravde@penske.com | Gayam | 05/31/23 1:02 AM
Row 22 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 22 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/ccms-web/pull-requests/3/overview Thanks. | Gayam | 02/16/23 11:05 PM
Row 22 | @rajesh.haravde@penske.com , we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:45 PM
Row 22 | validation work in progress. | Rajesh | 01/18/23 8:23 PM
Row 22 | @yvette.urso@penske.com - Its with CAP for Maven development changes | Mathumala Nachiappan | 12/15/22 10:26 AM
Row 22 | Moved to AO Maven status | Yvette Urso | 12/15/22 2:51 AM
Row 22 | Yes please upload it to Artifactory. as we are as per class path using this jar dependancy. | Rajesh | 12/12/22 10:10 PM
| Thanks @rajesh.haravde@penske.com . We will upload and will progress on ccms app. @mathumala.nachiappan@penske.com | Gayam | 12/13/22 12:01 AM
Row 22 | @krishna.tanga@penske.com , @rajesh.haravde@penske.com - SVN to BB Migration issue, mentioned previously is resloved now for ccms.war. We are looking for the update on the dependent jar. Here is the Artifactory details suggested for this jar from the package information. Pls. confirm this if you are fine to upload it to Artifactory. Group ID - com.penske.salessys Artifact ID - salessysutil Version - default CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 3:27 PM
Row 22 | @praneeth.gayam@penske.com - Adding the SVN to BB migration issue too | Mathumala Nachiappan | 12/01/22 9:13 PM
Row 22 | @krishna.tanga@penske.com / @yogesh.sinha@penske.com , ccms app depends on the jar salessysutil.jar. This jar is not available in SVN/BB repo and don't have bamboo build. Can we upload the jar into artifactory? @mathumala.nachiappan@penske.com | Gayam | 11/25/22 11:29 PM
Row 23 | In the build log. | Rajesh | 06/13/23 11:32 PM
| @rajesh.haravde@penske.com , Narsimha able to build from feature/maven branch and deployed to dev. | Gayam | 06/14/23 3:09 AM
Row 23 | @praneeth.gayam@penske.com please guide. Error 2-Jun-2023 14:19:17 Finished publishing of artifact Non required shared artifact: [Source], pattern: [src/**] in 19.73 ms 12-Jun-2023 14:19:17 Publishing an artifact: target 12-Jun-2023 14:19:17 Unable to publish artifact [target]: 12-Jun-2023 14:19:17 The artifact is required for down stream Stages and Jobs, build will now fail. 12-Jun-2023 14:19:17 The artifact hasn't been successfully published after 4.918 ms 12-Jun-2023 14:19:17 Publishing an artifact: XML 12-Jun-2023 14:19:17 Unable to publish artifact [XML]: 12-Jun-2023 14:19:17 The artifact is required for down stream Stages and Jobs, build will now fail. 12-Jun-2023 14:19:17 The artifact hasn't been successfully published after 5.120 ms 12-Jun-2023 14:19:17 Running post build plugin 'Artifactory Release Management Staging' 12-Jun-2023 14:19:17 Running post build plugin 'Artifactory Build Info Copier' 12-Jun-2023 14:19:17 Running post build plugin 'Artifactory Gradle Properties Info Copier' 12-Jun-2023 14:19:17 Running post build plugin 'npm Cache Cleanup' 12-Jun-2023 14:19:17 Running post build plugin 'NCover Results Collector' | Rajesh | 06/12/23 11:54 PM
| @rajesh.haravde@penske.com , where are you getting above error? | Gayam | 06/13/23 1:35 AM
Row 23 | @praneeth.gayam@penske.com can we proceed with "develop_log4j" branch for maven validation? | Rajesh | 05/30/23 10:46 PM
| Sure @rajesh.haravde@penske.com | Gayam | 05/31/23 1:01 AM
| @rajesh.haravde@penske.com , Onboard develop_log4j to bamboo and deploy to dev is completed. https://bamboo.penske.com/deploy/viewEnvironment.action?id=142802957 | Gayam | 06/01/23 12:08 AM
Row 23 | @rajesh.haravde@penske.com , Bamboo build for this app is https://bamboo.penske.com/browse/CCMS-CCMSSVVC | Gayam | 03/07/23 12:22 AM
Row 23 | GIT URL info: https://bitbucket.penske.com/scm/ptlcorp/ccmsservice-web.gitBranch :develop_log4J | Rajesh | 03/04/23 1:16 AM
Row 23 | Please build bamboo deployment script for development environment. | Rajesh | 03/04/23 1:11 AM
Row 23 | Thanks @rajesh.haravde@penske.com . Please review the below PR when you get a chance. https://bitbucket.penske.com/projects/PTLCORP/repos/ccmsservice-web/pull-requests/3/overview | Gayam | 02/16/23 10:44 PM
Row 23 | Its false positive please do the needful. no action needed at this time. | Rajesh | 02/16/23 3:43 AM
Row 23 | we do not want to address secrete mitigation at this movement. please move forward with project upgrade with respect to bitbucket, maven and log4j | Rajesh | 02/16/23 3:41 AM
Row 23 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:46 PM
Row 23 | validation work in progress. | Rajesh | 01/18/23 8:23 PM
Row 23 | @rajesh.haravde@penske.com / @krishna.tanga@penske.com , Log4j team completed log4j/maven changes on this app. Please review them in below MR and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/ccmsservice-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/10/22 3:29 AM
| We will do the needful as requested and get back to you the build result as early as possible. | Rajesh | 12/12/22 10:14 PM
Row 24 | All configuration filed in wrong locations | Narsimhamurthy | 08/31/23 8:00 PM
Row 24 | This project worked earlier on QA with branch name like with AO testing. Now it is not generating logs in QA, we deployed develop branch . Observed lot of files moved from develop_log4 to develop in last merge request. Could you please check did we miss any package structure and other dependent applications are not connecting | Narsimhamurthy | 08/23/23 11:19 PM
| ccmsxservice-web-deploy- this branch worked properly on DEV | Narsimhamurthy | 08/23/23 11:22 PM
Row 24 | Reopen request sent to this project | Narsimhamurthy | 08/19/23 1:07 AM
Row 24 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:08 AM
| @rajesh.haravde@penske.com , develop_log4j branch is onboarded to Bamboo and build is failing because of test case failure. Please check. | Gayam | 06/10/23 1:38 AM
Row 24 | Getting following error, lava.lang.IllegalStateException: Failed to load ApplicationContext Caused by: org.springframework.beans.factory.UnsatisfiedDependencyException: Error creating bean with name 'customerContactService': Unsatisfied dependency expressed through field 'basicInformationDao'; nested exception is org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'basicInformationDao' defined in file [C:\Users\600224522\Workspaces\Git_Projects_workspace\ccmsxservice-git2\target\classes\com\penske\ccms\contact\basicinfo\BasicInformationDao.class]: Cannot resolve reference to bean 'primarySessionFactory' while setting bean property 'sqlSessionFactory'; nested exception is org.springframework.beans.factory.UnsatisfiedDependencyException: Error creating bean with name 'com.penske.ccms.configuration.PrimaryMapperConfiguration': Unsatisfied dependency expressed through field 'dataSource'; nested exception is org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'greenHillsDataSource' defined in com.penske.ccms.configuration.EmbeddedDataSourceConfiguration: Bean instantiation via factory method failed; nested exception is org.springframework.beans.BeanInstantiationException: Failed to instantiate [javax.sql.DataSource]: Factory method 'greenHillsDataSource' threw exception; nested exception is org.springframework.jdbc.datasource.init.CannotReadScriptException: Cannot read SQL script from class path resource [setup/create-ccms-database.sql]; nested exception is java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist Caused by: org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'basicInformationDao' defined in file [C:\Users\600224522\Workspaces\Git_Projects_workspace\ccmsxservice-git2\target\classes\com\penske\ccms\contact\basicinfo\BasicInformationDao.class]: Cannot resolve reference to bean 'primarySessionFactory' while setting bean property 'sqlSessionFactory'; nested exception is org.springframework.beans.factory.UnsatisfiedDependencyException: Error creating bean with name 'com.penske.ccms.configuration.PrimaryMapperConfiguration': Unsatisfied dependency expressed through field 'dataSource'; nested exception is org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'greenHillsDataSource' defined in com.penske.ccms.configuration.EmbeddedDataSourceConfiguration: Bean instantiation via factory method failed; nested exception is org.springframework.beans.BeanInstantiationException: Failed to instantiate [javax.sql.DataSource]: Factory method 'greenHillsDataSource' threw exception; nested exception is org.springframework.jdbc.datasource.init.CannotReadScriptException: Cannot read SQL script from class path resource [setup/create-ccms-database.sql]; nested exception is java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist Caused by: org.springframework.beans.factory.UnsatisfiedDependencyException: Error creating bean with name 'com.penske.ccms.configuration.PrimaryMapperConfiguration': Unsatisfied dependency expressed through field 'dataSource'; nested exception is org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'greenHillsDataSource' defined in com.penske.ccms.configuration.EmbeddedDataSourceConfiguration: Bean instantiation via factory method failed; nested exception is org.springframework.beans.BeanInstantiationException: Failed to instantiate [javax.sql.DataSource]: Factory method 'greenHillsDataSource' threw exception; nested exception is org.springframework.jdbc.datasource.init.CannotReadScriptException: Cannot read SQL script from class path resource [setup/create-ccms-database.sql]; nested exception is java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist Caused by: org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'greenHillsDataSource' defined in com.penske.ccms.configuration.EmbeddedDataSourceConfiguration: Bean instantiation via factory method failed; nested exception is org.springframework.beans.BeanInstantiationException: Failed to instantiate [javax.sql.DataSource]: Factory method 'greenHillsDataSource' threw exception; nested exception is org.springframework.jdbc.datasource.init.CannotReadScriptException: Cannot read SQL script from class path resource [setup/create-ccms-database.sql]; nested exception is java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist Caused by: org.springframework.beans.BeanInstantiationException: Failed to instantiate [javax.sql.DataSource]: Factory method 'greenHillsDataSource' threw exception; nested exception is org.springframework.jdbc.datasource.init.CannotReadScriptException: Cannot read SQL script from class path resource [setup/create-ccms-database.sql]; nested exception is java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist Caused by: org.springframework.jdbc.datasource.init.CannotReadScriptException: Cannot read SQL script from class path resource [setup/create-ccms-database.sql]; nested exception is java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist Caused by: java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist | Rajesh | 05/31/23 1:09 AM
| @narsimhamurthy.peddoju@penske.com , As discussed test cases are getting failed. Please check. Thanks. | Gayam | 06/01/23 12:27 AM
Row 24 | @praneeth.gayam@penske.com can we proceed with "develop_log4j" branch for maven validation? | Rajesh | 05/30/23 10:46 PM
| Sure @rajesh.haravde@penske.com | Gayam | 05/31/23 1:02 AM
Row 24 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 24 | we confirm its false positive. we do not want to address secrete mitigation at this movement. please move forward with project upgrade with respect to bitbucket, maven and log4j | Rajesh | 02/16/23 3:43 AM
| Thanks @rajesh.haravde@penske.com . Please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/ccmsxservice-web/pull-requests/3/overview Thanks. | Gayam | 02/16/23 11:20 PM
Row 24 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:46 PM
Row 24 | validation work in progress. | Rajesh | 01/18/23 8:24 PM
Row 24 | @krishna.tanga@penske.com / @yogesh.sinha@penske.com We have completed log4j, maven changes. Please review, merge and provide your approval for the deployment. https://bitbucket.penske.com/projects/PTLCORP/repos/ccmsxservice-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 11/29/22 7:15 AM
| We will do the needful and get back to you on build result with maven as requested. | Rajesh | 12/12/22 10:15 PM
Row 25 | @praneeth.gayam@penske.com Below is the error i am getting while doing a maven bulid, As discussed please let me know when i have the aceess [FATAL] Non-resolvable parent POM for com.penske.hr:cds:2.0.0-SNAPSHOT: Could not transfer artifact com.penske.mis.common:web-parent:pom:1.0.0-DJ-WEB-17-430727b from/to hr-mvn-virtual (https://artifactory.penske.com/artifactory/hr-mvn-virtual): Access denied to https://artifactory.penske.com/artifactory/hr-mvn-virtual/com/penske/mis/common/web-parent/1.0.0-DJ-WEB-17-430727b/web-parent-1.0.0-DJ-WEB-17-430727b.pom. Error code 403, Forbidden and 'parent.relativePath' points at wrong local POM @ line 3, column 10 Thanks | Shabeer | 10/14/23 1:54 AM
| @shabeer.shaik@penske.com , As discussed please raise a FP ticket to add your id to artifactory hr read and write access. Thanks. | Gayam | 10/17/23 1:07 AM
Row 25 | Yes, starting the review and local workspace setup. | Shabeer | 10/11/23 3:07 AM
Row 25 | @praneeth.gayam@penske.com Let me know if access is provided to the repositories. | Shabeer | 10/06/23 6:27 PM
| @shabeer.shaik@penske.com As per our chat you got the access. | Gayam | 10/11/23 1:40 AM
Row 25 | @praneeth.gayam@penske.com i am getting Access denied to the above path. | Shabeer | 10/05/23 2:22 AM
| @shabeer.shaik@penske.com , We raised an email to add you adn sathish to RBAC group. | Gayam | 10/06/23 12:34 AM
Row 25 | Review: @shabeer.shaik@penske.com , This app is ready for your review. Please check and merge. https://bitbucket.penske.com/projects/HR/repos/cds-web/pull-requests/3/overview | Gayam | 10/05/23 1:42 AM
Row 25 | @praneeth.gayam@penske.com Yes Please | Shabeer | 09/13/23 1:48 AM
| Sure @shabeer.shaik@penske.com . We will start working from log4j stage but we skip the secrets stage becuase you already confirmed the secrets. Thanks. | Gayam | 09/14/23 2:27 AM
Row 25 | Current SVN Branch Details for CDS: Dev: https://svn.penske.com/svn/ecomm/hr/cds/branches/dev_gh/cds/ QA: https://svn.penske.com/svn/ecomm/hr/cds/branches/qa/cds/ PROD: https://svn.penske.com/svn/ecomm/hr/cds/trunk/cds We have analyzed the secrets in the application with refrence of provided secrets file most of them are from old branches which we don't use. Please initiate the next steps from your side for this Application and let us know. FYI - @praneeth.gayam@penske.com @satish.polubothu@penske.com | Shabeer | 09/13/23 12:27 AM
| @shabeer.shaik@penske.com , Can we take base code branch from PROD? https://svn.penske.com/svn/ecomm/hr/cds/trunk/cds | Gayam | 09/13/23 12:58 AM
Row 25 | @vinay.ramanand@penske.com , I sent the secrets in the email. Could you please verify them. | Gayam | 03/10/23 2:01 AM
| Hi all , there are no issues with CDS on secrets and can move farward | Satish | 09/12/23 6:18 PM
Row 25 | Bamboo Project Setup 2/1/23 - Yvette sent Tim Fox the below question via email: Tim, We are submitting a request for a Bamboo Project and would like to know who to add from the HR team as the Admin of that Project? That person can then create what ever they need for other access and repositories, etc. | Yvette Urso | 02/01/23 8:53 PM
Row 26 | Review & Query: @jeremiah.ashway@penske.com This app is ready for your review with an open query. PR: https://bitbucket.penske.com/projects/EBCE/repos/cedadatachanges/pull-requests/14/overview Query: This application has separate application.properties fille for each environment under Deploy folder. It looks like build is environment dependent. But in environment agnostic build, only one build can be deployed to different environments. So there is a code change required to satisfy the environment agnostic build. Please check. Thanks. | Gayam | 10/19/23 8:01 AM
Row 26 | Secrets: @jeremiah.ashway@penske.com / @frank.d'angelo@penske.com , I have sent the secrets of this app in the email. Could you please verify and let us know whether it requires any code changes to mitigate the secrets. Thanks. | Gayam | 09/14/23 2:03 AM
| Hi @praneeth.gayam@penske.com , this is taken care of and the repo is up to date. Thanks | Jeremiah Ashway | 09/15/23 1:10 AM
| Thanks @jeremiah.ashway@penske.com . Pushing the app to next step. | Gayam | 09/15/23 7:05 AM
Row 26 | Thanks @frank.d'angelo@penske.com . We will start on this application as soon as possible depends on teams availablity | Gayam | 08/30/23 2:27 AM
Row 26 | @praneeth.gayam@penske.com , there is recent development activity with this application, however, we are going to pause that effort (it's in a different branch) and eventually merge it into the completed, modernized application. Please proceed forward using MASTER. Thank you. | Gianfranco | 08/29/23 2:11 AM
Row 26 | @praneeth.gayam@penske.com WAIT - there are changes not yet in production and we have to finish testing. I recommend waiting until we wrap up testing. | Gianfranco | 08/14/23 11:37 PM
Row 26 | @jeremiah.ashway@penske.com / @frank.d'angelo@penske.com , We are seeing recent activity on this application. So, do you want us to start modernizing this application or need to wait until you complete all of your changes? What is the branch we need to take as base branch if you want us to start modernizing? Bamboo build: https://bamboo.penske.com/browse/CEP-BCC BB repo : https://bitbucket.penske.com/projects/EBCE/repos/cedadatachanges/browse | Gayam | 08/08/23 2:03 AM
Row 27 | Is there a PR pending @praneeth.gayam@penske.com? | Gianfranco | 10/09/23 5:54 PM
| @frank.d'angelo@penske.com , Review and PR: https://bitbucket.penske.com/projects/EBCE/repos/notify-batch/pull-requests/3/overview is the PR and I mentioned query also in this PR. Thanks. | Gayam | 10/10/23 12:28 AM
Row 27 | @praneeth.gayam@penske.com where are we at with the log4j2 upgrade? that can and should be done independently of the other work here from what I understand. | Jeremiah Ashway | 10/03/23 12:46 AM
| please update the spreadsheet for apps so we can see what is completed and what is in progress as well. | Jeremiah Ashway | 10/03/23 12:47 AM
| @jeremiah.ashway@penske.com , Log4j upgrade completed but not the mavanization. We are waiting for the queries asked above. Please let us know whether you want to handle the queries after completing mavanization ? | Gayam | 10/03/23 1:26 AM
| Thanks, I left some comments in the pr. Once the log4j changes and maven chagnes are in their own branches/pr we can move foward with releasing log4j and then my team will look at the maven blockers. Will your team handle moving the jar to artifactory? Thanks https://bitbucket.penske.com/projects/EBCE/repos/notify-batch/pull-requests/2/overview | Jeremiah Ashway | 10/03/23 2:18 AM
| @jeremiah.ashway@penske.com , We will push jar artifactory manually. | Gayam | 10/04/23 1:42 AM
| @jeremiah.ashway@penske.com Uploaded the notification-client.jar to artifactory and updated the dependency in pom. Please check. Thanks. | Gayam | 10/05/23 1:09 AM
Row 27 | Questions: 1. This application has applicationcontext.xml and notification.properties files which are different for Prod and QA. These are available under DEPLOY/TARGET folder. It looks like build depends on environment. But in environment agnostic build, one build can be deployed to different environments. So code needs to satisfy in that way. Could you please rectify this. Thanks. 2. This app depends on notificateion-client.jar and it is not available in artifactory. But we find the repo for this jar. https://bitbucket.penske.com/projects/EBCE/repos/notify-batch/browse/lib/notification-client.jar Do you want us to modernize this jar too or upload the jar manually to artifactory? | Gayam | 09/14/23 2:41 AM
| Hi @praneeth.gayam@penske.com , Question #2 - let's just move this jar into artifactory. We will look into question 1. | Jeremiah Ashway | 10/03/23 12:45 AM
Row 27 | @praneeth.gayam@penske.com All items found are validated as false positive. Please proceed. | Gianfranco | 08/24/23 1:49 AM
| Thanks @frank.d'angelo@penske.com | Gayam | 08/24/23 4:13 AM
Row 27 | @jeremiah.ashway@penske.com , I sent the secrets file of this app in email. Could you please check it and let su know whether it requires any code changes. Thanks. | Gayam | 08/22/23 2:20 AM
Row 28 | Secrets: @manish.sisodiya@penske.com / @mark.weaver@penske.com , I sent the secrets file to you in the email. Please check and let us know whether the app requires any code changes. Thanks. | Gayam | 09/28/23 1:21 AM
| @praneeth.gayam@penske.com Please go ahead and implement the log4j/manven changes. we will handle the secrets. | Venkatesh | 09/29/23 2:45 AM
| @venkatesh.hossalinever@penske.com , Do you want to handle the secrets later? | Gayam | 10/03/23 12:14 AM
Row 28 | @praneeth.gayam@penske.com cmns application looks like it has a dependency on the "billingservice" application. The class "RepairOrderDetail" that you were looking for is inside the BIllingService application: https://svn.penske.com/svn/fieldsys/other/billing-service/trunk/BillingUtility/src/com/penske/cns/models/RepairOrderDetail.java NotificationContract object is also in there. | Dylan | 06/07/23 12:33 AM
| Thanks @dylan.price@penske.com . we will check and get back to you. | Gayam | 06/07/23 5:45 AM
| @dylan.price@penske.com , It looks like the java classes which you mentioned above are under BillingUtility. There is a jar under lib folder of cmns application with name BillingUtility. I believe this jar is created from the svn location which you mentioned above. So do we need to create a separate repo for BillingUtility and Bamboo build and modernize it. | Gayam | 06/10/23 2:30 AM
| We are modernizing billing utility as we got the approval in another app. So changing the status to Cap Log4j. | Gayam | 07/18/23 6:10 PM
Row 28 | @mark.weaver@penske.com / @dylan.price@penske.com , We are facing build issues with below import statements while doing initial setup in local. We are unable to find the dependent jar in ptlcommon or inside the project. class name ; RepairOrderReportPrint.java import com.penske.cns.models.RepairOrderDetail; Other imports causing issues import com.penske.cns.models.mailer.NotificationContact; Could you please check and provide the correct dependency jar to resolve these issues. Thanks. | Gayam | 03/14/23 11:34 PM
Row 28 | @praneeth.gayam@penske.com please use the following SVN url: https://svn.penske.com/svn/fieldsys/other/customer-notification-system/trunk/cns-web/ | Dylan | 03/07/23 12:43 AM
Row 28 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 28 | @manish.sisodiya@penske.com , This application has complex folder structure at https://svn.penske.com/svn/fieldsys/other/customer-notification-system/tags/prod/1.0.3_20170531/ We are not sure on which folder we need to start working on it. Could you please check and guide us. Thanks. | Gayam | 01/30/23 3:48 AM
Row 28 | @praneeth.gayam@penske.com - To discuss with AO on folder structure | Mathumala Nachiappan | 01/10/23 10:46 AM
Row 29 | @yvette.urso@penske.com , There is a app already under billing group with the same name 'cmns.war'. Is this duplicate or there is another app under Maintenance group with the same name? | Gayam | 05/10/23 1:08 AM
| @praneeth.gayam@penske.com This is a duplicate application. one under Billing is correct. | Stella george | 06/14/23 2:30 AM
Row 30 | Thanks for the update @sreekanth.kancharla@penske.com | Gayam | 08/30/23 10:39 PM
Row 30 | App deployed in PROD on 08/29/2023 | Sreekanth | 08/30/23 6:23 PM
Row 30 | @sreekanth.kancharla@penske.com , Onboarded to bamboo and dev deployment is done with develop branch. Please verify. Thanks. https://bamboo.penske.com/browse/CMSP-CMSPLP0/deployments | Gayam | 07/25/23 12:03 AM
Row 30 | @sreekanth.kancharla@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ITFIS/repos/cmsplus-web/pull-requests/3/overview | Gayam | 07/20/23 12:38 AM
| @praneeth.gayam@penske.com PR is merged. Please proceed with bamboo configuration. | Sreekanth | 07/20/23 7:16 PM
| Sure @sreekanth.kancharla@penske.com | Gayam | 07/20/23 10:51 PM
Row 30 | @praneeth.gayam@penske.com Please let me know in case any update on this application. | Sreekanth | 07/07/23 8:26 PM
Row 30 | Hugo suggests grabbing the prod jar and reuse in artifactory since Prod is the most current jar. Assigned to Kalrav | Yvette Urso | 05/12/23 12:54 AM
| @yvette.urso@penske.com / @praneeth.gayam@penske.com Please take the "dassupport.jar" & "iasservice-client.jar" from SVN location. https://svn.penske.com/svn/webprojects/admin/cmsplus/trunk/CMSplusPhaseIII/WebContent/WEB-INF/lib We are not using "IAS_Agent.jar" in CMSPlus application and not sure where we can get this jar. | Sreekanth | 06/08/23 11:21 PM
| @sreekanth.kancharla@penske.com , We required iasservice-client.jar and IAS_Agent.jar for this app. It doesn't require dassupport.jar. Without IAS_Agent.jar application is giving compilation issues and the jar exist at https://svn.penske.com/svn/webprojects/admin/cmsplus/trunk/CMSplusPhaseIII/targeted/prod/ Could you please check and provide your approval to upload the jar. | Gayam | 06/10/23 2:22 AM
| @praneeth.gayam@penske.com Yes, we can use the IAS_Agent.jar from the trunk branch. | Sreekanth | 06/13/23 2:13 AM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 06/13/23 2:29 AM
Row 30 | @dylan.price@penske.com confirmed that we can upload the 'iasservice-client.jar' to artifactory. This app depends on IAS_Agent.jar and dassupport.jar also. So could you please let us know whether we can upload these jars into artifactory. | Gayam | 04/03/23 2:47 AM
Row 30 | Thanks @yvette.urso@penske.com . @mark.weaver@penske.com - Pls. have a look on the previous discussions and confirm your approval to upload to artifactory. Suggested Artifactory details as per the package information iasservice-client.jar --------------------- Group ID - com.penske.ias.services Artifact ID - iasservice-client Version - Default IAS_Agent.jar --------------------- Group ID - com.penske.invoice Artifact ID - IAS_Agent Version - Default CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 3:31 PM
| @mark.weaver@penske.com , Could you please respond to above query. Thanks. | Gayam | 03/09/23 2:01 AM
Row 30 | This is blocked by Billing Team. Kalrav sent Rafiq the question on which Jar is needed for this Application. | Yvette Urso | 02/16/23 12:11 AM
Row 30 | @kalrav.khamar@penske.com - Hi Kalrav..Any update on this | Mathumala Nachiappan | 12/01/22 9:03 PM
| @mathumala.nachiappan@penske.com I'm working with Sreekanth.Kancharla@penske.com. He will contact you and after that will update here. | Kalrav | 12/01/22 9:21 PM
| @mathumala.nachiappan@penske.com IAS_Agent.jar and iasservice-client.jar both are provided by invoice archive systems. @mark.weaver@penske.com is application owner and he should be able to provide more details about these jar files. | Kalrav | 12/01/22 9:44 PM
| @mark.weaver@penske.com Can you update IAS_Agent.jar and iasservice-client.jar? It's been waiting for your response since long time. | Kalrav | 02/13/23 9:01 PM
Row 30 | @mathumala.nachiappan@penske.com moving to the appropriate status to assign to AO for review. I chose AO Maven. | Yvette Urso | 12/15/22 2:08 AM
| @yvette.urso@penske.com - This is not review from App Owner. This is a dependency on the approval to proceed to upload to Artifactory. For Action - @mark.weaver@penske.com . CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/15/22 10:11 AM
Row 30 | @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com @mark.weaver@penske.com - Reassigned this application from Kalrav to Mark per Kalrav response. Thank you | Yvette Urso | 12/02/22 2:13 AM
Row 30 | @rafiq.melath@penske.com / @kalrav.khamar@penske.com , cmsplus.war has a dependency on IAS_Agent.jar and iasservice-client.jar. But these jars are not available in artifactory and unable to find source code of these jars in SVN/BitBucket. Can we upload these jars into artifactory? FYI: @mathumala.nachiappan@penske.com | Gayam | 11/23/22 10:29 PM
Row 31 | @praneeth.gayam@penske.com we are going to retire this app | Shawn | 08/31/23 6:37 PM
| @shawn.mcmurtry@penske.com , Thanks for the update. | Gayam | 08/31/23 11:35 PM
Row 31 | @shawn.mcmurtry@penske.com - tagging you for test | Patel | 07/28/23 10:23 PM
Row 31 | Testing Shawn's email notification | Patel | 07/28/23 9:39 PM
Row 31 | Question: @shawn.mcmurtry@penske.com / @dave.kost@penske.com , cns_application.properties.ant file contains a variable 'version' having value @DEPLOYMENT_INSTANCE@. It looks like this value comes from the bamboo build for each environment. But after modernization, it is going to be environment agnostic build. So it needs to be rectified if this variable used in code. Please check. Thanks. | Gayam | 07/19/23 3:23 AM
Row 31 | AO confirmed that all secrets are false positives. No code changes required. | Gayam | 06/16/23 1:12 AM
Row 31 | @shawn.mcmurtry@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:51 AM
Row 32 | @praneeth.gayam@penske.com It was working with Ant previously, now it should work with maven changes. Let me know if any property values are missing. | Venkatesh | 09/30/23 1:24 AM
| @venkatesh.hossalinever@penske.com , Please check the query mentioned in the previous comment. App will not work without resolving that query. | Gayam | 10/03/23 12:12 AM
Row 32 | Review and Query: This app is ready for your review with an open query. Please check. https://bitbucket.penske.com/projects/PB/repos/cnsmailer-batch/pull-requests/3/overview Query: This application has applicationcontext.xml and it has dynamic jdbc properites and other values which are getting populated from ant build file. But after mavanization it will not work. Could you please check and resolve the issue. | Gayam | 09/29/23 1:59 AM
Row 32 | @praneeth.gayam@penske.com Please deploy the changes on QA and let us know. we will validate and confirm. Note: There is no dev environment for batch application. | Venkatesh | 09/25/23 11:00 PM
| @venkatesh.hossalinever@penske.com , this app has secrets. Do you want to ignore them for now and provide secrets once we mavanize the application? | Gayam | 09/26/23 12:58 AM
| @venkatesh.hossalinever@penske.com informed in the email that he is going take care of the secrets later. | Gayam | 09/29/23 1:58 AM
Row 32 | @dylan.price@penske.com , This app also relies on BillingUtility jar. We are currently discussing the details of this jar in the context of cmns.war application. Once we get the clarification overthere then it clarifies for this app also. | Gayam | 06/10/23 2:36 AM
| We are modernizing billing utility as we got the approval in another app. So changing the status to Cap Log4j. | Gayam | 07/18/23 6:11 PM
Row 32 | @praneeth.gayam@penske.com SVN link to use should be https://svn.penske.com/svn/fieldsys/other/customer-notification-system/trunk/Mailer/ | Dylan | 06/07/23 12:37 AM
| Sure @dylan.price@penske.com . We will check. thanks. | Gayam | 06/07/23 5:47 AM
Row 32 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 32 | @praneeth.gayam@penske.com - To discuss with AO on folder structure | Mathumala Nachiappan | 01/10/23 10:46 AM
| Question: @manish.sisodiya@penske.com , This application has complex folder structure at https://svn.penske.com/svn/fieldsys/other/customer-notification-system/tags/prod/1.0.3_20170621/ We are not sure on which folder we need to start working on it. Could you please check and guide us. Thanks. | Gayam | 02/02/23 1:03 AM
Row 33 | Duplicate of contextframework | Mathumala Nachiappan | 11/23/22 3:11 AM
Row 34 | Thank you for the support | Hugo Scavino | 02/10/23 12:18 AM
Row 34 | Bamboo DEV - The plan is coomplete. I wll deploy to DEV and if there are issues I will let you all know. https://bamboo.penske.com/browse/CONNECTIONMAINT-CONNECTIONMT0-5 | Hugo Scavino | 02/10/23 12:18 AM
Row 34 | I also reviewed the secrets. The word password is used for a column and does not actually store passwords | Hugo Scavino | 02/09/23 2:27 AM
Row 34 | Please proceed with the Bamboo plan for this application. The new plan should replace the below project and use the below Bitbucket repo https://bamboo.penske.com/browse/CONNECTIONMAINT-CONNECTIONMAINTDEV https://bitbucket.penske.com/projects/AR-SEC/repos/connectionmaint-web/browse?at=develop | Hugo Scavino | 02/09/23 2:26 AM
Row 34 | Blocker :removed. security_util is in artifactory. | Hugo Scavino | 02/09/23 2:25 AM
Row 34 | Blocker: security_util.jar | Yvette Urso | 02/01/23 8:29 PM
Row 34 | @hugo.scavino@penske.com , This app contains true positive secrets. I will send the zip which contains all of your apps secrets. Please check. | Gayam | 01/19/23 3:25 AM
Row 34 | @praneeth.gayam@penske.com - Dependency with security_util.jar | Mathumala Nachiappan | 12/02/22 5:23 PM
Row 35 | Development has been finished by Amit. We have not yet deployed into QA but Amit completed local testing. We are concerned about affecting QA environment with our deploy. | David Graf | 09/14/23 6:38 PM
Row 35 | If it hasn't been done before we are signing off on Maven changes and log4j2 changes. Please create the agnostic Bamboo build plan. | David Graf | 07/06/23 5:10 PM
| Sure @david.w.graf@penske.com | Gayam | 07/07/23 12:19 AM
| @david.w.graf@penske.com , Onboarding to bamboo and build is successful after disabling tests. https://bamboo.penske.com/browse/CFWBP-CFRW0 Please deploy to QA. Thanks. | Gayam | 07/09/23 11:11 PM
Row 35 | @david.w.graf@penske.com , Following is the bitbucket location. https://bitbucket.penske.com/projects/AR-SEC/repos/contextframework-batch/browse?at=refs%2Fheads%2Fdevelop Regarding bamboo, from my documentation I can say that Hugo was looking into it and he said that it is a complex deployment structure. After that there was no progress on this app. | Gayam | 07/06/23 3:21 AM
Row 35 | where is the Bamboo build plan? | David Graf | 06/29/23 11:28 PM
Row 35 | I guess the jar that it builds is called contextframework | David Graf | 06/29/23 11:20 PM
Row 35 | I'm going to start Amit on this project instead of the one assigned earlier. | David Graf | 06/29/23 11:17 PM
Row 35 | I think the name of this Application is Connection Management Framework. For some reason the Bamboo project is called Context Framework but we should be naming based on the IT Contact information going forward. Here is SVN for some evidence: https://svn.penske.com/svn/architecture/security/connection_mngmt/ | David Graf | 06/29/23 11:17 PM
Row 35 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:27 AM
Row 35 | @hugo.scavino@penske.com working with Connect Fleet to provide a status on 12/20/22 | Yvette Urso | 12/15/22 2:25 AM
Row 35 | From Hugo. Custom deployment to be planned | Mathumala Nachiappan | 11/23/22 3:14 AM
Row 36 | @mahipal.podduturi@penske.com , Following is the PR for review. https://bitbucket.penske.com/projects/ARPROJ/repos/contribreport-batch/pull-requests/2/overview Bamboo build: https://bamboo.penske.com/browse/CONTRIBREPORTBP-CONTRIBREPOR4 Please verify. | Gayam | 09/29/23 1:41 AM
Row 36 | @praneeth.gayam@penske.com I deployed feature branch in local and tested it looks good can you move next steps | Mahipal | 09/26/23 12:14 AM
| Thanks @mahipal.podduturi@penske.com . We will check the maven branch and will add if anything missing. Then will raise a PR and onboard to bamboo. | Gayam | 09/26/23 1:15 AM
Row 36 | @praneeth.gayam@penske.com @mahipal.podduturi@penske.com it is the AO's responsibility to perform the necessary code changes for agnostic builds. I want to make sure that Mahipal is completing this work. It is difficult to tell from the conversation but Preneeth should not be changing the properties file to achieve agnostic artifacts. | David Graf | 09/15/23 12:17 AM
Row 36 | @praneeth.gayam@penske.com I spoke to webmaster the have alreaday have "ds_contribute_rdg.properties" file security config location. xmls you can add in resource folder. "contribute.properties" add like contribute-dev.properties like all the properties | Mahipal | 09/14/23 7:47 PM
Row 36 | Question: @mahipal.podduturi@penske.com / @shane.myers@penske.com , The app has the targeted folder which is having dev,prod and qa environment folders. Each folder have different conf folder which is having different files. It looks like app build is environment dependent. But in environment agnostic build, one build should be deployed to different environments. Could you please check this issue and rectify. Thanks. Note: We replaced the pom file which you provided in feature/contribreport_MavenChanges branch. | Gayam | 09/14/23 2:22 AM
Row 36 | @praneeth.gayam@penske.com can mark this complete | Mahipal | 05/04/23 7:10 PM
| @mahipal.podduturi@penske.com , make the app to Done is not the log4j team's responsibility. If it is deployed to production, you or yvette mark it as done. | Gayam | 05/05/23 6:19 AM
| @mahipal.podduturi@penske.com , As discussed with you, you said that the testing is not completed yet on this app. So changing the status to AO Maven. Also, we have a question in maven step. Please find the question below. Thanks. | Gayam | 09/14/23 2:16 AM
Row 36 | @hugo.scavino@penske.com tested the contribution report changes and confirmed it is working as expected with new modernization changes. | Mahipal | 05/04/23 7:09 PM
Row 36 | @praneeth.gayam@penske.com we see the deployed name "contribreport-batch.jar" it supposed to be "contribreport.jar" can you change POM and necessary location | Mahipal | 04/07/23 6:43 PM
| @mahipal.podduturi@penske.com , we will look into it. | Gayam | 04/07/23 10:39 PM
| @mahipal.podduturi@penske.com , Changes are completed in develop_log4j branch and created MR https://bitbucket.penske.com/projects/ARPROJ/repos/contribreport-batch/pull-requests/6/overview Please check and merge. Thanks. | Gayam | 04/10/23 11:58 PM
Row 36 | @mahipal.podduturi@penske.com , contribreport - build & Deploy plan onboarding completed. This is batch application. So it doesn't have dev environment and log4j team can't do the QA deployment. So please do the QA deployment and verify. Thanks. https://bamboo.penske.com/browse/CONTRIBREPORTBP-CONTRIBREPOR/deployments | Gayam | 04/04/23 11:17 PM
Row 36 | @praneeth.gayam@penske.com review completed and meraged can you work on next steps | Mahipal | 04/03/23 9:38 PM
Row 36 | @praneeth.gayam@penske.com can you check review comment https://bitbucket.penske.com/projects/ARPROJ/repos/contribreport-batch/pull-requests/3/overview | Mahipal | 03/22/23 9:11 AM
Row 36 | Review: @shane.myers@penske.com , this app is ready for your review. Could you please verify. Thanks. https://bitbucket.penske.com/projects/ARPROJ/repos/contribreport-batch/pull-requests/3/overview | Gayam | 03/16/23 12:56 AM
Row 36 | @praneeth.gayam@penske.com please create under Architecture Projects repo and you have my approval to add the sx.jar to artifactory in the location you specified above. Thanks! | William | 02/22/23 3:08 AM
Row 36 | @shane.myers@penske.com , contribreport app depends on the jar sx.jar and it is not available in artifactory. Could you please provide the approval to upload this jar into artifactory at following location. Thanks. groupid - com.smartxls artifactid - SX | Gayam | 02/21/23 10:14 PM
Row 36 | I believe https://svn.penske.com/svn/architecture/general/contributionreport/trunk/src is the correct source path - the other directory contained much older files. | William | 02/11/23 1:38 AM
| Thanks @shane.myers@penske.com . I think we can delete trunk\contributionreport folder as it contains older or duplicate files. | Gayam | 02/11/23 1:51 AM
| @shane.myers@penske.com , Is this application needs to be created under Architecture Projects or Commons or Security? | Gayam | 02/17/23 1:44 AM
Row 36 | @shane.myers@penske.com , There are multiple src folders for this app in trunk branch. 1. src folder under trunk\contributionreport 2. src folder under trunk Not sure which one is the correct one. Could you please clarify. Thanks. | Gayam | 02/11/23 1:16 AM
Row 36 | please start moving this forward and if you have questions or need clarification I will assist | William | 02/10/23 10:37 PM
Row 36 | After investigation, I found this confluence article, which contains a link to SVN and a bamboo build for this application. https://confluence.penske.com/display/ATSD/Contribution+Report | William | 02/10/23 10:37 PM
Row 36 | I am not sure I should be the owner of this, reaching out to Don for clarification. | William | 02/08/23 2:35 AM
Row 36 | This app has a complext folder structure. @hugo.scavino@penske.com to discuss with Don and to take the ownership. contribreport is owned by Corp. And Java app by Arch team. Requesting @hugo.scavino@penske.com 's support to resolve this confusion. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:32 AM
Row 36 | Need to ensure this is assigned to the team. | Yvette Urso | 11/30/22 12:29 AM
Row 37 | @praneeth.gayam@penske.com We are working web services now. We have no source. It was deleted 11 years ago. Keep you posted. We'll leave this one in Waiting on AO for now. | Gianfranco | 08/30/23 3:46 AM
Row 37 | @praneeth.gayam@penske.com , after further review with Architecture team, I am putting this application back to Waiting on AO. FISHEYE query: https://fisheye.penske.com/qsearch?q=PSessionCookieServlet&t=0&s=2&bucket=ANY_DATE&userFilter= Best match to SVN Repo: https://svn.penske.com/svn/ebusiness/erental/obsolete/redesign/trunk/cookieprovider/ We have to have someone go through the WAR file on the production server, reverse engineer the servlets, look at the JSPs and ensure what is in SVN matches what is in production. Then migrate the application over to the new environment. I'm not sure how much of that is actually doable by CapGemini and what will be our responsibility. | Gianfranco | 08/28/23 11:31 PM
| @frank.d'angelo@penske.com , we don't do that work as it not part of the project and we don't know anything about the application. We always get the production branch from AO incase if there is no Bamboo build. If bambo prod build exist then we take the production branch from that build. So could you please assign this work to some one from your team. thanks. | Gayam | 08/30/23 2:02 AM
Row 37 | I am marking this as Retire App for now. We believe that this is an obsolete app from when Penske affiliated with GE. | Gianfranco | 08/28/23 5:23 PM
| Thanks @frank.d'angelo@penske.com for the update. | Gayam | 08/28/23 10:41 PM
Row 37 | @praneeth.gayam@penske.com , we are pretty sure that this is obsolete and was just never retired in IT Contacts. The documentation is from 2008 and references PSession and registrar.ge.com, which I don't believe we use anymore. Don did a Fisheye scan and can't find any source for PSession. We did find an old link, but I don't have SVN access. Can the team check to see if this is valid? We'll check Monday as well. https://svn.penske.com/svn/ebusiness/erental/redesign/branches/dev_gh/cookieprovider/src/com/penske/cookie/servlets/PSessionCookieServlet.java | Gianfranco | 08/26/23 6:18 PM
Row 37 | @praneeth.gayam@penske.com , wanted to share the latest with you. We found this application only running on Prod. ghlx152ptlge:/opt/websphere/profiles/wsv/installedApps/ghlx051ptlgeNetwork-remoting/cookie.ear/cookie.war. Don looked at the WEB-INF/classes (com.penske.cookie.servlets.PSessionCookieServlet) and then did a fisheye scan. See image. We are not sure if this is actually an active application. We find it hard to believe that we would be using a remoting service on Prod but not have it installed on QA. Most of the SVN directories in the image are for eRental and are 11+ years old. Checking to see if obsolete. | Gianfranco | 08/25/23 8:25 PM
Row 37 | @praneeth.gayam@penske.com I have also not found this when I previously searched. I’ll try once more. | Gianfranco | 08/14/23 11:38 PM
Row 37 | @jeremiah.ashway@penske.com / @frank.d'angelo@penske.com , We couldn't find Bamboo and code repo for this app. Could you please help us to find them. Thanks. | Gayam | 07/27/23 11:22 PM
Row 38 | @hugo.scavino@penske.com , For this application we observed that log4j and maven changes are completed by you. https://bitbucket.penske.com/projects/AR-SEC/repos/csar/commits?until=refs%2Fheads%2Frelease%2Flog4j-remediation Could you please check and confirm whether my team needs to do anything else. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/14/23 1:24 AM
| No code changes required. This application is waiting for fleet insight to complete and then move to QA to regression test. But the secure bamboo is required. That was not available last year. The maven build is agnostic and there are NO secrets. | Hugo Scavino | 01/17/23 3:19 AM
| Sure @hugo.scavino@penske.com . Do you want my team to built Bamboo plans for this application? @haribabu.challa@penske.com , @mathumala.nachiappan@penske.com | Gayam | 01/17/23 3:23 AM
| Yes please, build the "secure bamboo" plans and I will retest. | Hugo Scavino | 01/18/23 2:10 AM
| @hugo.scavino@penske.com , csar application bamboo onboarding and dev deployment completed. war file location: https://artifactory.penske.com/artifactory/architecture-mvn-development-local/com/penske/architecture/csar/1.0.0-develop-SNAPSHOT/csar-1.0.0-develop-20230208.160821-1.war ghlx008ptlge.penske.com: /opt/websphere/profiles/internal/checkpoints/Delta-1675872550437/cells/ghlx008ptlgeCell-internal/applications/csar.ear/deployments/csar @haribabu.challa@penske.com | Gayam | 02/08/23 11:54 PM
Row 39 | Review: @dylan.price@penske.com , This app is ready for your review. Please review and merge. https://bitbucket.penske.com/projects/PBT/repos/csb-web/pull-requests/3/overview | Gayam | 07/14/23 6:44 AM
Row 39 | Hi @praneeth.gayam@penske.com 2. Yes please include production.properties with this application. I see the file out on our current build. 3. I checked with Mark Weaver and this file is no longer needed. Please delete out rentalservice.xml | Dylan | 06/07/23 1:01 AM
| Thanks @dylan.price@penske.com . we will work on them. | Gayam | 06/07/23 5:51 AM
Row 39 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/28/23 3:31 AM
| Thanks @venkatesh.hossalinever@penske.com . Could you please resolve the query which I asked above. | Gayam | 02/28/23 11:48 PM
| applicationcontext.xml file use from production target folder. | Venkatesh | 03/17/23 7:43 PM
| Thanks @venkatesh.hossalinever@penske.com . What about other 2 questions in the same messgae? | Gayam | 03/17/23 11:53 PM
Row 39 | Question: @mark.weaver@penske.com Adding to above secrets mitigation, we have below questions. Could you please clarify. 1.Under the targeted folder this app have different applicationcontext.xml files for different environments . Which one we need to use ? 2. production.properties file exist in prod folder, but not in qa and dev. So can we move that to resources folder ? 3.There is rentalservice.xml under dev and qa. It is not exist in prod folder . so do we need to delete this or need to keep it under resources ? | Gayam | 02/17/23 2:23 AM
Row 39 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 39 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:53 AM
Row 40 | @praneeth.gayam@penske.com Application is failing to run on QA environment. Immediate attention needed as we are getting ready to push for next step. | Rajesh | 08/29/23 12:32 AM
| @rajesh.haravde@penske.com , as discussed in the email, the error related to dlinks auth filter. AOs are discussing with Architecture tema on this issue. | Gayam | 08/30/23 2:21 AM
Row 40 | We are seeing only master and develop branch in bamboo. what happens to rest of bitbucket branches. | Rajesh | 06/14/23 12:12 AM
| @rajesh.haravde@penske.com , As part of the process when we onboard to bamboo only master and develop will be onboarded. If you want any other branch, please let us know. we will add. | Gayam | 06/15/23 12:50 AM
Row 40 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:08 AM
| @rajesh.haravde@penske.com , this app is deployed to dev using develop branch - https://bamboo.penske.com/browse/CVIBP-CVIW2/deployments | Gayam | 06/10/23 1:40 AM
Row 40 | Its merged. please take it forward. | Rajesh | 04/26/23 8:24 PM
| @rajesh.haravde@penske.com , this app is deployed to dev using develop_log4j branch - https://bamboo.penske.com/browse/CVIBP-CVIW1/deployments Please verify and merge the code to develop branch. | Gayam | 04/27/23 1:34 AM
Row 40 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 40 | Bitbucket and maven validation completed. awaiting on development environment configuration to move forward. | Rajesh | 04/25/23 5:58 PM
| Thanks @rajesh.haravde@penske.com . PR is still in open status. Could you please merge. In the mean time we will onboard to bamboo. | Gayam | 04/26/23 1:20 AM
Row 40 | @rajesh.haravde@penske.com / @venkata.bobba@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/PTLCORP/repos/cvi-web/pull-requests/5/overview | Gayam | 03/03/23 1:36 AM
Row 40 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So changing the status to (Cap) Maven | Gayam | 02/16/23 11:26 PM
Row 40 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:47 PM
Row 40 | Validation work in progress | Rajesh | 01/18/23 8:21 PM
Row 40 | @rajesh.haravde@penske.com , log4j and maven changes are completed for this application. Could you please review them in the below PR and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/cvi-web/pull-requests/5/overview @mathumala.nachiappan@penske.com | Gayam | 12/14/22 10:36 AM
Row 40 | Need to determine who will work this app. Was notified by @hugo.scavino@penske.com we may not have an resource. | Yvette Urso | 11/22/22 2:43 AM
| we are the owner of the application. please let us know if you need any information on source URL. but we do want to move to maven and bitbucket. | Rajesh | 12/12/22 10:16 PM
Row 41 | Decision is to retire these applications | Yvette Urso | 05/01/23 9:17 PM
Row 41 | smvendors feeds cyclops.war. So dependent to this app. | Yvette Urso | 05/01/23 9:13 PM
Row 41 | @scott.bortzel@penske.com / @scott.pemrick@penske.com , For this application both SVN and Bamboo are not available. Could you please let us know the SVN and Bamboo details. Thanks. | Gayam | 01/14/23 1:06 AM
| @scott.bortzel@penske.com / @scott.pemrick@penske.com , Could you please provide the response to above question. Thanks. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 03/24/23 10:54 PM
Row 42 | @yvette.urso@penske.com / @mathumala.nachiappan@penske.com , This is mentioned as Dup App but I am not seeing any duplicate entry for delegatedAdmin. Could you please check. | Gayam | 02/13/23 11:46 PM
Row 42 | Duplicate of delegatedAdmin | Mathumala Nachiappan | 11/23/22 3:15 AM
Row 43 | @praneeth.gayam@penske.com Can you run the secret scan and see if it reports anything | Sherin | 06/23/23 12:49 AM
| Sure @sherin.basheer@penske.com | Gayam | 06/23/23 11:41 PM
| @sherin.basheer@penske.com , We did rescan and sent the file in the email. Please verify. Thanks. | Gayam | 06/27/23 5:27 AM
| @praneeth.gayam@penske.com please send the secret scan email to me and Elan Arulsamy | David Graf | 10/13/23 8:06 PM
| @david.w.graf@penske.com , Sent the secrets file in email. Please check. | Gayam | 10/14/23 1:56 AM
Row 43 | @praneeth.gayam@penske.com Was secrets removed from this application? | Sherin | 06/23/23 12:12 AM
| @sherin.basheer@penske.com , I am not sure but seeing some Hugo's commits in develop_log4j branch. | Gayam | 06/23/23 12:40 AM
Row 43 | Please send the secrets along. I will checkout the branch and remediate. | Hugo Scavino | 04/06/23 3:23 AM
| @hugo.scavino@penske.com , emailed the secrets to you. Thanks. | Gayam | 04/07/23 1:42 AM
Row 43 | @hugo.scavino@penske.com, We have completed the secrets scanning on this application and found that there are true positive exist. I will share the excel report in the email. Could you please check and remediate the secrets. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/06/23 1:10 AM
| @hugo.scavino@penske.com , When you get a chance, could you please check these. Thanks. | Gayam | 04/06/23 3:11 AM
Row 43 | @hugo.scavino@penske.com - True positives found in commented code need confirmation on this | Mathumala Nachiappan | 11/23/22 3:16 AM
Row 44 | QA testing compelted | Gayam | 05/14/23 9:23 PM
Row 44 | @praneeth.gayam@penske.com can you mark this to complete | Mahipal | 05/04/23 7:03 PM
| @mahipal.podduturi@penske.com , make the app to Done is not the log4j team's responsibility. If it is deployed to production, you or yvette mark it as done | Gayam | 05/05/23 6:20 AM
Row 44 | This app can be marked complete - I have completed my testing in QA and gotten end user signoffs. | William | 03/01/23 2:42 AM
Row 44 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:29 AM
Row 44 | This is waiting on 1 final user signoff in QA. It has passed my testing and the testing of 2 other users. I will follow up with the tester for an update | William | 12/09/22 2:37 AM
| Thanks William. FYI - @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/12/22 4:31 PM
Row 44 | @shane.myers@penske.com - QA deployment done on 1st Nov. | Mathumala Nachiappan | 11/23/22 3:19 AM
Row 45 | Agree this should be marked duplicate and removed | William | 03/01/23 2:43 AM
Row 45 | @yvette.urso@penske.com , I think this is a duplicate row item. dasservice.war already exist in another row and comments/status updated correctly in that line item. Please mark this as Dup app. | Gayam | 02/13/23 11:44 PM
Row 46 | @gregg.obst@penske.com , Onboarded to bamboo and deployed to dev. https://bamboo.penske.com/browse/DTABP-DIGIW/deployments | Gayam | 09/26/23 1:31 AM
| Guyam, the Bamboo builds are failing when I run https://bamboo.penske.com/download/DTABP-DIGIW-BLD/build_logs/DTABP-DIGIW-BLD-2.log with the message "Finished task 'Set Artifact Version' with result: Failed". It seems to be something when interfacing with Artifactory. | Gregg | 09/28/23 10:00 PM
| @gregg.obst@penske.com , you are trying to build the master branch which doesn't have the latest mavanized code. That is the reason build is failing. Please build develop branch. | Gayam | 09/29/23 1:05 AM
| I was able to successfully build the develop branch and deploy to both dev and QA servers and I successfully tested Digitech in QA. We don't have any valid data in dev but do in QA. | Gregg | 10/05/23 2:30 AM
| Thanks for the update @gregg.obst@penske.com . Please let us know once it is deployed to prod. | Gayam | 10/06/23 12:35 AM
Row 46 | I have the environment specific code removed from digitech and I'm about to commit that to the BitBucket repo in develop_log4j.I have the environment specific code removed from digitech and I'm about to commit that to the BitBucket repo in branch develop_log4j. I need to be sure that you are OK with me changeing the existing Bamboo build for https://bamboo.penske.com/browse/DTABP-DIGDEV to po nt to the BitBucket repo instead of SVN because you mentioned building a environment agnostic Bamboo build. Are you OK with me testing my changes with the older build pointed to BitBucket and building off that develop_log4j branch ? | Gregg | 08/17/23 2:43 AM
| @gregg.obst@penske.com , I think you already merged your changes to develop branch. We will take care of merging them to develop_log4j branch and eventually we will mavanize the application. Once mavanization completed, we will provide the PR for your review. I am not sure if you point your current builds from svn to bitbucket whether it is going to work. | Gayam | 08/18/23 12:52 AM
| I'll wait until you Mavenize the app then we can test it with the new Maven build project pointing to BitBucket. | Gregg | 08/18/23 1:24 AM
| Sure @gregg.obst@penske.com . We will do mavanization on top of you changes and will let you know. | Gayam | 08/18/23 8:59 PM
| @praneeth.gayam@penske.com Is there an update on when Digitech mavenization and the new Bamboo build will be complete so we can test ? | Gregg | 09/07/23 6:43 PM
| @gregg.obst@penske.com , Following is the PR. Please review and merge. https://bitbucket.penske.com/projects/MAIN/repos/digitech-web/pull-requests/6/overview | Gayam | 09/08/23 12:35 AM
| The PR has been merged. | Gregg | 09/08/23 1:26 AM
| I just loaded the develop branch after the merge of that pull request and I notices in pom.xml it is missing a variable "war.packaging.excludes". Do you know what value that needs to be set to? | Gregg | 09/08/23 2:31 AM
| @gregg.obst@penske.com ,Will check get back to you | Gayam | 09/09/23 2:18 AM
| @gregg.obst@penske.com , included the missed value. Please check. | Gayam | 09/12/23 12:11 AM
| Gayam I was able to successfully build the digitech war with maven now. Thanks for that update. Do we have a new maven build in Bamboo for this yet so I can try building this in dev and QA ? | Gregg | 09/22/23 5:38 PM
| @gregg.obst@penske.com , It is not yet onboarded to bamboo. We wait till the AO confirms the code. We will onboard to bamboo as you confirmed. Thanks | Gayam | 09/22/23 11:28 PM
Row 46 | Is the version in Git now where you are leaving it off? I thought you were Mavening these as well? Please confirm that I am supposed to mavenize it and rewrite the application in such a way that it is not using environment specific property files. | Gregg | 08/15/23 2:53 PM
Row 46 | @gregg.obst@penske.com / @sarath.mani@penske.com , This application has dta_qa.properties, dta_dev.properties and dta_prod.properties files which are specific to the enviroment. But as we are going to do the environment agnostic build we should use only 1 file under resources. So, please resolve this issue. Thanks. | Gayam | 07/14/23 12:50 AM
Row 46 | AO confirmed that there are no code changes required for secrets in the email. | Gayam | 06/14/23 2:02 AM
Row 46 | @gregg.obst@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:52 AM
Row 47 | @praneeth.gayam@penske.com done merged to develop | Mahipal | 05/23/23 6:42 PM
| Thanks @mahipal.podduturi@penske.com . we will onboard to Bamboo and will let you know | Gayam | 05/24/23 1:10 AM
| @mahipal.podduturi@penske.com , This is onbaorded to bamboo. Please deploy to QA. Thanks. | Gayam | 05/25/23 3:32 AM
Row 47 | @shane.myers@penske.com , We changed the scope of log4j jars from provided to compile scope. Could you please review and merge in below PR. https://bitbucket.penske.com/projects/AR-SEC/repos/dlinkappremoval/pull-requests/8/overview Also, not sure why this app (Cap/AO)Dev deploy/test status. The develop branch is not yet onboarded to Bamboo. It should be in Cap Bamboo status. Once you confirm the above merge, we will onboard develop branch to bamboo and will build it. Thanks | Gayam | 05/22/23 11:44 PM
Row 47 | @shane.myers@penske.com , We completed secrets scanning on this app and looks like all are false positives. I will send the sheet in email and please check and confirm. Thanks. | Gayam | 01/10/23 12:32 AM
| Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:30 AM
Row 47 | @shane.myers@penske.com I moved to AO Final Testing Status - Let us know what your next steps are. | Yvette Urso | 12/15/22 2:28 AM
Row 47 | @praneeth.gayam@penske.com - Pls. check is anything for us to support | Mathumala Nachiappan | 12/12/22 4:32 PM
Row 47 | application does not run in QA. Here is the output when the start script is invoked:[600123729@clelx150ptlge dlinkappremoval]$ sudo -u apps ./dlinkappremoval.sh [600123729@clelx150ptlge dlinkappremoval]$ Usage: java [-options] class [args... ] (to execute a class) or java [-options] -jar jarfile [args...] (to execute a jar file) where options include: -d32 use a 32-bit data model if available -d64 use a 64-bit data model if available -server to select the "server" VM The default VM is server, because you are running on a server-class machine. -cp <class search path of directories and zip/jar files> -classpath <class search path of directories and zip/jar files> A : separated list of directories, JAR archives, and ZIP archives to search for class files. -D<name>=<value> set a system property -verbose:[class¦gc¦jni] enable verbose output -version print product version and exit -version:<value> Warning: this feature is deprecated and will be removed in a future release. require the specified version to run -showversion print product version and continue -jre-restrict-search ¦ -no-jre-restrict-search Warning: this feature is deprecated and will be removed in a future release. include/exclude user private JREs in the version search -? -help print this help message -X print help on non-standard options -ea[:<packagename>...¦:<classname>] -enableassertions[:<packagename>...¦:<classname>] enable assertions with specified granularity -da[:<packagename>...¦:<classname>] -disableassertions[:<packagename>...¦:<classname>] disable assertions with specified granularity -esa ¦ -enablesystemassertions enable system assertions -dsa ¦ -disablesystemassertions disable system assertions -agentlib:<libname>[=<options>] load native agent library <libname>, e.g. -agentlib:hprof see also, -agentlib:jdwp=help and -agentlib:hprof=help -agentpath:<pathname>[=<options>] load native agent library by full pathname -javaagent:<jarpath>[=<options>] load Java programming language agent, see java.lang.instrument -splash:<imagepath> show splash screen with specified image See http://www.oracle.com/technetwork/java/javase/documentation/index.html for m ore details. | William | 12/09/22 2:53 AM
Row 47 | @shane.myers@penske.com - Deployed in QA on 21st Nov. Pls. go ahead with your testing and confirmation | Mathumala Nachiappan | 12/02/22 5:53 PM
Row 47 | @mathumala.nachiappan@penske.com - To check the deployment status | Mathumala Nachiappan | 11/23/22 3:22 AM
Row 48 | Application deployed to QA and working everything fine. | Sama | 05/16/23 7:45 PM
Row 48 | Hi @praneeth.gayam@penske.com dev deployment looks good so please proceed to deploy to QA. | Sama | 05/09/23 8:05 PM
| @bhagya.sama@penske.com , As per management, AO needs to take care of QA deployment. | Gayam | 05/09/23 10:58 PM
Row 48 | @praneeth.gayam@penske.com code is merged to develop branch. Please onboard the branch to Bamboo and deploy to dev.Thanks! | Sama | 05/02/23 1:34 AM
| @bhagya.sama@penske.com Dev deployment is done from develop branch. | Gayam | 05/03/23 1:28 AM
Row 48 | Hi Praneeth PR is approved and you can proceed for next steps.Thanks! | Sama | 04/29/23 12:04 AM
| Thanks @bhagya.sama@penske.com . Can you merge the code https://bitbucket.penske.com/projects/ARPROJ/repos/dlinks/pull-requests/42/overview Once you merge, we will onboard develop branch to Bamboo and deploy to dev from this branch. Thanks. | Gayam | 05/02/23 1:03 AM
Row 48 | Hi @praneeth.gayam@penske.com Dev deploy is successful and confirming that Please proceed to deploy to QA on Tuesday(04/25). Thanks! | Sama | 04/21/23 2:11 AM
| @bhagya.sama@penske.com , dev deployment is done from develop_log4j branch for your testing to complete. Could you please approve the PR https://bitbucket.penske.com/projects/ARPROJ/repos/dlinks/pull-requests/42/overview So thatwe will onbaord develop branch to Bamboo and deploy to dev from develop branch. | Gayam | 04/22/23 2:10 AM
Row 48 | Sure @praneeth.gayam@penske.com ,thank you for letting us know. | Sama | 04/19/23 3:56 AM
| @bhagya.sama@penske.com , We corrected the build and dev deployment is completed from develop_log4j branch. Please check. https://bamboo.penske.com/browse/DBP-DLINK/ | Gayam | 04/20/23 2:01 AM
Row 48 | Please compare with https://bamboo.penske.com/build/admin/edit/defaultBuildArtifact.action?buildKey=SECUTIL-CSARSECUTL-BLD and see WAR is missing from artifact definitions.https://bamboo.penske.com/build/admin/edit/defaultBuildArtifact.action?buildKey=DBP-DLINK-BLD | Sama | 04/14/23 12:21 AM
| Hi @bhagya.sama@penske.com , I don't have access to above urls. But I am seeing that develop_log4j branch is deployed to dev. https://bamboo.penske.com/browse/DBP-DLINK1/deployments | Gayam | 04/14/23 12:38 AM
| We corrected the issue. My team is deploying the app to Dev. We will let you know as soona s it completes. | Gayam | 04/19/23 3:36 AM
Row 48 | Hi @praneeth.gayam@penske.com I see that war is not deployed and can you see that here artifact is not defined. https://bamboo.penske.com/build/admin/edit/defaultBuildArtifact.action?buildKey=DBP-DLINK-BLD | Sama | 04/13/23 11:56 PM
Row 48 | Please build the new Bamboo plan for this web application. I reviewed the application and I can compile locally. @bhagya.sama@penske.com Please checkout the latest develop/log4j branch when you are ready and deploy locally. | Hugo Scavino | 04/07/23 11:31 PM
| Sure @hugo.scavino@penske.com Thanks! | Sama | 04/07/23 11:54 PM
| @hugo.scavino@penske.com / @bhagya.sama@penske.com , We have onboarded this app to Bamboo. Please check build plan: https://bamboo.penske.com/browse/DBP-DLINK/ deploy plan log: https://bamboo.penske.com/browse/LOG-DEPY-159/log App is deployed to Dev | Gayam | 04/12/23 11:11 PM
Row 48 | @david.w.graf@penske.com , this app is still in AO Review stage and new bamboo plans are not yet onboarded. | Gayam | 03/21/23 1:31 AM
| thanks. It must be the dev environment. @bhagya.sama@penske.com Please check the Dev environment to ensure that there is a working version there. For now, it can match the same as the last production deploy. https://confluence.penske.com/display/ATSD/DLinks | David Graf | 03/21/23 5:50 AM
Row 48 | The Dev environment does not seem to be working this morning when I tried. I'm not sure if it is related to this project or not. | David Graf | 03/20/23 6:03 PM
Row 48 | @sherin.basheer@penske.com - - This app is available for your final review. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/02/22 5:41 PM
Row 48 | @yvette.urso@penske.com - This app is ready for AO Review. What can be the App Status from the available ones? | Mathumala Nachiappan | 11/23/22 3:23 AM
| @mathumala.nachiappan@penske.com Please email the AO if you are ready for them to start their work. I do not need to be emailed. | Yvette Urso | 11/30/22 12:24 AM
Row 49 | until further notice please do not do any work on Dlinks Auth Filter, that includes running bamboo builds. We are attempting to deploy to production soon and that will require complete control from AO. CC: @praneeth.gayam@penske.com CC: @sherin.basheer@penske.com CC: @ritesh.bhattacharyya@penske.com | David Graf | 06/12/23 11:57 PM
Row 49 | @praneeth.gayam@penske.com I had to update the VARIABLES section in Bamboo for the dlinks auth filter to deploy to the shared library IN DEV Specifically, I had to update the variable instance to have the value shared. This will be true of all shared libraries. https://bamboo.penske.com/deploy/config/configureEnvironmentVariables.action?environmentId=129826820 | Hugo Scavino | 02/06/23 8:19 PM
| @praneeth.gayam@penske.com - Pls. check Hugo's message | Mathumala Nachiappan | 02/07/23 10:36 PM
| Yes @mathumala.nachiappan@penske.com . I already updated this message to @haribabu.challa@penske.com . | Gayam | 02/07/23 10:44 PM
| @hugo.scavino@penske.com , We have updated the spec file of dlinks_filter with 'shared' instance variable. https://bamboo.penske.com/deploy/config/configureEnvironmentVariables.action?environmentId=129826820 @haribabu.challa@penske.com | Gayam | 02/08/23 11:49 PM
Row 49 | Thanks @hugo.scavino@penske.com for your support. I have changed the App Status. | Mathumala Nachiappan | 02/08/23 11:14 AM
Row 49 | Great timing. The build suceeded. I will be deploying to DEV and QA tomorrow if all goes well https://bamboo.penske.com/browse/DFBP-DLINKAUTH0-3 | Hugo Scavino | 01/31/23 1:19 AM
Row 49 | This bamboo project did not run the first time due to an auth error trying to push to artifactory. I checked and there is a parent pom setup for batch. https://bamboo.penske.com/browse/DFBP-DLINKAUTH0-2/log Let me know if there is something wrong with the pom. | Hugo Scavino | 01/25/23 3:34 AM
| @hugo.scavino@penske.com https://bamboo.penske.com/browse/DFBP-DLINKAUTH0 We have changed the settings.xml file in build plan. Could you please run the develop branch and let us know if you still see any issues. @haribabu.challa@penske.com | Gayam | 01/27/23 10:29 PM
Row 49 | Issue: Code needs to modernized to move forward. Put in AO Code Work so @hugo.scavino@penske.com can work on it. | Yvette Urso | 12/15/22 2:32 AM
Row 49 | @praneeth.gayam@penske.com and @hugo.scavino@penske.com - As per the latest discussion, No FP tickets needed. ITs a peer review from the AO side. | Mathumala Nachiappan | 12/08/22 3:44 PM
Row 49 | I have made log4j changes and also maven agnostic changes. This will need a peer review with the architecture team before moving even to DEV. | Hugo Scavino | 11/24/22 2:34 AM
| Thanks @hugo.scavino@penske.com ! | Mathumala Nachiappan | 12/02/22 5:25 PM
| As discussed with @hugo.scavino@penske.com , this is getting reviewed by other architecture team. Once that confirms, hugo will merge the code. @mathumala.nachiappan@penske.com , I believe this should be in AO Maven status as Hugo is taking care of Maven things. | Gayam | 12/07/22 11:13 PM
Row 49 | @praneeth.gayam@penske.com - Pls. create a FP ticket for arch team review | Mathumala Nachiappan | 11/30/22 3:19 PM
Row 50 | @sherin.basheer@penske.com / @david.w.graf@penske.com , This dependency jar is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/docservice-client/pull-requests/2/overview | Gayam | 07/21/23 12:10 AM
| @shane.myers@penske.com / @david.w.graf@penske.com , Could you please review this and merge the code. Thanks. | Gayam | 08/17/23 1:45 AM
Row 51 | Review: @venkata.bobba@penske.com / @rajesh.haravde@penske.com , this app is ready for your review. Please check. https://bitbucket.penske.com/projects/PTLCORP/repos/domicileservice/pull-requests/2/overview | Gayam | 04/25/23 12:56 AM
Row 51 | Review: @venkata.bobba@penske.com / @Raje | Gayam | 04/25/23 12:56 AM
Row 51 | @venkata.bobba@penske.com confirmed that there are no changes required for secrets in the email. | Gayam | 04/15/23 12:58 AM
Row 51 | Added per AO requested it. As this jar used in other corp projects which are migrating to java8 and this jar is not in java8. It may causes issues. | Yvette Urso | 03/29/23 12:54 AM
Row 52 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:08 AM
| @rajesh.haravde@penske.com , this is already onboarded to Bamboo. Please check at https://bamboo.penske.com/browse/DOM-DOMS0/ | Gayam | 06/09/23 1:55 AM
Row 52 | The PR is merged. We will deploy to dev and let you know. Thanks. | Gayam | 05/18/23 11:35 PM
| @rajesh.haravde@penske.com , Build is failing for this app due to test cases failure. Could you please work with your team to fix them. Thank you. https://bamboo.penske.com/browse/DOM-DOMS0-UTEST-2 | Gayam | 05/22/23 9:32 PM
Row 52 | The secrets of this app are false positives. please proceed with next steps of modernization | Rajesh | 04/15/23 12:50 AM
Row 52 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/domservice-web/pull-requests/3/overview Thanks. | Gayam | 02/16/23 11:30 PM
Row 52 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:48 PM
Row 52 | Validation work in progress | Rajesh | 01/18/23 8:21 PM
Row 52 | @krishna.tanga@penske.com / @yogesh.sinha@penske.com , Please review the code in MR https://bitbucket.penske.com/projects/PTLCORP/repos/domservice-web/pull-requests/3/overview and merge. | Gayam | 11/28/22 8:04 AM
| we will do the needful as requested and get back to you. | Rajesh | 12/12/22 10:17 PM
Row 53 | Kalrav looking into next steps for this application. | Yvette Urso | 06/05/23 9:07 PM
| @yvette.urso@penske.com This application is added to Penske Migration smart sheet and we've added comments in that file. Please update the App Status accordingly OR remove from this smart sheet. | Sreekanth | 06/08/23 11:17 PM
Row 53 | @yvette.urso@penske.com / @kalrav.khamar@penske.com , As per our discussion, ebill app is removed from Log4j team's scope. Thanks. @mathumala.nachiappan@penske.com @balu.mohan@penske.com | Gayam | 02/17/23 7:09 PM
| @yvette.urso@penske.com , If this app is removed from log4j team's scope, please remove from this list. | Gayam | 03/24/23 10:57 PM
Row 53 | @mathumala.nachiappan@penske.com moved status for this as well. Should be in the AO Bamboo status. | Yvette Urso | 12/15/22 2:22 AM
Row 53 | @rafiq.melath@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:33 AM
Row 54 | @yvette.urso@penske.com I don't see AO Code Work as a status | David Graf | 12/15/22 2:53 AM
Row 54 | Issue: Code needs to modernized to move forward. Put in AO Code Work so @david.w.graf@penske.com can work on it. | Yvette Urso | 12/15/22 2:32 AM
Row 54 | That right, I am working to remove the jar that cannot be placed in artifactory. | David Graf | 12/09/22 1:38 AM
Row 54 | Will be resumed once the dependency is cleared from AO | Mathumala Nachiappan | 12/08/22 8:00 PM
Row 54 | @david.w.graf@penske.com - ebsworker.jar dependency | Mathumala Nachiappan | 11/23/22 3:28 AM
Row 55 | @praneeth.gayam@penske.com maven has been confirmed, moving to Cap Bamboo. | David Graf | 09/27/23 5:13 PM
| @david.w.graf@penske.com , Onboarded to bamboo. Please check. https://bamboo.penske.com/browse/ECBP-EBADMN1 | Gayam | 09/29/23 1:35 AM
Row 55 | This cannot move forward until I remove the references to ebsworker.jar | David Graf | 02/09/23 12:02 AM
Row 55 | Blocker: ebsworker.jar | Yvette Urso | 02/01/23 8:30 PM
Row 55 | I'm will address this after the ebs.war is complete | David Graf | 12/09/22 1:38 AM
Row 55 | Will be resumed once the dependency is cleared from AO | Mathumala Nachiappan | 12/08/22 8:01 PM
Row 55 | @david.w.graf@penske.com - ebsworker.jar dependency | Mathumala Nachiappan | 11/23/22 3:28 AM
Row 55 | Testing | Yvette Urso | 11/11/22 9:42 PM
Row 56 | maven is confirmed. changing to Cap Bamboo fyi: @praneeth.gayam@penske.com | David Graf | 09/27/23 5:01 PM
| @david.w.graf@penske.com , Onboarded develop_log4j branch to bamboo - https://bamboo.penske.com/browse/ECBP-EBSSVC1 Please check. | Gayam | 10/03/23 1:37 AM
Row 56 | sure I will check @david.w.graf@penske.com | Sama | 05/30/23 6:40 PM
Row 56 | @bhagya.sama@penske.com please see check the ebsservice.war is being created by Maven correctly. | David Graf | 05/26/23 7:37 PM
Row 56 | Review: @david.w.graf@penske.com , This app ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/ebsservice/pull-requests/7/overview | Gayam | 03/04/23 1:26 AM
Row 56 | I reviewed. There are no secrets in ebsservice | David Graf | 02/24/23 2:38 AM
| Thank you. Changed to (Cap)Maven | Gayam | 02/25/23 12:55 AM
Row 56 | Secrets: @david.w.graf@penske.com , I sent the secrets file previously. Please check and let us know your thoughs on secrets. Thanks. | Gayam | 02/23/23 1:44 AM
Row 56 | @praneeth.gayam@penske.com - To review the maven rework done. | Mathumala Nachiappan | 11/23/22 3:26 AM
Row 57 | @praneeth.gayam@penske.com Amit confirmed maven is creating the same artifact. Please move on to Bamboo stage. | David Graf | 09/26/23 5:07 PM
| Sure @david.w.graf@penske.com | Gayam | 09/27/23 12:46 AM
| @david.w.graf@penske.com , Onboarded develop_log4j to bamboo successfully - https://bamboo.penske.com/browse/ECBP-EBSCLNT1 | Gayam | 09/28/23 12:56 AM
Row 57 | @bhagya.sama@penske.com , This app is ready for your review. Please check. https://bitbucket.penske.com/projects/AC/repos/ebs_service_client/pull-requests/4/overview | Gayam | 06/14/23 4:16 AM
Row 58 | This app is completely done with all steps of modernization. | David Graf | 03/21/23 5:43 AM
Row 58 | Looks like RBAC is in place and working. I am moving this to complete. The next deploy of this app will have version 2.0.0 to signify it is modernized. | David Graf | 02/18/23 1:53 AM
Row 58 | Today's update is that we figured out the instance issue in the spec so that the jar deploys to var/tmp. Last Bamboo Item to complete is the RBAC groups. Please assign RBAC groups to ebsworker. | David Graf | 02/08/23 11:59 PM
Row 58 | @praneeth.gayam@penske.com Per @david.w.graf@penske.com this was deployed 1/19/23. I believe he may be out of the office so please give him time to complete. | Yvette Urso | 01/24/23 8:19 PM
Row 58 | @david.w.graf@penske.com , Please create a release branch from develop and run the build from release. It will create a production version of the code. Production deploy plan are already ready but till now no log4j projects deployed to production. @mathumala.nachiappan@penske.com / @hugo.scavino@penske.com | Gayam | 12/22/22 10:16 PM
Row 58 | I have merged my changes to develop and tested the Dev and QA deployments. Please confirm that prod deployment is set up correctly so that we can deploy in Jan. Also this Bamboo plan needs role based access. Right now, I have an override for my account which gives me access. @mathumala.nachiappan@penske.com @praneeth.gayam@penske.com | David Graf | 12/21/22 7:14 PM
Row 58 | No Problem @david.w.graf@penske.com . We finished the setup today and. Build and deployment to Dev is done from the bugfix branch. Please check the Bamboo https://bamboo.penske.com/chain/viewChain.action?planKey=ECBP-EBWYP6 Let us know if you need any other information. Thanks. @mathumala.nachiappan@penske.com | Gayam | 12/16/22 11:31 PM
| @praneeth.gayam@penske.com I don't have access. Link is Access Denied message | David Graf | 12/17/22 12:56 AM
Row 58 | I created a branch with the pom changes to use the suggested group id and properties. Please update the bamboo plan from template; effectively removing the manual changes. Let me know once done and I will test it out. | David Graf | 12/14/22 8:45 PM
| Sure @dave.graff@penske.com . We will let you know once build and deployment completes. @mathumala.nachiappan@penske.com | Gayam | 12/14/22 10:56 PM
| The branch is the following: https://bitbucket.penske.com/projects/ARPROJ/repos/ebsworker/browse?at=refs%2Fheads%2Fbugfix%2Fdwg-confirm-to-issue | David Graf | 12/15/22 10:36 PM
| @praneeth.gayam@penske.com I noticed in the last message that you annotated a david graff whom is not me. Please use David W Graf. my email address is david.w.graf@penske.com Sorry for the confusion. Is there any update on this request? | David Graf | 12/16/22 8:50 PM
Row 58 | @david.w.graf@penske.com - Soon will resolve the deployment issue | Mathumala Nachiappan | 12/06/22 7:55 PM
Row 58 | is there any update on the bamboo build plan from spec that was requested for this app? | David Graf | 12/02/22 2:07 AM
Row 58 | EBS worker is in QA with slf4j and log4j2. Because it is on the IFS we can deploy to production and plan to with the current changes on 11/29. | David Graf | 11/17/22 1:45 AM
Row 59 | App deployed to PROD on 08/22/2023 | Sreekanth | 08/23/23 7:33 PM
Row 59 | @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: ecm-deploy New deployment project name: ecm-web-deploy Thank you. | Gayam | 05/14/23 9:34 PM
Row 59 | @sreekanth.kancharla@penske.com , This app is deployed to Dev. Please verify. Thanks. | Gayam | 03/30/23 12:47 AM
| @praneeth.gayam@penske.com We are waiting on resolution from @hugo.scavino@penske.com for issues we are facing in all web based applications related to SessionValidationFilter. Please change the status. @kalrav.khamar@penske.com | Sreekanth | 03/30/23 10:49 PM
| @sreekanth.kancharla@penske.com , There is no status to represent this. I think we can keep the Dev Deploy status as this is waiting from AO side. Please correct it if you have any other thoughts. | Gayam | 03/30/23 11:10 PM
Row 59 | @sreekanth.kancharla@penske.com , Also log4j/maven changes are completed. Please review them in the below MR. https://bitbucket.penske.com/projects/ITFIS/repos/ecm-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/09/22 2:57 AM
| @praneeth.gayam@penske.com I took a glance of the code & the file you shared. All the href links seems the request URLs (which we use to maintain usually in java script) & CSS file references. I don’t see any secrets in them. Hope we can leave them as it is. | Sreekanth | 12/09/22 8:17 PM
| Thanks @sreekanth.kancharla@penske.com . In that case please review the log4j,maven changes in the below MR and merge please. https://bitbucket.penske.com/projects/ITFIS/repos/ecm-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/10/22 12:42 AM
| @praneeth.gayam@penske.com The PR is merged. Please proceed with next steps. @mathumala.nachiappan@penske.com @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/04/23 3:44 AM
Row 59 | @james.minisce@penske.com - PR is raised for this app for your review and signoff to proceed for Dev deployment. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:04 PM
| Where do I review? | James | 12/01/22 9:08 PM
| @james.minisce@penske.com , Please review in the following PR and merge. https://bitbucket.penske.com/projects/ITFIS/repos/ecm-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/07/22 11:00 PM
| @sreekanth.kancharla@penske.com Can you please review and merge as per the above? Thank you. | James | 12/08/22 6:16 PM
| @praneeth.gayam@penske.com I've added comment to PR. Please check and reply back to take further action. @mathumala.nachiappan@penske.com @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 2:58 AM
| @sreekanth.kancharla@penske.com , I think you are referring to securityfilter in web.xml is different for diff regions and keeping those in targeted folder. But @hugo.scavino@penske.com suggested not to keep targeted folder and he is working on workaround to resolve this issue. Could you please check with @hugo.scavino@penske.com on this. Thanks. @mathumala.nachiappan@penske.com @yvette.urso@penske.com | Gayam | 01/27/23 10:08 PM
| Had discussion with @hugo.scavino@penske.com and came to know that Dlinkfilter is going to take care of everything. Once we get a working project and instructions on implementation, we'll implement the same in all the web applications wherever the filters are handled either with targeted folder or with java filters. @kalrav.khamar@penske.com | Sreekanth | 02/03/23 3:19 AM
Row 59 | Thanks @sreekanth.kancharla@penske.com for the updates on secrets part. I have changed the secret status as 'Not Needed'. This is FYI. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/12/22 4:28 PM
Row 59 | @sreekanth.kancharla@penske.com - In secret scanning process, Many hardcoded href links are found. Pls. check and confirm whether they need redaction. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 7:02 PM
| @mathumala.nachiappan@penske.com This is a very old application and we've no project to migrate this application. So we've to move forward with the hardcoded href links. Please advice incase this is a stopper for Log4j migration. | Sreekanth | 12/09/22 12:15 AM
| @sreekanth.kancharla@penske.com , We can share the secrets file to you with all the hardcoded links. Please check and let us know whether those are false positives. @mathumala.nachiappan@penske.com | Gayam | 12/09/22 2:32 AM
Row 60 | @praneeth.gayam@penske.com yes, this app is retired. | Venkatesh | 10/10/23 2:26 AM
| Thanks @venkatesh.hossalinever@penske.com . Changed the status to retired. | Gayam | 10/11/23 12:56 AM
Row 60 | @praneeth.gayam@penske.com edi_encryption application will get retired as new batch application is developed and its been tested on QA. | Venkatesh | 06/21/23 6:00 PM
| @venkatesh.hossalinever@penske.com , Do we need to change the status of this app to retired? @yvette.urso@penske.com / @shane.myers@penske.com | Gayam | 06/22/23 3:14 AM
Row 60 | @praneeth.gayam@penske.com We are not going to do log4j changes. Please close this request. We have redesigned this batch application. | Venkatesh | 05/16/23 6:26 PM
| @venkatesh.hossalinever@penske.com , Do you mean is this application retired or no need of log4j/maven changes and Bamboo onboarding? FYI: @yvette.urso@penske.com , @shane.myers@penske.com | Gayam | 05/18/23 12:51 AM
Row 60 | Review: @venkatesh.hossalinever@penske.com this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/edi-encryption-batch/pull-requests/3/overview | Gayam | 04/13/23 1:00 AM
Row 60 | Completed reviewing the log4j secrets, no code changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 2:06 AM
Row 60 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 60 | @praneeth.gayam@penske.com - True positives found on this application. To review once and share it to AO | Mathumala Nachiappan | 01/10/23 10:44 AM
Row 60 | Per Sam S. on 11/23/22 - I am not certain on the EDI_encryption… I think ITDS Operations actually owns the encryption routines. Sreenivasulu is my all in one EDI specialist. If Brian thinks it should be mine just insert my name. | Yvette Urso | 11/24/22 2:10 AM
Row 61 | This application is deployed to QA and ready for UAT. cc: @praneeth.gayam@penske.com @sreenivasulu.mupparaju@penske.com | Venkatesh | 10/06/23 6:18 PM
| @venkatesh.hossalinever@penske.com , We are not seeing any deployments in bamboo. Could you please check and confirm. https://bamboo.penske.com/browse/EDIBBP-EBHALBD2/deployments | Gayam | 10/10/23 12:02 AM
Row 61 | @praneeth.gayam@penske.com Changes related to old log4j property file was removed and merged the code to Develop branch, Please wait, we will confirm on deployment to QA environment. | Venkatesh | 05/16/23 6:24 PM
| @venkatesh.hossalinever@penske.com , We just onboard and build the app for batch apps. AO needs to deploy to QA. If you are ok we will onboard to Bamboo. Please confirm. | Gayam | 05/18/23 12:52 AM
Row 61 | @praneeth.gayam@penske.com Do we have any updates on above comments. Apart from above comments we are good with log4j and maven changes review. | Kadu | 05/11/23 6:55 PM
| @dhanashree.kadu@penske.com , We did complete the changes and committed to develop_log4j branch. Please verify and merge the PR. https://bitbucket.penske.com/projects/ARPROJ/repos/edi-batch/pull-requests/4/overview | Gayam | 05/11/23 11:30 PM
Row 61 | We have found below findings while reviewing Log4j and Maven changes in edi-batch application. Maven: We need below dependencies in the application which are not available in pom.xml. Can you please add them. These jars are already available in svn lib folder as well. <dependency> <groupId>commons-httpclient</groupId> <artifactId>commons-httpclient</artifactId> <version>3.0.1</version> </dependency> <dependency> <groupId>commons-dbcp</groupId> <artifactId>commons-dbcp</artifactId> <version>1.4</version> </dependency> Log4j: Can you move log4j.properties file from 'src\main\resources\conf' to 'src\main\resources'. So that application can read it properly. Batch application is using penskebatch.jar/contextframework.jar to use connection framework. And these jars are using older log4j version, it requires older log4j and mail dependencies to be available in pom.xml. Please add below dependencies in pom.xml. <!-- Logging --> <dependency> <groupId>log4j</groupId> <artifactId>log4j</artifactId> <version>1.2.17</version> </dependency> <!--mail dependencies --> <dependency> <groupId>javax.activation</groupId> <artifactId>activation</artifactId> <version>1.1.1</version> </dependency> <dependency> <groupId>com.sun.mail</groupId> <artifactId>javax.mail</artifactId> <version>1.6.0</version> </dependency> | Kadu | 05/08/23 4:17 PM
| Sure @dhanashree.kadu@penske.com . We will check your comments and will make the changes. | Gayam | 05/08/23 10:26 PM
Row 61 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. Please check. https://bitbucket.penske.com/projects/ARPROJ/repos/edi-batch/pull-requests/4/overview | Gayam | 03/24/23 11:09 PM
Row 61 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/27/23 10:25 PM
| Thanks @venkatesh.hossalinever@penske.com . Updated the status to Cap Maven. | Gayam | 02/27/23 11:36 PM
Row 61 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 61 | @rafiq.melath@penske.com / @sreenivasulu.mupparaju@penske.com , We have completed the secrets scanning and analysis on this app and found that all are false positives. I will send the sheet in the email. Could you please check and confirm. Thanks. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/10/23 1:16 AM
Row 62 | @venkatesh.hossalinever@penske.com , App is onboarded to bamboo and deployed to dev successfully. Please verify. bamboo plan: https://bamboo.penske.com/browse/EDICBOSBP-EDBSALBD Dev deployment: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151195129 | Gayam | 07/27/23 10:43 PM
Row 62 | We have found below findings while reviewing Log4j and Maven changes in edicbos web application. Maven: We need below dependency in the application which is not available in pom.xml. Can you please add it. This jar is already available in svn lib folder. <dependency> <groupId>org.springframework</groupId> <artifactId>spring-webmvc-struts</artifactId> <version>2.5</version> </dependency> We need to remove below jars from pom.xml as its conflicting the version with spring-webmvc 4.3.30 dependency. <dependency> <groupId>com.trigonic</groupId> <artifactId>spring-utils</artifactId> <version>0.3</version> </dependency> <dependency> <groupId>org.springframework</groupId> <artifactId>spring-core</artifactId> <version>${spring.version}</version> </dependency> <dependency> <groupId>org.springframework</groupId> <artifactId>spring-web</artifactId> <version>${spring.version}</version> </dependency> Log4j: We need to remove log4j.properties and InitializeLoggingServlet from the web code. We will make the code changes and commit them in develop_log4J branch. | Rane | 05/12/23 6:49 PM
| @praneeth.gayam@penske.com : Any update on the pom.xml | Kandasamy | 05/15/23 6:46 PM
| @revathi.kandasamy@penske.com , We have completed the changes in develop_log4j branch. Could you please verify. Thanks. | Gayam | 05/18/23 12:46 AM
| @praneeth.gayam@penske.com Please create the pull request. we will review the changes. | Venkatesh | 06/22/23 2:31 AM
| @venkatesh.hossalinever@penske.com , Please review https://bitbucket.penske.com/projects/PBTED/repos/edicbos-web/pull-requests/3/overview | Gayam | 06/22/23 3:55 AM
| @praneeth.gayam@penske.com Changes are merged, please deploy on dev environment. | Venkatesh | 07/26/23 7:47 PM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 07/27/23 8:56 AM
Row 62 | @venkatesh.hossalinever@penske.com , this app is ready for your review. Please verify. https://bitbucket.penske.com/projects/ARPROJ/repos/edicbos-web/pull-requests/3/overview | Gayam | 03/24/23 11:10 PM
Row 62 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/27/23 10:26 PM
| Thanks @venkatesh.hossalinever@penske.com . Updated the status to Cap Maven. | Gayam | 02/27/23 11:36 PM
Row 62 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 62 | @sreenivasulu.mupparaju@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:46 AM
Row 63 | This application is deployed to QA and ready for UAT. cc: @praneeth.gayam@penske.com @sreenivasulu.mupparaju@penske.com | Venkatesh | 10/06/23 6:18 PM
| @venkatesh.hossalinever@penske.com , We are not seeing any deployments in bamboo. Could you please check and confirm. https://bamboo.penske.com/browse/EDIPOSTCLIENT-EPCTALBD1/deployments | Gayam | 10/10/23 12:04 AM
Row 63 | @praneeth.gayam@penske.com Could you please change log4j version from 2.20.0 to 2.17.2, slf4j version from 2.0.6 to 1.7.36 and add below dependencies for mailing : <dependency> <groupId>com.sun.mail</groupId> <artifactId>javax.mail</artifactId> <version>1.6.0</version> </dependency> <dependency> <groupId>javax.activation</groupId> <artifactId>activation</artifactId> <version>1.1.1</version> </dependency> | Nayum | 09/04/23 6:19 PM
| @pathan.nayum@penske.com , Changes are completed. Please verify. | Gayam | 09/06/23 12:17 AM
Row 63 | @praneeth.gayam@penske.com Reviewed the changes and merged the code to Develop branch, Please wait, we will confirm deployment to QA environment. | Venkatesh | 05/16/23 6:21 PM
Row 63 | @praneeth.gayam@penske.com Thanks for the updates. We are good for log4j and maven changes review. Please deploy the changes in further environment. | Kadu | 05/11/23 7:01 PM
| Sure @dhanashree.kadu@penske.com . But could you please merge the PR. So that we will onboard develop branch to Bamboo. | Gayam | 05/11/23 11:28 PM
| @dhanashree.kadu@penske.com , We onboarded the develop branch to Bamboo. But build is failing. Could you please merge the PR https://bitbucket.penske.com/projects/ARPROJ/repos/edipostclient-batch/pull-requests/3/overview So that build will be successful. | Gayam | 05/13/23 2:16 AM
Row 63 | @dhanashree.kadu@penske.com , Please check the below comment from @hugo.scavino@penske.com . "BATCH apps can count on log4j 1.2 (legacy) being in the ./ptlcommon_1 and that directory will load first. BATCH apps do not need to add log4j (legacy) as a dependency in their pom's. penskebatch.jar/contextframework.jar will load the log4j legacy as WebServices will add ptl_common_1 at the beginning " So we don't need to add log4j 1 dependency in the pom. Please check and let us know if you have any questions. | Gayam | 05/10/23 12:17 AM
Row 63 | @praneeth.gayam@penske.com : can we proceed to retain the log4j.properties along with log4j2.xml. Kindly update us with the discussion with Hugo. | Kandasamy | 05/03/23 6:16 PM
Row 63 | @praneeth.gayam@penske.com Please confirm for log4j from Hugo. The penskebatch jar is not available in svn lib folder as this jar will be available in shared lib path and application will point from there. Almost all batch applications are using this jar for connection framework. | Kadu | 04/28/23 11:28 AM
Row 63 | We have found below findings while reviewing Log4j and Maven changes in edi-postclient batch application. Log4j: Batch application is using penskebatch.jar/contextframework.jar to use connection framework. And these jars are using older log4j version, it requires older log4j and mail dependencies to be available in pom.xml. Please add below dependencies in pom.xml. <!-- Logging for Batchframework --> <dependency> <groupId>log4j</groupId> <artifactId>log4j</artifactId> <version>1.2.17</version> </dependency> <!--mail dependencies --> <dependency> <groupId>javax.activation</groupId> <artifactId>activation</artifactId> <version>1.1.1</version> </dependency> <dependency> <groupId>com.sun.mail</groupId> <artifactId>javax.mail</artifactId> <version>1.6.0</version> </dependency> Maven: We have observed that the .tgz file created after maven build does not contain .jar file in it. Please make necessary changes to include .jar file in the bin.xml file. | Kadu | 04/27/23 6:59 PM
| @dhanashree.kadu@penske.com , If we use the log4j 1 jar then the purpose of log4j migration deviated. We need to discuss about this with @hugo.scavino@penske.com . Also, we are not seeing the penskebatch dependency in the lib folder. That is the reason we did not add that dependency and app also compiled successfully. | Gayam | 04/28/23 2:04 AM
Row 63 | @dylan.price@penske.com / @sreenivasulu.mupparaju@penske.com , this app is ready for your review. Please check. https://bitbucket.penske.com/projects/ARPROJ/repos/edipostclient-batch/pull-requests/3/overview | Gayam | 03/24/23 10:43 PM
Row 63 | @praneeth.gayam@penske.com please add cxml.jar to artifactory. We also do not need any updates for the secret file. | Dylan | 03/07/23 12:46 AM
| Thanks @dylan.price@penske.com . Changing the status to Cap Maven | Gayam | 03/07/23 11:57 PM
Row 63 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 63 | @sreenivasulu.mupparaju@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:47 AM
Row 63 | @rafiq.melath@penske.com / @sreenivasulu.mupparaju@penske.com , This application is dependent on the jar cxml.jar but this jar is not available in artifactory. Could you please provide your approval to upload this jar to artifactory. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/11/23 9:19 AM
Row 64 | Secrets: @stella.george@penske.com , I sent the secrets in the email. Please verify and let us know whether this app requires code changes. | Gayam | 06/28/23 12:44 AM
| False alert. no code change required. | Stella george | 07/06/23 8:01 PM
| Thanks @stella.george@penske.com . Changed the status to Cap Maven. | Gayam | 07/07/23 12:18 AM
Row 64 | @david.long@penske.com , Log4j team started working on modernizing this application. When we verified the old production bamboo build we are seeing following 2 repositories mentioned in the build. EDVIR_PROD - https://svn.penske.com/svn/fieldsys/maintenance/edvir/tags/PROD/_T_PROD_Build_20160721 SERVICEREQUESTUTTILITY_JAR (Jar repo)- https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/Jar/PROD I am expecting 2nd one is the dependency jar for the first repo. Is that correct? If yes, we need to do the log4j and mavanization for the dependency jars also. Could you please check and confirm. Thanks. FYI: @shane.myers@penske.com | Gayam | 05/18/23 1:36 AM
| @praneeth.gayam@penske.com Yes the second one is dependency jar. it should be included in Servicereqsvc.war.yes you need to do the log4j and mavanization to that dependency also. | Stella george | 06/14/23 1:46 AM
| Thanks @stella.george@penske.com . What option do you prefer for this app. 1. If SERVICEREQUESTUTTILITY_JAR is not used by any other application then this folder can be included inside the EDVIR app's source. It requires work from AO. Or 2. Need to extract the SERVICEREQUESTUTTILITY_JAR folder and create separate repo and bamboo build. Use this jar as a dependency in EDVIR app. It doesn't require work from AO. | Gayam | 06/14/23 2:25 AM
| Thanks @stella.george@penske.com . I got the response to create a separate bamboo build and bitbucket repo for serviceRequestUtility from you in different application 'servicereqbatch'. | Gayam | 06/14/23 3:31 AM
Row 64 | @praneeth.gayam@penske.com you should use below tag https://svn.penske.com/svn/fieldsys/maintenance/edvir/tags/PROD/20200804. I dont why bamboo build is showing wrong tag. please validate latest build tag. | Stella george | 06/14/23 2:11 AM
| Thanks @stella.george@penske.com . We will take the provided tag as base branch. | Gayam | 06/14/23 2:29 AM
Row 65 | This application is deployed to production. cc: @praneeth.gayam@penske.com @william.spohn@penske.com | Venkatesh | 10/06/23 6:17 PM
| Thanks @venkatesh.hossalinever@penske.com . Changing the status to App Deployed. | Gayam | 10/10/23 12:00 AM
Row 65 | @praneeth.gayam@penske.com , could you please change the reuse jar version for efuel in develop branch as 1.1.3 as app is redirecting to dlinks, It might be issue with reuse jar version mismatch. there might be some discrepancy. it's just a work around. if it is working fine in dev, we can move the same changes in QA as well. | Nayum | 08/18/23 1:38 PM
| @pathan.nayum@penske.com , changed the code. Please check the develop branch. Thanks | Gayam | 08/18/23 9:08 PM
Row 65 | @praneeth.gayam@penske.com Could you please change slf4j version for efuel in develop branch from 2.0.6 to 1.7.36 as the logs are not printing in dev and qa. Dev deployment is not successful as the app name is not correct in bamboo deploy script. Requested Ritesh to check that. | Kandasamy | 08/16/23 2:46 PM
| @revathi.kandasamy@penske.com My team Changed and merged the code develop branch. Please verify. Thanks. | Gayam | 08/17/23 12:46 AM
Row 65 | @praneeth.gayam@penske.com , for efuel application, Dev changes looks good and logs also rolling correctly on Dev server. | Nayum | 06/12/23 8:24 PM
| Thanks @pathan.nayum@penske.com . Please deploy to QA and test it. | Gayam | 06/13/23 1:31 AM
Row 65 | @praneeth.gayam@penske.com Changes related to old log4j property file was removed and merged the code to Develop branch, Please deploy to Dev environment. | Venkatesh | 05/16/23 6:16 PM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 05/18/23 12:54 AM
| @venkatesh.hossalinever@penske.com , The develop branch for efuel.war has already been onboarded to Bamboo, and the dev deployment was successfully completed. Please verify. | Gayam | 05/18/23 10:43 PM
Row 65 | Created the pull request for Nayum's change. Pls approve and merge. | Kandasamy | 05/15/23 6:38 PM
Row 65 | Log4j/Maven Changes are looking good. Removed log4j.properties from the web code and committed to maven branch. Please deploy the changes to dev server. | Nayum | 05/11/23 7:00 PM
| @pathan.nayum@penske.com , Can you merge your changes to develop branch. So that we will onbaord develop branch to Bamboo. | Gayam | 05/11/23 11:33 PM
Row 65 | yes, working on changes to remove hardcoded changes to load old log4j file. | Venkatesh | 05/03/23 2:33 AM
Row 65 | @venkatesh.hossalinever@penske.com , bamboo build & deploy plan onboarding completed. Dev deployment done using develop_log4j branch. https://bamboo.penske.com/browse/EFUELBP-EFLALBD/ Also, please merge the code to develop branch. https://bitbucket.penske.com/projects/ARPROJ/repos/efuel-web/pull-requests/3/overview | Gayam | 04/19/23 3:09 AM
| @praneeth.gayam@penske.com Code has been merged. Currently we are working on code changes to remove loading of existing log4j property file from the code. | Venkatesh | 04/29/23 2:36 AM
| @venkatesh.hossalinever@penske.com , are you making the changes on top of develop_log4j branch? | Gayam | 05/02/23 1:06 AM
Row 65 | Yes, Please proceed with bamboo setup | Venkatesh | 04/17/23 8:25 PM
| Thanks @venkatesh.hossalinever@penske.com . We will let you know once it is onboarded to Bamboo. | Gayam | 04/18/23 3:14 AM
Row 65 | Log4j and Maven Changes are looking good. log4j.properties file location is hardcoded in the code, and hence required code fix to read the log4j2.xml and ensure the log files are created. | Nayum | 04/13/23 6:43 PM
| @pathan.nayum@penske.com , Can we onboard this app to Bamboo and deploy? | Gayam | 04/13/23 11:27 PM
Row 65 | @william.spohn@penske.com / @venkatesh.hossalinever@penske.com , Please review log4j/maven changes at https://bitbucket.penske.com/projects/ARPROJ/repos/efuel-web/pull-requests/3/overview | Gayam | 03/02/23 3:07 AM
Row 65 | Venkatesh has completed reviewing the log4j secrets - there are no coding changes required. | William Spohn | 02/23/23 3:03 AM
| Thanks @william.spohn@penske.com . Changing the status to (Cap)Maven | Gayam | 02/23/23 3:23 AM
Row 65 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 65 | @william.spohn@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:39 AM
Row 66 | @praneeth.gayam@penske.com Thanks praneeth, changes has been deployed to production successfully. | Venkatesh | 10/04/23 1:08 AM
| Thanks @venkatesh.hossalinever@penske.com | Gayam | 10/04/23 1:47 AM
Row 66 | @praneeth.gayam@penske.com : Could you please change slf4j version for efueladmin in develop branch from 2.0.6 to 1.7.36 as the logs are not printing in dev and qa. | Kandasamy | 08/16/23 12:45 PM
| @revathi.kandasamy@penske.com My team Changed and merged the code develop branch. Please verify. Thanks. | Gayam | 08/17/23 12:45 AM
Row 66 | @praneeth.gayam@penske.com , Logs are not rolling in dev as well as no mails were triggered, hence we need to add the attached Javamail dependencies in pom.xml. Kindly, update the pom.xml and deploy the same in dev. | Nayum | 06/16/23 6:49 PM
| @pathan.nayum@penske.com , we will add and get back to you. | Gayam | 06/16/23 10:27 PM
| @pathan.nayum@penske.com , We have updated the pom.xml with the mentioned dependencies. Please check and approve the PR. https://bitbucket.penske.com/projects/PBTFUEL/repos/efueladmin-web/pull-requests/7/overview | Gayam | 06/19/23 7:41 PM
| @praneeth.gayam@penske.com Merged the changes. Can you please deploy the changes on Dev. | Venkatesh | 07/26/23 8:00 PM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 07/27/23 8:58 AM
| @venkatesh.hossalinever@penske.com / @pathan.nayum@penske.com / @william.spohn@penske.com , App is deployed to dev. Please verify. | Gayam | 07/27/23 10:45 PM
Row 66 | @praneeth.gayam@penske.com , for efueladmin application, Dev URL is working correctly, but logs are not rolling in correct location in Dev log server. | Nayum | 06/12/23 8:25 PM
| @pathan.nayum@penske.com . Please provide where the logs are rolling out. Also provide the correct location where logs need to be rolled out. | Gayam | 06/13/23 1:32 AM
Row 66 | @praneeth.gayam@penske.com , efueladmin is working fine in local. But, In dev after deployment, Dev URL is not working. PFA for page loaded in dev. URL used for dev : https://web3dev.penske.com/efueladmin/entry/ApplicationEntry?LoginUserID=505025033 | Nayum | 06/08/23 8:33 PM
| @pathan.nayum@penske.com , Please debug the issue and check the logs. We don't know any information about the application other than mavanizing the application. | Gayam | 06/09/23 1:11 AM
Row 66 | @praneeth.gayam@penske.com Changes related to old log4j property file was removed and merged the code to Develop branch, Please deploy to Dev. | Venkatesh | 05/16/23 6:14 PM
| Sure @venkatesh.hossalinever@penske.com . We will onaboard the develop branhc to Bamboo and deploy to Dev. | Gayam | 05/18/23 12:48 AM
| @venkatesh.hossalinever@penske.com , The build plan and deploy plan for efueladmin.war have been successfully onboarded to Bamboo and completed the dev deployment through the develop branch. Please verify | Gayam | 05/18/23 10:42 PM
Row 66 | @praneeth.gayam@penske.com : Created Pull request for the changes. | Kandasamy | 05/15/23 6:42 PM
Row 66 | Log4j/Maven Changes are looking good. Removed log4j.properties from the web code and committed to maven branch. Please deploy the changes to dev server. | Nayum | 05/11/23 6:58 PM
| @pathan.nayum@penske.com Can you merge your changes to develop branch. | Gayam | 05/11/23 11:35 PM
Row 66 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. Please check. Thanks. https://bitbucket.penske.com/projects/ARPROJ/repos/efueladmin-web/pull-requests/3/overview | Gayam | 04/07/23 12:25 AM
Row 66 | Venkatesh has completed reviewing the log4j secrets - there are no coding changes required. | William Spohn | 02/23/23 3:03 AM
| Thanks @william.spohn@penske.com . Changing the status to (Cap)Maven | Gayam | 02/23/23 3:26 AM
Row 66 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 66 | @william.spohn@penske.com / @venkatesh.hossalinever@penske.com , @william.spohn@penske.com , Adding to Bamboo build question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:41 AM
Row 66 | Venkatesh Hossalinever provided me the following repo URL with folder and branch details for efueladmin.var Dev, QA, and Prod. Prod- https://svn.penske.com/svn/webprojects/admin/efueladmin/trunk/efueladmin7 Dev - https://svn.penske.com/svn/webprojects/admin/efueladmin/branches/dev_gh/efueladmin7 QA- https://svn.penske.com/svn/webprojects/admin/efueladmin/branches/qa/efueladmin7 | William Spohn | 12/09/22 11:15 PM
| Thanks @william.spohn@penske.com . Can we also get the Bamboo build for this project. @mathumala.nachiappan@penske.com | Gayam | 12/10/22 12:49 AM
| @william.spohn@penske.com / @venkatesh.hossalinever@penske.com, could you please provide the requested info when you get a chance. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 7:40 PM
Row 66 | Moved to AO Bamboo - Please move to CAP Bamboo when done @william.spohn@penske.com | Yvette Urso | 12/15/22 2:45 AM
Row 66 | Yes, we've made this request and are awaiting delivery. | William Spohn | 12/14/22 3:09 AM
Row 66 | Hi Praneeth, I will contact my GDC offshore web app contact for this information and get back to you. | William Spohn | 12/09/22 8:23 PM
Row 66 | @william.spohn@penske.com - Pls. share the Repo URL and confirm the folder/branch for log4J modernization CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 11:16 PM
Row 67 | @praneeth.gayam@penske.com @jeremiah.ashway@penske.com After meeting with the business team, a decision has been made to retire this application. You may cease all modernization activity on this application . Please mark it as Retired as soon as you see this message. | Gianfranco | 10/03/23 12:55 AM
| Sure @frank.d'angelo@penske.com . Thaks for the update. | Gayam | 10/03/23 1:27 AM
Row 67 | @praneeth.gayam@penske.com All items found are validated as false positive. Please proceed. | Gianfranco | 08/24/23 1:49 AM
| Thanks @frank.d'angelo@penske.com | Gayam | 08/24/23 4:11 AM
Row 67 | @jeremiah.ashway@penske.com , I sent the secrets file of this app in email. Could you please check it and let su know whether it requires any code changes. Thanks. | Gayam | 08/22/23 2:20 AM
Row 68 | App deployed to PROD on 08/20/2023 as part of Project Neo deployment. | Sreekanth | 08/21/23 7:08 PM
Row 68 | Review: @sreekanth.kancharla@penske.com , This is ready for your review. Please verify. https://bitbucket.penske.com/projects/ITFIS/repos/employee-master-batch/pull-requests/4/overview | Gayam | 06/28/23 2:47 AM
| @praneeth.gayam@penske.com I'm not sure why the PR is created to a feature branch. By mistake offshore lead merged that but I didn't want that to be merged as we've not tested log4j2 changes in QA & there is some Oracle cloud migration testing going. I couldn't revert the merged commit. I may need to manually revert the changes. | Sreekanth | 06/28/23 7:11 PM
| @sreekanth.kancharla@penske.com , I think there is a confusion whether to merge to develop branch or to the branch which contains recent commits. Do you want us to raise the PR from develop_log4j to develop branch? | Gayam | 06/29/23 2:21 AM
| @praneeth.gayam@penske.com Yes. The PRs should be always to develop branch. | Sreekanth | 06/29/23 8:46 PM
| @sreekanth.kancharla@penske.com , Raised PR to develop branch. Please check. https://bitbucket.penske.com/projects/ITFIS/repos/employee-master-batch/pull-requests/5/overview | Gayam | 06/30/23 12:35 AM
Row 68 | @sreekanth.kancharla@penske.com , we are seeing that you already worked on this app and mavanized. Do you want log4j team to work on it anything or please close the status of this app. @yvette.urso@penske.com / @shane.myers@penske.com | Gayam | 06/07/23 3:02 AM
| @praneeth.gayam@penske.com Yes, this app is already mavenized. If your team could work on Log4j migration changes, then we can test this app. | Sreekanth | 06/08/23 8:02 PM
| Sure @sreekanth.kancharla@penske.com | Gayam | 06/09/23 1:35 AM
Row 69 | This application was deployed to PROD on 07/25/2023. | Sreekanth | 07/27/23 7:24 PM
Row 69 | @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: eram-deploy New deployment project name: eram-web-deploy Thank you. | Gayam | 05/14/23 9:36 PM
Row 69 | @sreekanth.kancharla@penske.com , app is onboarded to Bamboo. https://bamboo.penske.com/browse/EBP-ERAMW/ Please let us know whether we can deploy to dev. | Gayam | 03/10/23 11:23 PM
| @praneeth.gayam@penske.com Please proceed with DEV deployment. We don't have access to add "Plan branch" for any future builds. Please provide access on all the new admin projects. | Sreekanth | 03/13/23 10:17 PM
| Hi @sreekanth.kancharla@penske.com , Deployed the code to dev. Please verify. Also, to add a plan branch you need to be part of RBAC group PTL-Admin-Production. I believe currently you are not part of it. | Gayam | 03/15/23 11:43 PM
| @praneeth.gayam@penske.com We need the access to add the plan branch if they are not automatically being created in Bamboo as we'll be deploying whatever the branch we wanted to test. Please do the need. Schedule a meeting with architect team if needed. | Sreekanth | 03/16/23 12:28 AM
| @sreekanth.kancharla@penske.com , I will send an email to add the people to 'PTL-Admin-Production' RBAC group. Could you please give us the list of people whom you want to add to that group. Once you added to that gorup you will also have permission to deploy to production. | Gayam | 03/16/23 2:29 AM
| @praneeth.gayam@penske.com Developers also need access to add Plan branch in some cases but they shouldn't have PROD deployment access. Please consider this scenario and let us know how this can be handled | Sreekanth | 03/16/23 7:51 PM
Row 69 | Maven Review: @sreekanth.kancharla@penske.com , We ahve completed the modernization on this app. Please review and confirm for the next step. https://bitbucket.penske.com/projects/ITFIS/repos/eram-web/pull-requests/3/overview Thanks. | Gayam | 03/01/23 12:29 AM
| @praneeth.gayam@penske.com The PR is already merged by Jim. We are good with the changes. Please proceed with the further steps. @james.minisce@penske.com | Sreekanth | 03/04/23 2:56 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to Cap Bamboo | Gayam | 03/07/23 12:19 AM
Row 69 | @sreekanth.kancharla@penske.com , This app has some true positive secrets. I sent the file in email. Could you please check it. Thanks. | Gayam | 01/27/23 10:45 PM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. We are good to proceed further. true positives: SearchCompanyDAO.java - This file code is commented. BaseConstants.java - PASSWORD is just a string constant. All the remain are false positives. @mathumala.nachiappan@penske.com @james.minisce@penske.com | Sreekanth | 01/28/23 12:12 AM
Row 69 | @yvette.urso@penske.com , I asked the question regarding group above. It still needs to be resolved by @sreekanth.kancharla@penske.com . @mathumala.nachiappan@penske.com | Gayam | 12/10/22 2:43 AM
| @praneeth.gayam@penske.com If this is for cpe.jar file, then please proceed with creating new group in artifactory and make the required import changes in code. @james.minisce@penske.com Regarding the Bamboo, FP ticket 1765373 is created to Architect team to confirm whether this app's Java version in Bamboo is upgraded to 1.8 or not. | Sreekanth | 12/15/22 3:23 AM
| @praneeth.gayam@penske.com & @james.minisce@penske.com The bamboo plans of ERAM application are with Java 1.8 confirmed by Architect team. | Sreekanth | 12/15/22 7:37 PM
| Thanks @sreekanth.kancharla@penske.com . We will upload the jar and continue the maven changes. @mathumala.nachiappan@penske.com | Gayam | 12/15/22 8:00 PM
Row 69 | @sreekanth.kancharla@penske.com Please review the Bamboo plan for eRAM. Thank you. | James | 12/15/22 2:20 AM
Row 69 | @james.minisce@penske.com @mathumala.nachiappan@penske.com - James can you review the Bamboo for Mathu? | Yvette Urso | 12/15/22 2:12 AM
Row 69 | @rafiq.melath@penske.com / @james.minisce@penske.com , One more issue on this app. This application is using different version of cpe.jar which is not available in artifactory. thre is a different version of cpe.jar available artifactory which is not resolving the issues in this app. Do we need to upload the different version of cpe.jar in artifactory for this application ? Following class have the import from cpe. src/main/java/eram/actions/ViewProductAction.java @mathumala.nachiappan@penske.com | Gayam | 12/08/22 3:16 AM
| @sreekanth.kancharla@penske.com Please provide review the above and provide the necessary requested input. Thank you. | James | 12/08/22 6:17 PM
| @praneeth.gayam@penske.com When I search through the application source code, I found many classes are using the cpe.jar If the jar which is already available in Artifactory doesn't resolve the errors, then we need to have this version jar in artifactory. In this case my answer is "Yes" for your question. | Sreekanth | 12/08/22 7:30 PM
| Thanks @sreekanth.kancharla@penske.com . The current artifactory version of cpe is uplaoded with group com.penske.ebus which is working fine for ebus application. Do you want us to upload the eram version of cpe with group com.penske.eram? FYI: @mathumala.nachiappan@penske.com | Gayam | 12/08/22 10:49 PM
| @praneeth.gayam@penske.com If the group has to be changed, then the imports in java files also should be changed. Please correct me if I'm wrong. Are you planning to make those changes as well. If so, we are good, so that there will not be any issues in functionality of the application. | Sreekanth | 12/09/22 12:19 AM
| @sreekanth.kancharla@penske.com , Group is for where to upload in artifactory. It doesn't affect any code. @mathumala.nachiappan@penske.com | Gayam | 12/09/22 1:34 AM
Row 69 | @praneeth - Should this status change from blocked for this app or is there another reason you are still blocked? | Yvette Urso | 12/09/22 12:41 AM
Row 69 | Yes, the bamboo plan should be with Java 1.8. | James | 12/09/22 12:03 AM
Row 69 | @james.minisce@penske.com - Pls. confirm this Artifactory details. dnbi-acctmgmt.jar -------------------- Group ID - com.dnbi.eai Artifact ID - dnbi-acctmgmt Version - Default dnbi-creditapp.jar -------------------- Group ID - com.dnbi.eai Artifact ID - dnbi-creditapp Version - Default CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:40 PM
| I can confirm the above Artifactory details. CC: @sreekanth.kancharla@penske.com | James | 12/01/22 9:38 PM
| Thanks @james.minisce@penske.com . Jars are uploaded | Mathumala Nachiappan | 12/08/22 3:33 PM
Row 69 | @rafiq.melath@penske.com , This application has cpe.jar dependency for getting loggers in one class. But as per suggestion from Hugo/Architect team, it is good to create logger independently in each class. So we are doing this in all other apps. Same thing we are following in this app. FYI: @mathumala.nachiappan@penske.com | Gayam | 12/06/22 7:42 AM
Row 69 | @rafiq.melath@penske.com / @james.minisce@penske.com eram-web depends on below 2 jars. dnbi-acctmgmt.jar dnbi-creditapp.jar We are unable to find Bamboo build plan or SVN/BB Repo for these 2 jars. So need confirmation from you for uploading these 2 jars to Artifactory. FYI: @mathumala.nachiappan@penske.com | Gayam | 11/23/22 10:56 PM
| Yes, the identified jars will need to be uploaded to Artifactory. They are jars used to connect and get data from the DnBi web services. | James | 11/24/22 2:08 AM
Row 70 | @praneeth.gayam@penske.com Please proceed with Bamboo plan creation with develop branch. Once that is available, we'll test this app in DEV and if the app works fine with no issues, we'll merge our recent changes from SVN to Bitbucket. | Sreekanth | 06/08/23 6:38 PM
| @sreekanth.kancharla@penske.com , Build plan and deploy plan onboarded successfully. Deployed to dev also completed. Please verify. Thanks. | Gayam | 06/13/23 2:12 AM
Row 70 | @praneeth.gayam@penske.com We are good with all the secrets as those are in common files & used across all the Penske web applications. The java version in Bamboo DEV: 1.6, QA: 1.8, PROD: 1.6 We recommend 1.8 CC: @charles.csoky@penske.com | Sreekanth | 01/25/23 2:00 AM
| Thanks @sreekanth.kancharla@penske.com . We have completed the modernization changes. Please review and merge them. PR is https://bitbucket.penske.com/projects/ITFIS/repos/esr-web/pull-requests/3/overview Changed the status to (AO)Maven. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 11:13 PM
| @praneeth.gayam@penske.com The PR is merged to develop. We are currently working on some changes in this application. Mostly we'll deploy the changes before March. Post deployment, we can merge the same changes from SVN to the new bitbucket source code. CC: @mathumala.nachiappan@penske.com @charles.csoky@penske.com | Sreekanth | 01/26/23 2:38 AM
| Thanks @sreekanth.kancharla@penske.com . We will hold this app until you confirm. | Gayam | 01/26/23 9:05 PM
| @praneeth.gayam@penske.com Can we proceed with next step in configuring the bamboo plan, so that when we are don with our current development and get UAT sign off, we can use the new build plan and test the application in DEV. Post that we'll take care of merging the change from SVN to Bitbucket. | Sreekanth | 01/27/23 12:14 AM
| @praneeth.gayam@penske.com and @sreekanth.kancharla@penske.com - As the log4j and mven changes are done from Log4J team and the application is blocked for some other enhancements, i am chanding the status to Waiting on AO. CC: @yvette.urso@penske.com | Mathumala Nachiappan | 01/27/23 10:10 AM
| @praneeth.gayam@penske.com We are making the enhancements to this application and we'll close by this month (2/28/2023). Once that is done, we'll merge the changes to new branch and test the application. @mathumala.nachiappan@penske.com @charles.csoky@penske.com | Sreekanth | 02/15/23 3:18 AM
| @sreekanth.kancharla@penske.com , Could you please merge https://bitbucket.penske.com/projects/ITFIS/repos/esr-web/pull-requests/6/overview These changes are for making the scope of log4j2 to compile. Thanks. | Gayam | 05/30/23 8:48 AM
| @praneeth.gayam@penske.com Merge completed. | Sreekanth | 06/01/23 12:11 AM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 06/01/23 10:47 PM
Row 70 | @charles.csoky@penske.com , We sent an email with secrets for this application. We observed all are false positives. Could you please verify and confirm. Thanks. | Gayam | 01/24/23 10:15 AM
Row 70 | @steve.mcmullen@penske.com / @charles.csoky@penske.com , Log4j and Mavn changes are completed. Could you please review and merge. PR is https://bitbucket.penske.com/projects/ITFIS/repos/esr-web/pull-requests/3/overview | Gayam | 12/03/22 12:19 PM
Row 71 | App deployed to PROD on 09/28/2023 | Sreekanth | 09/29/23 10:05 PM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 10/03/23 1:36 AM
Row 71 | @praneeth.gayam@penske.com could you please change the deploy plan names as "Staging-Deploy" & "Prod-Deploy" as this is a batch application. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=142737418 | Sreekanth | 09/07/23 12:47 AM
| @sreekanth.kancharla@penske.com , I already this question to log4j CICD team and they said that core plans are defined in that way and not possible to change at this point of time. | Gayam | 09/07/23 1:24 AM
Row 71 | @sreekanth.kancharla@penske.com , App is onboarded to bamboo and ready to deploy to QA. Please deploy. https://bamboo.penske.com/browse/ESRBP-ESRBCH0/ | Gayam | 03/30/23 12:34 AM
| @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: esrbatch-deploy New deployment project name: esr-batch-deploy Thank you. | Gayam | 05/14/23 9:41 PM
| @sreekanth.kancharla@penske.com , We changed the scope of log4j jars from provided to compile. Could you please merge the changes. https://bitbucket.penske.com/projects/ITFIS/repos/esr-batch/pull-requests/6/overview | Gayam | 05/24/23 1:55 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 05/24/23 9:04 PM
Row 71 | @charles.csoky@penske.com - Found a hardcoded credential during secret scanning process. Pls. have a look for redaction. @praneeth.gayam@penske.com - Pls. share the secret report to Charles | Mathumala Nachiappan | 12/08/22 10:13 PM
| @praneeth.gayam@penske.com Please loop me while sharing the report. | Sreekanth | 12/16/22 3:34 AM
| @sreekanth.kancharla@penske.com / @charles.csoky@penske.com , Shared the secrets in the email. Please check. @mathumala.nachiappan@penske.com | Gayam | 12/16/22 3:40 AM
| @praneeth.gayam@penske.com The secrets seems fine to me. "database.properties" differs for each environment. For SUPPORT only this file is used from the source location. For QA & PROD, this file is maintained in a specific path in Batch Box server where no one has access except admins. FYI, we don't have any SUPPORT environments for Batch applications. Except this one file, all other seems good to me. One remediation I can think of is by using the Connection Framework instead of maintaining the credentials in a file which required some development effort. Hope we are not planning to make those changes as of now. Please let us know incase any issues/suggestions. CC: @charles.csoky@penske.com | Sreekanth | 12/23/22 2:07 AM
| @sreekanth.kancharla@penske.com , Any changes you are planning for this application or can we go forward for the next step? | Gayam | 01/06/23 1:16 AM
| @praneeth.gayam@penske.com we are good with all the secrets as most of them are related to database credentials and in QA & PROD those credentials are being referred from “conf” folder which admins only can access. Bamboo Java version is 1.8 for QA & PROD CC: @charles.csoky@penske.com | Sreekanth | 01/25/23 2:24 AM
| Thanks @sreekanth.kancharla@penske.com . Passwords are referred in java class files. Is that ok to keep them over there? @hugo.scavino@penske.com / @yvette.urso@penske.com / @mathumala.nachiappan@penske.com | Gayam | 01/25/23 11:16 PM
| @praneeth.gayam@penske.com The only java file that is provided in secrets is "TestCopyFilesWithJcifs.java" This file is not available in trunk branch in SVN and only available in offshore branch. Hope the log4j migration changes be done on top of trunk branch which is used for PROD deployment. If so, hope we should be good with this file. | Sreekanth | 01/26/23 3:18 AM
| Thanks @sreekanth.kancharla@penske.com for confirming. Yes we created log4j branch from trunk which is master in bitnucket. Changing the status to (Cap) Maven | Gayam | 01/26/23 8:43 PM
| @praneeth.gayam@penske.com I've added a comment to the existing PR. Please take care, so that I can merge the request. https://bitbucket.penske.com/projects/ITFIS/repos/esr-batch/pull-requests/3/overview | Sreekanth | 02/16/23 8:35 PM
| @sreekanth.kancharla@penske.com , I responded to the comment. Could you please check. | Gayam | 02/17/23 1:15 AM
| @sreekanth.kancharla@penske.com , Could you please check my response and provide your input. Thanks. | Gayam | 03/03/23 1:29 AM
| @praneeth.gayam@penske.com We've requested for new DL email for logger. Once that is created, we'll share that with you, so that can be added in log4j2.xml For now, I've approve the PR, so please proceed with further steps. @charles.csoky@penske.com @sampada.bhusari@penske.com | Sreekanth | 03/04/23 2:49 AM
Row 72 | I did a deploy to QA environment but I do not see any logging in the /logs/apps folder for the etimservice application in any of the three qa app servers. I think the code is running as I do get a certificate error message back when it tries to communicate with ADP. However, without the loging I am not sure what is the direct cause. Can the logging be fixed? thank you. | Dale Porter | 09/22/23 8:42 PM
| @dale.porter@penske.com , We will check and update you. | Gayam | 09/26/23 1:11 AM
| @dale.porter@penske.com , we changed the log4j configuration in web.xml and deployed to Dev. Logs are getting generated in dev. Please check. Thanks. | Gayam | 09/29/23 1:32 AM
Row 72 | Did another test and I do see the latest files being packaged in the war file for the Dev build. thank you. | Dale Porter | 08/30/23 7:45 AM
Row 72 | Sure @dale.porter@penske.com . We will check and get back to you. | Gayam | 07/31/23 2:26 AM
| @dale.porter@penske.com CICD team checked build log of deployment to artifactory(archive) stage report and found that error statement is coming, but those errors are coming for all the applications and those are not causing any issues. https://bamboo.penske.com/download/ETSBP-ETSW0-DTA/build_logs/ETSBP-ETSW0-DTA-2.log. Then team verified whether the war is getting deployed to artifactory or not and found that it is deploying. Also verified in ghlx008 server and found that etimeservice.war is deploying in server also. So please validate the app. Thanks. | Gayam | 08/01/23 12:46 AM
| Hi all, I ran the buld again for develop branch and I do see the war file for etimeservice is being put to ghlx008 as noted. However, it is not running the ssh app deployment process as I check the application installed in websphere at /opt/websphere/profiles/wsv/installedApps/ghlx006ptlgeNetwork-remoting/etservice.ear and it is still dated as 7/18/2023. I also included a reference to the bamboo build log with errors. https://bamboo.penske.com/download/ETSBP-ETSW0-DTA/build_logs/ETSBP-ETSW0-DTA-3.log | Dale Porter | 08/01/23 8:20 PM
| @dale.porter@penske.com , dev server was down for the past couple of days. That is the reason deployment is failing. Now the server is up and deployment is successful. Please check. https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151196087. | Gayam | 08/04/23 1:04 AM
| Hi I ran a dev build and see that the deployment is being executed (the file folders at and under the below directory are dated today's deploy date 8/9/2023 I ran but the class object files were dated 8/1/2023. I do not think the build is working correctly as the class compiled files should also be dated with current build date. Please take a look. thank you. /opt/websphere/profiles/wsv/installedApps/ghlx006ptlgeNetwork-remoting/etservice.ear | Dale Porter | 08/09/23 11:50 PM
| @dale.porter@penske.com , I don't think there is any issue in the build. If you see the log4j2.xml file it is dated as 8/1. Not sure why the server dated them as 8/1 but total package is correctly built by bamboo. | Gayam | 08/10/23 12:57 AM
| I ran another develop deploy for etimeservice to Dev, this time I do see the class files with the correct tiemstamps. However, I am not seeing any logging to the log on ghlx008ptlge in directory /logs/apps/etimeservice. Can someone check the logging for the application. Thank you. | Dale Porter | 08/16/23 8:49 AM
| @dale.porter@penske.com , Is that application creating logs in local? | Gayam | 08/17/23 1:26 AM
| not sure what you mean by local, prior modernization, it was logging in dev to /logs/apps/etimeservice, now I do not see logging occurring there. | Dale Porter | 08/17/23 9:03 AM
| @dale.porter@penske.com , The application needs to run in local and verify whether logs are creating in local. Cap Log4j team only compiles the applicaition once mavanization completes. We don't know the information about running the application. So AOs are running the apps in local and checking whether things are working fine. If you want to verify in server, I heard that dev is not a good environment to check for most of the apps. QA is best. Please deploy to QA and check. | Gayam | 08/18/23 12:41 AM
| Hi, I ran the Dev deployed on 8/26 and the class files deployed on "" are dated 8/15 not the correct build ones for 8/26. Folder I checked on dev app server ghlx008ptlge /opt/websphere/profiles/wsv/installedApps/ghlx006ptlgeNetwork-remoting/etimeservice.ear/etimeservice.war/WEB-INF/classes/com/penske/apps/etimeservice/domain The build log in bamboo is https://bamboo.penske.com/deployment-download/151912485/build_logs/151814151-151912485-151200197.log Also, I tested the QA build and saw same issue when inspected the WAR file placed in /var/tmp of QA deploy manager clelx150ptlge I saw class file dates of 8/15 and not 8/26 for current build date. The bamboo build log for qa is https://bamboo.penske.com/deployment-download/151912486/build_logs/151814151-151912486-151200196.log | Dale Porter | 08/27/23 3:16 AM
| @dale.porter@penske.com , If you see that all the folder dates are 08/26 and log4j2.xml files also available in the server. I am not sure why the file dates are 08/15 but I can say that latest build is deployed to dev. Please verify the application and check whether all the things are working fine. | Gayam | 08/28/23 10:55 PM
Row 72 | hi All, I am getting access denied error when clicking on the link above from Bamboo. Can I be given access to the above project in bamboo for the link. Thank you. | Dale Porter | 07/17/23 7:37 PM
| @dale.porter@penske.com , you have all the required access. Please check again. https://bamboo.penske.com/browse/ETSBP-ETSW/deployments | Gayam | 07/20/23 12:14 AM
| Hi, I am seeing errors in the Bamboo build for the final Archive stage and included link to bamboo for showing the error. Also, I did not see a war file created on ghlx008ptlge. Can you take a look. Thank you https://bamboo.penske.com/download/ETSBP-ETSW0-DTA/build_logs/ETSBP-ETSW0-DTA-2.log | Dale Porter | 07/28/23 1:35 AM
Row 72 | @dale.porter@penske.com , onboarded to bamboo and dev deployment is successful. Please verify. Thanks. https://bamboo.penske.com/browse/ETSBP-ETSW/deployments | Gayam | 07/12/23 1:39 AM
Row 72 | I have verified and merged. thank you | Dale Porter | 07/07/23 1:03 AM
| Thanks @dale.porter@penske.com . We will onboard to bamboo. | Gayam | 07/10/23 11:31 PM
Row 72 | Review: @dale.porter@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/etimeservice/pull-requests/4/overview | Gayam | 06/24/23 12:46 AM
Row 72 | The xml file in question “EncryptionKeyStoreDao” is a mybatis sql call to procedure GETENCRYPTIONKEY from EK_MASTER library. It does not have a specific key id or key password stored, it is just the variable placeholder for receiving the password when returned from the procedure call to be using in the application. This should not be an issue. | Dale Porter | 06/06/23 6:18 AM
| Thanks @dale.porter@penske.com . Changed the status to Cap Maven | Gayam | 06/06/23 8:30 AM
Row 72 | @dale.porter@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:48 AM
Row 73 | @praneeth.gayam@penske.com The team found hardcoded secrets that need to be addressed. Team will resolve. | Gianfranco | 08/24/23 2:05 AM
| Thanks @frank.d'angelo@penske.com | Gayam | 08/24/23 4:16 AM
Row 73 | @kenneth.french@penske.com , I sent the secrets file of this app in email. Could you please check it and let su know whether it requires any code changes. Thanks. | Gayam | 08/22/23 2:22 AM
Row 74 | @praneeth.gayam@penske.com please create bamboo plan the same as bill_avobatch | Dylan | 09/16/23 1:57 AM
| Sure @dylan.price@penske.com | Gayam | 09/19/23 12:52 AM
| @dylan.price@penske.com , Created the plan same as bill_avobatch. Build is getting failed due to jtest. So we disabled jtests. Please verify. Thanks. | Gayam | 09/21/23 12:48 AM
Row 74 | Review: @dylan.price@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/PBTCBOS/repos/fbwatermark-batch/pull-requests/5/overview | Gayam | 06/16/23 9:56 PM
Row 74 | Hi @praneeth.gayam@penske.com secrets look great. Please start with log4j/maven changes | Dylan | 06/07/23 1:07 AM
| Thanks @dylan.price@penske.com | Gayam | 06/07/23 5:52 AM
Row 74 | @mark.weaver@penske.com , Shared the secrets of this app in the email. Please check. Thanks. | Gayam | 03/24/23 12:13 AM
Row 74 | The other line item which has fbwatermark.jar has been marked a Dup App. So picking up this application for the next steps. | Gayam | 03/07/23 3:16 AM
Row 74 | This application is an internal CBOS batch application and deploys to ghlx097ptlge (our CBOS batch box). Not sure how you would mark this in your artifactory -- wondering if CBOS should have its own… | Dylan | 03/07/23 12:59 AM
Row 74 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 74 | @sam.skelding@penske.com / @mark.weaver@penske.com , Adding to above question, we have following query for this applicaiton. This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:59 AM
Row 74 | @mark.weaver@penske.com - Is this application repeated. #95 and #96. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 11:52 AM
Row 75 | @mark.weaver@penske.com and @rafiq.melath@penske.com - Marking this as duplicate of Row# 95. Pls. share the repo details if this is different. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:12 AM
Row 76 | There are no secrets found in this application. So pushing this to Cap maven stage. | Gayam | 09/20/23 1:52 AM
Row 76 | Sounds good, just want to get ahead of any development we may need to do for git leaks. thanks | Gianfranco | 08/30/23 3:45 AM
Row 76 | @praneeth.gayam@penske.com , this is 1 of 2 apps in the Not Started bucket. Can we get these into Cap Analysis and start to do the scans? | Gianfranco | 08/29/23 6:17 PM
| @frank.d'angelo@penske.com , My team already started analyzing. But completing the modernization may takes some times as team is busy with lot of apps. | Gayam | 08/30/23 2:35 AM
Row 77 | @praneeth.gayam@penske.com We have reviewed the PR and added comments to it, please review. | Gupta | 10/06/23 9:06 PM
| @shweta.gupta@penske.com , We will review and rectify them. | Gayam | 10/10/23 12:14 AM
| @shweta.gupta@penske.com , We have reviewed and provided the comment in the PR. Please check. | Gayam | 10/19/23 8:22 AM
Row 77 | Review: @shweta.gupta@penske.com , This app is ready for your review. Please verify. Thanks. https://bitbucket.penske.com/projects/EBMS/repos/fdtypebatch/pull-requests/3/overview | Gayam | 10/04/23 2:43 AM
Row 77 | @praneeth.gayam@penske.com We have reviewed the assessment and agree that these are false positives. Please proceed to the next step. | Gianfranco | 08/16/23 1:46 AM
| Thanks @frank.d'angelo@penske.com . Changing the status to Cap Maven. | Gayam | 08/17/23 12:57 AM
Row 77 | @shweta.gupta@penske.com , I sent the secrets file in an email for this app. Please check and let us know if app requires any code changes. Thanks. | Gayam | 08/10/23 1:17 AM
Row 78 | @praneeth.gayam@penske.com I changed the status. It was "Waiting on AO". Note the AO start date of 8/14. | Gianfranco | 08/15/23 10:22 PM
| Thanks @frank.d'angelo@penske.com | Gayam | 08/17/23 1:04 AM
Row 78 | @praneeth.gayam@penske.com FedEx Rental is not in scope for CapGemini, it is a retired application. Can we remove? | Gianfranco | 08/15/23 8:20 PM
| @frank.d'angelo@penske.com , status mentioned as 'Retire App'. So we are not working on this app. | Gayam | 08/15/23 9:04 PM
Row 78 | @frank.d'angelo@penske.com , Could you please let us know whether this application is going away. If not could you please provide the production branch. We are unable to find from bamboo as the prod deploy never ran on this application. Thanks. | Gayam | 02/15/23 12:36 AM
Row 78 | @frank.d'angelo@penske.com - Per Frank please get with him prior to starting - this app may go away. | Yvette Urso | 01/25/23 2:54 AM
Row 79 | Thanks @frank.d'angelo@penske.com | Gayam | 08/18/23 1:02 AM
Row 79 | @praneeth.gayam@penske.com That is fine. We will work to retire, but for your team you can mark it as retired. | Gianfranco | 08/17/23 1:46 AM
Row 79 | @praneeth.gayam@penske.com FI Migration batch is going to be retired by Penske team. We can consider this app completed at this time. | Gianfranco | 08/17/23 12:01 AM
| @frank.d'angelo@penske.com , Can I change the status as Retired? | Gayam | 08/17/23 1:13 AM
Row 79 | @praneeth.gayam@penske.com RETIREMENT? - there is a chance this app can just be retired and I have a task to research this. Please hold off for the time being on this application and focus on others. | Gianfranco | 08/14/23 11:38 PM
Row 79 | Query: @jeremiah.ashway@penske.com , We are able to find the bitbucket repo for this app but not bamboo build. Without bamboo build we couldn't figure out the production branch. Could you please let us know the latest branch which is deployed to production. BB Repo: https://bitbucket.penske.com/projects/EBCE/repos/fimigration/browse | Gayam | 07/27/23 8:50 AM
Row 80 | Ready to Deploy | Rajesh | 09/11/23 5:29 PM
Row 80 | @rajesh.haravde@penske.com , Build and deployment completed in Dev. Please verify the application in dev. https://bamboo.penske.com/browse/FIXEDASSETBP-FXDAT1/deployments | Gayam | 05/22/23 9:29 PM
Row 80 | PR been executed please take it forward. Thanks for guidance on process Praneeth appreciated. | Rajesh | 05/18/23 1:48 AM
Row 80 | @rajesh.haravde@penske.com , If you are able to verify the develop_log4j branch, could you please merge the PR. https://bitbucket.penske.com/projects/PTLCORP/repos/fixedasset-web/pull-requests/3/overview | Gayam | 05/17/23 3:14 AM
| @rajesh.haravde@penske.com Onboarding both develop_log4j and develop branches to bamboo is completed. Running the develop branch failed as pom.xml is not in develop. Also, deployment in dev from develop_log4j is successful. Please merge abiove PR. | Gayam | 05/18/23 12:59 AM
Row 80 | I am not able to change App Status using my login can anyone please reset my profile, as i was able to update it last week. Thanks. | Rajesh | 05/16/23 6:50 PM
Row 80 | We able to build project using maven. please change status "(AO) Maven completed. | Rajesh | 05/16/23 6:49 PM
Row 80 | Thanks @rajesh.haravde@penske.com . We have completed log4j/maven changes for this application. Please review in below PR. https://bitbucket.penske.com/projects/PTLCORP/repos/fixedasset-web/pull-requests/3/overview | Gayam | 02/16/23 11:33 PM
Row 80 | we do not want to address secrete mitigation at this movement. please move forward with project upgrade with respect to bitbucket, maven and log4j | Rajesh | 02/16/23 3:41 AM
Row 80 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:49 PM
Row 80 | @april.ottey@penske.com / @yogesh.sinha@penske.com ,Please review the PR and provide your approval. https://bitbucket.penske.com/projects/PTLCORP/repos/fixedasset-web/pull-requests/3/overview FYI: @mathumala.nachiappan@penske.com | Gayam | 11/24/22 3:46 AM
Row 81 | @venkatesh.hossalinever@penske.com , this lineitem is Duplicate. For Flex Billing, please check the line item which has application name as flexbilling.war | Gayam | 03/29/23 9:04 PM
Row 81 | We are working on the changes, please wait for sometime. | Venkatesh | 03/24/23 8:59 PM
Row 81 | As per above comment, marking this as Dup App and flexbilling.war is the original one. | Gayam | 03/08/23 12:12 AM
Row 81 | they are indeed duplicated on this sheet. The repo for this application is https://svn.penske.com/svn/avolent/ptl_customization/billing/appserver/trunk | Dylan | 03/07/23 1:02 AM
Row 81 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 81 | @mark.weaver@penske.com and @elliott.eames@penske.com - Flex billing entries are replicated thrice. Ref. Row #97, #99 and #129. Pls. confirm and share the Repo details for these applications to consider for log4J Modernization CC: @rafiq.melath@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:10 AM
| @mark.weaver@penske.com - Pls. ignore the row #s mentioned above. Applications under confusion are 1. flexbilling.war 2. flexbilling 3. Flex Billing CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com | Mathumala Nachiappan | 02/06/23 6:45 PM
Row 82 | Hi @praneeth.gayam@penske.com this is working great on local with the changes to SLF4J. Thank you! Could you please work on creating a bamboo plan for this application? It currently is being run on the IFS system and not the JDK batch box. I will check with my team to see how we want this deployed, but for now could you please have it deploy out to the JDK batch box like other batch applications? | Dylan | 08/28/23 8:53 PM
| Sure @dylan.price@penske.com | Gayam | 08/28/23 10:46 PM
| @dylan.price@penske.com , Onboarded develop_log4j branch to bamboo | Gayam | 08/30/23 3:30 AM
Row 82 | Hi @praneeth.gayam@penske.com while testing the code, we are getting the following error: SLF4J: No SLF4J providers were found. SLF4J: Defaulting to no-operation (NOP) logger implementation SLF4J: See https://www.slf4j.org/codes.html#noProviders for further details. SLF4J: Class path contains SLF4J bindings targeting slf4j-api versions 1.7.x or earlier. SLF4J: Ignoring binding found at [jar:file:/C:/Users/600158487/.m2/org/apache/logging/log4j/log4j-slf4j-impl/2.20.0/log4j-slf4j-impl-2.20.0.jar!/org/slf4j/impl/StaticLoggerBinder.class] SLF4J: See https://www.slf4j.org/codes.html#ignoredBindings for an explanation. Could you please look into and fix SLF4J issues? Thank you! | Dylan | 08/23/23 5:36 PM
| Sure @dylan.price@penske.com . We will verify and get back to you. | Gayam | 08/24/23 3:42 AM
| @dylan.price@penske.com , I think there is a mismatch version of sl4j-impl and we fixed it. COuld you please check now. Thanks | Gayam | 08/24/23 11:04 PM
Row 82 | @dylan.price@penske.com , This app is ready for your review. Please verify and merge. Thanks. https://bitbucket.penske.com/projects/PBTCBOS/repos/flexbilling-acl-batch/pull-requests/4/overview | Gayam | 07/07/23 1:13 AM
Row 82 | Hi @praneeth.gayam@penske.com you are good to move xmlgen_common.jar to artifactory. As for the conf folder, please use the "database.properties" inside /conf and not in /src/conf. This will get wiped out when I make the property file changes after log4j/maven is finished. | Dylan | 06/07/23 1:11 AM
Row 82 | @venkatesh.hossalinever@penske.com , Question1: In this application we have two conf folders. One is under src folder and another one is outside the src folder. So which one we need to use? Question2: This app is dependent on xmlgen_common.jar. But this is not available in artifactory. Could you please approve to upload this jar to following location in artifactory. groupid: com.penske.nb.xmlgen.common , artifactid: xmlgen_common | Gayam | 03/10/23 2:20 AM
| @venkatesh.hossalinever@penske.com , could you pelase check above questions and provide your response. Thanks. | Gayam | 04/18/23 3:30 AM
Row 82 | Completed reviewing the log4j secrets there is no code changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 3:41 AM
| Thank you. Changing the app status to Cap Maven | Gayam | 03/02/23 1:33 AM
Row 82 | Completed reviewing the log4j secrets -the hardcoded values in properties are not being used in application code and no changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 3:26 AM
Row 82 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 82 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:53 AM
Row 83 | As per @dylan.price@penske.com marking this line item as Dup App | Gayam | 03/08/23 12:11 AM
Row 83 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 83 | @mark.weaver@penske.com and @elliott.eames@penske.com - Flex billing entries are replicated thrice. Ref. Row #97, #99 and #129. Pls. confirm and share the Repo details for these applications to consider for log4J Modernization CC: @rafiq.melath@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:10 AM
| @mark.weaver@penske.com Pls. ignore the row #s mentioned above. Applications under confusion are 1. flexbilling.war 2. flexbilling 3. Flex Billing CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com | Mathumala Nachiappan | 02/06/23 6:46 PM
Row 84 | @praneeth.gayam@penske.com Please bring these down and we will remediate these during our AO testing when the app status moves to 6.1 | Dylan | 08/24/23 9:43 PM
| @dylan.price@penske.com , We have completed the modernization of this app. Please chekc the PR. https://bitbucket.penske.com/projects/PBT/repos/flexbilling-web/pull-requests/3/overview | Gayam | 08/30/23 3:13 AM
Row 84 | Question: @dylan.price@penske.com , Targeted folder of this application contains different ApplicationProperties.properties files under different enviornment folders. 'DEFAULT_MACHINE' property value is different between different ApplicationProperties files. As we are going to do the environment agnostic build we should use only 1 file under resources. Could you please check and let us know which one we need to use. Thanks. | Gayam | 06/13/23 1:46 AM
Row 84 | Hi @praneeth.gayam@penske.com I am seeing "conf" and "conf_test". For the time being could you please bring both conf folders down and when I make the changes for the properties files I will consolidate them into 1 conf folder | Dylan | 06/07/23 6:17 PM
| Sure @dylan.price@penske.com | Gayam | 06/08/23 7:51 AM
Row 84 | HI @praneeth.gayam@penske.com secrets file looks great -- please start with log4j/maven changes | Dylan | 06/07/23 1:14 AM
| Thanks @dylan.price@penske.com . Also, could you please the question I posted above. | Gayam | 06/07/23 6:02 AM
Row 84 | Secrets: @elliott.eames@penske.com , Adding to above question, I sent secrets in the email. Please check and respond whether any changes required to remediate the secrets. | Gayam | 03/24/23 12:07 AM
Row 84 | Question: @elliott.eames@penske.com , In this application we have two conf folder one is under src folder and another one is outside the src folder so need confirmation which one we need to use? Thanks. | Gayam | 03/09/23 2:12 AM
Row 84 | As per @dylan.price@penske.com , the other 2 line items are Duplicates. This is the original one. Repo is https://svn.penske.com/svn/avolent/ptl_customization/billing/appserver/trunk | Gayam | 03/08/23 12:12 AM
Row 84 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 84 | @mark.weaver@penske.com and @elliott.eames@penske.com - Flex billing entries are replicated thrice. Ref. Row #97, #99 and #129. Pls. confirm and share the Repo details for these applications to consider for log4J Modernization CC: @rafiq.melath@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:10 AM
| @mark.weaver@penske.com Pls. ignore the row #s mentioned above. Applications under confusion are 1. flexbilling.war 2. flexbilling 3. Flex Billing CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com | Mathumala Nachiappan | 02/06/23 6:45 PM
Row 85 | @gary.galyas@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/ARPROJ/repos/fmea-web/pull-requests/3/overview | Gayam | 08/18/23 9:27 PM
Row 85 | Question: @rohit.sharma@penske.com , This application dependent on fmea.jar which is available under application's lib folder. https://svn.penske.com/svn/webmasters/web/fmea/trunk/WebContent/WEB-INF/lib/ We need to upload fmea.jar to artifactory to mavanize this app under below location. Could you please provide your approval to upload to artifactory. <groupid>com.penske.fmeajar</groupid> <artifactid>fmea</artifactid> <version>Default</version> | Gayam | 06/13/23 1:52 AM
| go for it | Rohit | 06/13/23 2:17 AM
| Thank you. | Gayam | 06/13/23 2:36 AM
Row 85 | Secrets: @rohit.sharma@penske.com , I sent the secrets in the email for this app. Please check them. Thanks. | Gayam | 06/02/23 1:18 AM
| There are no secrets for this app. | Gayam | 06/07/23 2:54 AM
Row 85 | https://svn.penske.com/svn/webmasters/web/fmea/trunk/ | Hugo Scavino | 05/01/23 9:25 PM
| Thanks @hugo.scavino@penske.com . Do we have any existing bamboo build for this app? | Gayam | 05/02/23 12:53 AM
Row 85 | Please use trunk | Hugo Scavino | 05/01/23 9:24 PM
Row 85 | this application is in WebMasters SVN repository https://fisheye.penske.com/changelog/~br=trunk/Webmasters | Hugo Scavino | 05/01/23 9:24 PM
Row 85 | @scott.bortzel@penske.com / @scott.pemrick@penske.com , For this application both SVN and Bamboo are not available. Could you please let us know the SVN and Bamboo details. Thanks. | Gayam | 01/14/23 1:06 AM
Row 86 | Question: @gregg.obst@penske.com / @sarath.mani@penske.com / @stella.george@penske.com , This app depends on following jars. 1. VehicleInformationUtility.jar: We started working on modernizing this jar as part of other apps and uploading to artifactory through Bamboo. 2. highavail.jar: bamboo : https://bamboo.penske.com/browse/HABP SVN repo: https://svn.penske.com/svn/architecture/general/highavail/branches/dev_gh Please let us know whether we need to modernize the highavail.jar. Following jars are in lib folder but app is not giving any compilation issues even if we don't add them to build path. Please let us know whether we need to modernize the below jars or upload directly to artifactory. 3. coversheet.jar: No SVN/bamboo found 4. pos.jar: No SVN/bamboo found but pos.jar is also using in this app. And its looks like a internal penske project which is having log4j1 imports and log4j.xml as well. Thanks. | Gayam | 06/23/23 12:53 AM
| I don't know anything about the football other than what it does but looking at the highavail jar file you linked to shows it's some sort of MBean around high availability testing so I would say yes, convert it. I have no idea what coversheet.jar is but if I look on Confluence there is a reference to a RentalNet coversheet redesign in 2018 but never mentions that jar specifically. You may want to check with someone from RentalNet to see if it is needed, though as you say, it compiles without it so nothing can be referencing it. | Gregg | 08/15/23 3:00 PM
| Thanks @gregg.obst@penske.com . We will modernize the highavail.jar. We got the approval to upload coversheet jar manually to artifactory for unijkt application. Thank you. | Gayam | 08/15/23 8:54 PM
| @praneeth.gayam@penske.com Is there an update on when football mavenization and the new Bamboo build will be complete so we can test ? | Gregg | 09/07/23 6:44 PM
| @gregg.obst@penske.com , Football.war depends on Highavail.jar app. We have a query in Highavail.jar and we asked in the Highavail.jar app line item. We can work on football once the issue resolves in Highavail.jar | Gayam | 09/08/23 12:31 AM
Row 86 | Secrets: @stella.george@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:55 AM
| AO confirmed no changes required for secrets. | Gayam | 06/16/23 10:32 PM
Row 87 | This application is deployed to QA. cc: @praneeth.gayam@penske.com @william.spohn@penske.com | Venkatesh | 10/06/23 6:20 PM
Row 87 | @praneeth.gayam@penske.com : can you onboard the application for build and deployments. Regards, Revathi.K | Kandasamy | 09/16/23 2:08 AM
| Sure @revathi.kandasamy@penske.com | Gayam | 09/18/23 6:44 PM
| @revathi.kandasamy@penske.com , Onboarding of fuelbatch application build and deploy plans completed- https://bamboo.penske.com/browse/FBBP-FUELB/deployments | Gayam | 09/18/23 8:45 PM
Row 87 | @praneeth.gayam@penske.com Could you please change log4j version from 2.20.0 to 2.17.2, slf4j version from 2.0.6 to 1.7.36 | Nayum | 09/04/23 4:34 PM
| @pathan.nayum@penske.com , Changed are completed. Please check. | Gayam | 09/05/23 11:59 PM
Row 87 | @praneeth.gayam@penske.com : Gentle Reminder!!! Could you share the latest branch name to be validated | Kandasamy | 08/29/23 10:05 PM
| @revathi.kandasamy@penske.com , Team is busy several apps. We will try to provide the PR as soon as possible. | Gayam | 08/30/23 2:41 AM
| @revathi.kandasamy@penske.com , We have completed the modernization and code is in develop branch. Could you please check it and let us know if we need to do any modifications. Thanks. | Gayam | 08/31/23 10:50 PM
Row 87 | @praneeth.gayam@penske.com , Any update on the log4j/maven migrated code. Kindly share the branch to be validated. | Nayum | 08/24/23 12:34 PM
| @revathi.kandasamy@penske.com / @pathan.nayum@penske.com , we complated mavanization of this app but observed that @pathan.nayum@penske.com committed some changes recently. We need to accommodate those changes in the modernization branch. We will let you know once we compelte the changes. | Gayam | 08/25/23 12:00 AM
Row 87 | Praneeth, Any update on the log4j/maven migrated code. Kindly share the branch to be validated. Regards, Revathi.K | Kandasamy | 08/21/23 6:02 PM
| @revathi.kandasamy@penske.com , We will provide the app in a day. | Gayam | 08/21/23 9:43 PM
Row 87 | @praneeth.gayam@penske.com , wsdl files are configured inside conf folder. The wsdl file from targeted folder will not be used. Kindly, let us know once log4j/mavenization changes are done. | Nayum | 08/14/23 4:49 PM
| Thanks @pathan.nayum@penske.com . | Gayam | 08/14/23 11:44 PM
Row 87 | @praneeth.gayam@penske.com 1. dev folder might be used for local configuration. so we can have dev configuration folder. 2. MessageReceiverService.wsdl file has to be used from respective environment folder. 3. penske-service-security-framework.jar is not required, it can be removed. | Nayum | 07/19/23 7:02 PM
| @pathan.nayum@penske.com , In environment agnostic build there will be no separate builds for each environment. It should be handled in the code. Please check with Architecture team i.e @shane.myers@penske.com if you have any questions. | Gayam | 07/19/23 11:56 PM
Row 87 | @pathan.nayum@penske.com , While working on converting this app to mavenization we found following things. Please clarify them. 1.This application has dev environment in the targeted folder. But the batch apps don't have the dev enironment. Please confirm whether we can ignore the dev configurations. 2.App has MessageReceiverService.wsdl file in dev,prod and qa folders under targeted folder. But we need to use only 1 wsdl as this is a environment agnostic build. Could you please let us know which one we need to use. 3. This app is having penske-service-security-framework.jar. But build is successful without using this jar. Do we need to include the dependency or not? | Gayam | 05/24/23 1:25 AM
Row 87 | We have verified the secrets shared in the email, And they are not secret or confidential info. So no change required. | Nayum | 05/12/23 9:33 PM
| Thanks @pathan.nayum@penske.com . Changed the status to Cap Maven. | Gayam | 05/17/23 3:21 AM
Row 87 | @praneeth.gayam@penske.com The following is the complete url deployed in the prod https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_spring @william.spohn@penske.com please correct us if any concerns. Can I get the secret codes for this particular branch(fuelnetbatch_spring). | Nayum | 04/28/23 11:33 AM
| @praneeth.gayam@penske.com @pathan.nayum@penske.com Yes Its the correct Prod branch. https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_springPraneeth can you please share the secrets for production branch. | Venkatesh | 04/29/23 2:33 AM
| @venkatesh.hossalinever@penske.com / @pathan.nayum@penske.com , I will discuss with my team and will let you know. | Gayam | 05/02/23 1:21 AM
| @venkatesh.hossalinever@penske.com / @pathan.nayum@penske.com , The provided secrets file is from https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_spring only. Secrets scanning tool provides all commit history secrets too. | Gayam | 05/03/23 1:24 AM
| No Praneet, If it consider the commit history the svn path should be same and in the list we can find different path. Can you point the above svn url and share the new list of secret codes. The secrets you shared earlier was having duplicate entries. Hence requesting to share the secret codes for the above link alone. | Kandasamy | 05/03/23 5:51 PM
| @revathi.kandasamy@penske.com , we will do the secrets scanning one more time and will send the list. | Gayam | 05/04/23 12:15 AM
| @revathi.kandasamy@penske.com / @venkatesh.hossalinever@penske.com / @pathan.nayum@penske.com , I sent the secrets file which is produced from the scanning of https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_spring branch in the email. Scanning tool is scanning all the branches when we scan the bitbucket but scanning only the provided branch when we scan the svn. | Gayam | 05/05/23 6:46 AM
Row 87 | While analysing the secret codes in fuelbatch_secrets.xlsx, we could find the following different svn locations for fuelbatch application. Kindly, confirm appropriate svn location to be verified for secret codes. https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_spring https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet_batch_Spring_Migration https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet_batch https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet | Nayum | 04/27/23 3:29 PM
| @pathan.nayum@penske.com , You provided us the following URL for this repo. Please check above comments. Repository 1 name: FUELBATCH_PROD associated reposiory url: https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/ | Gayam | 04/28/23 1:59 AM
Row 87 | Secrets: @pathan.nayum@penske.com , We sent secrets file for this app in the email. Could you please verify. Thanks. | Gayam | 04/22/23 2:16 AM
Row 87 | Yes, we can refer it from the artifactory. | Nayum | 04/06/23 1:09 PM
Row 87 | Repository 1 name: FUELBATCH_PROD associated reposiory url: https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/ is the source code, the second repository is pointing to a jar. | Nayum | 04/05/23 4:47 PM
| @pathan.nayum@penske.com , that means can we add the jar which is pointing to repo2 as a dependency to repo1 app while mavanizing? | Gayam | 04/06/23 2:49 AM
Row 87 | @william.spohn@penske.com , Following is the old bamboo build. https://bamboo.penske.com/chain/viewChain.action?planKey=FBBP-FBPROD This Bamboo build have reference to 2 repositories. Repository 1 name: FUELBATCH_PROD associated reposiory url: https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/ Repository 2 name: SECURITYJAR_PROD associated reposiory url: https://svn.penske.com/svn/architecture/security/penske-service-security-framework Could you please check and clarify us which one is correct repo? | Gayam | 03/13/23 11:11 PM
Row 88 | I did not see any questions in the PR | Kenneth | 10/07/23 1:28 AM
| @kenneth.french@penske.com , Following is the query which is mentioned in the above comment. We did not provide the queries in PR because we are providing in the smartsheets. This is the way we have been following from the initial phase of the project. We will provide the queries if you need in PR too. Thanks. Question: This app has a propery file fuelcalc.prop which is having different values for dev/qa and prod. It needs to be handled to satisfy the environment agnostic build. | Gayam | 10/10/23 12:18 AM
Row 88 | @praneeth.gayam@penske.com i merged this PR | Kenneth | 10/07/23 1:07 AM
Row 88 | @praneeth.gayam@penske.com , are you tagging the application owners in the PR @kenneth.french@penske.com | Gianfranco | 10/04/23 12:20 AM
| No @frank.d'angelo@penske.com . we usually raise the PR and mention in the smathseets. This is the way all other teams are following. | Gayam | 10/04/23 1:51 AM
Row 88 | Review & Question: @frank.d'angelo@penske.com , We have completed the mavanization with an open query. PR is https://bitbucket.penske.com/projects/EBFC/repos/fuelcalc/pull-requests/3/overview Question: This app has a propery file fuelcalc.prop which is having different values for dev/qa and prod. It needs to be handled to satisfy the environment agnostic build. | Gayam | 09/26/23 1:49 AM
Row 88 | @praneeth.gayam@penske.com We have reviewed the assessment and agree that these are false positives. Please proceed to the next step. | Gianfranco | 08/16/23 1:49 AM
| Thanks @frank.d'angelo@penske.com . Changing the status to Cap Maven. | Gayam | 08/17/23 12:57 AM
Row 88 | @sree.gopal@penske.com , I sent the secrets file in an email for this app. Please check and let us know if app requires any code changes. Thanks. | Gayam | 08/10/23 1:19 AM
Row 89 | Application will be retired. No longer needed due to recent upgrades with automating fuel price data feed. I have marked application as App Status = Retired | Gianfranco | 08/21/23 9:42 PM
Row 89 | @praneeth.gayam@penske.com , yes Please hold. Will have an answer tomorrow | Gianfranco | 08/17/23 2:13 AM
Row 89 | @praneeth.gayam@penske.com , this application may be able to be retired. Checking with the business. Fuel prices are now automatically populated, so this may not be needed. | Gianfranco | 08/17/23 1:16 AM
| @frank.d'angelo@penske.com , Do you want us to hold this applicaton for now? | Gayam | 08/17/23 1:19 AM
Row 89 | @praneeth.gayam@penske.com We have reviewed the assessment and agree that these are false positives. Please proceed to the next step. | Gianfranco | 08/16/23 1:49 AM
| Thanks @frank.d'angelo@penske.com . Changing the status to Cap Maven. | Gayam | 08/17/23 12:58 AM
Row 89 | @sree.gopal@penske.com , I sent secrets in an email. Could you please verify it. Thanks. | Gayam | 08/05/23 12:33 AM
Row 90 | UAT is completed and ready for production deployment . cc: @praneeth.gayam@penske.com @william.spohn@penske.com | Venkatesh | 10/06/23 6:20 PM
Row 90 | @william.spohn@penske.com UAT completed, ready for production deployment. cc: @praneeth.gayam@penske.com @revathi.kandasamy@penske.com | Venkatesh | 10/05/23 11:56 PM
| Thanks @venkatesh.hossalinever@penske.com . Please let us know once the deployment completes. | Gayam | 10/06/23 12:55 AM
Row 90 | @praneeth.gayam@penske.com : could you modify the following: 1. remove log4j.properties cofiguaration from web.xml <context-param> <param-name>log4jConfigLocation</param-name> <param-value>classpath:conf/log4j.properties</param-value> </context-param> 2. Remove the log4j.properties from the app 3. In log4j2.xml: artifact id should be without war. Kindly update as fuelcardsplit alone. <Property name="app_name">fuelcardsplit.war</Property> | Kandasamy | 08/22/23 1:56 PM
| @revathi.kandasamy@penske.com , My team said that they completed these changes. Could you please let us know the status of this pp. Thanks. | Gayam | 09/28/23 6:51 PM
Row 90 | @praneeth.gayam@penske.com : application is not deployed in dev as the artifactory id in pom.xml is not given correctly <artifactId>fuelcardsplit-web</artifactId> Kindly change as below: <artifactId>fuelcardsplit</artifactId> | Kandasamy | 08/16/23 3:51 PM
| Sure @revathi.kandasamy@penske.com . | Gayam | 08/17/23 1:22 AM
| we need to change the SLF4j and LOG4j version as well. Let follow up with log4j team for the changes | Kandasamy | 08/18/23 9:31 PM
| @revathi.kandasamy@penske.com , Team chagned the versions. Please check. | Gayam | 08/21/23 9:41 PM
Row 90 | @praneeth.gayam@penske.com , After deploying fuelcardsplit changes to QA, new logs are not created. Kindly, check if you have to restart the aplication. | Nayum | 07/19/23 6:49 PM
| @pathan.nayum@penske.com , will check. | Gayam | 07/19/23 11:50 PM
| @pathan.nayum@penske.com , Ritesh told me that he already updated you. Could you please run the application in local and check whether logs are getting generated. We can't run the application in our local. | Gayam | 07/24/23 11:58 PM
Row 90 | @praneeth.gayam@penske.com / @venkatesh.hossalinever@penske.com , for fuelcardsplit application, Dev URL is not working, while accessing the Dev URL it is redirecting to dlinks(https://logindev.penske.com/dlinks/app/dlinksMain?LoginUserID=null). | Nayum | 06/12/23 8:28 PM
Row 90 | @praneeth.gayam@penske.com Reviewed the changes and merged code to develop branch, Please deploy to Dev environment. | Venkatesh | 05/16/23 6:31 PM
| @venkatesh.hossalinever@penske.com , Onboarding develop branch to bamboo and deploying to dev completed. Please verify. | Gayam | 05/18/23 12:55 AM
| @venkatesh.hossalinever@penske.com , Because of recent architectural change from Hugo / @shane.myers@penske.com , we changed the scope of log4j jars from provided scope compile scope. Please verify and merge to develop branch. Thanks. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelcardsplit-web/pull-requests/6/overview | Gayam | 05/22/23 11:57 PM
Row 90 | @revathi.kandasamy@penske.com , Dev deployment is completed from develop_log4j. https://bamboo.penske.com/browse/FCARDBP-FCRDALBLD1/deployments Could you please verify. Also please merge the PR which is raised from develop_log4j to develop branch. | Gayam | 04/25/23 12:59 AM
Row 90 | @praneeth.gayam@penske.com : log4j and Maven changes looks good. Can you do dev deployment for testing. | Kandasamy | 04/20/23 6:49 PM
| Sure @revathi.kandasamy@penske.com . It looks like the PR is not yet merged. Could you please merge. | Gayam | 04/21/23 1:33 AM
Row 90 | Review: @venkatesh.hossalinever@penske.com , this is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelcardsplit-web/pull-requests/3/overview | Gayam | 03/08/23 2:35 AM
Row 90 | Venkatesh Hossalinever reports "No remediation is required for all False positives, these files are not using credentials. There are no code changes required to fuelcardsplit.var" | William Spohn | 02/24/23 9:16 PM
| Thank you. Changed the status to (Cap)Maven | Gayam | 02/25/23 12:51 AM
Row 90 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 90 | @william.spohn@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:42 AM
Row 90 | I am responsible for testing efuel.war, efueladmin.war, fuelbatch(UAT done), fuelcardsplit.war(UAT done), fuelnetsvc.war(UAT done), and fuelpricing.war. | William Spohn | 01/10/23 10:17 PM
Row 90 | @william.spohn@penske.com , we did not start the log4j/maven changes for this application. Could you please let us know whether you are providing sign off for any other changes. But this sheet is only for log4j/maven changes updates. @mathumala.nachiappan@penske.com | Gayam | 12/12/22 11:52 PM
Row 90 | Yes, Anju Nair emailed me on 11/24 that log4j2 changes to fuelcardsplit.var were ready for testing in QA. I completed my QA testing of this web app - all tests passed. Please consider this my QA testing signoff. | William Spohn | 12/08/22 7:44 PM
| Thanks @william.spohn@penske.com . Will take it forward. @praneeth.gayam@penske.com - Pls. ask Dev team to identify the rest other modernization changes requried | Mathumala Nachiappan | 12/12/22 4:53 PM
Row 90 | hi @william.spohn@penske.com - Is it related to Log4j modernization? | Mathumala Nachiappan | 12/08/22 3:53 PM
Row 90 | I tested "fuelcardsplit.war" in QA for Anju Nair and all tests passed. | William Spohn | 12/07/22 7:17 PM
Row 91 | Thanks @venkatesh.hossalinever@penske.com / @revathi.kandasamy@penske.com . I am changing the status to duplicate app as per your instructions. | Gayam | 05/31/23 12:56 AM
Row 91 | @praneeth.gayam@penske.com FuelNet application doesn't require migration. Please close this task. | Venkatesh | 05/30/23 9:36 PM
Row 91 | @praneeth.gayam@penske.com , the given bamboo build has only the test code. Hence it doesnt require any migration. The following is the svn path https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet_testing | Kandasamy | 05/26/23 4:46 PM
Row 91 | Hi Gayam, I have discussed with Venkatesh - he will review and confirm if this bamboo build and svn repo are related to fuelnet or not. | William Spohn | 05/09/23 3:03 AM
Row 91 | Hi Gayam. I know of only 2 Java applications for my Telapoint/FuelNet module: fuelnetsvc.war and fuelbatch.war. In my nearly 12 years as project lead for Fuel, I have never heard of a 3rd Java application. I will confirm with Venkatesh. | William Spohn | 05/04/23 6:42 PM
| Sure @william.spohn@penske.com . Thank you. | Gayam | 05/05/23 6:32 AM
| Hi Gayam. I checked with Venkatesh. We both think this entry "fuelnet" is a duplicate of "fuelnetsvc.war". | William Spohn | 05/06/23 1:04 AM
| Thanks @william.spohn@penske.com . Just for your info. We found following Bamboo build and SVN URL which are not related to fuelbatch and fuelnetsvc. https://bamboo.penske.com/browse/FNSVC-FNWSPROD SVN Repo associated with this bamboo build: https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet_testing/ Please check and confirm whether this bamboo build and svn repo are related to fuelnet or not. Depends on that we can take the decision whether it is a duplicate or not. | Gayam | 05/06/23 2:30 AM
Row 91 | @william.spohn@penske.com / @venkatesh.hossalinever@penske.com , We are unable to find the Bamboo build and svn repo for fuelnet batch application. Could you please help us to find the info. Thanks. | Gayam | 05/04/23 12:23 AM
Row 92 | This application is deployed to QA and ready for UAT. cc: @praneeth.gayam@penske.com @william.spohn@penske.com | Venkatesh | 10/06/23 6:22 PM
| @venkatesh.hossalinever@penske.com , We are not seeing the deployments in bamboo. Could you please check and confirm. https://bamboo.penske.com/browse/FNSVC-FNSALBLD3/deployments | Gayam | 10/10/23 12:06 AM
Row 92 | @praneeth.gayam@penske.com Could you please change slf4j version for FuelNetSvc in develop branch from 2.0.6 to 1.7.36 as the logs are not printing in dev Also we need to remove the context param, listener refering to old log4j property file in web.xml. Then delete the log4j.properties file from the application code. Kindly let me know after the changes are done, to test in dev. Regards, Revathi.K | Kandasamy | 08/18/23 6:03 PM
| @revathi.kandasamy@penske.com , We will change and get back to you. | Gayam | 08/18/23 8:12 PM
| @revathi.kandasamy@penske.com , Changes are completed and merged to develop branch | Gayam | 08/22/23 1:21 AM
Row 92 | @revathi.kandasamy@penske.com , Dev deployment is completed from develop_log4j. https://bamboo.penske.com/browse/FNSVC-FNSALBLD Could you please verify. Also please merge the PR which is raised from develop_log4j to develop branch. | Gayam | 04/25/23 1:01 AM
| @venkatesh.hossalinever@penske.com , Please merge https://bitbucket.penske.com/projects/PBTFUEL/repos/fuelnetsvc-web/pull-requests/3/overview and deploy the version from develop branch. | Gayam | 06/08/23 3:39 AM
| @praneeth.gayam@penske.com Code changes are merged. can you please deploy changes on dev branch. | Venkatesh | 06/22/23 2:26 AM
| @venkatesh.hossalinever@penske.com , Build is automatic once the code merged to develop branch. Please deploy to dev and QA and test it. Thanks. | Gayam | 06/22/23 3:18 AM
Row 92 | @praneeth.gayam@penske.com : Log4j and Maven changes looks good. Can you deploy app in dev for testing. | Kandasamy | 04/20/23 6:55 PM
| Sure @revathi.kandasamy@penske.com . It looks like the PR is not yet merged. Could you please merge. | Gayam | 04/21/23 1:36 AM
Row 92 | Review: @venkatesh.hossalinever@penske.com / @william.spohn@penske.com , This app is ready for your review. Please check. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelnetsvc-web/pull-requests/3/overview | Gayam | 03/04/23 2:01 AM
Row 92 | Venkatesh Hossalinever reports "No remediation is required for all False positives, these files are not using credentials. There are no code changes required for fuelnetsvc.war. | William Spohn | 02/24/23 9:40 PM
| Thank you. Changed to (Cap)Maven. | Gayam | 02/25/23 12:57 AM
Row 92 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 92 | @william.spohn@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:43 AM
Row 92 | @william.spohn@penske.com , This application is using sun.misc.* import statements from rt.jar which is part of java 6 version . But the rt.jar of java 1.8 doesn't have those packages. So code is not compiling. The code changes may required for this app. Could you please check it. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 01/17/23 12:32 AM
| I will update Venkatesh; then he/his team can assist you. | William Spohn | 01/17/23 7:19 PM
| Is this application in BItbucket or SVN still? Can you please sure the URL. Thank you. I can review. | Hugo Scavino | 01/18/23 2:09 AM
| @hugo.scavino@penske.com , https://svn.penske.com/svn/fieldsys/other/fuelnetwebservice/ is the URL. Branch is branches/fuelnetsvc/fuelnetsvc | Gayam | 01/18/23 2:14 AM
| I Moved the code to to src/main/ root. and also replaced the Base64 code with hopefully a JDK compliant replacement. Updated the imports to slf4j but still need a ported log4j2.xml Also added a maven pom.xml. The mavenization is not complete but the old compiler dependency should be resolved. In the pom.xml please update the development.distribution.url value and distributionManagement elements. More work is required but you should be over this blocker. see the branch here and proceed please https://svn.penske.com/svn/fieldsys/other/fuelnetwebservice/branches/maven/ | Hugo Scavino | 01/18/23 10:29 PM
| Thanks @hugo.scavino@penske.com . We will check and get back to you. Changing the status to (Cap)Log4j | Gayam | 01/18/23 11:19 PM
Row 92 | am responsible for testing efuel.war, efueladmin.war, fuelbatch(UAT done), fuelcardsplit.war(UAT done), fuelnetsvc.war(UAT done), and fuelpricing.war. | William Spohn | 01/10/23 10:17 PM
Row 92 | @william.spohn@penske.com , we did not start the log4j/maven changes for this application. Could you please let us know whether you are providing sign off for any other changes. But this sheet is only for log4j/maven changes updates. @mathumala.nachiappan@penske.com | Gayam | 12/12/22 11:52 PM
Row 92 | Yes, Anju Nair emailed me on 11/24 that log4j2 changes to fuelnetsvc.var were ready for testing in QA. I completed my QA testing - all tests passed. Please consider this my QA testing signoff. | William Spohn | 12/08/22 7:45 PM
| Thanks @william.spohn@penske.com . Will take it forward. @praneeth.gayam@penske.com - Pls. ask Dev team to identify the rest other modernization changes requried | Mathumala Nachiappan | 12/12/22 4:53 PM
Row 92 | hi @william.spohn@penske.com - Is it related to Log4j modernization? | Mathumala Nachiappan | 12/08/22 3:53 PM
Row 92 | I tested fuelnetsvc.war in QA for Anju Nair and all tests passed. | William Spohn | 12/07/22 7:18 PM
Row 93 | @revathi.kandasamy@penske.com , This app is ready for your review. Please check. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelpricing-web/pull-requests/3/overview | Gayam | 04/05/23 2:43 AM
| @praneeth.gayam@penske.com Changes looks good and merged to dev branch. please deploy application on dev environment. | Venkatesh | 06/22/23 2:30 AM
| Thanks @venkatesh.hossalinever@penske.com | Gayam | 06/22/23 3:25 AM
| @venkatesh.hossalinever@penske.com , This app is onboarded to bamboo but test cases are failing. Currently, we disabled the test cases. So build got successful an deployed to dev. | Gayam | 06/23/23 11:49 PM
| @revathi.kandasamy@penske.com Can you review and if changes looks good than plan for Dev and QA deployment. | Venkatesh | 08/15/23 8:48 PM
Row 93 | PFA for the issue we get while executing application maven build. Architect team has recommended us to use a different version for below artifacts. <artifactId>security-author-filter</artifactId> <version>2.0.0-develop-20230220.233353-1</version> <artifactId>security-util</artifactId> <version>2.0.0-develop_log4j-20230202.213506-2</version> Kindly update the pom.xml with the above versions | Kandasamy | 03/29/23 6:19 PM
| @revathi.kandasamy@penske.com , Not sure for which app and which branch you are referring to. Log4j team is still working on this app and waiting for the response from AO to the question which we asked above. Question is regarding 'dassupport.jar'. Could you please check and provide your response. | Gayam | 03/29/23 9:02 PM
| I was referring to fuelpricing.war. While checking in local with svn code, dassupport.jar was not required. There was no compilation issue. Pls go ahead with your changes. | Kandasamy | 04/03/23 7:05 PM
Row 93 | @william.spohn@penske.com This app has dependency with 'dassupport.jar' is available. SVN repo is identified for this jar - https://svn.penske.com/svn/architecture/general/das_support/ Bamboo build is not available for this jar. So need confirmation on whether to upload this jar to artifactory or to consider for log4J modernization. If confirmed for Log4J changes, pls. share the reference folder/branch for log4J development. CC: @praneeth.gayam@penske.com , @rafiq.melath@penske.com | Mathumala Nachiappan | 01/10/23 10:54 AM
| @william.spohn@penske.com , Just want to update you, fuelpricing build is getting successful without using dassupport.jar. Do you want us to continue without including dassupport.jar. If not please let us know whether we can upload this jar to artifactory. | Gayam | 02/23/23 12:39 AM
Row 93 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 93 | Secrets Mitigation: @william.spohn@penske.com , Adding to above questions, we have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:44 AM
Row 93 | Let me know when fuelpricing.war is ready to test. | William Spohn | 01/10/23 10:18 PM
| @william.spohn@penske.com , Could you please check above question and provide your response. | Gayam | 01/11/23 8:58 AM
| I will update Venkatesh, then he/his team can assist you. | William Spohn | 01/17/23 7:20 PM
| @william.spohn@penske.com / @venkatesh.hossalinever@penske.com , Could you please provide the response to the question which i asked above. | Gayam | 01/27/23 11:55 PM
Row 94 | Please start mavenization on the code and we will work on creating property files during app status 6.1 | Dylan | 08/24/23 9:44 PM
| @dylan.price@penske.com , We have completed the changes. But I believe current bamboo plans are not supporting multi module projects. Could you please check with Architecture team and guide us whether we need to separate the modules into different projects. https://bitbucket.penske.com/projects/PBTFUEL/repos/fuel-promotions-service/pull-requests/11/overview | Gayam | 09/01/23 9:57 AM
Row 94 | Secrets: @elliott.eames@penske.com , I sent the secrets of this app in an email. Please check and confirm whether it requires any code changes. Thanks. | Gayam | 07/18/23 1:33 AM
Row 94 | Hi @praneeth.gayam@penske.com https://bitbucket.penske.com/projects/PBTFUEL/repos/fuel-promotions-service/browse?at=refs%2Fheads%2Fdevelop should be the branch to use | Dylan | 06/07/23 1:37 AM
| Thanks @dylan.price@penske.com | Gayam | 06/08/23 7:58 AM
Row 94 | as per @elliott.eames@penske.com here is the Fuel Promotions Service out on BitBucket. It was placed in EBIZ CUSTOMER EXTRANET because that is where Saumya Bhatnagar and his team placed it when developing! https://bitbucket.penske.com/projects/EBCE/repos/fuel-promotions-service/browse?at=refs%2Fheads%2Felliott_upgrade_fuel_promotion | Dylan | 03/07/23 7:40 PM
| Thanks @dylan.price@penske.com . Which branch we need to take as base branch for the log4j changes? | Gayam | 03/07/23 11:54 PM
Row 94 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 94 | @elliott.eames@penske.com - As per the app details, bamboo project key mentioned is 'FP'. But this project is identified with the Bamboo project key as 'EXTSER'. Pls. confirm and share the Repo details as well as the branch to be referred for log4J Modernization. CC: @rafiq.melath@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:18 AM
Row 95 | @praneeth.gayam@penske.com merged the MR | Mahipal | 05/16/23 7:53 PM
| @mahipal.podduturi@penske.com , We will let you know once we onabord develop branch to bamboo and build it. | Gayam | 05/17/23 3:24 AM
| Onboarding develop branch to bamboo is done and build is completed. Please deploy to QA. | Gayam | 05/18/23 1:00 AM
Row 95 | @sherin.basheer@penske.com alreday tested this application good move completed status | Mahipal | 05/09/23 8:06 PM
| @mahipal.podduturi@penske.com , MR is still in open status. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelrecpt-batch/pull-requests/8/overview Could you please merge. Then we will onboard develop branch to Bamboo. | Gayam | 05/09/23 10:38 PM
Row 95 | @praneeth.gayam@penske.com can you deploy this app as well in QA | Mahipal | 05/04/23 6:34 PM
| @mahipal.podduturi@penske.com we will update the main class in pom and will let you know. | Gayam | 05/05/23 6:28 AM
| @mahipal.podduturi@penske.com , Changed the pom file and committed to develop_log4j branch. we are not supposed to do the QA deployment. Only AO needs to do the QA deployment. Please build and do the deployment from develop_log4j branch which is already onbaorded in bamboo. thanks. | Gayam | 05/06/23 2:53 AM
Row 95 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:30 AM
Row 95 | I think the error above also applies to the issue with dlinkappremoval - please verify that the main class is being set by the bamboo plan in the manifest file | William | 12/23/22 11:07 PM
Row 95 | This batch is not running properly in QA. The message in the logs says "2022-11-04 10:00:43,195 FATAL (BatchMain.java:main():75) - There was an unhandled exception java.lang.IllegalArgumentException: The batch jar main class property [batch-jar-main-class] was not set. at com.penske.architecture.batchframework.config.PropertiesConfigurator.loadConfiguration(PropertiesConfigurator.java:48) at com.penske.architecture.batchframework.launcher.Launcher.<init>(Launcher.java:51) at com.penske.architecture.batchframework.BatchMain.main(BatchMain.java:71) | William | 12/23/22 11:07 PM
Row 95 | @mathumala.nachiappan@penske.com assuming you are done with everything and ready to handoff for AO to final test - I moved it to AO Final Testing. @shane.myers@penske.com Please work with Mathu on what is needed to complete this app. Thank you | Yvette Urso | 12/09/22 12:50 AM
Row 95 | @yvette.urso@penske.com - This App is available for testing in QA. Pls. suggest the status | Mathumala Nachiappan | 11/23/22 3:30 AM
Row 95 | @sherin.basheer@penske.com - QA Deployment done on 13th Nov. | Mathumala Nachiappan | 11/23/22 3:29 AM
Row 96 | Maven log4j changes were deployed to production. | Sherin | 06/20/23 11:53 PM
Row 96 | Application threw new error: The was an error: org.springframework.beans.factory.BeanInitializationException: Could not load properties; nested exception is java.io.FileNotFoundException: class path resource [conf/fuelreceiptbatch.properties] cannot be opened because it does not exist Properties file and mappers were inside conf folder pre-mavenizing. Moving them to conf folder should fix this issue. | Sherin | 03/02/23 3:20 AM
Row 96 | App threw start up error 2022-12-16 23:57:18,272 FATAL (BatchMain.java:main():75) - There was an unhandled exception java.lang.IllegalArgumentException: The batch jar main class property [batch-jar-main-class] was not set. at com.penske.architecture.batchframework.config.PropertiesConfigurator.loadConfiguration(PropertiesConfigurator.java:48) This was fixed by adding fuelrecpt-qa.prop file and including *.prop in bin.xml file | Sherin | 03/02/23 3:18 AM
Row 96 | @yvette.urso@penske.com - Repeated entry of #37. Pls. remove this | Mathumala Nachiappan | 11/23/22 3:59 AM
Row 97 | App deployed to PROD on 09/26/2023 | Sreekanth | 09/27/23 1:32 AM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 09/27/23 2:04 AM
Row 97 | @sreekanth.kancharla@penske.com , This app is onboarded to Bamboo. Please verify. https://bamboo.penske.com/browse/GEWEBCASH-GEWEB | Gayam | 03/30/23 11:07 PM
| @sreekanth.kancharla@penske.com , We chagned the log4j2 jars scope from provided to compile. So please merge the code. https://bitbucket.penske.com/projects/ITFIS/repos/gewebcash-batch/pull-requests/5/overview | Gayam | 05/24/23 2:18 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 05/24/23 9:04 PM
Row 97 | @sreekanth.kancharla@penske.com , this app is onboarded to Bamboo. Please check and let us know whether it can be deployed to Dev. | Gayam | 03/23/23 11:05 PM
| @praneeth.gayam@penske.com Please change the name in bamboo from "gewebcash" to "gewebcash-batch" similar to bitbucket repo name. I suggest to make similar changes to keep the name in both Bamboo & Bitbucket as same for all the new plans. | Sreekanth | 03/25/23 2:22 AM
| @praneeth.gayam@penske.com Do you've any update on changing the names? This is batch app, so no DEV environment. We'll take care of deploying to QA once validated in local. | Sreekanth | 03/30/23 12:22 AM
Row 97 | @praneeth.gayam@penske.com The PR got auto declined by bitbucket, so I've re-opened it and merged also. Hope that won't cause any issues as the status is still with Cap team. | Sreekanth | 03/21/23 6:03 PM
| No Issues @sreekanth.kancharla@penske.com . Thanks. We will onbaord this app to Bamboo. | Gayam | 03/22/23 12:43 AM
Row 97 | @praneeth.gayam@penske.com Since the status is under Cap team, please remove me from the review list for the existing PR in bitbucket. https://bitbucket.penske.com/projects/ITFIS/repos/gewebcash-batch/pull-requests/3/overview You can add back, once the PR is available for my review. | Sreekanth | 03/16/23 1:01 AM
| Sure @sreekanth.kancharla@penske.com . Thanks. | Gayam | 03/17/23 2:59 AM
Row 97 | @praneeth.gayam@penske.com In that case please create a new project for this application in Bamboo as there is no existing plan available. @mathumala.nachiappan@penske.com @srinivasan.narayanan@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/03/23 2:10 AM
Row 97 | @rafiq.melath@penske.com / @srinivasan.narayanan@penske.com / @sreekanth.kancharla@penske.com , We found the SVN url for this app https://svn.penske.com/svn/webprojects/admin/gewebcash/ But there is no bamboo build. Could you please provide the production version of the branch and under which project we need to create Bamboo specs. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/11/23 9:08 AM
| @praneeth.gayam@penske.com This is a batch application running on IBMi server from IFS. There is no trunk svn source available, so we compared the production source with offshore source and committed the PROD source under https://svn.penske.com/svn/webprojects/admin/gewebcash/trunk FYI, this application has only 1 java file. @mathumala.nachiappan@penske.com @swati.saxena@penske.com @srinivasan.narayanan@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/02/23 3:06 AM
| Thanks @sreekanth.kancharla@penske.com . Do you want us to take up the https://svn.penske.com/svn/webprojects/admin/gewebcash/trunk and do the modernization? Also, under which project do you want us to create Bamboo builds for this project? | Gayam | 02/02/23 3:23 AM
| @praneeth.gayam@penske.com Yes, please continue modernization with trunk branch. Which project means? This is separate application comes under Admin group, so separate plan in Bamboo is required. OR If we can have "admin-as400-utilities" as a project and under that also we can've build plans as we've few more similar batch applications runs on IBMi. @kalrav.khamar@penske.com @srinivasan.narayanan@penske.com | Sreekanth | 02/02/23 3:47 AM
| @sreekanth.kancharla@penske.com , In Bamboo, every application or group of similar apps have project. For example, under the below project in bamboo all ACH(Batch, Service and Web) build & deploy plans are created. All these are old plans. But we know where to create the new plans for ACH as the project already exist in Bamboo. https://bamboo.penske.com/browse/ACH But for gewbcash, there is no old build plans i.e no project exist in Bamboo. So could you please let us know whether to create a new project or use any other existing Admin project? @haribabu.challa@penske.com @mathumala.nachiappan@penske.com | Gayam | 02/02/23 11:05 PM
Row 97 | @rafiq.melath@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for these applications. | Gayam | 11/23/22 12:31 AM
| @rafiq.melath@penske.com / @srinivasan.narayanan@penske.com / @sreekanth.kancharla@penske.com , Could you please respond to above question. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 1:12 AM
Row 97 | @rafiq.melath@penske.com @praneeth.gayam@penske.com @mathumala.nachiappan@penske.com Hi Rafiq, We are testing out the email functionality in Smartsheet confirming you are receiving emails from here. Regards, Yvette | Yvette Urso | 11/25/22 11:29 PM
Row 98 | @praneeth.gayam@penske.com Thanks praneeth, changes has been deployed to production. | Venkatesh | 10/04/23 1:06 AM
| Thanks @venkatesh.hossalinever@penske.com | Gayam | 10/04/23 1:48 AM
Row 98 | @praneeth.gayam@penske.com Could you please add the below dependency , for invarcsftpbatch in develop branch. <dependency> <groupId>com.penske.mis.common.customlib.oracle</groupId> <artifactId>ojdbc8</artifactId> <scope>${sharedLibScope}</scope> </dependency> scope :: <sharedLibScope>provided</sharedLibScope> | Nayum | 08/30/23 7:14 PM
| Sure @pathan.nayum@penske.com . We will modify and let you know. | Gayam | 08/30/23 10:44 PM
| @pathan.nayum@penske.com , Completed. Please verify the develop branch. | Gayam | 09/01/23 12:16 AM
Row 98 | @praneeth.gayam@penske.com Could you please change log4j version from 2.20.0 to 2.17.2, slf4j version from 2.0.6 to 1.7.36 and spring version 4.3.8.RELEASE to 4.3.30.RELEASE for invarcsftpbatch in develop branch. | Nayum | 08/24/23 12:41 PM
| @pathan.nayum@penske.com , Changes are compelted and merged to develop. Pelase check. | Gayam | 08/25/23 12:01 AM
Row 98 | @praneeth.gayam@penske.com High Radius application will not be retired. Please proceed with the log4j migration. CC: @rafiq.melath@penske.com @mark.weaver@penske.com @revathi.kandasamy@penske.com | Venkatesh | 08/17/23 8:29 PM
| @venkatesh.hossalinever@penske.com , alredy mavanization completed and deployed to QA. Plese verify. Thanks. https://bamboo.penske.com/browse/INVARCBATCHBP-INVSFTP/deployments | Gayam | 08/18/23 12:45 AM
Row 98 | Business has decided not to use this product. this app will be retired. | Rafiq Melath | 08/15/23 11:47 PM
Row 98 | @praneeth.gayam@penske.com : could you pls provide access to the project folder https://bitbucket.penske.com/projects/PA/repos/invarcsftpbatch/browse | Kandasamy | 08/14/23 8:22 PM
| I asked team to add you in RBAC group PTL-Billing-Development | Gayam | 08/15/23 1:02 AM
Row 98 | @venkatesh.hossalinever@penske.com , Deploy plan onboarded and deployed to QA. Please check and verify. Thanks. deploy plan: https://bamboo.penske.com/browse/INVARCBATCHBP-INVSFTP/deployments qa deployment: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151196298 | Gayam | 08/04/23 1:07 AM
Row 98 | Review: @venkatesh.hossalinever@penske.com , This app is ready for your review. Please validate and merge. https://bitbucket.penske.com/projects/PA/repos/invarcsftpbatch/pull-requests/3/overview | Gayam | 06/30/23 1:06 AM
| @praneeth.gayam@penske.com code has been merged. Please deploy changes on QA. As we don't have Dev box for batch application. | Venkatesh | 08/02/23 2:58 AM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 08/02/23 3:04 AM
Row 98 | @praneeth.gayam@penske.com Can you please share the secrets once again. | Venkatesh | 05/16/23 12:55 AM
| @venkatesh.hossalinever@penske.com , Sent secrets in email. | Gayam | 05/17/23 3:28 AM
| @praneeth.gayam@penske.com secrets has been reviewed there are no hardcoded values. Please proceed with the next step. | Venkatesh | 06/22/23 2:27 AM
| Thanks @venkatesh.hossalinever@penske.com . Changing the status to Cap Maven. | Gayam | 06/22/23 3:23 AM
Row 98 | @mark.weaver@penske.com , secrets of this app shared in the email. Please check. Thanks. | Gayam | 03/24/23 12:19 AM
Row 98 | Repo for this application is https://bitbucket.penske.com/projects/PBJB/repos/invarcsftpbatch/browse/src and bamboo link is https://bamboo.penske.com/browse/INVARCBATCHBP-INV | Dylan | 03/07/23 1:57 AM
Row 98 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 98 | Moved to AO Bamboo status | Yvette Urso | 12/15/22 2:45 AM
Row 98 | @mark.weaver@penske.com - Pls. share the Repo URL or the Bamboo project key for this applicaiton. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 12:00 PM
Row 99 | Query: @gregg.obst@penske.com , In this app, HighAvailabilityDataSource class is giving an error which is "The type HighAvailabilityDataSource must implement the inherited abstract method CommonDataSource.getParentLogger()". If we add this unimplemented method the error is getting resolved. But log4j team can't modify or implement any new code. Could you please suggest How can we proceed further? | Gayam | 08/25/23 12:48 AM
| Guyam which BitBucket Repo and branch am I supposed to be looking at for this ? In the football-web in BitBucket I see several branches, which one should I be using to investigate ? | Gregg | 08/30/23 2:08 AM
| @gregg.obst@penske.com , Location of repo is https://svn.penske.com/svn/architecture/general/highavail/branches/dev_gh/ | Gayam | 08/30/23 6:26 PM
| @praneeth.gayam@penske.com not SVN. There is a BitBUcket repo at ssh://git@bitbucket.penske.com:7999/main/football-web.git which has several branches in it. See: https://bitbucket.penske.com/projects/MAIN/repos/football-web/branches Which of those branches should I be using ? | Gregg | 08/30/23 8:42 PM
| @gregg.obst@penske.com , We are using following branch for football modernization. https://svn.penske.com/svn/fieldsys/maintenance/digital-football/tags/prod/20220405/ This branch is moved to bitbucket master branch and we completed log4j upgradation on top of that and the branch is develop_log4j. Following is the bitucket URL. https://bitbucket.penske.com/projects/MAIN/repos/football-web/browse | Gayam | 08/30/23 10:04 PM
| @praneeth.gayam@penske.com is Football also being mavenized? I see a branch for feature/football_MavenChanges but there doesn't appear to be any pom.xml in there yet. | Gregg | 08/31/23 1:20 AM
| @gregg.obst@penske.com , Please ignore that branch. That is still is in progress. | Gayam | 08/31/23 10:58 PM
| On the error in the highavail.jar I think you will need to go to the Architecture Team to look into that. highavail was an Architecture Team, project not a Maintenance Team project and we are not aware of who uses that jar outside of football so we would have no way of testing that jar with any other app that may be using it. | Gregg | 09/08/23 2:03 AM
| @gregg.obst@penske.com , Do we need to change the AppGroup of this app to Architecture from Maintenance? @yvette.urso@penske.com | Gayam | 09/09/23 12:32 AM
| @praneeth.gayam@penske.com Yes. | Stella george | 09/09/23 12:47 AM
| @shane.myers@penske.com , As per @gregg.obst@penske.com , this application belongs to architecture team . So I changed the owner to you. Could you please check the question asked above and provide your response please. Thanks. | Gayam | 09/09/23 2:14 AM
Row 100 | App deployed in PROD on 08/29/2023 | Sreekanth | 08/30/23 6:23 PM
Row 100 | @sreekanth.kancharla@penske.com , We changed the log4j2 jars scope from provided to compile. So please merge the code. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/70/overview | Gayam | 05/24/23 2:25 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 05/24/23 9:03 PM
Row 100 | @sreekanth.kancharla@penske.com , Changes are completed for this app. For some reason, I am unable to merge the few maven changes to develop_log4j branch. Could you please merge below PR. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/66/overview Once you merge the above PR, please review the code in the below PR. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/67/overview Thanks. | Gayam | 04/19/23 3:24 AM
| @praneeth.gayam@penske.com The below PR is merged. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/66/overview I've added review comments to below PR. Please check and do the need. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/67/overview | Sreekanth | 04/19/23 9:23 PM
| @sreekanth.kancharla@penske.com , We implemented the requested changes. Could you please merge them following PR https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/68/overview Then review the changes in PR https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/67/overview Thanks. | Gayam | 04/22/23 1:55 AM
| @praneeth.gayam@penske.com Thank you for making the changes for review comments. Both the PR are merged. Since we already have bamboo plan for this app with mavenized source, if any changes requires in the plan as per the new log4j template, please proceed with those changes and update the status in the smartsheet. We'll start testing the app once it is delivered to AO. | Sreekanth | 04/24/23 8:18 PM
| @sreekanth.kancharla@penske.com , thank you. We will do the Bamboo setup and will let you know. | Gayam | 04/25/23 1:28 AM
| @sreekanth.kancharla@penske.com , this app is deployed to dev using develop branch - https://bamboo.penske.com/browse/HBP-HRCCALBP0/deployments Please verify. | Gayam | 04/27/23 1:32 AM
| @praneeth.gayam@penske.com This app source code was already available in Bitbucket and the bamboo plans also available. Separate plans for both Web & UI code. Now I see a new plan is created for web https://bamboo.penske.com/browse/HBP-HRCCALBP but no UI plan is created. Have you used existing https://bamboo.penske.com/browse/HBP-HRCCAL plan itself for DEV deployment. Since we've new plan for web, it is good to have new plan for UI also. | Sreekanth | 04/27/23 1:59 AM
| @sreekanth.kancharla@penske.com , we worked on only hrcc-web and the bamboo build for that is https://bamboo.penske.com/browse/HBP-HRCCALBP We did not work hrcc-ui project as this is not mentioned in our list or smartsheets. | Gayam | 04/27/23 3:11 AM
| @praneeth.gayam@penske.com hrcc-ui is not a separate project. That repo has front end code (angular) & hrcc-web has back end code (java). With both those sources only HRCC app can be tested. I suggest to have a new bamboo plan created for hrcc-ui as well, so that we can retire the old plans once we complete the log4j testing. If needed, please schedule a meeting with @raghuramredd.thummalapalli@penske.com / @balu.mohan@penske.com / @hugo.scavino@penske.com for further clarification. | Sreekanth | 04/27/23 6:54 PM
| Sure @sreekanth.kancharla@penske.com . But before onboarding bamboo plan for hrcc-ui, we need to modernize the hrcc-ui project. If you are ok, we can take up the work. | Gayam | 04/28/23 1:44 AM
| @praneeth.gayam@penske.com hrcc-ui is an angular app and available in bitbucket itself. Hope no need of any modernization for UI source code and new bamboo plan can be created with existing source code itself. We can discuss over call on code changes for modernization. | Sreekanth | 05/01/23 6:40 PM
| @sreekanth.kancharla@penske.com , if it contains total UI code and a Bamboo plan already exist, I don't think we need to re onboard any new plan. You can continue using the old bamboo plan of hrcc-ui. Please correct me if I am wrong. @hugo.scavino@penske.com | Gayam | 05/02/23 12:49 AM
| @praneeth.gayam@penske.com We are good to use the existing plan itself for UI. In that case, just to follow the naming convention, is it possible to change the name of the build plan https://bamboo.penske.com/browse/HBP-HRCCAL to "hrcc-ui" & the deploy plan also with the new naming convention. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=91160582 | Sreekanth | 05/02/23 7:24 PM
| @sreekanth.kancharla@penske.com , I think you need to raise a fp ticket to change the names of hrcc-ui . Because the plans of hrcc-ui not created by log4j team and we don't have control on that. Thanks. | Gayam | 05/03/23 1:49 AM
| @praneeth.gayam@penske.com Sure, thank you! | Sreekanth | 05/03/23 7:47 PM
Row 100 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:54 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets as all of them are related to mybatis xml files. You are good to proceed further. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 12:22 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (Cap) Maven | Gayam | 01/27/23 2:41 AM
Row 101 | @mahipal.podduturi@penske.com , As discussed develop branch already contains all the code. Please check. | Gayam | 05/31/23 12:58 AM
Row 101 | for build and deploy | Mahipal | 05/30/23 6:48 PM
Row 101 | @praneeth.gayam@penske.com i am not seeing develop _log4j branch | Mahipal | 05/30/23 6:48 PM
Row 101 | am not seeing the devlop branch | Mahipal | 05/04/23 6:33 PM
| We will onboard develop and will let you know. | Gayam | 05/05/23 6:12 AM
| @mahipal.podduturi@penske.com , Test cases are getting falied. But for now, we skipped the test cases. So build is getting successful. Please deploy to QA using below plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=142737434 Also, please fix the test cases. Because the manual configuration may be overridden in future. | Gayam | 05/06/23 3:01 AM
Row 101 | @praneeth.gayam@penske.com can you deploy the app | Mahipal | 05/04/23 6:33 PM
Row 101 | @shane.myers@penske.com - QA Deployment done on 17th Nov. @yvette.urso@penske.com - This app is available for testing in QA. Pls. suggest the status | Mathumala Nachiappan | 11/23/22 3:32 AM
Row 102 | App deployed to PROD on 10/12/2023 | Sreekanth | 10/12/23 10:27 PM
Row 102 | @praneeth.gayam@penske.com this app depends on irs.jar and irs.jar is built with xsd folder. We thought the xsd folder is not being used in hvutefile explicitly but we are wrong. This app requires both irs.jar & xsd also to be part of the source in order to run. So, we've placed the xsd folder also in hvutefile source. Latest code is available in "develop" branch. If possible, can we generate the java source from xsd in hvutefile application itself & generate hvutefilebatch.jar file with both hvutefile (com.penske.apps.hvut) & irs (gov.irs.efile) packages. If this works, we can completely remove the irs repo in bitbucket & corresponding bamboo plans & irs artifactory dependency. All the source can be maintained in single repo i.e. hvutefilebatch. | Sreekanth | 10/05/23 1:04 AM
| Sue @sreekanth.kancharla@penske.com . We will check and get back to you. | Gayam | 10/05/23 1:11 AM
| I could see a PR is created to develop branch. Posted a comment in Bitbucket. Please check. We are also going live without combining both the applications. If we've the source ready with combined logic, then we'll use that next time when we make any changes to the application. | Sreekanth | 10/10/23 9:04 PM
Row 102 | Review: @sreekanth.kancharla@penske.com , This app is ready for youe review. https://bitbucket.penske.com/projects/PTLCORP/repos/hvutefile-batch/pull-requests/3/overview | Gayam | 07/09/23 11:50 PM
| @praneeth.gayam@penske.com Thank you! Merged the PR. We'll start testing this app. Please change the App Status accordingly. | Sreekanth | 07/10/23 7:09 PM
| @sreekanth.kancharla@penske.com , Do we need to onboard to bamboo? | Gayam | 07/10/23 11:27 PM
| @praneeth.gayam@penske.com Yes, please! | Sreekanth | 07/11/23 12:02 AM
| @praneeth.gayam@penske.com In develop branch, the version "2.0.0-feature-irs_Maven_XSD-to-java--20230628.124813-3" is provided. Do we need to have the version hard coded. We'll place the irs source in the irs repo and execute the build plan which should placed the jar in artifactory & this latest jar should be loaded in hvutefile batch app. Hope in this case, hard coded version would not work. | Sreekanth | 07/11/23 12:05 AM
| @sreekanth.kancharla@penske.com , I think if we remove the version, it always brings the latest version. But when you execute the build of irs, you should build the hvute also to get the latest irs files to hvute. | Gayam | 07/11/23 11:47 PM
| @praneeth.gayam@penske.com Yes, that is how the hvutefile app works. We always build the irs jar with latest source code and then once that build is successful, we'll initiate the build for hvutefile app, so latest irs will be used in the build. So getting the latest version of irs.jar is expected. | Sreekanth | 07/12/23 2:08 AM
| @sreekanth.kancharla@penske.com , Changed the version from specific number to 'RELEASE'. It is taking whatever latest IRS release from artifactory. | Gayam | 07/25/23 12:00 AM
| @praneeth.gayam@penske.com Perfect! We'll work on testing the app, once the issue with irs.jar is resolved. | Sreekanth | 07/25/23 5:35 PM
| irs issue is resolved. Please check this application. Thanks. | Gayam | 08/02/23 2:47 AM
| @praneeth.gayam@penske.com Great, we'll continue testing this application as well. Thank you! | Sreekanth | 08/03/23 9:20 PM
| @sreekanth.kancharla@penske.com , Release version of irs jar is available in artifactory and build of develop_log4j branch of hvute is working fine. Please verify. | Gayam | 08/18/23 12:24 AM
| @praneeth.gayam@penske.com Please create PR to develop branch. | Sreekanth | 08/18/23 7:43 AM
| @sreekanth.kancharla@penske.com Following is the PR. https://bitbucket.penske.com/projects/PTLCORP/repos/hvutefile-batch/pull-requests/6/overview | Gayam | 08/18/23 8:03 PM
| @praneeth.gayam@penske.com PR merged. Thank you! We'll continue testing. | Sreekanth | 08/18/23 8:37 PM
| @praneeth.gayam@penske.com We are getting below warning with IRS jar with version as RELEASE in local maven build. Is there anything we need to do? Some problems were encountered while building the effective model for com.penske.corp:hvutefilebatch:jar:2.0.0-SNAPSHOT 'dependencies.dependency.version' for com.penske.corp:irs:jar is either LATEST or RELEASE (both of them are being deprecated) @ line 79, column 13 It is highly recommended to fix these problems because they threaten the stability of your build. For this reason, future Maven versions might no longer support building such malformed projects. | Sreekanth | 09/06/23 7:40 PM
| Yes @sreekanth.kancharla@penske.com . They are recommending to maintain the version numbers. But if we want always the latest then we have to use RELEASE which is not recommended. | Gayam | 09/07/23 1:31 AM
| @praneeth.gayam@penske.com As suggested, used 1.0.0-SNAPSHOT in hvutefile but getting below error in local build. Could not resolve dependencies for project com.penske.corp:hvutefilebatch:jar:2.0.0-SNAPSHOT: Could not find artifact com.penske.corp:irs:jar:1.0.0-SNAPSHOT in corp-mvn-virtual (https://artifactory.penske.com/artifactory/corp-mvn-virtual) | Sreekanth | 09/09/23 12:17 AM
Row 102 | Query: @veronique.labeille@penske.com , Adding to above secrets validation, there is one more query. This app depends on irs.jar but it is not available in artifactory. Could you please provide your approval to upload this jar into artifactory at below location. Groupid: gov.irs.efile Artifactid: irs Thanks. | Gayam | 04/07/23 10:55 PM
| @praneeth.gayam@penske.com irs.jar file is not static dependency. Every 6 months, we get latest files from IRS and with those files the irs.jar file be created via existing bamboo plan (https://bamboo.penske.com/browse/HVUTBP-HVUTFDEV) used for the application jar creation as well. The current bamboo plan generates, both irs.jar and hvutefile.jar which is app specific jar. Post testing the irs.jar file in SUPPORT by users, the same will be pushed to QA & PROD. In this case, please suggest how the irs.jar file can be moved to artifactory. @veronique.labeille@penske.com | Sreekanth | 04/12/23 12:27 AM
| @sreekanth.kancharla@penske.com , what is the repo of irs.jar? If the repo exist, we can mavanize IRS and create a new bamboo plan which uploads the jar to artifactory. Update that dependency in hvutefile pom and rebuild and deploy the hvutefile app. I hope it resolves our issue. Let me know whether I did not understand the requirement correctly. | Gayam | 04/12/23 1:00 AM
| @praneeth.gayam@penske.com The repo for irs.jar also resides in same location of hvutefile i.e. "https://svn.penske.com/svn/webprojects/corp/hvutefile/branches/support/production_latest/xsd" Every time we get the files from IRS, we replace them under xsd folder. We are not sure how the existing bamboo plan generating the 2 jar files. Hope analyzing the bamboo script should help us how the irs.jar is being generated. | Sreekanth | 04/12/23 7:13 AM
| @sreekanth.kancharla@penske.com I extracted the irs.jar and it looks like it has the files from the folder https://bitbucket.penske.com/projects/PTLCORP/repos/hvutefile-batch/browse/irs%20java%20files?at=refs%2Fheads%2Fdevelop In my opinion, we have to segregate hvutefile and irs files into 2 separate projects in bitbucket and 2 separate bamboo builds. We can setup a call with @hugo.scavino@penske.com to discuss on this further. thanks. | Gayam | 04/13/23 12:50 AM
| @praneeth.gayam@penske.com Thank for the details. So are those irs java files not depending on the files from below folder which we need to replace yearly twice? https://bitbucket.penske.com/projects/PTLCORP/repos/hvutefile-batch/browse/xsd?at=refs%2Fheads%2Fdevelop Sure, we can connect with Hugo. Please proceed with scheduling the meeting. | Sreekanth | 04/13/23 1:14 AM
| @sreekanth.kancharla@penske.com , it doesn't seem like that jar has those xsd files. But I am not sure. Could you please check whether there is any relation. | Gayam | 04/13/23 11:25 PM
| @praneeth.gayam@penske.com FP ticket# 1834638 is created to architect team for clarification on irs.jar generation. | Sreekanth | 04/19/23 9:16 PM
| @praneeth.gayam@penske.com We received clarification from Architect team with FP# 1834638. The irs.jar is completely dependent on source/xsd/ETEC/2290/Return2290.xsd folder & source/lib/jaxb-xjc.jar With this the xsd folder is required to build the irs.jar file and these will be changed twice per year. If this can be built as a separate bamboo plan and add this jar as dependency in artifactory, we are ok with that. If so, please have this new plan under the existing bamboo project itself. We can connect with @hugo.scavino@penske.com on this for any further guidance if needed. | Sreekanth | 04/24/23 8:35 PM
| Thanks @sreekanth.kancharla@penske.com . So we need to create separate bitbucket repository for the irs files. Is that correct? @hugo.scavino@penske.com | Gayam | 04/26/23 1:15 AM
| @praneeth.gayam@penske.com Yes, if that needs to be maintained as a separate dependency. | Sreekanth | 04/26/23 6:15 PM
| Sure @sreekanth.kancharla@penske.com . Sent an email to Yvette to add one more line item irs.jar in smartsheets. We will start working on it. Thanks | Gayam | 04/28/23 2:19 AM
| @sreekanth.kancharla@penske.com , Yvette create a separate line item for irs.jar. We will complete that and add that dependency to this project and will let you know. Thanks | Gayam | 05/02/23 1:14 AM
| @sreekanth.kancharla@penske.com , Could you please confirm what are the folders from hvutefile repo need to move to irs repo. I know following. 1. You said source/xsd/ETEC/2290/Return2290.xsd folder. Do you mean total xsd folder source/xsd? 2. source/lib/jaxb-xjc.jar Any other folders are files need to move to irs repo? | Gayam | 05/03/23 2:05 AM
| @praneeth.gayam@penske.com Replied the answer in the irs.jar item. | Sreekanth | 05/03/23 7:46 PM
| @sreekanth.kancharla@penske.com , We are getting compilation issues because of irs.jar doesn't have required java classes. 1.import gov.irs.efile.ObjectFactory; 2.import gov.irs.efile.Return; I believe we need to add 'irs java files' fold r under hvutefile to irs.jar. Could you please check and confirm. Thanks. | Gayam | 05/25/23 3:09 AM
| @praneeth.gayam@penske.com These imports are part of irs.jar file only. Is that dependency added to hvutefile pom, if so we shouldn't get these compiler errors. | Sreekanth | 05/25/23 8:19 PM
| @sreekanth.kancharla@penske.com But irs.jar file doesn't have these java classes. Only schema files. | Gayam | 05/25/23 11:54 PM
| @praneeth.gayam@penske.com The irs.jar file should be generated with the xsd files available under xsd folder. Once the irs.jar file is generated, that needs to be uploaded to artifactory every time, so that hvutefile app used that as dependency. | Sreekanth | 06/01/23 12:14 AM
| @sreekanth.kancharla@penske.com , We are working on it. | Gayam | 06/01/23 10:48 PM
Row 102 | @veronique.labeille@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:28 AM
| @praneeth.gayam@penske.com Except the "conf/as400server.prop" file, no other file required any mitigation. "conf/as400server.prop" - To remove the dependency, we need to implement the connection framework which required some analysis. Either we'll implement the connection framework OR we'll continue with the prop file itself. Please proceed with the log4j changes. @veronique.labeille@penske.com | Sreekanth | 04/12/23 12:22 AM
| Sure @sreekanth.kancharla@penske.com . We will continue with the current code as you suggested. | Gayam | 04/12/23 1:21 AM
Row 102 | @praneeth.gayam@penske.com - SVN to BB migration issue | Mathumala Nachiappan | 02/02/23 10:28 AM
Row 102 | Sure @veronique.labeille@penske.com . Thanks for the confirmation | Mathumala Nachiappan | 02/01/23 8:12 PM
Row 102 | @mathumala.nachiappan@penske.com , would you please add this app to your plan? Thank you | Veronique Labeille | 01/27/23 10:38 PM
Row 102 | @mathumala.nachiappan@penske.com please share that information to me via email with the Fleet Service Team, hugo and Don included. I am not aware of any change to assignment for these. | Yvette Urso | 01/11/23 2:09 AM
Row 102 | @yvette.urso@penske.com - To confirm this application to be taken by CAP for Modernization activity. CC: @brian.hug@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:40 AM
Row 102 | hi @yvette.urso@penske.com - as per the previous communication, modernization will be taken care by the Fleet services team. from the latest update of yours, is it moved under CAP scope for modernization? | Mathumala Nachiappan | 12/08/22 3:51 PM
Row 102 | @mathumala.nachiappan@penske.com this will remain where it it per @veronique.labeille@penske.com - I moved to (Cap) Analysis. Please move to the correct status per your work. | Yvette Urso | 12/02/22 12:15 AM
Row 102 | @veronique.labeille@penske.com @mathumala.nachiappan@penske.com @praneeth.gayam@penske.com - Veronique, can you please confirm this application is no longer a part of Corp App Group and it should be moved to fall under the Fleet Services Team? Thank you | Yvette Urso | 12/01/22 8:39 PM
| @yvette.urso@penske.com , It is part of Fleet Services which is under CORP systems | Veronique Labeille | 12/01/22 9:22 PM
Row 102 | Scope is moved to Fleet services Team. CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com and @april.ottey@penske.com | Mathumala Nachiappan | 12/01/22 8:10 PM
Row 103 | @praneeth.gayam@penske.com please create bamboo plan | Dylan | 09/12/23 1:27 AM
| Sure @dylan.price@penske.com | Gayam | 09/12/23 2:38 AM
| @dylan.price@penske.com , We onboarded this to bamboo but we have a question on this app. This is a batch application but has the dev environment. If we need to deploy to dev environment then instance type is needed. So could you pleaase provide the instance type. Thanks | Gayam | 09/13/23 11:15 PM
Row 103 | Please start mavenization on the code and we will work on creating property files during app status 6.1 | Dylan | 08/24/23 9:44 PM
| @dylan.price@penske.com , Modernization completed on this app. Please verify. https://bitbucket.penske.com/projects/PA/repos/ias-broker-batch/pull-requests/3/overview | Gayam | 09/07/23 12:53 AM
Row 103 | Secrets: @mark.weaver@penske.com / @dylan.price@penske.com , I sent the secrets in the email. Please verify and let us know whether this app requires code changes. | Gayam | 06/28/23 12:55 AM
Row 103 | hi @praneeth.gayam@penske.com this application does not currently have a successful bamboo build for production. The SVN code location for this app is https://svn.penske.com/svn/webprojects/admin/ias/branches/dev_gh/ias-batch-broker7/ The current DEV bamboo build for this app is https://bamboo.penske.com/browse/IAS-IASD | Dylan | 06/13/23 4:56 PM
Row 103 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 103 | @praneeth.gayam@penske.com moved to AO Bamboo status | Yvette Urso | 12/15/22 2:47 AM
Row 103 | @sam.skelding@penske.com / @mark.weaver@penske.com , We are working modernizing(log4j and maven upgrades) the applications. we want to get the production reference branch for this application from bamboo build. We find the Plan branch 'branches/dev_gh/ias-batch-broker7' but there is no successful build from this branch. So could you please check and provide the production branch. @mathumala.nachiappan@penske.com | Gayam | 12/14/22 12:19 AM
Row 104 | @praneeth.gayam@penske.com please create bamboo plan | Dylan | 09/12/23 1:28 AM
| @dylan.price@penske.com , develop_log4j branch onboarded to bamboo https://bamboo.penske.com/browse/IAS-IASINV/deployments | Gayam | 09/13/23 12:50 AM
Row 104 | Hi @praneeth.gayam@penske.com please add pdfservice-client.jar to artifactory. It is only one interface so no need to mavenize it. | Dylan | 09/05/23 10:02 PM
| sure @dylan.price@penske.com | Gayam | 09/06/23 12:59 AM
| @dylan.price@penske.com , Uploaded the jar to artifactory and added the dependency to pom. | Gayam | 09/07/23 12:51 AM
Row 104 | When you mavenize ias-lbs could you please then mavenize this application? | Dylan | 08/24/23 9:43 PM
| @dylan.price@penske.com , We completed mavanization and log4j upgrade. Following is the PR. https://bitbucket.penske.com/projects/PA/repos/ias-invoiceimage-batch/pull-requests/3/overview Couple of things for your reference. 1. This app depends on ias-lbs jar which we are working on it. 2. this app depends on pdfservice-client.jar and it looks like penske jar. Do you want us to upload this jar to artifactory or do you want to modernize this jar. If you want to modernize could you please provide the svn and bamboo location. | Gayam | 08/30/23 3:07 AM
Row 104 | @dylan.price@penske.com , This app relies on lbs-ias.jar which is generated from the app ias-lbs. Therefore, I am marking the status as blocker because this app cannot be completed until the ias-lbs app if finished. | Gayam | 06/30/23 12:52 AM
Row 104 | @dylan.price@penske.com , There are no secrets on this application. So continuing the mavanization. | Gayam | 06/27/23 5:32 AM
Row 104 | hi @praneeth.gayam@penske.com this application does not currently have a successful bamboo build for production. The SVN code location for this app is https://svn.penske.com/svn/webprojects/admin/ias/branches/qa/ias-batch/invoiceimage The current DEV bamboo build for this app is https://bamboo.penske.com/browse/IAS-IASM | Dylan | 06/13/23 4:58 PM
| Thanks @dylan.price@penske.com | Gayam | 06/23/23 5:35 PM
Row 104 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 104 | Issue: Cap is unable to find the code - Move status to AO Bitbucket Review. | Yvette Urso | 12/15/22 2:49 AM
Row 104 | Hi @mark.weaver@penske.com - For this App, we can see only the QA build. Is this deployed in PROD? Pls. confirm this. Also the folder/branch, we can consider for Log4J modernization | Mathumala Nachiappan | 12/07/22 12:04 PM
Row 105 | @praneeth.gayam@penske.com please create bamboo plan | Dylan | 09/12/23 1:28 AM
| Sure @dylan.price@penske.com | Gayam | 09/12/23 2:39 AM
| @dylan.price@penske.com , develop_log4j branch onboarded to bamboo https://bamboo.penske.com/browse/LBS-IASLBS/deployments | Gayam | 09/13/23 12:51 AM
Row 105 | Please bring these down and we will remediate these during our AO testing when the app status moves to 6.1 Please add “LogisticsBilling.jar” to artifactory for use in this app | Dylan | 08/24/23 9:43 PM
| @dylan.price@penske.com , Modernization completed on this app. Please check https://bitbucket.penske.com/projects/PA/repos/ias-lbs-batch/pull-requests/3/overview | Gayam | 08/30/23 9:09 PM
Row 105 | Questions: @dylan.price@penske.com 1. This application consists of a total of 4 classes, each of which contains a main method. i.LBSArchiveLaunch.java ii.LBSDailyArchive.java iii.OnFlyInvoiceTest.java iv.JMXEnvironment.java Which one we need to use? 2. Also, this app depends on LogisticsBilling.jar and need to upload this jar into artifactory. Please provide your approval. | Gayam | 06/16/23 3:14 AM
Row 105 | Hi @praneeth.gayam@penske.com there is one issue where a password is in the property file for this application. I will update this when I merge my changes with the "develop_log4j" changes like in other applications. Could you please start on log4j/maven changes? | Dylan | 06/13/23 5:01 PM
| Sure @dylan.price@penske.com | Gayam | 06/14/23 2:36 AM
Row 105 | Secrets: @mark.weaver@penske.com , secrets of this app shared in the email. Please check. Thanks. | Gayam | 03/24/23 12:11 AM
Row 105 | the repo for this application is https://svn.penske.com/svn/webprojects/admin/lbs/trunk/lbs-ias and the bamboo build is https://bamboo.penske.com/browse/LBS-LBSIASPROD | Dylan | 03/07/23 2:02 AM
| Thanks @dylan.price@penske.com . Changing the status to Cap log4j | Gayam | 03/07/23 6:24 AM
Row 105 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 105 | @mark.weaver@penske.com / @sam.skelding@penske.com , For this application, Bamboo key mentioned in the given excel sheet IAS. Following is the URL for this key. https://bamboo.penske.com/project/viewProject.action?projectKey=IAS But we found this project under the key LBS. URL is https://bamboo.penske.com/project/viewProject.action?projectKey=LBS Could you please check let us know which one is correct. Thanks. @mathumala.nachiappan@penske.com | Gayam | 12/17/22 2:00 AM
Row 106 | @praneeth.gayam@penske.com please create bamboo plan | Dylan | 09/12/23 1:28 AM
| Sure @dylan.price@penske.com | Gayam | 09/12/23 2:37 AM
| @dylan.price@penske.com , develop_log4j branch onboarded to bamboo. https://bamboo.penske.com/browse/IAS-IASW1 | Gayam | 09/13/23 12:48 AM
Row 106 | Hi @praneeth.gayam@penske.com getting the following error: Class path contains SLF4J bindings targeting slf4j-api versions 1.7.x or earlier. could you please look into the SLF4J bindings for this application? | Dylan | 06/14/23 2:26 AM
| Sure @dylan.price@penske.com . we will check | Gayam | 06/14/23 3:41 AM
| @dylan.price@penske.com , we fixed the issue. Please check. | Gayam | 06/16/23 1:40 AM
Row 106 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/ias-web/pull-requests/3/overview | Gayam | 03/23/23 11:40 PM
Row 106 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/27/23 11:15 PM
| Thanks @venkatesh.hossalinever@penske.com . Changing the status to (Cap)Maven. We will let you know when it is ready. | Gayam | 02/27/23 11:22 PM
Row 106 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 106 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:54 AM
Row 107 | @praneeth.gayam@penske.com please create bamboo plan | Dylan | 09/12/23 1:29 AM
| Sure @dylan.price@penske.com | Gayam | 09/12/23 2:35 AM
| @dylan.price@penske.com , develop_log4j branch onboarded to bamboo https://bamboo.penske.com/browse/IAS-ARCHIAS | Gayam | 09/13/23 12:53 AM
Row 107 | Please start mavenization on the code and we will work on creating property files during app status 6.1 | Dylan | 08/24/23 9:44 PM
| @dylan.price@penske.com , We have completed the modernization work of this app. Please verify. Thanks. https://bitbucket.penske.com/projects/PA/repos/iasarchiver-batch/pull-requests/3/overview | Gayam | 08/30/23 3:18 AM
Row 107 | @dylan.price@penske.com / @mark.weaver@penske.com , I sent the secrets file to you in the email. Please verify. Thanks. | Gayam | 07/09/23 11:25 PM
Row 107 | hi @praneeth.gayam@penske.com this application does not currently have a successful bamboo build for production. The SVN code location for this app is https://svn.penske.com/svn/architecture/general/iasarchiver/branches/qa The current QA bamboo build for this app is https://bamboo.penske.com/browse/IAS-IASARCHIVERQA | Dylan | 06/13/23 5:02 PM
Row 107 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 107 | Moved to AO Bamboo Status | Yvette Urso | 12/15/22 2:46 AM
Row 107 | @sam.skelding@penske.com / @mark.weaver@penske.com , We are working modernizing(log4j and maven upgrades) the applications. we want to get the production reference branch for this application from bamboo build. But couldn't figure it out. Could you please check and provide the info. @mathumala.nachiappan@penske.com | Gayam | 12/14/22 12:14 AM
Row 108 | @praneeth.gayam@penske.com please create bamboo plan | Dylan | 09/12/23 1:29 AM
| Sure @dylan.price@penske.com | Gayam | 09/12/23 2:36 AM
| @dylan.price@penske.com , develop_log4j branch onboarded to bamboo https://bamboo.penske.com/browse/IAS-INVSVC | Gayam | 09/13/23 12:54 AM
Row 108 | @venkatesh.hossalinever@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/iasinvservice-web/pull-requests/3/overview | Gayam | 04/06/23 3:14 AM
Row 108 | Completed reviewing the log4j secrets - there are no code changes required. | Venkatesh | 02/27/23 10:11 PM
| Thanks @venkatesh.hossalinever@penske.com . Changing the status to (Cap)Maven. We will let you know when it is ready. | Gayam | 02/27/23 11:24 PM
Row 108 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 108 | @dylan.price@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:49 AM
Row 109 | Making as QA complete waiting for production deploy. | David Graf | 05/09/23 5:16 PM
Row 109 | @hugo.scavino@penske.com log4j2 isn't working please analyze for International Web. https://bitbucket.penske.com/projects/ARPROJ/repos/international-web/browse?at=develop_log4j | David Graf | 04/11/23 5:26 PM
Row 109 | @praneeth.gayam@penske.com just confirming if you saw my last message. | David Graf | 04/04/23 5:33 PM
| @david.w.graf@penske.com , We will onboard the develop_log4j to bamboo and will deploy to Dev. I already informed to my team. They are working on it. Thanks. | Gayam | 04/04/23 11:03 PM
| @david.w.graf@penske.com , develiop_log4j branch is onboarded to bamboo and dev deployment is done from this branch. Please verify. https://bamboo.penske.com/browse/INTRNL-INTERNL | Gayam | 04/06/23 2:35 AM
Row 109 | We can mvn install but cannot run locally so moving to Bamboo stage in order to gain access to testing in the dev environment. Confirming Maven. | David Graf | 03/30/23 5:24 PM
Row 109 | @david.w.graf@penske.com , Following is the PR for your review., Changing the status to (AO)Maven. https://bitbucket.penske.com/projects/ARPROJ/repos/international-web/pull-requests/8/overview | Gayam | 02/23/23 1:21 AM
Row 109 | I reviewed the secrets report. I don’t believe that any of them are true secrets. The closest one is the ApplicationConstants.MEMBER_COMPANY_FOREIGN_CAT_KEY but I think that is just a catalog key which the other system needs to identify us. I don’t think it is used for authentication. Still we could move it into the database table that it already connects to be safe: PSK_INTERNATIONAL.SECRET_VIEW | David Graf | 02/11/23 2:08 AM
| Thanks @david.w.graf@penske.com . Updated the status of the app to (Cap)Maven | Gayam | 02/14/23 11:47 PM
Row 109 | I have added this to work on next. | David Graf | 02/09/23 12:03 AM
Row 109 | @david.w.graf@penske.com , We have completed the secrets scanning on this application and found that there are couple of true positives. I will share the excel report in the email. Could you please check and confirm the true and false positives. Please remediate if there are true positives. Thanks. | Gayam | 01/06/23 1:27 AM
Row 109 | @david.w.graf@penske.com - This app has few hardcoded key values, which need to be confirmed from your side. Let me share this in mail . CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/06/22 8:41 PM
Row 109 | @david.w.graf@penske.com - This app is available for your final review. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/02/22 5:40 PM
Row 109 | @praneeth.gayam@penske.com - PR to raise for AO Review | Mathumala Nachiappan | 11/23/22 3:35 AM
Row 110 | Review: @jeremiah.ashway@penske.com , We have completed all modernization changes on this application without any queries. Please review and merge. https://bitbucket.penske.com/projects/EBCE/repos/intsecuritysvc/pull-requests/3/overview | Gayam | 10/13/23 8:54 AM
Row 110 | Hi, This application has 2 repos. One for the service and one for the client jar. Each repo has it's own build as well. Also, I'm assuming the green star means log4j is ready for review but there is no PR for this. Thanks https://confluence.penske.com/display/EDTS/Intranet+Security+Service @praneeth.gayam@penske.com | Jeremiah Ashway | 10/06/23 9:01 PM
| @jeremiah.ashway@penske.com , Currently we are working on following repo. https://bitbucket.penske.com/projects/EBCE/repos/intsecuritysvc/browse Please let us know whether this is correct or not. Note: Please review the PRs which are raised to develop branch only. There are some PRs which are raised to develop_log4j branch. I need to review the PRs which are raised to develop_log4j. | Gayam | 10/10/23 12:34 AM
Row 110 | There are no secrets found on this app. | Gayam | 10/04/23 2:36 AM
Row 111 | @praneeth.gayam@penske.com please create bamboo plan | Dylan | 09/12/23 1:29 AM
| @dylan.price@penske.com , develop_log4j branch onboarded to bamboo https://bamboo.penske.com/browse/INVARCBATCHBP-INVRCBCH | Gayam | 09/13/23 12:55 AM
Row 111 | @dylan.price@penske.com , This app is ready for your review. Please validate and merge. https://bitbucket.penske.com/projects/PA/repos/invarcbatch-batch/pull-requests/4/overview | Gayam | 06/30/23 12:58 AM
Row 111 | Hi @praneeth.gayam@penske.com this application is fine with secrets. It connects to the database using 2 data sources. Please start maven/log4j changes for this application. | Dylan | 06/02/23 12:52 AM
Row 111 | @praneeth.gayam@penske.com please add iasservice-client to artifactory. I also saw that the secrets file only contained a secret for me for TRSExtract. Could you please resend me the secrets file for invarcbatch? | Dylan | 03/30/23 9:16 PM
| Thanks @dylan.price@penske.com . I just sent secret file to you. Please verify, | Gayam | 03/30/23 11:24 PM
Row 111 | Secrets: @dylan.price@penske.com , shared the secrets in the email. Please check. Thanks. | Gayam | 03/24/23 12:25 AM
Row 111 | the invarcsftpbatch is actually the "High Radius" application. This application is located at https://svn.penske.com/svn/webprojects/admin/invarcbatch/trunk and the bamboo build is https://bamboo.penske.com/browse/INVARCBATCHBP-INVARCBATCHPROD | Dylan | 03/07/23 2:00 AM
| Thanks @dylan.price@penske.com for the clarification. This means the other line item which has same name 'invarcbatch' in this smartsheet is the duplicate one? | Gayam | 03/08/23 12:29 AM
| @dylan.price@penske.com , Could you please provide me the response for above question. Also we have another question on this app. This app has a dependency on iasservice-client.jar. But this jar is not available in artifactory and unable to find source code of this jar in SVN/BitBucket. Can we upload this jar into artifactory in the below location? Groupid: com.penske.ias.services Artfactid: iasservice-client Thanks. | Gayam | 03/16/23 6:58 PM
Row 111 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 111 | @dylan.price@penske.com / @mark.weaver@penske.com , In the smartsheets 2 apps named same invarcbatch and the sheet provided by penske to us have the same name but web filenames are different (invarcbatch, invarcabatch). Following are the more details which we observed. Both are pointing to same bamboo key following is the bamboo URL. "https://bamboo.penske.com/browse/INVARCBATCHBP" This has 2 different plans. One is "INVARCBATCH_PROD_BUILD" and it is generating artifacts "INVARCBATCH_PROD_TGZ". Another is "INVARCSFTPBATCH_PROD_BUILD" and it is generating "INVARCSFTPBATCH_PROD_TGZ" SVN urls are : https://svn.penske.com/svn/webprojects/admin/invarcbatch/ https://svn.penske.com/svn/webprojects/admin/invarcsftpbatch/ Could you please check and clarify the confusion. @mathumala.nachiappan@penske.com | Gayam | 12/16/22 12:43 AM
Row 112 | @praneeth.gayam@penske.com can you please remove this app? it is a duplicate | Dylan | 05/25/23 1:36 AM
| Changed the status to Dup App. | Gayam | 05/25/23 2:35 AM
Row 112 | @yvette.urso@penske.com , This is duplicate line item. There is another line item which has app name as invarcbatch in which we are updating the comments. Please mark this line item as duplicate one. Thanks. | Gayam | 03/30/23 11:15 PM
Row 112 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 113 | @praneeth.gayam@penske.com, I have not found any feature branches after we got response from Shane Myers . What is the update on this | Narsimhamurthy | 08/16/23 1:03 AM
| @narsimhamurthy.peddoju@penske.com , We have migrated the code of docserviceclient and asked Shane, David to review it. Once they review and merge the PR, we will onbaord to bamboo and upload to artifactory. Then we will pickup this app. Thanks. | Gayam | 08/17/23 1:47 AM
| @praneeth.gayam@penske.com did you get update on this | Narsimhamurthy | 08/19/23 1:19 AM
| Not yet @narsimhamurthy.peddoju@penske.com | Gayam | 08/21/23 9:44 PM
| @narsimhamurthy.peddoju@penske.com , In the mean time please check the comments about secrets mitigation and provide your response. Please let me know if you need the irm secrets file. | Gayam | 09/16/23 1:04 AM
Row 113 | @praneeth.gayam@penske.com , did you get any response on this | Narsimhamurthy | 07/12/23 11:11 PM
| No response. | Gayam | 07/13/23 12:59 AM
Row 113 | Any update on this ? | Narsimhamurthy | 07/05/23 7:35 PM
| Still waiting for the response from @sherin.basheer@penske.com | Gayam | 07/07/23 12:21 AM
Row 113 | Question: Hi @shane.myers@penske.com , This is regarding irm.war application. irm app dependent on docserviceclient.jar and Rajesh said that you are the AO for this jar. We found 2 repos for this jar. https://svn.penske.com/svn/architecture/general/documentsvc/branches/dev_gh/JavaSource/com/penske/apps/documentservice/ https://svn.penske.com/svn/architecture/general/documentsvc_cmis/src/main/java/com/penske/apps/documentservice/ Could you please check and let us know which one is correct. Also, let us know whether modernization required for the docservice. | Gayam | 06/29/23 2:08 AM
| Sent an email about this issue to @shane.myers@penske.com and Shane forwarded the email to @sherin.basheer@penske.com. Waiting for the response. | Gayam | 07/03/23 10:56 PM
Row 113 | @praneeth.gayam@penske.com @yvette.urso@penske.com Please use following branch to implement changes with respect to log4j upgrade. Hugo work on maven and jdk 8 upgrade. https://bitbucket.penske.com/projects/PTLCORP/repos/irm-web/commits?until=refs%2Fheads%2Ffeature%2Fdevelop_jdk8_maven Thanks. | Rajesh | 06/26/23 8:37 PM
| Sure @rajesh.haravde@penske.com | Gayam | 06/27/23 3:22 AM
Row 113 | @narsimhamurthy.peddoju@penske.com / @rajesh.haravde@penske.com , If you are validating the branch 'feature/develop_jdk8_maven' then the work is completed by Hugo / Olukemi Olaewe only. Log4j team did not do any changes on this branch. Please verify with Olukemi Olaewe. | Gayam | 06/21/23 2:10 AM
| so which branch I have to take and check, Let us know the final branch to test in local and give to sign-off then move to QA | Narsimhamurthy | 06/21/23 8:46 PM
| @narsimhamurthy.peddoju@penske.com , As an AO please suggest which route we need to take. The toal migration work is completed by Penske team(Hugo and Olukemi) in the branch 'feature/develop_jdk8_maven'. So please verify and suggest whether we need to take this branch as base branch and start making the changes or do we need to take master branch as base branch? | Gayam | 06/22/23 3:58 AM
Row 113 | Below is the error in console while try to deploy on WAS server : [6/20/23 16:20:51:430 EDT] 000000b0 SystemErr R org.eclipse.jst.j2ee.commonarchivecore.internal.exception.ArchiveWrappedException Stack trace of nested exception: org.eclipse.jst.j2ee.commonarchivecore.internal.exception.NoModuleFileException: A file does not exist for module element having uri: irm-web.war | Narsimhamurthy | 06/21/23 1:52 AM
Row 113 | We are seeing below in eclipse problems. we are unable to deploy this on WAS server 'C:/apps/bamboows/maven/repository/com/penske/mis/common/sharedlib/dlinks_filter/2.0.0-develop-SNAPSHOT/dlinks_filter-2.0.0-develop-SNAPSHOT.jar' in project 'irm-web' cannot be read or is not a valid ZIP file irm-web Build path Build Path Problem | Narsimhamurthy | 06/21/23 1:50 AM
Row 113 | if we need to move this to appropriate status, validate this branch and let me know. we will move back as you suggested. Thanks | Rajesh | 06/15/23 8:40 PM
| @rajesh.haravde@penske.com , Do you want us to work on the above branch? But recently I am seeing a commit from Olukemi on this branch. Could you please let us know whether there is any active changes are going on on this app. | Gayam | 06/16/23 10:52 PM
Row 113 | This is the branch HUGO work on which is on bitbucke with maven integration. https://bitbucket.penske.com/projects/PTLCORP/repos/irm-web/browse?at=refs%2Fheads%2Ffeature%2Fdevelop_jdk8_maven | Rajesh | 06/15/23 8:39 PM
Row 113 | Hugo work on this application and created branch due of urgency of nature as per my information, But i will verify. | Rajesh | 06/14/23 9:14 PM
Row 113 | Please confirm if we can we start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:08 AM
| @rajesh.haravde@penske.com , Please check the above comments. I don't think mavanization completed on this app. We are waiting for the AO to resolve some queries which I mentioned above. Please check. Thanks. | Gayam | 06/09/23 1:54 AM
Row 113 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 113 | Please onboard fully local development environment qualified branch for IRM : https://bitbucket.penske.com/projects/PTLCORP/repos/irm-web/browse?at=refs%2Fheads%2Ffeature%2Fdevelop_jdk8_maven | Rajesh | 04/14/23 12:03 AM
| @rajesh.haravde@penske.com , We onboarded this app to bamboo. https://bamboo.penske.com/browse/IRMBUILD-IRMW0 But build is failing due to dlinks_filter.jar version is not available in artifactory. Could you please check with the developer who did work on this app mavanization. | Gayam | 04/18/23 2:59 AM
Row 113 | Praneeth, we got the information we look. Thank you. We are currently validation IRM on QA environment. if anything needed we will reach out to you. | Rajesh | 02/17/23 2:41 AM
Row 113 | Maven configuration implemented. awaiting on the reply from Praneeth | Rajesh | 01/18/23 8:22 PM
| Sorry @rajesh.haravde@penske.com . What is the thing you are waiting from me? | Gayam | 01/18/23 11:31 PM
Row 113 | Regarding irm secrets, We went over the irm.war_secrete.xlsx file. Above 95% of the file content information about the java doc html pages. Which is not actual application code. I don’t know if they can be classified as actual secrete violation. There is one function in the application, where we do use password key constant which is not real password. It’s a key info we are using to get generated encrypted password from database to send request to document management service to upload and retrieve document. We won’t mind changing that, but in that case, we need to involved document service group and take it forward. We will take look if we can deploy application without java doc html pages, which is over 95% violation content as per attached secrete file. If you have any other option for us to exclude java doc let us know. Thanks & Regards, Rajesh Haravde. | Yvette Urso | 12/16/22 12:48 AM
| @rajesh.haravde@penske.com , Log4j team don't know any details about the application. We are just doing log4j upgradation, mavenization, Secret scanning and Bamboo deployment. While doing these things if we encounter any problem or if we find any secrets then we need AO help. @hugo.scavino@penske.com may help you on this. Thanks. @mathumala.nachiappan@penske.com , @yvette.urso@penske.com | Gayam | 12/16/22 10:36 PM
Row 113 | @praneeth.gayam@penske.com - Changed status to AO Secrets and pending @shane.myers@penske.com response. | Yvette Urso | 12/15/22 2:54 AM
Row 113 | @shane.myers@penske.com , irm app has dependency docserviceclient.jar. we found 2 repos for this jar. https://svn.penske.com/svn/architecture/general/documentsvc/branches/dev_gh/JavaSource/com/penske/apps/documentservice/ https://svn.penske.com/svn/architecture/general/documentsvc_cmis/src/main/java/com/penske/apps/documentservice/ @rajesh.haravde@penske.com updated that you are AO for docservice. Not sure whether the above 2 repos are correct. Could you please check and let us know. Also, let us know whether modernization required for the docservice and can we upload this jar into artifactory? @mathumala.nachiappan@penske.com | Gayam | 12/14/22 12:49 AM
Row 113 | IRM do uses docservice to manage documents. This service app belongs to difference group. you can reach out to Myers, Shane for repo information. Thanks. | Rajesh | 12/14/22 12:43 AM
Row 113 | @krishna.tanga@penske.com - This jar is not available in Artifactory. So need confirmation on this. 1. Is Modernization required? If so, Pls. share the repo and the folder to be considered for modernization. 2. Are you planning to remove this dependency. Pls. confirm with your updates. CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com | Mathumala Nachiappan | 12/08/22 3:19 PM
| Here is IRM repo : | Rajesh | 12/08/22 10:24 PM
| PRE-Chrome: https://svn.penske.com/svn/webprojects/corp/irm/ branches/qa/irm_test Chrome : https://svn.penske.com/svn/webprojects/corp/irm/ branches/qa/irm_chrome | Rajesh | 12/08/22 10:25 PM
| @praneeth.gayam@penske.com and @rajesh.haravde@penske.com - Any update regd. docserviceclient.jar | Mathumala Nachiappan | 12/13/22 10:20 AM
Row 113 | @rajesh.haravde@penske.com - While scanning for secrets, this applicaiton has many hardcoded credentials and href links present. Pls. have a look whether redaction is required. @praneeth.gayam@penske.com - Pls. share the secret report to Rajesh | Mathumala Nachiappan | 12/08/22 10:10 PM
| Please share the report via email we will analyze the same and get back to you or resolution. | Rajesh | 12/08/22 10:26 PM
| @rajesh.haravde@penske.com , I have shared. Please check | Gayam | 12/09/22 1:44 AM
Row 113 | @krishna.tanga@penske.com / @yogesh.sinha@penske.com , irm app has dependency docserviceclient.jar. we found 2 repos for this jar. https://svn.penske.com/svn/architecture/general/documentsvc/branches/dev_gh/JavaSource/com/penske/apps/documentservice/ https://svn.penske.com/svn/architecture/general/documentsvc_cmis/src/main/java/com/penske/apps/documentservice/ Not sure whether these 2 app are correct. Could you please check and let us know. Also, can we upload this jar into artifactory? @mathumala.nachiappan@penske.com | Gayam | 11/26/22 1:00 AM
Row 114 | <groupId>com.penske.websphere8.lib</groupId> <artifactId>mail</artifactId> <version>1.0.0</version> </dependency> | Narsimhamurthy | 08/30/23 8:22 AM
| From where did you take this jar and added to pom.xml | Narsimhamurthy | 08/30/23 8:22 AM
Row 114 | @praneeth.gayam@penske.com can you clarify below 1. is bamboo script triggering .sh files to start this batch same like old job 2.logs not generated after scheduled deployment in QA.does this job in scheduled deployment list? 3. can you provide the details which script is using to start this batch from bamboo | Narsimhamurthy | 08/18/23 10:44 PM
| @narsimhamurthy.peddoju@penske.com , As far as we know, ant scripts are used for creating the package only. After that, webservices scripts will trigger the batch apps in the respective server. Please verify the app and let us know if we miss anything. | Gayam | 08/21/23 9:48 PM
Row 114 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:09 AM
| @rajesh.haravde@penske.com , this is already onboarded to Bamboo. Please deploy to QA and verify. https://bamboo.penske.com/browse/IRMBUILD-IRMBACH1/ | Gayam | 06/09/23 1:50 AM
| provide access to above url | Narsimhamurthy | 08/18/23 10:39 PM
Row 114 | PR been executed please take it forward. Thanks for guidance on process Praneeth appreciated. | Rajesh | 05/18/23 1:48 AM
| @rajesh.haravde@penske.com , build on develop branch is successful. Please deploy to QA. | Gayam | 05/18/23 10:49 PM
Row 114 | @praneeth.gayam@penske.com We able to build project JAR FILE using maven. please change the status to next step. Thanks. | Rajesh | 05/17/23 1:32 AM
| @rajesh.haravde@penske.com , could you please merge the PR. https://bitbucket.penske.com/projects/PTLCORP/repos/irm-batch/pull-requests/3/overview | Gayam | 05/17/23 3:10 AM
| @rajesh.haravde@penske.com , Onboarding both develop_log4j and develop branches to bamboo are completed. Please merge the above PR. So that build on develop branch will be successful. | Gayam | 05/18/23 12:57 AM
Row 114 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/irm-batch/pull-requests/3/overview | Gayam | 02/16/23 11:41 PM
Row 114 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:49 PM
Row 114 | Work in progress. | Rajesh | 01/18/23 8:22 PM
Row 114 | @rajesh.haravde@penske.com - Pls. approve the PR after your review and confirmation. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:21 PM
Row 115 | @yvette.urso@penske.com , I think irs.jar app is already there. I don't think we need this line item. @hugo.scavino@penske.com / @sreekanth.kancharla@penske.com | Gayam | 05/03/23 1:51 AM
| @yvette.urso@penske.com , This is a duplicate item. Please mark this as Dup. | Gayam | 06/06/23 3:35 AM
Row 115 | @sreekanth.kancharla@penske.com | Yvette Urso | 05/02/23 7:16 PM
Row 115 | New jar added to support the irs.jar | Yvette Urso | 05/02/23 7:15 PM
Row 116 | App deployed to PROD on 10/12/2023 as part of hvutefile batch application. | Sreekanth | 10/12/23 10:28 PM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 10/13/23 6:35 AM
Row 116 | @praneeth.gayam@penske.com You are correct. Even we've to use RELEASE version, shouldn't we've version? So should we use the dependency as below with no version at all? <dependency> <groupId>com.penske.corp</groupId> <artifactId>irs</artifactId> </dependency> OR as below <dependency> <groupId>com.penske.corp</groupId> <artifactId>irs</artifactId> <version>RELEASE</version> </dependency> | Sreekanth | 08/14/23 6:29 PM
| @sreekanth.kancharla@penske.com , we will create a release version and will let you know. thanks | Gayam | 08/15/23 1:02 AM
Row 116 | @sreekanth.kancharla@penske.com , Following question already asked in hvutefile line item. Just moving the conversation from hvutefile line item to irs.jar line item. Could you please confirm what are the folders from hvutefile repo need to move to irs repo. I know following. 1. You said source/xsd/ETEC/2290/Return2290.xsd folder. Do you mean total xsd folder source/xsd? 2. source/lib/jaxb-xjc.jar Any other folders are files need to move to irs repo? | Gayam | 05/03/23 2:08 AM
| @praneeth.gayam@penske.com Those are the only files needed to build the jar. We can check on any other dependency when we have the bamboo build issues. | Sreekanth | 05/03/23 7:45 PM
| @praneeth.gayam@penske.com The status is "Waiting on AO". Please let us know in case any other details required from us. | Sreekanth | 05/08/23 9:32 PM
| @sreekanth.kancharla@penske.com , Changed to Cap. | Gayam | 05/08/23 10:21 PM
| @sreekanth.kancharla@penske.com , Completed the changes for irs.jar. Please check https://bitbucket.penske.com/projects/PTLCORP/repos/irs/pull-requests/2/overview | Gayam | 05/13/23 2:44 AM
| @praneeth.gayam@penske.com Added review comment. | Sreekanth | 05/17/23 2:39 AM
| @sreekanth.kancharla@penske.com , Modified the folder name. Please verify. | Gayam | 05/18/23 1:44 AM
| @praneeth.gayam@penske.com Merged the PR. | Sreekanth | 05/18/23 2:02 AM
| We are wokring on XSD to java files binding on this jar. | Gayam | 06/01/23 10:49 PM
| @sreekanth.kancharla@penske.com , This utility app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/irs/pull-requests/4/overview | Gayam | 06/24/23 12:28 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 06/26/23 6:34 PM
| @sreekanth.kancharla@penske.com , This app is onboarded to Bamboo and jar is deployed to artifactory. Please verify. thanks. | Gayam | 06/28/23 12:57 AM
| @praneeth.gayam@penske.com We'll validate this once hvutefile app completed as the irs.jar is the dependency for another app. | Sreekanth | 06/28/23 2:46 AM
| @sreekanth.kancharla@penske.com , We created a release version of this jar and used in hvutefile. But we observed recently that build of irs is failing after the creation of release version. Team is checking on this. Thanks. | Gayam | 07/25/23 12:01 AM
| @praneeth.gayam@penske.com Ok, thank you! | Sreekanth | 07/25/23 5:33 PM
| @praneeth.gayam@penske.com Please let us know in case any update on above mentioned issue fix. | Sreekanth | 07/31/23 11:22 PM
| @sreekanth.kancharla@penske.com , Log4j CICD team is working with Architecture team to resolve the issue. Hopefully we will get some solution in a day. Thanks. | Gayam | 08/01/23 12:39 AM
| @sreekanth.kancharla@penske.com , issue got resolved and created a release version. Please check bitbucket and bamboo. Thanks. | Gayam | 08/02/23 2:46 AM
| @praneeth.gayam@penske.com We are using irs dependency in hvut as below which is giving error. Please provide the version value for the release version which you created. <dependency> <groupId>com.penske.corp</groupId> <artifactId>irs</artifactId> <version>2.0.0-develop_log4j-20230628.200202-3</version> </dependency> | Sreekanth | 08/11/23 6:25 PM
| @sreekanth.kancharla@penske.com , you said that you don't want to provide the version number..right? Instead you can provide RELEASE which brings the latest release version. | Gayam | 08/13/23 3:26 AM
Row 117 | Per Pramod - This application will be retired by Q2 2024. | Yvette Urso | 05/12/23 12:46 AM
Row 117 | Question: @pete.macmahon@penske.com , Could you please provide the response to above question. Thanks. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 03/24/23 10:53 PM
Row 117 | Peter - Currently off SVN. Will be moving Savion platform but not until 2024. We want to go ahead and upgrade this app by end of JSM project. | Yvette Urso | 03/24/23 7:10 PM
Row 117 | @pete.macmahon@penske.com , For this application both SVN and Bamboo are not available. Could you please let us know the SVN and Bamboo details. Thanks. | Gayam | 01/14/23 1:05 AM
Row 118 | Yes Praneeth | Shabeer | 10/05/23 2:26 AM
Row 118 | @praneeth.gayam@penske.com for current PROD this is the Branch we have used. https://svn.penske.com/svn/webprojects/admin/itcontact/branches/dev_gh/itcontact7 | Shabeer | 10/04/23 11:33 PM
| @shabeer.shaik@penske.com , So we need to ignore the changes which we have already completed and need to take the above branch as base reference. | Gayam | 10/05/23 1:13 AM
Row 118 | @praneeth.gayam@penske.com we are good with Secrets, you go ahead with the next steps. | Shabeer | 10/03/23 11:20 PM
| Thanks @shabeer.shaik@penske.com | Gayam | 10/04/23 1:49 AM
Row 118 | @satish.polubothu@penske.com , I sent the secrets in the email. Could you please verify them. | Gayam | 03/10/23 1:58 AM
Row 118 | Bamboo Project Setup 2/1/23 - Yvette sent Tim Fox the below question via email: Tim, We are submitting a request for a Bamboo Project and would like to know who to add from the HR team as the Admin of that Project? That person can then create what ever they need for other access and repositories, etc. | Yvette Urso | 02/01/23 8:53 PM
Row 119 | Will you be looking into the jtest? | Chokshi | 10/11/23 5:57 PM
| @maitri.chokshi@penske.com , jtest issue is fixed. Could you please check now. | Gayam | 10/13/23 6:36 AM
Row 119 | @praneeth.gayam@penske.com I have reviewed the develop_log4j branch. Let us not merge with develop at this time as it seems there may be some env agnostic changes required. Lets proceed with the bamboo build and then I will review again. Thanks! | Chokshi | 09/29/23 1:22 AM
| Sure @maitri.chokshi@penske.com | Gayam | 10/03/23 12:57 AM
| @maitri.chokshi@penske.com , Onboarded develop_log4j branch to bamboo but jtest is failing so disabled it -https://bamboo.penske.com/browse/JAVAPOSTOP-JAVAPB1 | Gayam | 10/05/23 1:44 AM
Row 119 | @sherin.basheer@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/ARPROJ/repos/javapostop/pull-requests/14/overview | Gayam | 07/14/23 1:16 AM
Row 119 | application context.xml -use one under prod. Applicationcontext.xml should be same across all environments. Setting.properties file are different. we have to create setting-qa.properties and settings-prod.properties file. | Sherin | 06/23/23 12:17 AM
| Sure @sherin.basheer@penske.com . thanks. | Gayam | 06/27/23 3:26 AM
Row 119 | Question: @sherin.basheer@penske.com , This application having different settings.properties and applicationcontext.xml for different environments . Which one we need to use ? (the urls and properties are different in each environment in settings.properties) | Gayam | 04/06/23 3:08 AM
Row 119 | No we don't want to move rt jar to artifactory. We should use jaxws-rt jar instead. | Sherin | 03/29/23 1:02 AM
| @sherin.basheer@penske.com , we will try and let you know. | Gayam | 03/29/23 9:05 PM
Row 119 | Question: @sherin.basheer@penske.com, This application having rt.jar in lib folder. While doing mavenization we are getting issues as this jar is not available in artifactory. Can we upload this jar to artifactory? Class name : OTMWebServiceConfiguration.java import statements : import com.sun.xml.internal.ws.client.BindingProviderProperties; | Gayam | 03/24/23 10:49 PM
Row 119 | Secrets left over from testing are removed from the code. 2 out of 5 are not actual passwords they are key to passwords stored in a table. That is added to the comments. | Sherin | 02/24/23 2:48 AM
| Thanks @shawn.mcmurtry@penske.com . Is develop branch contains all the secrets code changes? | Gayam | 03/01/23 12:02 AM
| @praneeth.gayam@penske.com looks like you tagged wrong developer to the chat. Changes are in secrets remediation branch | Sherin | 03/01/23 10:40 PM
| Thanks @sherin.basheer@penske.com . Could you please let us know which branch we need to take as base branch for log4j/maven changes. Otherwise please merge your changes to develop branch and we will consider develop as base branch | Gayam | 03/02/23 2:09 AM
| Please use secrets remediation branch afor your changes | Sherin | 03/07/23 1:42 AM
| Thanks @sherin.basheer@penske.com . We will complete the log4j and maven changes on top of 'hotfix/secrets_remediation' branch. | Gayam | 03/08/23 12:23 AM
Row 119 | This is not Cap Blocked - moved to 2.2 Secrets Mitigation. | Yvette Urso | 12/09/22 12:51 AM
Row 119 | Hi @sherin.basheer@penske.com - Looks there are some hardcoded values for the property PWD. Pls. revisit the secret scanning report if redaction is required. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 7:18 PM
Row 119 | Question: @sherin.basheer@penske.com , As discussed in the call before your vacation, this app is using packages from rt.jar and rt.jar is part of java8 and causing several issues in the classes. It is a bad practice to use con.sun classes directly. These are not getting compiled in maven. These should be removed. | Gayam | 12/08/22 1:51 AM
Row 119 | @mathumala.nachiappan@penske.com What errors are you receiving? | Yvette Urso | 11/30/22 12:36 AM
Row 119 | @praneeth.gayam@penske.com - Blocked by Megha. Getting build errors while doing the maven because of rt.jar | Mathumala Nachiappan | 11/23/22 3:36 AM
Row 120 | Hi @praneeth.gayam@penske.com develop_log4j has been merged into develop branch. Could you please start the bamboo build? | Dylan | 06/06/23 7:22 PM
| Sure @dylan.price@penske.com . Thanks. | Gayam | 06/07/23 3:03 AM
| @dylan.price@penske.com , Onboarded develop branch to Bamboo and deployed to dev. Please verify. | Gayam | 06/09/23 2:02 AM
Row 120 | Hi @praneeth.gayam@penske.com I am seeing the following error when trying to run the application: [6/1/23 17:02:12:505 EDT] 0000003b SystemErr R SLF4J: No SLF4J providers were found. [6/1/23 17:02:12:505 EDT] 0000003b SystemErr R SLF4J: Defaulting to no-operation (NOP) logger implementation [6/1/23 17:02:12:505 EDT] 0000003b SystemErr R SLF4J: See https://www.slf4j.org/codes.html#noProviders for further details. [6/1/23 17:02:12:507 EDT] 0000003b SystemErr R SLF4J: Class path contains SLF4J bindings targeting slf4j-api versions 1.7.x or earlier. [6/1/23 17:02:12:507 EDT] 0000003b SystemErr R SLF4J: Ignoring binding found at [wsjar:file:/C:/ptl_mis/pbt-billing/.metadata/.plugins/com.genuitec.eclipse.blue.websphere.core/WebSphere_20_Application_20_Server_20_8_2e_5_20_at_20_localhost/lbs/lbs/WEB-INF/lib/log4j-slf4j-impl-2.20.0.jar!/org/slf4j/impl/StaticLoggerBinder.class] [6/1/23 17:02:12:507 EDT] 0000003b SystemErr R SLF4J: See https://www.slf4j.org/codes.html#ignoredBindings for an explanation. Looks like slf4j is not configured correctly? | Dylan | 06/02/23 2:39 AM
| @dylan.price@penske.com , we will check and get back to you. | Gayam | 06/03/23 12:11 AM
| @dylan.price@penske.com , We fixed the issue. Could you please check again. Thanks. | Gayam | 06/06/23 3:38 AM
Row 120 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. Please verify. https://bitbucket.penske.com/projects/ARPROJ/repos/lbs-web/pull-requests/3/overview | Gayam | 03/23/23 11:20 PM
Row 120 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/28/23 3:32 AM
| Thanks @venkatesh.hossalinever@penske.com . Changed the status to Cap Maven | Gayam | 02/28/23 11:56 PM
Row 120 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 120 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:54 AM
Row 121 | Has this gone through the log4j2 upgrade @praneeth.gayam@penske.com. I don't see the spreadsheet updated with any info on that. This step can be done without being blocked by mavenization Thanks | Jeremiah Ashway | 10/03/23 12:52 AM
| @jeremiah.ashway@penske.com , I ahve provided the PR in the above comment. That contains both log4j and maven changes. Status of the app is mentioned as (AO)Maven. That means AO needs to review the code. Thanks | Gayam | 10/03/23 12:56 AM
| Thank you I did not notice that. Going forward, would it be possible to assign me to any PRS you open for one of my applications? It would make it easier for me to notice your new prs and they will show up in my open work. Thanks - I added myself to this one now. | Jeremiah Ashway | 10/03/23 1:02 AM
| Sure @jeremiah.ashway@penske.com | Gayam | 10/03/23 1:07 AM
| Thank you @praneeth.gayam@penske.com . I left you a comment in the PR. | Jeremiah Ashway | 10/03/23 1:57 AM
| @Jeremiah Ashway , We got the instructions to complete till mavanization and provide the PR from the starting of log4j project because other AOs do not want to spend time to review every step of the project. That is the reason we are completing till mavanaization and providing one PR. Not sure whether the direction is getting changed. I sent an email to frank and others. Let us see what they respond. | Gayam | 10/04/23 1:29 AM
| @jeremiah.ashway@penske.com , Please check with @frank.d'angelo@penske.com regarding log4j PR. Also, I updated the query in PR. Please verify. Thanks. | Gayam | 10/10/23 12:39 AM
Row 121 | @frank.d'angelo@penske.com , This app is ready for your review with a open query. Please check. PR: https://bitbucket.penske.com/projects/EBCE/repos/ldapcompanybatch/pull-requests/5/overview Query: This application has applicationcontext.xml and application.properties files which are different for dev,Prod and QA. These are available under DEPLOY/TARGET folder. It looks like build depends on environment. But in environment agnostic build, one build can be deployed to different environments. So code needs to satisfy in that way. Could you please rectify this. Thanks. | Gayam | 09/21/23 12:59 AM
Row 121 | @praneeth.gayam@penske.com We have reviewed the assessment and agree that these are false positives. Please proceed to the next step. | Gianfranco | 08/16/23 1:42 AM
| Thanks @frank.d'angelo@penske.com . Changing the status to Cap Maven. | Gayam | 08/17/23 12:57 AM
Row 121 | @jeremiah.ashway@penske.com , I sent the secrets file in an email for this app. Please check and let us know if app requires any code changes. Thanks. | Gayam | 08/10/23 1:16 AM
Row 122 | Maven/log4j changes are moved to production | Sherin | 06/23/23 8:11 PM
Row 122 | it is moved to QA and test was successful | Sherin | 06/20/23 11:20 PM
Row 122 | Yes, we have removed the dependency and app is deployed to qa and running. | Sherin | 04/12/23 1:22 AM
| Thanks @sherin.basheer@penske.com . Changed the app status to QA Test | Gayam | 04/13/23 12:41 AM
| @sherin.basheer@penske.com , we changed the scope of log4j2 jars to compile. Could you please deploy these changes to QA and test. Thanks. | Gayam | 06/03/23 12:49 AM
Row 122 | Thanks @sherin.basheer@penske.com . We will check and get back to you | Gayam | 04/04/23 11:11 PM
| @sherin.basheer@penske.com , without spring-ldap-resource jar also build is getting successful. So can we remove that dependency from the pom? | Gayam | 04/06/23 11:58 PM
Row 122 | Here is the transitive dependency error:The POM for com.penske.mis.common.customlib:spring-ldap-resource:jar:1.0.0 is invalid, transitive dependencies (if any) will not be available, enable debug logging for more details [INFO] | Sherin | 04/04/23 1:46 AM
Row 122 | reference : https://bitbucket.penske.com/projects/ARPROJ/repos/vdrfilebatch/browse/pom.xml?at=refs%2Fheads%2Fdevelop_log4j | Sherin | 04/04/23 1:44 AM
Row 122 | Not properties file, this was missing in pom file<plugin> <groupId>org.apache.maven.plugins</groupId> <artifactId>maven-jar-plugin</artifactId> <version>2.4</version> <configuration> <archive> <manifest> <addDefaultImplementationEntries>true</addDefaultImplementationEntries> <addDefaultSpecificationEntries>true</addDefaultSpecificationEntries> <addClasspath>true</addClasspath> <mainClass>com.penske.filetransferbatch.main.FileTransferBatchMain</mainClass> <classpathPrefix>lib/</classpathPrefix> </manifest> </archive> </configuration> </plugin> | Sherin | 04/04/23 1:43 AM
Row 122 | There are 2 issues in pom file. 1.manifest section where you mention main class is missing. 2) maven build throws transitive dependency on <artifactId>spring-ldap-resource</artifactId> | Sherin | 03/31/23 7:42 PM
| @sherin.basheer@penske.com , are you referring about .prop file which has a propeorty to point to main class? If so, we did not see this kind of file in original code of this app. Could you please provide the error which throws transitive dependency. | Gayam | 04/04/23 12:00 AM
Row 122 | @sherin.basheer@penske.com , This is onboarded to Bamboo. https://bamboo.penske.com/browse/LDAPISMGERBP-LDAPISMR1 But build is failing on develop branch because log4j/maven changes are not yet merged. Could you please merge if you satisfy the changes. Thanks. https://bitbucket.penske.com/projects/AR-SEC/repos/ldapismgr-batch/pull-requests/7/overview | Gayam | 03/29/23 12:56 AM
Row 122 | @praneeth.gayam@penske.com Please create bamboo plan if it has not been created yet. | Sherin | 03/23/23 1:05 AM
Row 122 | @sivagamasundari.suresh@penske.com is working on this app. | Sherin | 03/10/23 9:28 PM
Row 122 | @sherin.basheer@penske.com - This app is available for AO Review | Mathumala Nachiappan | 11/23/22 3:38 AM
| @sherin.basheer@penske.com , Following is the PR for your review https://bitbucket.penske.com/projects/AR-SEC/repos/ldapismgr-batch/pull-requests/7/overview | Gayam | 02/16/23 2:04 AM
Row 123 | @praneeth.gayam@penske.com @shweta.gupta@penske.com We have done some additional research and found that this application is obsolete. We are flagging this for retirement. You may stop working on modernizing it. | Gianfranco | 08/31/23 2:37 AM
| Thanks @frank.d'angelo@penske.com for the update. | Gayam | 08/31/23 11:28 PM
Row 123 | @praneeth.gayam@penske.com All items found are validated as false positive. Please proceed. | Gianfranco | 08/24/23 1:44 AM
| Thanks @frank.d'angelo@penske.com . Changing the stauts to Cap Maven. | Gayam | 08/24/23 3:59 AM
Row 123 | @shweta.gupta@penske.com , I sent the secrets file of this app in email. Could you please check it and let su know whether it requires any code changes. Thanks. | Gayam | 08/22/23 2:24 AM
Row 124 | Secrets: @shweta.gupta@penske.com / @frank.d'angelo@penske.com , I have sent the secrets of this app in the email. Could you please verify and let us know whether it requires any code changes to mitigate the secrets. Thanks. | Gayam | 09/14/23 1:57 AM
Row 124 | @praneeth.gayam@penske.com I spoke with Don Kichline about multi-module applications. They are going to review internally. In the meantime, he told us to complete the modernization steps that we can. Log4j, Secrets, and having the code support a single artifact (environment agnostic build). Bamboo pipelines are handled by the CICD team and that is when we will need Architect team's help on what to do. We can address those later when we have a decision on the direction we want to go. We do understand that we may have to be the ones to handle this, but CapGemini team can do the prep work up until this point. Please proceed with the application in its current state. Is this the only application assigned to CapGemini that is multi-module that you are aware of presently? | Gianfranco | 09/12/23 8:27 PM
| Sure @frank.d'angelo@penske.com . Yes, as far as I remember this is the only application have mutliple modules . But I will check with my team and get back to you. Changing the status Cap. | Gayam | 09/13/23 1:00 AM
Row 124 | @praneeth.gayam@penske.com , can we make this application the top priority application for CapGemini. It is coming up as a shared client jar in our dependency analyzer for other applications. | Gianfranco | 09/07/23 8:49 PM
| @frank.d'angelo@penske.com , We analyzed this application and found that this is a multi module application. My team had a discussion with Architecture CICD team and they said that the current bamboo architecture does not support the multi module apps and modules have to be separated. Each module should be a separate application. In this case, both client and service modules need to be separated. Could you please check and let us know. Depends on your decision we will go forward. Thanks. | Gayam | 09/08/23 12:26 AM
| @praneeth.gayam@penske.com , I'm not sure what decision you are looking for? If the CICD team says we need to split them apart, then that's what we have to do. What is the alternative? | Gianfranco | 09/08/23 9:47 PM
| @frank.d'angelo@penske.com , I am asking whether you agree for segrgating the modules. We can't go forwards without informing and getting the approval from AO. | Gayam | 09/09/23 2:48 AM
| @praneeth.gayam@penske.com, yes but if you are telling me that it will not work to keep it as a multi-module app, then what option do we have? What will happen if we choose to keep it multi-module? | Gianfranco | 09/11/23 6:47 PM
| @frank.d'angelo@penske.com , The bamboo build will not support multi module as per CICD team. So, there will be no build and no deployment to any environment. So, it will be a problem. | Gayam | 09/11/23 10:44 PM
Row 124 | @praneeth.gayam@penske.com How is this application going from Maven to Waiting on AO. Are you following the natural progression of work? | Yvette Urso | 09/08/23 6:25 PM
| @yvette.urso@penske.com , It never went to maven stage. It is not even pass to log4j stage. | Gayam | 09/09/23 2:15 AM
Row 124 | @praneeth.gayam@penske.com , do you have what you need for LocationSearch now? | Gianfranco | 08/17/23 2:15 AM
| Yes @frank.d'angelo@penske.com . Changing the status to Cap Ananlysis | Gayam | 08/18/23 12:34 AM
Row 124 | Ideally, we should prioritize this one higher and try to complete faster as we do occasionally get requests for enhancements. | Gianfranco | 08/15/23 1:17 AM
| Sure @frank.d'angelo@penske.com . Could you please provide the branch which we need to take the base reference for log4j/mavan changes? | Gayam | 08/15/23 2:41 AM
| @praneeth.gayam@penske.com You can use develop branch. Master and Develop are same and up-to-date. | Gupta | 08/16/23 12:57 AM
Row 124 | @praneeth.gayam@penske.com The recent changes team made is deployed to PROD. So you can start the modernization of the app. | Gianfranco | 08/15/23 1:16 AM
| Thanks @frank.d'angelo@penske.com . Which branch we need to take the reference for this application? | Gayam | 08/15/23 2:21 AM
Row 124 | @shweta.gupta@penske.com / @frank.d'angelo@penske.com , We observed that there are recent commits in this application. Do you want log4j team need to stop modernize this app until you completed your changes? Because, once it is modernized, total folder structure is going to changes. Please let us know what step we need to take. Thanks. | Gayam | 08/01/23 1:01 AM
Row 125 | Question: @frank.d'angelo@penske.com , This application has ApplicationResources.properties file which are different for Prod, QA and Dev. These are available under DEPLOY/TARGET folder. It looks like build depends on environment. But in environment agnostic build, one build can be deployed to different environments. So code needs to satisfy in that way. Could you please rectify this. Thanks. | Gayam | 09/14/23 2:49 AM
| @frank.d'angelo@penske.com , As mentioned in the email, we will complete the mavanization and will provide the PR with the query. Thanks. | Gayam | 09/22/23 1:44 AM
Row 125 | @praneeth.gayam@penske.com Team has validated and confirms these are false positives. Please proceed. | Gianfranco | 08/24/23 2:06 AM
| Thanks @frank.d'angelo@penske.com | Gayam | 08/24/23 4:24 AM
Row 125 | @praneet | Gianfranco | 08/24/23 2:06 AM
Row 125 | @kenneth.french@penske.com , I sent the secrets file of this app in email. Could you please check it and let su know whether it requires any code changes. Thanks. | Gayam | 08/22/23 2:23 AM
Row 125 | @praneeth.gayam@penske.com Bitbucket -- https://bitbucket.penske.com/projects/EBRM/repos/rule_maintenance_service/browse Bamboo -- https://bamboo.penske.com/browse/RMP-RMB/deployments | Gianfranco | 08/14/23 11:35 PM
| Thanks @frank.d'angelo@penske.com . Changing the status to Cap Analysis. | Gayam | 08/15/23 1:00 AM
Row 125 | @elanchezhian.ochathevan@penske.com / @sree.gopal@penske.com , We couldn't find Bamboo and code repo for this app. Could you please help us to find them. Thanks. | Gayam | 07/27/23 11:41 PM
Row 126 | @yvette.urso@penske.com - mailreader_1_0 is not a separate application. Its part of mailreader_2_0. Hence not applicable for modernization. Pls. remove it from the scope or suggest us with the correct App status cc: @praneeth.gayam@penske.com , @kalrav.khamar@penske.com | Mathumala Nachiappan | 02/17/23 1:15 PM
Row 126 | @rafiq.melath@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:32 AM
| @praneeth.gayam@penske.com We're looking into JEUPLOAD application in SVN. It create mailreader.jar to use in start_journal.sh script. This application runs from GNRHILLS IFS. We will update you as soon as, we find correct svn location. | Kalrav | 12/21/22 3:07 AM
| @praneeth.gayam@penske.com Mailreader_1_0 is not indivudual application. is uses mailreder.jar file which get generated through mailreader_2_0 and used in JEUPLOAD application. Once you update the code for mailreader_2_0, we will use mailreder.jar file in JEUPLOAD script and verify changes. | Kalrav | 01/10/23 2:14 AM
Row 126 | See outside email for info. @mathumala.nachiappan@penske.com please update this with the results of that email. | Yvette Urso | 12/15/22 2:21 AM
| @yvette.urso@penske.com - Its a blocker for CAP as we are not sure about the Repo details. This app hasnt entered the log4J stage. Hope (AO) Bamboo Review would be the better choice. | Mathumala Nachiappan | 12/15/22 8:17 PM
Row 127 | App deployed to PROD on 10/12/2023 | Sreekanth | 10/12/23 10:28 PM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 10/13/23 6:35 AM
Row 127 | Review: @sreekanth.kancharla@penske.com / @kalrav.khamar@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ITFIS/repos/mailreader_2_0-batch/pull-requests/5/overview | Gayam | 05/02/23 2:33 AM
| @praneeth.gayam@penske.com I've merged the PR. One small suggestion. We don't need to maintain the app name as "mailreader_2_0-batch", instead we can've it as "mailreader-batch" Please change the repo name and the same new name can be used for Bamboo plan as well. @kalrav.khamar@penske.com | Sreekanth | 05/08/23 9:31 PM
| Sure @sreekanth.kancharla@penske.com . We will make the change and will let you know. Thanks. | Gayam | 05/08/23 10:16 PM
| @sreekanth.kancharla@penske.com , Repo name and Bamboo build/deploy plan names are changed to mailreader-batch. Please check and confirm. | Gayam | 05/10/23 12:24 AM
| @praneeth.gayam@penske.com the repo name & bamboo build/deploy plan names are good now. | Sreekanth | 05/10/23 2:45 AM
| @sreekanth.kancharla@penske.com , Please merge https://bitbucket.penske.com/projects/ITFIS/repos/mailreader-batch/pull-requests/7/overview The changes are for making log4j2 scope to compile. Thank you. | Gayam | 05/30/23 8:54 AM
| @praneeth.gayam@penske.com Merge completed. | Sreekanth | 06/01/23 12:10 AM
| Thanks @sreekanth.kancharla@penske.com . Build is done | Gayam | 06/01/23 10:45 PM
Row 127 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:55 AM
| @praneeth.gayam@penske.com Passowrd is used to access mailbox details. This utility extract file from mail box and load data in AP or JE system. | Kalrav | 03/08/23 2:01 AM
| @kalrav.khamar@penske.com , So it is not a secret? | Gayam | 03/08/23 2:55 AM
| @praneeth.gayam@penske.com yes, its not secrets. | Kalrav | 03/08/23 11:32 PM
Row 127 | @rafiq.melath@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:32 AM
| @praneeth.gayam@penske.com We're looking into JEUPLOAD application in SVN. It uses .jar file from this folder. We will update you as soon as, we find correct svn location. | Kalrav | 12/21/22 3:05 AM
| @praneeth.gayam@penske.com use follow svn path to update code. https://svn.penske.com/svn/webprojects/admin/as400_utilities/trunk/mailreader | Kalrav | 01/10/23 2:10 AM
Row 127 | @mathumala.nachiappan@penske.com changed status. | Yvette Urso | 12/15/22 2:21 AM
Row 128 | @kenneth.mikos@penske.com , Onboarded to bamboo and dev deployment is completed with develop branch - https://bamboo.penske.com/browse/MCBP-MAINTCW0/deployments Please verify. | Gayam | 10/17/23 11:50 PM
Row 128 | @kenneth.mikos@penske.com , All the modernization chagnes are completed. Please review the PR and merge. https://bitbucket.penske.com/projects/MAIN/repos/maintconfig-web/pull-requests/4/overview | Gayam | 10/12/23 8:01 AM
| @praneeth.gayam@penske.com The PR has been reviewed and merged. Thanks! | Mikos | 10/12/23 5:52 PM
| Thanks @kenneth.mikos@penske.com . We will onbaord to Bamboo. | Gayam | 10/13/23 6:33 AM
Row 128 | @praneeth.gayam@penske.com We had the same in servicenet application except the .build file in src/conf. I recommend following the same way how it is implemented in servicenet application. | Vaddi Mani | 08/18/23 10:08 PM
| @sarath.mani@penske.com , It doesn't look like both apps are same. Please check and provide the solution which is best for maintconfig app. | Gayam | 08/21/23 10:01 PM
| @praneeth.gayam@penske.com Platform agnostic changes are complete for maint-config and can be found in the "mainconfig_PlatformAgnosticChanges" feature branch. | Mikos | 10/06/23 3:26 AM
| Thanks @kenneth.mikos@penske.com . We will check and will include all the remaining mavanization steps if anything missed. | Gayam | 10/09/23 11:58 PM
Row 128 | Those should be the variables which have to defined in bamboo plan for each environment. | Vaddi Mani | 08/04/23 7:26 PM
| @sarath.mani@penske.com , there will be no separate builds for each environment after modernization. Please check the files below and provide your decision what to do for the next step. Thanks. build_script/maintconfig_specificBuild.xml src/conf/maintconfig.properties.build | Gayam | 08/08/23 1:23 AM
Row 128 | Query: @sarath.mani@penske.com / @falgun.patel@penske.com , In this application build folder having maintconfig_specificBuild.xml. The build is including maintconfig.properties on environment basis. how to implement this in environment agnostic build as we don't have separate builds for each environment. | Gayam | 07/25/23 9:15 PM
| Can you tell which variables from maintconfig_specificBuild.xml & maintconfig.properties? | Vaddi Mani | 07/28/23 2:07 AM
| @sarath.mani@penske.com , check the 39th to 45 line. | Gayam | 07/31/23 2:40 AM
Row 128 | Sarath already replied to the email on 6/27 that this application does not require any code changes related to secret. Please proceed. | Patel | 06/29/23 1:46 AM
| Thanks. Changed the status to Cap Maven. | Gayam | 06/29/23 2:37 AM
Row 128 | Secrets: @sarath.mani@penske.com / @falgun.patel@penske.com , I sent the secrets in the email. Please verify and let us know whether this app requires code changes. | Gayam | 06/28/23 12:47 AM
Row 128 | @sarath.mani@penske.com - may you please assist Gayam with the question? | Patel | 06/08/23 11:09 PM
| @praneeth.gayam@penske.com that was very old tag. you should use https://svn.penske.com/svn/fieldsys/maintenance/maint-config/tags/prod/maint-config20230605 | Stella george | 06/14/23 2:08 AM
| Thanks @stella.george@penske.com | Gayam | 06/14/23 3:39 AM
Row 128 | @david.long@penske.com , In the current bamboo build the prod reference mentioned as complete "https://svn.penske.com/svn/fieldsys/maintenance/maint-config/tags/prod/maint-config20201215". But this path doesn't exist in svn. Could you please help us to find the prod reference branch. Thanks. | Gayam | 05/09/23 2:42 AM
Row 129 | thanks @frank.d'angelo@penske.com | Gayam | 08/24/23 4:28 AM
Row 129 | @praneeth.gayam@penske.com Team has validated and confirms these are false positives. Please proceed. | Gianfranco | 08/24/23 2:06 AM
Row 129 | @kenneth.french@penske.com , I sent the secrets file of this app in email. Could you please check it and let su know whether it requires any code changes. Thanks. | Gayam | 08/22/23 2:24 AM
Row 130 | @praneeth.gayam@penske.com This application has a Password in the GitLeaks scan. The team marked it as False Positive, however, this is something we need to remediate. Working with @kenneth.french@penske.com on research and development prioritization. | Gianfranco | 08/17/23 1:45 AM
| Thanks @frank.d'angelo@penske.com | Gayam | 08/18/23 12:57 AM
Row 130 | @kenneth.french@penske.com , I sent secrets in an email. Could you please verify it. Thanks. | Gayam | 08/05/23 12:34 AM
Row 131 | I have reviewed the pull request and left comments. The main issue is the log4j migration has some issues please refer to this confluence section about no web.xml log4j configuration https://confluence.penske.com/display/ATSD/Log4j2+Modernization+Best+Practices#Log4j2ModernizationBestPractices-java-config if any questions during your time, Karthikgayan Mahalingam may be able to answer them as he works on the consumer rental backend which has this configuration on the cap side. | Kenneth | 09/20/23 6:59 PM
| @kenneth.french@penske.com , we have completed the requested changes. Please check and let us know if we need to change anything else. | Gayam | 09/23/23 1:07 AM
Row 131 | Review: @kenneth.french@penske.com , This app is ready for your review. Please review and merge. https://bitbucket.penske.com/projects/EB/repos/mfaservice/pull-requests/5/overview | Gayam | 09/19/23 12:58 AM
Row 131 | @praneeth.gayam@penske.com these are false positives, please proceed with the modernization | Kenneth | 09/15/23 8:06 PM
| Thanks @kenneth.french@penske.com . Pushing the app to next step. | Gayam | 09/16/23 12:17 AM
Row 131 | Secrets: @kenneth.french@penske.com / @sree.gopal@penske.com / @frank.d'angelo@penske.com , I have sent the secrets of this app in the email. Could you please verify and let us know whether it requires any code changes to mitigate the secrets. Thanks. | Gayam | 09/14/23 1:59 AM
Row 131 | We should always use Master. It SHOULD contain the most recent production code base. | Gianfranco | 08/17/23 2:41 AM
| Thanks @frank.d'angelo@penske.com . That should be the idle case. But in lot of applications, different branches are referred as latest production branches. That is the reason we are trying to get the latest prod branch from AO for most of the apps if we are not clear. | Gayam | 08/18/23 12:58 AM
Row 131 | From @kenneth.french@penske.com : Please use Master. It is current. | Gianfranco | 08/17/23 2:40 AM
Row 131 | @praneeth.gayam@penske.com Can we change status to clear off dashboard? | Gianfranco | 08/15/23 8:23 PM
| @frank.d'angelo@penske.com , Could you please provide the response for the branch question asked above. Thanks. | Gayam | 08/17/23 12:56 AM
Row 131 | @praneeth.gayam@penske.com No Active development. | Gianfranco | 08/14/23 11:36 PM
| Thanks @frank.d'angelo@penske.com . In that case can we take release/v16.1.0 branch as base branch for log4j/mavan changes. | Gayam | 08/15/23 12:59 AM
Row 131 | @kenneth.french@penske.com / @sree.gopal@penske.com , There are commits recently done in this application. Is there any active development on this app? Is this app ready for the modernization work? Please clarify. Thanks | Gayam | 08/03/23 1:04 AM
Row 132 | Thanks @dylan.price@penske.com . Changing the status to Retired. @yvette.urso@penske.com , @shane.myers@penske.com | Gayam | 06/08/23 7:59 AM
Row 132 | Hi @praneeth.gayam@penske.com we have determined that this application is no longer being used. Could you please delete out the Bitbucket repo, as well as remove it from the smartsheet? | Dylan | 06/07/23 1:15 AM
Row 132 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/mileageforecast-web/pull-requests/3/overview | Gayam | 03/23/23 11:42 PM
Row 132 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/28/23 3:32 AM
| Thanks @venkatesh.hossalinever@penske.com . Changed the status to Cap Maven | Gayam | 02/28/23 11:50 PM
Row 132 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:54 AM
| @yvette.urso@penske.com Hello, this application should be assign to 'Billing' App group and AO Manager should change to Rafiq Melath. | Kalrav | 02/13/23 9:28 PM
| Thanks @kalrav.khamar@penske.com @praneeth.gayam@penske.com - For your note and to share the updates to the team, as this has the dependency with distribution management | Mathumala Nachiappan | 02/15/23 2:06 PM
Row 133 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/mileagereporting-web/pull-requests/3/overview | Gayam | 04/06/23 3:12 AM
Row 133 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/28/23 3:33 AM
| Thanks @venkatesh.hossalinever@penske.com . Changed the status to Cap Maven | Gayam | 02/28/23 11:51 PM
Row 133 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 133 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:55 AM
Row 134 | @praneeth.gayam@penske.com We have reviewed the assessment and agree that these are false positives. Please proceed to the next step. | Gianfranco | 08/16/23 1:33 AM
| Thanks @frank.d'angelo@penske.com . Changing the status to Cap Maven. | Gayam | 08/17/23 12:57 AM
Row 134 | @jeremiah.ashway@penske.com , I sent secrets in an email. Could you please verify it. Thanks. | Gayam | 08/05/23 12:36 AM
Row 135 | Review & Query: This app is ready for your review with an open query. PR: https://bitbucket.penske.com/projects/EBCE/repos/notification-batch/pull-requests/2/overview Query: This application has multiple resources folders resources.qa,resources.prod,resources.local,resources.dev and all of them having differnt batchconfig.properties files. Each folder's batchconfig.properties file has different serviceurl. I believe there was a separate build for each environment but in the environment agnostic build it is going to be 1 build needs to deploy to all environments. So this issue needs to be fixed to successfully deploy to any environment. Please check. Thanks. | Gayam | 10/11/23 1:57 AM
Row 135 | Hi @praneeth.gayam@penske.com , I have left a comment in this pr for you to review. Maven changes are currently blocked and waiting for my team. It would be great if the team can remove log4j changes from the maven changes so we can deploy log4j to prod on its own. Thanks https://bitbucket.penske.com/projects/EBCE/repos/notification-batch/pull-requests/1/overview | Jeremiah Ashway | 10/03/23 2:11 AM
| @Jeremiah Ashway , We got the instructions to complete till mavanization from the starting of this project. That is the reason we completed. Not sure whether the direction is getting changed. | Gayam | 10/04/23 1:18 AM
| Changed the status to Cap Maven. We will provide the PR with queries once we complete the mavanization. Thanks. | Gayam | 10/10/23 12:41 AM
Row 135 | @praneeth.gayam@penske.com Sent via email (be much easier to read on Outlook): For Notification Batch and UpdLatLong, we have been discussing the approach for the environment agnostic build in the Smartsheet. You have been asking us to analyze the folders and tell you which properties file to use. I believe what you are actually asking us to do is to externalize our configurations into a database and make application changes to a single folder structure so that we can ultimately have 1 artifact. We are asking that the team take a different approach, one that we have gotten approved already through the architecture code review process. This would allow for consistency in applications that are already set up with the multiple folder structure and should only require minor changes to get the properties based on environment. This also meets the end goal of a single artifact. Eventually, we will be looking to leverage Spring Cloud Config Server once we are able to use it. I am providing an example that has already been completed and approved, Location API, for the team to use to review the approach. Folder Structure: https://bitbucket.penske.com/projects/EBCE/repos/locations-api/browse/src/main/resources/environment?at=refs%2Fheads%2Fdevelop EnvironmentType.Java - Line number 19/20 based on system properties, environment variables are set: https://bitbucket.penske.com/projects/EBCE/repos/locations-api/browse/src/main/java/com/penske/ce2/locations/configuration/web/EnvironmentType.java?at=develop WebApplication.Java - Line number 31 based on environment the Spring profiles are set: https://bitbucket.penske.com/projects/EBCE/repos/locations-api/browse/src/main/java/com/penske/ce2/locations/configuration/web/WebApplication.java?at=develop ApiConfig.Java - Line number 36 it dynamically loads specific environment property file: https://bitbucket.penske.com/projects/EBCE/repos/locations-api/browse/src/main/java/com/penske/ce2/locations/configuration/spring/ApiConfig.java?at=refs%2Fheads%2Fdevelop WebApplication.Java - Line 22 and line 43 for loading env specific log4j file: https://bitbucket.penske.com/projects/EBCE/repos/locations-api/browse/src/main/java/com/penske/ce2/locations/configuration/web/WebApplication.java?at=refs%2Fheads%2Fdevelop | Gianfranco | 09/06/23 4:05 AM
| Yes @frank.d'angelo@penske.com . That is a good approach. Thanks. | Gayam | 09/07/23 1:37 AM
Row 135 | @praneeth.gayam@penske.com I am assuming that the question around resource folders is because the team has been instructed to consolidate the folders down and externalize any configuration that is environment specific. I've also been told, and we've done this for our new apps going through the CI/CD conversion process that the guideline for modernizing applications is to have a single artifact that is built once and deployed several times to different environments (dev, qa, prod). We are permitted to have the different resource folders, but we also need a mechanism to determine which environment the application is in, and then load the appropriate configuration at run-time. So if your approach is to consolidate, I don't think the right question is which one to pick. I think the team needs to analyze the differences and report back what those differences are. The AO can then decide how to best handle those environment variations and determine what to do. The alternative is that the team just maintains those folders. I have an example of what we just did and got approved through CI/CD review with Architecture team. Please review and let me know how you want to proceed. https://bitbucket.penske.com/projects/EBCE/repos/locations-api/browse/src/main/java/com/penske/ce2/locations/configuration/web/EnvironmentType.java?at=refs%2Fheads%2Fdevelop https://bamboo.penske.com/browse/EXT-LOCA7-5/artifact | Gianfranco | 08/25/23 1:56 AM
| @frank.d'angelo@penske.com , I believe currently there is a separate build for each environment. But in environment agnostic build, it should be one build and it can be deployed to different environments. We are seeing notification.service.url is different for different environment resource folders. That should be handled to satisfy the environment agnostic build. | Gayam | 08/28/23 11:11 PM
Row 135 | Still reviewing 8/17 question | Gianfranco | 08/24/23 1:59 AM
Row 135 | @praneeth.gayam@penske.com re: Secrets. All items found are validated as false positive. | Gianfranco | 08/24/23 1:50 AM
Row 135 | Secrets: @jeremiah.ashway@penske.com , Adding to above question, I sent the secrets file of this app in email. Could you please check it and let su know whether it requires any code changes. Thanks. | Gayam | 08/22/23 2:21 AM
Row 135 | @frank.d'angelo@penske.com , @jeremiah.ashway@penske.com , This application has multiple resources folders resources.qa,resources.prod,resources.local,resources.dev and all of them having differnt batchconfig.properties and log4j.xml files. Each folder's batchconfig.properties file has different serviceurl. Could you please check which one we should use. | Gayam | 08/18/23 1:06 AM
Row 136 | @dale.porter@penske.com , Bamboo build is completed. Please deploy to QA and verify. https://bamboo.penske.com/browse/OROSBBP-OROSSUMM | Gayam | 07/20/23 12:06 AM
| Hi, I am seeing errors in the Bamboo build for the final Archive stage and included link to bamboo for showing the error. Also, I did not see a war file created on ghlx008ptlge. Can you take a look. Thank you https://bamboo.penske.com/download/OROSBBP-OROSSUMM0-DTA/build_logs/OROSBBP-OROSSUMM0-DTA-2.log | Dale Porter | 07/28/23 1:41 AM
| @dale.porter@penske.com , we will check. | Gayam | 07/31/23 2:30 AM
| @dale.porter@penske.com , This is a batch application. So it doesn't have war package. Also, whatever the errors you are seeing are not causing@dale.porter@penske.com , This is a batch application. So it doesn't have war package. Also, whatever the errors you are seeing are not causing any issues. Jars are pushed to artifactory successfully and tgz file is pushed to targeted location correctly. Please check. | Gayam | 08/01/23 12:43 AM
| Hi all, I ran the deploy to QA but it did not place the tgz file of the build in the /var/tmp of the qa deploymanager (clelx150ptlge). I included url of qa build log, thank you https://bamboo.penske.com/browse/OROSBBP-OROSSUMM0-DTA-3/log | Dale Porter | 08/05/23 1:15 AM
| We will check and get back to you. | Gayam | 08/08/23 1:11 AM
| @dale.porter@penske.com , we have completed the QA deployment and tgz file also generated. Please verify and let us know if you have any questions. Thanks. | Gayam | 08/10/23 12:46 AM
| Hi, I ran the open repair order summary batch deplioy but afterwards, I do not see the tgz file on /var/tmp of clelx150ptlge. I have included reference to bamboo log below, thank you https://bamboo.penske.com/browse/OROSBBP-OROSSUMM0-DTA-4/log | Dale Porter | 08/17/23 6:32 PM
| @dale.porter@penske.com , will check and get back to you. Thanks | Gayam | 08/18/23 12:31 AM
| @dale.porter@penske.com , It looks like you only run the build but you need to run the deploy plan also. If you want to deploy to QA, you need to run the QA deploy plan and for prod need to run the prod deploy plan. | Gayam | 08/18/23 8:01 PM
| I ran the QA build and it did create a TGZ file on /var/tmp of deploy manager. However, upon inspecting the file, the internal code base for the openrepairsumm-batch.jar is dated 8/4/2023 not the current date of build 8/25/2023. Can someone take a look? thank you. Build log https://bamboo.penske.com/deployment-download/151912538/build_logs/151814164-151912538-151200192.log | Dale Porter | 08/26/23 7:47 AM
| @dale.porter@penske.com , we will check and get back to you. | Gayam | 08/28/23 10:40 PM
| I made a small code change without affecting code, "verbiage in log comment" and upon doing the qa build, I did get class files built for current build which is good. However, when I tried to run the application, no logs where showing in the /logs/apps/openrepairsumm folder on the qa batch box and also I did not see any emails generated to the ebs mailer in QA so it appears to not be running when I start it. | Dale Porter | 08/30/23 8:46 AM
| @dale.porter@penske.com , We will check and get back to you. | Gayam | 08/30/23 10:33 PM
| @dale.porter@penske.com , My team ran the build and deployed to QA and it is also moved to targeted location correctly. Please check. | Gayam | 09/02/23 4:18 AM
| @praneeth.gayam@penske.com , I ran a qa deploy and did see the tgz file get built and placed in /var/tmp of qa batch machine. However, when I tried to run it, the process did not run and there is no logging in the /logs/apps/openrepairsumm I do not know if logging is working. But the process is not working either. I did not see a log4j warning on starting the process like I do with ServiceNet batch. | Dale Porter | 09/08/23 7:30 PM
| @praneeth.gayam@penske.com its same issue we faced with other batch applications too. Please address this ASAP and let us know. | Stella george | 09/08/23 8:10 PM
| @stella.george@penske.com / @dale.porter@penske.com , Can your un the application in local and check the issue. Log4j team does not have knowledge to run the application. We only mavanize and compile the application as per defined process. | Gayam | 09/09/23 2:29 AM
Row 136 | I have reviewed and merged pull request. Thank you. | Dale Porter | 07/17/23 7:30 PM
Row 136 | Review: @dale.porter@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/MAIN/repos/openrepairsumm-batch/pull-requests/3/overview | Gayam | 07/16/23 9:21 PM
Row 136 | Thanks @dale.porter@penske.com | Gayam | 06/14/23 4:18 AM
Row 136 | I approve of adding velocity-1.7 to artifactory as needed for the application. Thank you. | Dale Porter | 06/14/23 2:20 AM
Row 136 | Regarding Secrets: I went ahead to analyze this and see this appears to be the guest user id and password for SVN repository access. I removed these on all of the property files as Bamboo does not use this. I believe this was from prior to using Bamboo back in the day. After removing the id and password references, I made a new qa tag and run a qa build in Bamboo without any issue. This should be fine now. | Dale Porter | 06/06/23 6:25 AM
| Thanks @dale.porter@penske.com . Could you please check the query mentioned above regarding the dependency jar and provide your response | Gayam | 06/06/23 8:36 AM
Row 136 | Secrets: @shawn.mcmurtry@penske.com , adding to above question, I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:53 AM
Row 136 | Query: @shawn.mcmurtry@penske.com , This app depends on velocity-1.7-dep.jar which is not availabe in artifactory. Could you please provide your approval to uplaod to artifactory in the following location. <groupid>org.apache.velocity</groupid> <artifactid>velocity-1.7-dep</artifactid> <version>Default</version> | Gayam | 06/01/23 1:59 AM
Row 137 | Yes it is needed in all batch applications to start up. | Sherin | 06/23/23 12:29 AM
| Thanks @sherin.basheer@penske.com . We have been implementing this section in all batch apps. | Gayam | 06/23/23 11:44 PM
Row 137 | <plugin> <groupId>org.apache.maven.plugins</groupId> <artifactId>maven-jar-plugin</artifactId> <version>2.4</version> <configuration> <archive> <manifest> <addDefaultImplementationEntries>true</addDefaultImplementationEntries> <addDefaultSpecificationEntries>true</addDefaultSpecificationEntries> <addClasspath>true</addClasspath> <mainClass>com.penske.filetransferbatch.main.FileTransferBatchMain</mainClass> <classpathPrefix>lib/</classpathPrefix> </manifest> </archive> </configuration> </plugin> | Sherin | 04/19/23 2:10 AM
| @sherin.basheer@penske.com , Do we need to keep this section for all batch applications? If yes, please point out to the confluence page which has this info. So that I will inform to my team to update this in every batch app. FYI: @hugo.scavino@penske.com | Gayam | 04/20/23 2:08 AM
Row 137 | @praneeth.gayam@penske.com This section is missing in this application as well | Sherin | 04/19/23 2:09 AM
Row 137 | @sherin.basheer@penske.com , this app is onboarded to Bamboo. Please check. https://bamboo.penske.com/browse/ORACLE2LDAPBP-ORACLE2LDP/ | Gayam | 04/13/23 11:44 PM
Row 137 | @praneeth.gayam@penske.com Thank you. Build is successful in local now. COuld you create Bamboo plan for this application. | Sherin | 04/12/23 1:22 AM
Row 137 | @praneeth.gayam@penske.com Getting this error when you run the build. Could not resolve dependencies for project com.penske.architecture:oracle2ldap:jar:1.0.0-SNAPSHOT: Failure to find com.penske.salesnet.common.dev:enterprise:jar:3.0.0 in https://artifactory.penske.com/artifactory/architecture-mvn-virtual was cached in the local repository | Sherin | 04/04/23 2:04 AM
| @sherin.basheer@penske.com , we will check and get back to you. | Gayam | 04/04/23 11:07 PM
| @sherin.basheer@penske.com , salesnet-mvn-development-local repo is added to architecture-mvn-virtual repo for oracle2ldap applicaion to download the enterprise:jar. Please check now. | Gayam | 04/06/23 2:42 AM
Row 137 | Review: @sherin.basheer@penske.com , Please review the app at https://bitbucket.penske.com/projects/AR-SEC/repos/oracle2ldap-batch/pull-requests/3/overview | Gayam | 03/23/23 11:14 PM
Row 137 | @praneeth.gayam@penske.com what is the next step on this application | Sherin | 03/23/23 9:05 PM
Row 137 | I have verified the secrets and can confirm they are all false positives | Sherin | 03/09/23 2:38 AM
Row 137 | Yes ,I'm looking into this one. will get back to you | Sherin | 03/09/23 2:25 AM
Row 137 | @sherin.basheer@penske.com - There are many hardcoded values found during secret scanning. Pls. review it once CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 6:23 PM
| @sherin.basheer@penske.com , We reviewed the secrets again and it looks like all are false positives. I will send all of your apps secrets files in a zip. Please verify them. Thanks. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/19/23 11:55 PM
| @sherin.basheer@penske.com , Could you please check the secrets and respond. | Gayam | 03/09/23 1:39 AM
Row 137 | @sherin.basheer@penske.com - This app is available for AO Review | Mathumala Nachiappan | 11/23/22 3:39 AM
Row 138 | Update from the DBA's is that the app will become obsolete around July-August 2023 but it is not confirmed yet. I am moving this app into retired status or whatever is equivalent. We can reevaluate in September. | David Graf | 02/28/23 10:08 PM
Row 138 | I agree. We shouldn't be doing any modernization work on this app as this will be retired soon. | Sherin | 02/28/23 1:10 AM
Row 138 | We just got notice that this app will be retired in the future. We may not want to go forward with modernization. I'll leave it to @sherin.basheer@penske.com to decide. | David Graf | 02/24/23 10:36 PM
Row 138 | Hi @yvette.urso@penske.com - Hope (AO) Final Testing would be correct. Once @sherin.basheer@penske.com is back from her PTO, she can look into this | Mathumala Nachiappan | 12/12/22 4:39 PM
Row 138 | @mathumala.nachiappan@penske.com - What was deployed? I do not think this is blocked. I picked a bucket - please work with @sherin.basheer@penske.com with specifically what you need. | Yvette Urso | 12/09/22 12:52 AM
Row 138 | @sherin.basheer@penske.com - Deployed in QA on 2nd Nov | Mathumala Nachiappan | 11/23/22 3:40 AM
Row 139 | Hi @praneeth.gayam@penske.com , The application is working good. We are deploying it into production next week. Thanks, Sai Kothapalli. | Kothapalli | 09/09/23 12:48 AM
| @saisatyakrishna.kothapalli@penske.com Thanks for the update. | Gayam | 09/09/23 2:41 AM
Row 139 | @praneeth.gayam@penske.com The app deployed to qa | Kothapalli | 09/08/23 7:34 PM
Row 139 | @praneeth.gayam@penske.com Sure, Thanks | Kothapalli | 09/06/23 6:10 PM
| @saisatyakrishna.kothapalli@penske.com , onboarded to bamboo successfully. build plan: https://bamboo.penske.com/browse/PARTSPO-PRTSPBH0/ deploy plan: https://bamboo.penske.com/browse/PARTSPO-PRTSPBH0/deployments Please deploy to QA and test. Thanks | Gayam | 09/07/23 12:49 AM
Row 139 | @praneeth.gayam@penske.com , we have merged the changes to the develop branch. May I know whether the pipeline is configured for this to deploy in QA?? | Kothapalli | 09/05/23 10:59 PM
| @saisatyakrishna.kothapalli@penske.com , we need to onboard the app to bamboo. We will let you know once we complete that task. | Gayam | 09/06/23 1:02 AM
Row 139 | In above attached document. In Jee resources.xml we are seeing the JDBC was changed GHDBC1 from support may I know the reason? | Kothapalli | 08/31/23 8:41 PM
| @saisatyakrishna.kothapalli@penske.com , Check the targeted/prod/jee-resources.xml | Gayam | 09/01/23 12:10 AM
Row 139 | @praneeth.gayam@penske.com @karthikeyan.srinivasan@penske.com We have made changes in pom.xml we have fixed the spring version issue and have modified the log4j2.Please have a look on Develop_Log4j branch.. I request please go through the pom and we are seeing lot of spring dependencies we are thinking that some of them are not required can you please validate pom and remove the unused dependencies.. | Kothapalli | 08/30/23 2:22 AM
| @saisatyakrishna.kothapalli@penske.com , We added the dependencies by checking into lib folder of master branch. it contains all the spring ones. | Gayam | 08/30/23 10:57 PM
Row 139 | @praneeth.gayam@penske.com @saisatyakrishna.kothapalli@penske.com The partspo-batch app is set in Sai's machine and it is running. Mavenization is complete. Yet log4j2 configuration is not printing log messages. I have asked Sai to look in to that. The application set up with mavenization is done. We have modified the pom.xml with version modifications and dependency additions for mavenization. | Karthikeyan | 08/30/23 12:06 AM
Row 139 | The code (PropertiesFilesManager.PROPERTIES_FILE_NAME) refers the location of the file as "/conf/init_propfiles.properties" which seems logically correct. But upon execution, the file could not be found. @praneeth.gayam@penske.com | Karthikeyan | 08/23/23 1:22 AM
| I tried giving the absolute path as well. That failed too. | Karthikeyan | 08/23/23 1:22 AM
| @karthikeyan.srinivasan@penske.com , all the files under resources folders will be added to classpath as per maven. I am seeing init_propfiles.properties file under resournces/conf folder. That means this file is in classpath. | Gayam | 08/23/23 8:06 AM
Row 139 | The properties files are not being read when I checked them recently when I have pulled the code from this branch (https://bitbucket.penske.com/projects/MAIN/repos/partspo-batch/browse?at=refs%2Fheads%2Fdevelop_Log4j). @praneeth.gayam@penske.com | Karthikeyan | 08/21/23 11:35 PM
| @karthikeyan.srinivasan@penske.com , Please explain what properties files you are refrring to. We copied all the resource files to src/main/resources. Let us know whether we missed anything. | Gayam | 08/22/23 9:33 PM
Row 139 | @praneeth.gayam@penske.com I pulled the latest code. I still see the following spring-jms-5.1.18.RELEASE - 6.0.0 spring-messaging - 5.3.15 spring-orm - 5.3.14 spring-oxm - 5.3.15 Is the same branch used? The branch shows that the latest commit was on 10th August. https://bitbucket.penske.com/projects/MAIN/repos/partspo-batch/pull-requests/3/commits Am I missig something? | Karthikeyan | 08/19/23 12:02 AM
| @karthikeyan.srinivasan@penske.com , Yes the develop_log4j branch is correct. | Gayam | 08/21/23 9:37 PM
Row 139 | Let me check. | Karthikeyan | 08/18/23 11:03 PM
Row 139 | @praneeth.gayam@penske.com The pom uses Spring 4.3 while the application context uses 3.1 | Karthikeyan | 08/18/23 2:57 AM
| @karthikeyan.srinivasan@penske.com , We followed the confluence and changed the versions. Please check and let us know the issue. | Gayam | 08/18/23 8:22 PM
Row 139 | I am unable to run the main method. | Karthikeyan | 08/18/23 2:46 AM
Row 139 | @praneeth.gayam@penske.com The application is not running after log4j2 conversion. | Karthikeyan | 08/18/23 2:46 AM
Row 139 | @praneeth.gayam@penske.com the project compiles successfully. However, I have to check the configuration and execution of the code. | Karthikeyan | 08/17/23 2:39 AM
Row 139 | @praneeth.gayam@penske.com I am currently checking the local build and deploy for this application. Will provide an update by EOD | Karthikeyan | 08/16/23 5:56 PM
Row 139 | Review: @karthikeyan.srinivasan@penske.com / @stella.george@penske.com , This app is ready for your review. Please validate and merge. Thanks. https://bitbucket.penske.com/projects/MAIN/repos/partspo-batch/pull-requests/3/overview | Gayam | 06/30/23 1:01 AM
| @praneeth.gayam@penske.com Karthik is working on it. | Stella george | 08/15/23 2:59 AM
Row 139 | Secrets: @stella.george@penske.com I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:56 AM
| @praneeth.gayam@penske.com There is no secrets in this application. | Stella george | 06/14/23 1:38 AM
| Thanks @stella.george@penske.com . We will do the mavanization. | Gayam | 06/14/23 3:10 AM
Row 140 | @praneeth.gayam@penske.com the secrets references in the provided file are from Ant build files to login to SVN and SFTP the Artifacts so we can ignore those since we are not going to use Ant any more. | Shabeer | 10/04/23 11:24 PM
| Thanks @shabeer.shaik@penske.com | Gayam | 10/05/23 1:17 AM
Row 140 | @shabeer.shaik@penske.com , I sent the secrets file in an email. Please check and confirm. | Gayam | 10/04/23 2:22 AM
Row 140 | ok As discussed in the last call, we are ok. | Shabeer | 09/15/23 8:36 PM
| Thanks @shabeer.shaik@penske.com Changing the status Ananlysis | Gayam | 09/16/23 12:22 AM
Row 140 | @praneeth.gayam@penske.com For PCC this should be the base which is current PROD. https://svn.penske.com/svn/architecture/general/pcc-tollgate-review/branches/tags/tag-17521-3 I have created a Dev branch out of current PROD you can also use the same https://svn.penske.com/svn/architecture/general/pcc-tollgate-review/branches/Dev_gh1 Please do secrets scan on this branch and let us know As dicussed this same branch is getting used by PCC web and Batch. FYI - @satish.polubothu@penske.com | Shabeer | 09/13/23 1:57 AM
| @shabeer.shaik@penske.com , So are you ok to create separate bitbucket repos for pcc batch and pcc web? | Gayam | 09/14/23 2:33 AM
Row 140 | @satish.polubothu@penske.com , Can we take this app for modernization? | Gayam | 03/24/23 10:56 PM
| @satish.polubothu@penske.com informed us that we need to reconnect in August or September regarding this app. | Gayam | 06/09/23 7:48 PM
Row 140 | Bamboo Project Setup 2/1/23 - Yvette sent Tim Fox the below question via email: Tim, We are submitting a request for a Bamboo Project and would like to know who to add from the HR team as the Admin of that Project? That person can then create what ever they need for other access and repositories, etc. | Yvette Urso | 02/01/23 8:53 PM
| @praneeth.gayam@penske.com - FYA | Mathumala Nachiappan | 02/06/23 6:49 PM
Row 140 | @mathumala.nachiappan@penske.com based on the comment above it looks like you are ready to start doing this work. Did you send out a question you are waiting to have answered? I moved to Cap Analysis based on your 1/9/23 comment. Thanks | Yvette Urso | 01/24/23 3:43 AM
Row 140 | @praneeth.gayam@penske.com - To check with AO on the APP ready for log4J Modernization | Mathumala Nachiappan | 01/10/23 10:21 AM
Row 141 | @praneeth.gayam@penske.com the secrets references in the provided file are from Ant build files to login to SVN and SFTP the Artifacts so we can ignore those since we are not going to use Ant any more. | Shabeer | 10/04/23 11:24 PM
| Thanks @shabeer.shaik@penske.com | Gayam | 10/05/23 1:18 AM
Row 141 | @shabeer.shaik@penske.com , I sent the secrets file in an email. Please check and confirm. | Gayam | 10/04/23 2:22 AM
Row 141 | @praneeth.gayam@penske.com For PCC this should be the base which is current PROD. https://svn.penske.com/svn/architecture/general/pcc-tollgate-review/branches/tags/tag-17521-3 I have created a Dev branch out of current PROD you can also use the same https://svn.penske.com/svn/architecture/general/pcc-tollgate-review/branches/Dev_gh1 Please do secrets scan on this branch and let us know As dicussed this same branch is getting used by PCC web and Batch. FYI - @satish.polubothu@penske.com | Shabeer | 09/13/23 1:53 AM
| @shabeer.shaik@penske.com , So are you ok to create separate bitbucket repos for pcc batch and pcc web? | Gayam | 09/14/23 2:33 AM
Row 141 | @satish.polubothu@penske.com , Can we take this app for modernization? | Gayam | 03/24/23 10:55 PM
| @satish.polubothu@penske.com informed us that we need to reconnect in August or September regarding this app. | Gayam | 06/09/23 7:48 PM
Row 141 | Bamboo Project Setup 2/1/23 - Yvette sent Tim Fox the below question via email: Tim, We are submitting a request for a Bamboo Project and would like to know who to add from the HR team as the Admin of that Project? That person can then create what ever they need for other access and repositories, etc. | Yvette Urso | 02/01/23 8:53 PM
| @praneeth.gayam@penske.com - FYA | Mathumala Nachiappan | 02/06/23 6:49 PM
Row 141 | @mathumala.nachiappan@penske.com based on the comment above it looks like you are ready to start doing this work. Did you send out a question you are waiting to have answered? I moved to Cap Analysis based on your 1/9/23 comment. Thanks | Yvette Urso | 01/24/23 3:44 AM
Row 141 | @praneeth.gayam@penske.com - To check with AO on the APP ready for log4J Modernization | Mathumala Nachiappan | 01/10/23 10:21 AM
Row 142 | Confirmed. This JAR is at its end. It will not be modernized and is now available in artifactory if there are any dependencies. | Hugo Scavino | 04/15/23 1:36 AM
Row 142 | After further review, please add this JAR to artifactory. This JAR will not be modernized. Take JAR from here https://svn.penske.com/svn/webprojects/admin/pops/trunk/pops/WebContent/WEB-INF/lib/ group id: com.penske.architecture artifact id: penske-secure-logger version: 1.0.0 Do not add the number as the name in the artifact ID Thank You | Hugo Scavino | 02/10/23 9:45 PM
| Thanks @hugo.scavino@penske.com . We will upload and will let you know. | Gayam | 02/10/23 11:33 PM
| @hugo.scavino@penske.com , penske-secure-logger-1.0.0.jar is uploaded into artifactory <dependency> <groupId>com.penske.architecture</groupId> <artifactId>penske-secure-logger</artifactId> <version>1.0.0</version> </dependency> | Gayam | 02/13/23 11:41 PM
Row 142 | I will review on Friday Feb 10 | Hugo Scavino | 02/10/23 3:51 AM
Row 142 | Moved to AO Log4j Review | Yvette Urso | 12/15/22 2:40 AM
Row 142 | @hugo.scavino@penske.com - popsbatch app is dependent on this jar. Any suggestion on how to proceed that application? CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 3:38 PM
Row 142 | Update from @hugo.scavino@penske.com - this app totally dependent on log4j1 and it is not supposed to be modernized | Mathumala Nachiappan | 12/08/22 10:33 AM
Row 142 | @yvette.urso@penske.com - Original Scope is 'No' for this jar | Mathumala Nachiappan | 11/23/22 4:13 AM
Row 142 | @yvette.urso@penske.com - This is an additional scope. This jar is used in b2busercreation.war and pops_batch. This jar needs modernization before it is used in the above said applications. | Mathumala Nachiappan | 11/23/22 4:13 AM
Row 142 | Need to determine who can work on this application. Missing resource @hugo.scavino@penske.com | Yvette Urso | 11/22/22 2:39 AM
Row 143 | https://bitbucket.penske.com/projects/WL/repos/watchlistclient/browse | Mahipal | 10/10/23 11:00 PM
| Sure @mahipal.podduturi@penske.com , We will implement log4j and other mavne changes. | Gayam | 10/11/23 1:36 AM
| @mahipal.podduturi@penske.com , We have completed the changes. Please review them. https://bitbucket.penske.com/projects/AC/repos/watchlistclient/pull-requests/19/overview | Gayam | 10/17/23 7:39 AM
Row 143 | @praneeth.gayam@penske.com can you update lopg4j changes to the project | Mahipal | 10/10/23 11:00 PM
Row 143 | one thing I'm noticing is that there are two bitbucket repositories for the watchlist client: this one was created by Michael Johnson: https://bitbucket.penske.com/projects/WL/repos/watchlistclient/browse this one looks like it was created by modernization team: https://bitbucket.penske.com/projects/ARPROJ/repos/penske-watchlist-client/browse However, let's assume that Michael was first and may have developed new code after migration. Unless you can prove they both have the exact same commits | David Graf | 06/23/23 6:15 PM
| @david.w.graf@penske.com , Looks like https://bitbucket.penske.com/projects/WL/repos/watchlistclient/browse contains new code and mavanized. Do you want to close the app which modernization team opened? | Gayam | 06/23/23 11:40 PM
| We are putting this back on the backlog. Mahipal will be doing the watchlist client deploy and the confusion about penske-watchlist-client will be figured out later. | David Graf | 07/05/23 7:32 PM
Row 143 | I'm going to see if this can be started back up and worked on by Amit. | David Graf | 06/23/23 5:58 PM
Row 143 | Going to ask for help on how to test this project. https://bitbucket.penske.com/projects/ARPROJ/repos/penske-watchlist-client/browse?at=refs%2Fheads%2Fdevelop_log4j | Hugo Scavino | 01/31/23 9:56 PM
Row 143 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:28 AM
Row 143 | @hugo.scavino@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:16 AM
Row 144 | Looks good. | Vaddi Mani | 08/21/23 9:15 PM
| Thanks @sarath.mani@penske.com . | Gayam | 08/22/23 9:48 PM
Row 144 | @dale.porter@penske.com , build plan onboarded and deployment to artifactory is also successful. Please verify. Build plan: https://bamboo.penske.com/browse/PNSKESPLNGBP-PENSKESPLNGCLT0 | Gayam | 08/03/23 12:50 AM
Row 144 | @dale.porter@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/penske_spelling_client/pull-requests/3/overview | Gayam | 07/27/23 2:26 AM
| I reviewed and merged the code. Thank you. | Dale Porter | 07/28/23 1:50 AM
| Will onbaoard to bamboo. | Gayam | 07/31/23 2:33 AM
Row 144 | I approve and please move forward with uploading the needed jars. | Dale Porter | 07/10/23 11:58 PM
| Thanks @dale.porter@penske.com | Gayam | 07/11/23 6:55 AM
Row 144 | @dale.porter@penske.com , This app depends on RapidSpellMDict.jar and RapidSpellWeb.jar jars. They are not available in artifactory. Please provide your approval to upload to artifactory in below location@dale.porter@penske.com , This app depends on RapidSpellMDict.jar and RapidSpellWeb.jar jars. They are not available in artifactory. Please provide your approval to upload to artifactory in below lcoation. Thanks. groupid - com.keyoti.rapidSpell | Gayam | 07/06/23 4:18 AM
Row 144 | No secrets found on this app. So changing the status to Cap Maven. | Gayam | 07/03/23 11:02 PM
Row 145 | Yes, Thx! | Vaddi Mani | 08/23/23 9:00 PM
Row 145 | Looks good. | Vaddi Mani | 08/18/23 10:10 PM
| Thanks @sarath.mani@penske.com . Can I change the status to Done as this is just a dependency doesn't have to go to any server. | Gayam | 08/21/23 9:49 PM
Row 145 | @dale.porter@penske.com , onboarded to bamboo and deployed to artifactory. https://bamboo.penske.com/browse/PNSKESPLNGBP-PSUJ | Gayam | 07/12/23 1:40 AM
Row 145 | Sarath has approved and merged this back on June 28th in bitbucket. Thank you. | Dale Porter | 07/11/23 12:02 AM
Row 145 | Review: @stella.george@penske.com / @dave.kost@penske.com , This utility app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/penske_spellingutility/pull-requests/2/overview | Gayam | 06/24/23 12:25 AM
Row 145 | There are no secrets exist for this application. So changing the status of this app to Cap Maven. | Gayam | 06/23/23 12:13 AM
Row 146 | I am still the AO for this project but ankita.tiwary@penske.com is performing the active development. She is working on unit tests at the moment. | Hugo Scavino | 02/09/23 2:02 AM
Row 146 | @hugo.scavino@penske.com , One more question for this app. There is no existing bamboo build for this app. So under which project we need to create bamboo specs for this app. | Gayam | 01/11/23 9:23 AM
Row 146 | @hugo.scavino@penske.com , Adding to above question, we completed secrets scanning on this app and found that all are false positives. Could you please review them and confirm. @mathumala.nachiappan@penske.com @swati.saxena@penske.com @mankala.narendra@penske.com | Gayam | 01/10/23 12:19 AM
Row 146 | @hugo.scavino@penske.com , We have completed log4j/maven changes for this app but we are seeing java class files under targeted folder for each environment. Could you please verify this app. https://bitbucket.penske.com/projects/ARPROJ/repos/penskesso-ws-client/pull-requests/1/overview | Gayam | 12/07/22 10:55 AM
Row 147 | artifactory is confirmed. | Hugo Scavino | 04/15/23 2:39 AM
Row 147 | Secrets - No code changes are required | Hugo Scavino | 02/10/23 9:34 PM
Row 147 | I have deployed to artifactory. This is the JAR's final destination. | Hugo Scavino | 02/10/23 3:49 AM
| Thanks @hugo.scavino@penske.com . Also, please confirm the secrets part also whether the app requires any code changes. | Gayam | 02/10/23 9:27 PM
Row 147 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:28 AM
Row 147 | @hugo.scavino@penske.com - Artifactory upload is done for this jar. Pls. confirm and change to appropriate App Status Jar location in artifactory - https://artifactory.penske.com>artifactory>architecture-mvn-development-local>com>penske>architecture>penskesso>2.0.0-develop-SNAPSHOT>penskesso-2.0.0-develop-20221213.104211-1.jar. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/13/22 5:45 PM
| I have some questions on the "-SNAPSHOT" which was added to the version. I do not think that should be be there for artifacts we expect other teams to use. This is not a problem with WAR and application JARs but shared JARs should not be "SNAPSHOT"s. The CI/CD scripts will not allow a deployment with SNAPSHOT to PROD eventually. Please redeploy without "-SNAPSOT" in the version. <groupId>com.penske.architecture</groupId> <artifactId>penskesso</artifactId> <version>2.0.0-develop-SNAPSHOT</version> | Hugo Scavino | 12/13/22 8:57 PM
| This would be true for all shared JAR's | Hugo Scavino | 12/13/22 8:58 PM
| Hugo scheduled a meeting with Iswarya and raghu on to check whether Bamboo build is going to have multiple options to create the release or snapshot versions and other build questions. | Gayam | 12/14/22 12:31 AM
Row 147 | @hugo.scavino@penske.com - - This app is available for your final review. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/02/22 5:47 PM
Row 147 | Uploading to Artifactory is in Progress | Mathumala Nachiappan | 11/23/22 4:10 AM
Row 148 | Removed from Capgemini Scope and moved to Penske smartsheet | Yvette Urso | 09/22/23 12:37 AM
Row 148 | Review: @sreenivasa.papannagari@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/MAIN/repos/peoplenet-batch/pull-requests/3/overview | Gayam | 07/20/23 12:42 AM
| Payel is working on it. | Stella george | 08/18/23 8:24 PM
| @praneeth.gayam@penske.com After setting up the project at my local and clean build, when I am trying to run the application I'm getting this error - The last line (in the image) says - refresh:550 Exception encountered during context initialization - cancelling refresh attempt: org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'peopleNetIntegratorDAO' defined in class path resource [conf/xml/applicationContext.xml]: Cannot resolve reference to bean 'sqlSessionFactory' while setting bean property 'sqlSessionFactory'; nested exception is org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'sqlSessionFactory' defined in class path resource [conf/xml/applicationContext.xml]: Cannot resolve reference to bean 'dataSource' while setting bean property 'dataSource'; nested exception is org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'dataSource': Invocation of init method failed; nested exception is javax.naming.NoInitialContextException: Need to specify class name in environment or system property, or as an applet parameter, or in an application resource file: java.naming.factory.initial | Ganguly | 08/18/23 9:38 PM
| @payel.ganguly@penske.com , Log4j team can't run the application as per instructions and the error looks like application specific issue. Are you able to run the application successfully locally before modernization changes? | Gayam | 08/21/23 9:33 PM
Row 148 | @praneeth.gayam@penske.com : Sreeni will be the contact person for this. Please direct all questions to Sreeni. | Patel | 06/08/23 11:15 PM
| @sreenivasa.papannagari@penske.com , let me know whether you have the secrets of this app to validate. Otherwise I will send. Thanks. | Gayam | 06/09/23 1:40 AM
| @praneeth.gayam@penske.com There is no hardcoded secrets in this batch application. This is using connectionframe work and using Penske's EncryptionSecureId | Stella george | 06/14/23 1:43 AM
| Thanks @stella.george@penske.com | Gayam | 06/14/23 3:12 AM
Row 148 | @david.long@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:51 AM
Row 149 | This application is deployed to PROD on 07/20/2023 | Sreekanth | 07/21/23 10:42 PM
Row 149 | Post reverting the dlink_filter changes, we've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD. | Sreekanth | 07/05/23 7:33 PM
Row 149 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD but waiting on dlink-filter.jar PROD deployment by Architect team. | Sreekanth | 06/08/23 11:24 PM
Row 149 | @sreekanth.kancharla@penske.com , app is on boarded to Bamboo. https://bamboo.penske.com/browse/PETBP-PETTYC/ please let us know whether we can deploy this to dev. | Gayam | 03/10/23 11:20 PM
| @praneeth.gayam@penske.com Please proceed with DEV deployment. | Sreekanth | 03/13/23 10:17 PM
| @sreekanth.kancharla@penske.com , Dev deployment is completed. Please check. | Gayam | 03/15/23 11:44 PM
| @praneeth.gayam@penske.com DEV testing is in-progress @kalrav.khamar@penske.com | Sreekanth | 04/19/23 9:35 PM
| @praneeth.gayam@penske.com Please delete the old deploy plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=132710422 | Sreekanth | 05/09/23 7:19 PM
| Sure @sreekanth.kancharla@penske.com . Will do | Gayam | 05/09/23 10:30 PM
| @sreekanth.kancharla@penske.com , Old deploy plans are deleted. | Gayam | 05/10/23 11:19 PM
Row 149 | Secrets: @srinivasan.narayanan@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file to you in the email. Could you please check and provide your response over here. | Gayam | 02/25/23 1:22 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. I've validated the trunk branch files alone even though offshore branch is also included secrets. @srinivasan.narayanan@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/25/23 1:45 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the app status to Cap Maven | Gayam | 02/27/23 11:47 PM
| @praneeth.gayam@penske.com PR is merged. Please proceed with next steps. | Sreekanth | 03/04/23 3:21 AM
| Thanks @sreekanth.kancharla@penske.com . We will implement the next step which is Cap Bamboo. | Gayam | 03/07/23 12:02 AM
Row 149 | @srinivasan.narayanan@penske.com / @yvette.urso@penske.com , in this app logger classes are getting created with custom configuration using fileappender(getallappender) and simplelayout . Not able to configure using the slf4j and log4j2. providing link for class file. https://svn.penske.com/svn/webprojects/admin/pettycash/trunk/pettycash6/JavaSource/com/penske/apps/pettyCash/util/FileFunctions.java. Also @hugo.scavino@penske.com confirmed that he needs to discuss with app owner who needs to change the code. @mathumala.nachiappan@penske.com | Gayam | 12/07/22 11:04 PM
| @praneeth.gayam@penske.com Please share the remediation plan if we've any for such kind of custom configurations. Kindly loop me for future communications. | Sreekanth | 12/16/22 3:36 AM
| @praneeth.gayam@penske.com From the FileFunctions class file, we observed that readFile & readFileLines methods alone are being used and not any other methods. We can comment those unused methods and look for any compiler errors. If no compiler errors, we should be good. Moreover, this logging is already implemented with log4j.xml which is available under JavaSource folder, so hope we can migrate that. @hugo.scavino@penske.com @srinivasan.narayanan@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/03/23 3:14 AM
| Thanks @sreekanth.kancharla@penske.com . Hugo also suggested same thing for other apps. We will make the change and let you know if we face any other issues. Thanks | Gayam | 02/03/23 11:51 PM
Row 149 | Moved to AO Log4J status. @mathumala.nachiappan@penske.com | Yvette Urso | 12/15/22 2:14 AM
Row 149 | @mathumala.nachiappan@penske.com What is this dependency? | Yvette Urso | 12/02/22 2:14 AM
Row 149 | @srinivasan.narayanan@penske.com - Log4J1 dependency to be cleared or confirmed . CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:41 PM
Row 150 | App deployed to PROD on 09/14/2023 | Sreekanth | 09/15/23 6:41 PM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 09/16/23 12:19 AM
Row 150 | @praneeth.gayam@penske.com I've already has the bamboo plan created for this application. We are good. We'll continue to test this app in DEV/QA. | Sreekanth | 07/27/23 7:26 PM
Row 150 | @sreekanth.kancharla@penske.com , I think you already merged the code to develop branch for this application and created another branch feature/IFS-1494 from develop branch. Do you want us to onboard this app to bamboo? | Gayam | 07/27/23 2:35 AM
Row 150 | Added psndmail application due to needed for the pextfl. | Yvette Urso | 02/16/23 12:23 AM
Row 150 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed few true positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:59 AM
Row 151 | @praneeth.gayam@penske.com Can you check my privileges to update the phone service plan. I am not able to configure the plan at all | David | 08/31/23 8:43 PM
| @david.long@penske.com , We will check and update you. | Gayam | 08/31/23 11:56 PM
| @david.long@penske.com , You are part of Maintenance-development RBAC group and it has only view and build access. Only Maintenance-Production group has view configuration access. Temporarily, we gave the view configuration access to your id but it will be removed when the plan onbaords next time. | Gayam | 09/02/23 4:27 AM
Row 151 | @praneeth.gayam@penske.com how it currently is on dev is not working. I'm getting a 500 error because I think dependencies are missing. It's not logging in dev either so it's harder to find the exact issue | David | 08/23/23 11:34 PM
Row 151 | @praneeth.gayam@penske.com Still validating this as well. Almost done adding dependencies | David | 08/18/23 2:28 AM
| @praneeth.gayam@penske.com validating and building on dev again | David | 08/18/23 2:31 AM
Row 151 | @david.long@penske.com , We are just compiling the applications in local. We are not running the app as we are modernizing several apps and we don't know the functionality of each app. | Gayam | 07/15/23 1:57 AM
Row 151 | Review: @david.long@penske.com , This app is ready for your review. Please verify andmerge. https://bitbucket.penske.com/projects/MAIN/repos/phonesvc/pull-requests/3/overview | Gayam | 07/11/23 6:49 PM
| @praneeth.gayam@penske.com Looks good! Reviewed and merged to develop. Can you please continue with the bamboo build and all? Also there is a pending change that needs to be done for the phone service, so if you could prioritize this before the other maint apps in this list that would be awesome! Thanks :) | David | 07/11/23 7:29 PM
| sure @david.long@penske.com | Gayam | 07/12/23 1:35 AM
| @david.long@penske.com , onboarded to bamboo and deployed to dev. Please verify. Deployment link: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151192150 build & Deploy plan: https://bamboo.penske.com/browse/PBP-PHNSVC | Gayam | 07/13/23 1:58 AM
| @praneeth.gayam@penske.com I can access the bamboo build but I can't hit the dev endpoint. I'm getting a 500 error and I believe it can't find http related jars or classes in the logs | David | 07/13/23 9:01 PM
| @david.long@penske.com , We can't run the application as we don't know the details of the application. Could you please check and let us know the run time issues. Thanks. | Gayam | 07/14/23 12:36 AM
| @praneeth.gayam@penske.com I'll let you know. I've brought it down locally and it looks like it's issues with either log4j or just how the pom.xml file is? I don't have an answer just yet. When you do the maven migration does any developers try it on their local machine first or anything like that? | David | 07/14/23 6:09 PM
Row 151 | @david.long@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:51 AM
| @praneeth.gayam@penske.com I have removed the class that was marked for containing secrets. We no longer use the "AutoDialService" class as that was a retired integration. We now store our creds in an encrypted maint table in the CORP library. Pushed changes to dev branch, and merged changes with log4j update branch on SVN. | David | 06/06/23 10:08 PM
| Thanks @david.long@penske.com . we will do the mavanization and will let you know. | Gayam | 06/07/23 3:09 AM
Row 152 | @praneeth.gayam@penske.com - we are investigating the project name was changed from pmmailer to pmmailer-batch. We need to know why the project name was changed in POM file. | Patel | 10/13/23 1:21 AM
| @falgun.patel@penske.com , As part of modernization changes, we have to include the name 'batch' in app's name. But we can change the artifactid / name of the project in pom to whatever is configured in webservices script. | Gayam | 10/13/23 6:39 AM
| @praneeth.gayam@penske.com @falgun.patel@penske.com The artifact name has been changed to "pmmailer" after @neha.bhattacharya@penske.com confirmed it could be changed. The app has also been tested and is working as expected after deploying to QA, even after the artifact name change. | Mikos | 10/13/23 11:14 PM
| Thnaks @kenneth.mikos@penske.com | Gayam | 10/14/23 1:51 AM
Row 152 | @kenneth.mikos@penske.com , This app is onboarded to bamboo. Please check.https://bamboo.penske.com/browse/PMSCHEDBP-PMMAILB0/deployments | Gayam | 09/27/23 12:34 AM
Row 152 | Review: @kenneth.mikos@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/pmmailer-batch/pull-requests/4/overview | Gayam | 09/16/23 12:47 AM
| @praneeth.gayam@penske.com The PR has been merged with develop. Thank you! | Mikos | 09/23/23 1:48 AM
| Thanks @kenneth.mikos@penske.com . We will onboard to bamboo. | Gayam | 09/26/23 1:25 AM
Row 152 | @praneeth.gayam@penske.com The pmmailer project is now updated to be platform agnostic using Connection Framework. The changes can be found in the "feature/pmmailer_PlatformAgnosticChanges" branch on bitbucket. | Mikos | 09/11/23 8:11 PM
| Thanks @kenneth.mikos@penske.com . We will complete the remaining work. | Gayam | 09/11/23 10:39 PM
Row 152 | @yvette.urso@penske.com , @praneeth.gayam@penske.com May you please add @kenneth.mikos@penske.com to AO Assigned and AO Assigned Email columns? | Patel | 08/16/23 5:31 PM
| Done. @kenneth.mikos@penske.com | Gayam | 08/17/23 1:15 AM
Row 152 | Query: @dale.porter@penske.com , The jdbc configuration is configured in applicationcontext.xml file and depends on the environment the respective configuration loaded from different properties files. But when we modernize the app, the build is going to be environment agnostic. Means 1 build should be deployed to all environments. So, the current way of implementation doesn't work for jdbc configuration. Could you please check with Architecture team to resolve this issue. Thanks. | Gayam | 07/14/23 12:43 AM
| I have created ticket with architect team to help with the datasource configuration. This is not using connection framework and thinking it may need to be changed to do so. Footprint ticket# 1893601 | Dale Porter | 08/09/23 10:59 PM
| The ticket was closed as further development work is needed and the ticket is now being assinged to Falgun's team and I believe a member of his team will be helping with it. Can you please update the entry to remove myself "Dale" from the pmmailer. I do not have edit ability to do so. Thank you. | Dale Porter | 08/15/23 2:46 AM
| @dale.porter@penske.com Removed from AO columns as per your instructions. Thanks | Gayam | 08/15/23 8:46 PM
Row 152 | I went ahead and analyzed PM Mailer as well and see this appears to be the guest user id and password for svn repository access. I removed these on all of the property files as Bamboo does not use this. Certain this was from prior to using Bamboo long back. After removing the id and password reference, I made a new qa tag and ran a qa build in Bamboo without any issue. This should be fine now. | Dale Porter | 06/06/23 6:51 AM
| Thanks @dale.porter@penske.com . Changed the status to Cap Maven. | Gayam | 06/06/23 8:31 AM
Row 152 | @dave.kost@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:50 AM
Row 153 | @praneeth.gayam@penske.com , @yvette.urso@penske.com , @shawn.mcmurtry@penske.com - as I have mentioned in my email, the application is not loading on Dev and it looks like Maven issue. Can you please look into this? | Patel | 09/08/23 5:52 PM
Row 153 | @praneeth.gayam@penske.com , @shawn.mcmurtry@penske.com - PR has been reviewed and merged to Dev. | Patel | 08/19/23 1:25 AM
| Thanks @falgun.patel@penske.com . We will onabord to bamboo and deploy to dev. | Gayam | 08/21/23 9:52 PM
| @falgun.patel@penske.com , We onboarded to bamboo and deployed to Dev. Please verify. | Gayam | 08/24/23 11:09 PM
Row 153 | @praneeth.gayam@penske.com - is there any update on this? | Patel | 08/16/23 5:28 PM
| Yes @falgun.patel@penske.com . Pelase review https://bitbucket.penske.com/projects/MAIN/repos/pmscheduling-web/pull-requests/3/overview | Gayam | 08/17/23 1:21 AM
Row 153 | @falgun.patel@penske.com @shawn.mcmurtry@penske.com - test 2 | Patel | 07/28/23 10:30 PM
Row 153 | Test email two..... | Patel | 07/28/23 10:23 PM
Row 153 | @shawn.mcmurtry@penske.com / @falgun.patel@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:52 AM
| AO confirmed that all secrets are false positives. No code changes required. | Gayam | 06/16/23 1:13 AM
Row 154 | FP# 1890489 is open to architect team to get clarification on security_util.jar & security_authority_filter.jar | Sreekanth | 08/22/23 1:17 AM
Row 154 | Thanks @sreekanth.kancharla@penske.com for the secrets confirmation. We have 1 more question on this app. This application using the loggers from penske-secure-logger jar. If we use this jar we need to include log4j1 . You gave the confirmation for pops_batch app to replace the loggers from penske-secure-logger with slf4j loggers. For pops.war app also do you want us to replace the loggers from penske-secure-logger jar with slf4j? Please provide your confirmation. Thanks. | Gayam | 02/25/23 12:02 AM
| @praneeth.gayam@penske.com I could see penske-secure-logger is used only for logging. Please replace this with slf4j We'll test in DEV. Are you we good with other dependency jars which is marked as blocker security_util.jar security_author_filter.jar | Sreekanth | 02/25/23 4:00 AM
| Yes @sreekanth.kancharla@penske.com . Those 2 jars are already modernized and uploaded to artifactory. | Gayam | 02/27/23 11:19 PM
| @praneeth.gayam@penske.com Please find the commented added to the PR. | Sreekanth | 03/04/23 3:17 AM
| @sreekanth.kancharla@penske.com , Please don't review or merge until the app status is in (AO)Maven status. (Cap)Maven means, still CG/Log4j team still working on this application. We will review the comment and complete the required things. | Gayam | 03/07/23 12:06 AM
| @praneeth.gayam@penske.com Since the status is under Cap team, please remove me from the review list for the existing PR in bitbucket. https://bitbucket.penske.com/projects/ITFIS/repos/pops-web/pull-requests/3/overview You can add back, once the PR is available for my review. | Sreekanth | 03/16/23 1:02 AM
| Sure @sreekanth.kancharla@penske.com . Thanks for the notification and this is ready for the review. Changed the status to AO Maven | Gayam | 03/17/23 2:58 AM
| @praneeth.gayam@penske.com Added review comment, please check. | Sreekanth | 03/21/23 8:26 PM
| @sreekanth.kancharla@penske.com , Completed the changes provided in review comments. Please check. Thanks. | Gayam | 03/23/23 11:18 PM
| @praneeth.gayam@penske.com Thank you. PR is merged. | Sreekanth | 03/24/23 8:49 PM
| Thanks @sreekanth.kancharla@penske.com . We will let you know once onboarding to Bamboo and deploymnet to Dev completed. Thanks | Gayam | 03/24/23 11:04 PM
| @sreekanth.kancharla@penske.com , Bamboo build is onboarded. Dev deployment done using develop branch. Please verify. https://bamboo.penske.com/browse/POPBP-PP/ | Gayam | 04/20/23 2:03 AM
Row 154 | @praneeth.gayam@penske.com We've received new secrets on this application on 2/23/2023 and the secrets are on QA branch & also on offshore branches. Hope we should only worry on qa branch as that is the one you would've used for log4j changes and we are using for QA & PROD deployments. We may've multiple offshore branches and all wouldn't be in sync with production code. In QA SVN branch, no remediations required for the shared secrets. @kalrav.khamar@penske.com | Sreekanth | 02/24/23 9:18 PM
Row 154 | @rafiq.melath@penske.com - Holding on for the modernization of Dependency Jars security_util.jar security_author_filter.jar CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:37 PM
| @praneeth.gayam@penske.com we need both of following jars. security_util.jar security_author_filter.jar | Kalrav | 01/25/23 3:40 AM
| @kalrav.khamar@penske.com Thanks for confirming. Modernization is going on both of above apps. Until it completes, we can not work on this app. @hugo.scavino@penske.com / @mathumala.nachiappan@penske.com | Gayam | 01/25/23 11:35 PM
| @praneeth.gayam@penske.com @yvette.urso@penske.com Do you know who is working on these security related jars? Can we assign 'Major Blocker' to person who is working on security jars? | Kalrav | 01/31/23 10:10 PM
| @kalrav.khamar@penske.com , Hugo is working on Security_util and he almost completed the work. Security_author_filter depends on security_util. So CG team is waiting on security_util to complete. | Gayam | 02/03/23 3:02 AM
Row 154 | Blocker - security_util.jar security_author_filter.jar | Yvette Urso | 02/01/23 8:27 PM
Row 155 | @sreekanth.kancharla@penske.com , This app is onboarded to bamboo. Following is the url. https://bamboo.penske.com/browse/POPBP-POPSBCH0/ Please deploy to QA and test it. Thanks. | Gayam | 03/29/23 12:51 AM
Row 155 | Review: @sreekanth.kancharla@penske.com , This app ready for your review. https://bitbucket.penske.com/projects/ITFIS/repos/pops-batch/pull-requests/3/overview | Gayam | 03/16/23 12:49 AM
| @praneeth.gayam@penske.com The PR is merged. | Sreekanth | 03/16/23 12:54 AM
| Thanks @sreekanth.kancharla@penske.com . We will onboard to bamboo and will let you know. | Gayam | 03/16/23 2:33 AM
Row 155 | Question: @sreekanth.kancharla@penske.com , This application having different dao-spring-context.xml files in targeted folder for each environment. But for the environment agnostic build we have to keep only 1 xml file. Which one we need to move to resouces folder? | Gayam | 02/28/23 12:00 AM
| @praneeth.gayam@penske.com We can't have single dao-spring-context.xml file as there is 1 difference in all 3 environment specific files. We should load these from targeted folder or need to see the possibility of how we can change the implementation. The difference is we are using Remoting EBS Service with URL provider and that URL changes based on the environment, so we've 3 files for 3 environments (DEV/QA/PROD) @kalrav.khamar@penske.com | Sreekanth | 03/02/23 2:41 AM
| @sreekanth.kancharla@penske.com , Once we migrate to maven and new bamboo plans there is no option trigger separate builds. It is going to be only 1 build. Are you in the plans to change the implementation? @hugo.scavino@penske.com | Gayam | 03/03/23 12:29 AM
| @praneeth.gayam@penske.com We've no plans now to make any changes, but we can plan for that under this log4j migration ITG itself. @kalrav.khamar@penske.com | Sreekanth | 03/07/23 12:39 AM
| @sreekanth.kancharla@penske.com , Log4j team shouldn't make any application level changes. As per management decision, all app level changes needs to be done by App team. Could you please let us know the next step. | Gayam | 03/07/23 1:05 AM
| @praneeth.gayam@penske.com We'll look through the possible solutions in bring this app environment agnostic and make those changes. @kalrav.khamar@penske.com | Sreekanth | 03/07/23 3:50 AM
| Thanks @sreekanth.kancharla@penske.com . Do you want us to hold this app until you confirm or can we use the prod one and complete the mavanization and gave it to you to resolve the above issue in mavanized branch? | Gayam | 03/07/23 11:44 PM
| @praneeth.gayam@penske.com Please have the mavenized branch ready. Post that we'll work on dao-spring-context.xml environment agnostic changes. @kalrav.khamar@penske.com | Sreekanth | 03/08/23 3:04 AM
| Sure @sreekanth.kancharla@penske.com . We will use the targeted/prod one for dao-spring-context.xml. Thanks | Gayam | 03/09/23 12:09 AM
Row 155 | @praneeth.gayam@penske.com We've receive email on secrets for this app on 02/23/2023. Only 1 files is valid https://svn.penske.com/svn/webprojects/admin/pops/branches/qa/pops_batch/database.properties That too, in batch box server where this application is deployed in QA & PROD, this file is being referred from different location (which admin only have access) and not from the source location. So, we don't need any remediation for this file. The other secrets seem to be on offshore branches and also seems from commit history as well. Hope we don't need to worry on those. @kalrav.khamar@penske.com | Sreekanth | 02/24/23 9:27 PM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (Cap)Maven. | Gayam | 02/25/23 12:08 AM
Row 155 | Blocker: penske-secure-logger-1.0.0.jar | Yvette Urso | 02/01/23 8:29 PM
Row 155 | @kalrav.khamar@penske.com @mathumala.nachiappan@penske.com Can you look at this blocker and let us know what the next steps should be? Thank you | Yvette Urso | 12/02/22 2:19 AM
| @praneeth.gayam@penske.com we will look into penske-secure-logger-1.0.0.jar and see it required in app or not. Will update you soon. | Kalrav | 01/25/23 3:43 AM
| @praneeth.gayam@penske.com penske-secure-logger-1.0.0.jar is being used for logger only. If you are replacing this with SLF4j logger OR If this jar is being modernized and placed in artifactory, then reusing the same logger. We should be good with both the approaches as we could see only logger object being used from this jar file. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/30/23 11:40 PM
Row 155 | @kalrav.khamar@penske.com - Waiting for the modernization of the dependent jar penske-secure-logger-1.0.0.jar CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:43 PM
Row 156 | Print App deployed on 09/12 after log4j Mavernization caused an issue with Agent commission statements - having issues with data source and writeIFS procedure calls. Rollback of svn code is planned for 10/05. Log4j changes will be relooked to troubleshoot the issue and plan for deploy for future dates. | Rafiq Melath | 10/05/23 6:14 PM
Row 156 | @praneeth.gayam@penske.com thank you! we are deploying this out tonight. Will be closing out this application tomorrow | Dylan | 09/12/23 8:06 PM
Row 156 | @praneeth.gayam@penske.com Found batik-all jar is not the correct version. The maven repo for batik-all is not allowed by Penske's proxy however. Could you please add this jar into Artifactiory so we can grab it in our maven repos? https://mvnrepository.com/artifact/org.apache/batik-all/1.7.0 | Dylan | 09/05/23 10:13 PM
| Sure @dylan.price@penske.com . We will add above jar to artifactory. | Gayam | 09/07/23 1:32 AM
| @dylan.price@penske.com , batik-all uploaded in artifactory. <dependency> <groupId>org.apache.batik</groupId> <artifactId>batik-all</artifactId> <version>1.7</version> </dependency> | Gayam | 09/07/23 11:49 PM
Row 156 | Hi @praneeth.gayam@penske.com this application has been committed up to "Develop_Log4j" branch. Please setup Bamboo for this application. | Dylan | 08/22/23 2:42 AM
| Sure @dylan.price@penske.com . Do you want to onboard develop_log4j branch to bamboo because the code is not yet merged to develop? | Gayam | 08/22/23 9:39 PM
| yes please -- for now just use develop_log4j and I will merge my changes into develop when we have a working bamboo run | Dylan | 08/23/23 12:02 AM
| @dylan.price@penske.com , Build and deploy plan onboarded and develop_log4j branch onboarded to bamboo. https://bamboo.penske.com/browse/PRINTAPPBP-PRINTB1/deployments Please deploy. Thanks | Gayam | 08/24/23 12:44 AM
Row 156 | @Review: @venkatesh.hossalinever@penske.com , This app is ready for your review. Please check. Thanks. https://bitbucket.penske.com/projects/PBJB/repos/printapplication/pull-requests/3/overview | Gayam | 03/30/23 11:37 PM
Row 156 | Completed reviewing the log4j secrets there is no code changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 3:42 AM
| Thank you. Changed the status to Cap Maven. | Gayam | 03/02/23 1:22 AM
Row 156 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 156 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:52 AM
Row 157 | Deployed in production on 10/5/23 | Kalrav | 10/06/23 12:44 AM
| Thanks @kalrav.khamar@penske.com | Gayam | 10/06/23 12:56 AM
Row 157 | @sreekanth.kancharla@penske.com , Build and Deploy plans are onboarded to Bamboo. As this this the batch app, AO needs to do the QA deployment. Currently the build will deploy to /var/tmp folder of QA server. | Gayam | 03/20/23 11:44 PM
Row 157 | @praneeth.gayam@penske.com PR is merged. This application is a batch app running on IFS. We should've SUPPORT environment for IFS deployed apps as it is AS400 database system. @hugo.scavino@penske.com mentioned that the deployment to IFS also can be done from bamboo. We can test that auto deploy from bamboo for this app. Please let us know incase any information required while configuring the bamboo build & deploy plans. | Sreekanth | 03/16/23 12:32 AM
| @sreekanth.kancharla@penske.com , One of the @david.w.graf@penske.com 's app was deployed to IFS. But it was manual. Bamboo deploys to regular QA server's /var/tmp folder and after that David did the manual process to deploy to IFS server. Hope David will reach out to you regarding this. Thanks. | Gayam | 03/18/23 1:00 AM
Row 157 | Review: @sreekanth.kancharla@penske.com , Please review https://bitbucket.penske.com/projects/ITFIS/repos/psndmail-batch/pull-requests/4/overview | Gayam | 03/02/23 3:04 AM
Row 157 | Secrets: @kalrav.khamar@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/24/23 2:00 AM
| @praneeth.gayam@penske.com We don't need any remediation for the shared secrets as all the secrets are just variable name "password" and no password is stored inside the code. @kalrav.khamar@penske.com | Sreekanth | 02/24/23 9:30 PM
| Thanks @sreekanth.kancharla@penske.com . Changed the app status to (Cap)Maven | Gayam | 02/25/23 12:18 AM
Row 157 | As per our discussion with @kalrav.khamar@penske.com / @yvette.urso@penske.com This is the new application which is onboarded to log4j team's scope. @mathumala.nachiappan@penske.com / @balu.mohan@penske.com | Gayam | 02/17/23 7:21 PM
Row 158 | @yvette.urso@penske.com the modernization for this JAR is complete. One for your status report. | Hugo Scavino | 01/26/23 8:34 PM
Row 158 | We confirmed there are no secrets. Also we decided not to modernize this application and instead leave the source code in bitbucket and the binary in artifactory. No Bamboo will be created. No addiational work or bug fixes are ever intended. | Hugo Scavino | 01/25/23 10:46 PM
Row 158 | @praneeth.gayam@penske.com Most likely Secrets are False Postives | Yvette Urso | 01/25/23 12:44 AM
Row 158 | @praneeth.gayam@penske.com per @shane.myers@penske.com and @hugo.scavino@penske.com - Would like to move this to Bitbucket but not upgrade Maven | Yvette Urso | 01/25/23 12:43 AM
Row 158 | This is deprecated, but is being used so must be upgraded | Yvette Urso | 01/25/23 12:38 AM
Row 158 | @hugo.scavino@penske.com , One more question for this app. There is no existing bamboo build for this app. So under which project we need to create bamboo specs for this app. | Gayam | 01/11/23 9:23 AM
| So this should be under architecture and its own project for ptldao. There does seem some clients still using this package | Hugo Scavino | 01/19/23 3:42 AM
Row 158 | @hugo.scavino@penske.com ,Secret scanning and analysis are completed and found that true positives exist. We will send the sheet in email. Please check. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/10/23 12:24 AM
Row 159 | @praneeth.gayam@penske.com this application moved to the bitbucket looks good me . you can keep in your list it is done . we are not deploying this application . | Mahipal | 05/16/23 11:58 PM
| Sure @mahipal.podduturi@penske.com . I changed to Done status as there is no deployment. | Gayam | 05/17/23 1:58 AM
Row 159 | @praneeth.gayam@penske.com please point to new bitbucket url | Mahipal | 04/06/23 2:08 AM
| https://bitbucket.penske.com/projects/ARPROJ/repos/queryrunner-batch/browse | Gayam | 04/06/23 2:43 AM
Row 159 | @ yes can point that | Mahipal | 04/06/23 2:07 AM
Row 159 | @shane.myers@penske.com / @mahipal.podduturi@penske.com , Do you want us to point out the old Bamboo builds to new bitbucket URL? | Gayam | 04/03/23 9:44 PM
Row 159 | @praneeth.gayam@penske.com can you work on next steps | Mahipal | 04/03/23 9:41 PM
Row 159 | bitbucket looks good. @praneeth.gayam@penske.com @yvette.urso@penske.com should I just change the status to 6.3 AO app deployed - DONE? Not sure if that is the right step and don't want to mess up your process. | William | 03/01/23 2:44 AM
Row 159 | @praneeth.gayam@penske.com @mathumala.nachiappan@penske.com I discussed this app with Don - please simply move to bitbucket. No other steps needed at this time. | William | 02/08/23 7:12 PM
| In that case, we just need to do following things for this app. 1. SVN to BB migration of production branch 2. Change the Bamboo build to point to bitbucket @shane.myers@penske.com / @hugo.scavino@penske.com , Correct me if you think any other tasks we need to do for this app. @mathumala.nachiappan@penske.com , @haribabu.challa@penske.com | Gayam | 02/09/23 12:05 AM
| That is correct, please just migrate to bitbucket and we can consider this complete. | William | 02/10/23 10:31 PM
| @shane.myers@penske.com , queryrunner project is migrated to bitbucket. Following is the bitbucket URL https://bitbucket.penske.com/projects/ARPROJ/repos/queryrunner-batch/browse Changed the status to '(AO)Bitbucket Review' Could you please check and push the status to final stage as there is no further work on this project. | Gayam | 02/23/23 12:23 AM
Row 159 | @praneeth.gayam@penske.com - Pls. confirm the modernization steps required for this application? | Mathumala Nachiappan | 02/08/23 11:03 AM
Row 159 | @praneeth.gayam@penske.com per @shane.myers@penske.com - Would like to move this to Bitbucket but not upgrade Maven | Yvette Urso | 01/25/23 12:42 AM
Row 160 | @praneeth.gayam@penske.com The team completed their analysis of this batch. It has not processed any transactions since 2018. The application that initiated JMS queue transactions was sunset in 2018. This must have accidentally been left behind. We are going to shut down in QA and monitor, but we are 99.999% sure this is going to be retired. I am going to change the status to Retire App. Can you do me a favor and change the Current AO status dates to blank for any app that is marked as "retire app". Thanks. | Gianfranco | 08/24/23 3:07 AM
| @frank.d'angelo@penske.com , Current AO status is populating automatically. @yvette.urso@penske.com , Can you help on this please | Gayam | 08/24/23 4:22 AM
Row 160 | For our reference, ticket to shut down batch in QA submitted: https://jira.penske.com/browse/ITDSW-2647 | Gianfranco | 08/24/23 3:18 AM
Row 160 | @jeremiah.ashway@penske.com , I sent secrets in an email. Could you please verify it. Thanks. | Gayam | 08/05/23 12:35 AM
Row 161 | @praneeth.gayam@penske.com Please do not proceed with working on this application. We have a partner org who is going to be completely rewriting this application, so we want to hold off on modernizing presently. I am going to mark it as Retire App for now to get it off the list. If something changes, I will let you know. | Gianfranco | 08/22/23 7:05 PM
Row 162 | Hi @praneeth.gayam@penske.com we are not finding any applications that rely on this jar file. Could you please retire this application? | Dylan | 06/13/23 5:12 PM
| Thanks @dylan.price@penske.com . As per your instructions, changing the status to retired. @yvette.urso@penske.com / @shane.myers@penske.com | Gayam | 06/14/23 2:41 AM
Row 162 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 162 | Question: @mark.weaver@penske.com , Is the modernization for this app going to take care by app team? From @rafeeq.ahamed@penske.com , we heard that, this app has big scope and changes are happening in this app. So want to make sure whether this is in CG scope for log4j/maven modernization changes. Thanks. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 02/03/23 12:43 AM
Row 162 | @rafiq.melath@penske.com - Is this App group correct for this application. CC: @yvette.urso@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/23/23 7:33 PM
Row 163 | @praneeth.gayam@penske.com David asked me to create the PR through release branch so I merged the changes to it. So please build the bamboom plan for this.Thanks! | Sama | 09/26/23 7:24 PM
| @bhagya.sama@penske.com , build is successful for the branch release/ESS-27-restfilter-sec-modern | Gayam | 09/28/23 12:55 AM
Row 163 | Hi @praneeth.gayam@penske.com I reviewed the code, Please build the new Bamboo plan for this utility to deploy the changes. | Sama | 09/21/23 8:48 PM
| Sure @bhagya.sama@penske.com . Please merge the PR when you get a chance. Thanks. | Gayam | 09/22/23 12:13 AM
Row 163 | @shane.myers@penske.com will look at who to assign this to as the AO. | Yvette Urso | 01/25/23 12:48 AM
Row 163 | This is not really an app, but a utility. | Yvette Urso | 01/25/23 12:38 AM
Row 163 | @hugo.scavino@penske.com , This is ready for AO review. Please review in the below PR and merge. https://bitbucket.penske.com/projects/ARPROJ/repos/restfilter/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/16/22 3:08 AM
Row 166 | @praneeth.gayam@penske.com tested working as excepted you can close this | Mahipal | 04/06/23 2:07 AM
| @mahipal.podduturi@penske.com , I believe it will be closed only after prod deployment and AO is the owner to close it. And I think you tested in Dev environment only. It needs to be deployed to QA by AO and test over there. | Gayam | 04/06/23 2:40 AM
Row 166 | @praneeth.gayam@penske.com can you create the conf folder under resources folder and move db.porp | Mahipal | 04/03/23 9:59 PM
| @mahipal.podduturi@penske.com , It is done. Please check the develop branch. Thanks. | Gayam | 04/04/23 11:26 PM
Row 166 | I am doing testing it is not loading the database properties. | Mahipal | 03/31/23 6:40 PM
Row 166 | @mathumala.nachiappan@penske.com Please choose the appropriate bucket and specify what you are wanting @shane.myers@penske.com to do. Thank you | Yvette Urso | 12/09/22 12:53 AM
| Sure @yvette.urso@penske.com . Thought App Owner can understand the activity after deployment and change to their appropriate status once they start working on it. As the deployment is done long back, CAP is waiting for the confirmation on the changes | Mathumala Nachiappan | 12/12/22 4:41 PM
Row 166 | @shane - QA Deployment done on 14th Nov | Mathumala Nachiappan | 11/23/22 3:43 AM
Row 167 | @falgun.patel@penske.com , This app is ready for your review with an open question. https://bitbucket.penske.com/projects/MAIN/repos/rsareviewloop-web/pull-requests/3/overview Question: Targeted folder have different web.xmls for each environment. Dev web.xml is using LocalTestAuthenticationFilter in filters tag and qa, prod web.xmls are using DLinksAuthenticationFilter in filters tag. For now we are keeping the prod web.xml under Webapp/WEB-INF. But it needs to be handled for dev. Please check. Thanks. | Gayam | 09/23/23 2:00 AM
| @praneeth.gayam@penske.com I am currently doing a code review and review on the app entry files like you mentioned with the web.xml. There were some missing dependencies and the log4j stuff was not completely correct, so I'm working on making the needed updates and will address the code review PR soon. Been busy with other deploys this and last week. | David | 10/03/23 3:29 AM
| Sure @david.long@penske.com . Thank you. | Gayam | 10/04/23 1:47 AM
Row 167 | @praneeth.gayam@penske.com - is there any update on this? | Patel | 08/16/23 5:29 PM
| @falgun.patel@penske.com , It is almost completed. Let me know if you are waiting for this. We will take it as priority. | Gayam | 08/17/23 1:16 AM
| No, I was just checking as there was no update on this since 6/27. No need to change priority of this. | Patel | 08/17/23 8:28 PM
Row 167 | Secrets: @david.long@penske.com , I sent the secrets in the email. Please verify and let us know whether this app requires code changes. | Gayam | 06/28/23 12:44 AM
| @praneeth.gayam@penske.com Just validated and all secrets found were false positives. No code change needed. | David | 06/28/23 1:28 AM
| @david.long@penske.com confirmed all secrets are false positives in the email. | Gayam | 06/28/23 2:23 AM
Row 168 | Awaiting on Singoff | Rajesh | 09/11/23 5:29 PM
Row 168 | @praneeth.gayam@penske.com Application is failing to run on QA environment. Immediate attention needed as we are getting ready to push for next step. | Rajesh | 08/29/23 12:31 AM
| @rajesh.haravde@penske.com , as discussed in the email, the error related to dlinks auth filter. AOs are discussing with Architecture tema on this issue. | Gayam | 08/30/23 2:21 AM
Row 168 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:09 AM
| @rajesh.haravde@penske.com , This is already onbaorded to bamboo and deployed to Dev. https://bamboo.penske.com/browse/RSIBP-RSIB2/deployments | Gayam | 06/09/23 1:48 AM
Row 168 | Done. Please take it forward. | Rajesh | 04/26/23 8:28 PM
| @rajesh.haravde@penske.com , this app is deployed to dev using develop_log4j branch - https://bamboo.penske.com/browse/RSIBP-RSIB1/deployments Please verify and merge the code to develop branch. | Gayam | 04/27/23 2:07 AM
Row 168 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 168 | Validation with bitbucket & Maven done. we are awaiting on development environment configuration and validation. | Rajesh | 04/25/23 5:57 PM
| Thanks @rajesh.haravde@penske.com . PR is still in open status. Could you please merge. In the mean time we will onboard to bamboo. | Gayam | 04/26/23 1:19 AM
Row 168 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/rsi-web/pull-requests/3/overview | Gayam | 02/16/23 11:45 PM
Row 168 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:49 PM
Row 168 | Work in progress. | Rajesh | 01/18/23 8:22 PM
Row 168 | @rajesh.haravde@penske.com , We have completed the log4j/maven changes. Please review them and merge in below MR. https://bitbucket.penske.com/projects/PTLCORP/repos/rsi-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/09/22 6:43 AM
| We will do the needful as requested and get back to you on build results. Thanks. Please do the same thing as requested earlier for CVI project too. | Rajesh | 12/12/22 10:21 PM
Row 169 | as per my understanding we have only web application and that the URL for that. | Rajesh | 04/14/23 12:06 AM
Row 169 | Web project URL : https://svn.penske.com/svn/webprojects/corp/safety/ branches/dev_gh/ | Rajesh | 02/10/23 2:56 AM
| Thanks @rajesh.haravde@penske.com . This is batch project. I am posting the above URL in the safetydata.war project. | Gayam | 02/10/23 3:09 AM
| @praneeth.gayam@penske.com - Are we still looking details for safetydata? CC: @rajesh.haravde@penske.com | Mathumala Nachiappan | 02/14/23 10:32 AM
| Yes @mathumala.nachiappan@penske.com . We got the details for safetyData web app but not on the batch app. This line item is for batch app. | Gayam | 02/14/23 11:39 PM
| @rajesh.haravde@penske.com , This line item is for safetydata batch app. We got the details for only web app. Changing the status to 'Waiting for AO' | Gayam | 02/16/23 7:48 PM
Row 169 | we will confirm about the batch but for web project that the url. | Rajesh | 02/10/23 2:55 AM
Row 169 | SafetyData has both batch and web applications pointing to same repo which is discussed in safetydata.war app. So following these things in that app. | Gayam | 01/26/23 12:09 AM
Row 169 | Safety Data’s repository is empty. Praneeth been informed , awaiting on reply. | Rajesh | 01/18/23 8:23 PM
Row 169 | @rajesh.haravde@penske.com - Pls. share the repo details for this application. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:17 PM
| I shared the info on safetydata war project. | Rajesh | 12/09/22 1:37 AM
| Please find details of repo and bamboo build for QA environment. Repo: https://svn.penske.com/svn/webprojects/corp/safety/ Branch : branches/dev_gh/ Bamboo Build : https://bamboo.penske.com/browse/SAF-SAFQA Thanks. | Rajesh | 12/12/22 10:24 PM
Row 169 | Thanks @rajesh.haravde@penske.com . Let me discuss with @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/12/22 4:56 PM
Row 169 | Thanks @yvette.urso@penske.com . | Mathumala Nachiappan | 12/01/22 9:16 PM
Row 169 | @mathumala.nachiappan@penske.com please proceed with resources assigned. If you have any questions, we can discuss. This should be resolved. | Yvette Urso | 12/01/22 8:32 PM
Row 169 | @don.kichline@penske.com @hugo.scavino@penske.com @yvette.urso@penske.com - How do we resolve the Resource Issue with corp for this application? | Yvette Urso | 11/30/22 12:33 AM
| The resource issue has to be resolved by the application owner. From our team we move on. However, at a certain point they will need to prioritize people to work on this. This is a production issue that impacts security on multiple platforms. If they need further clarification on priorities, have their manager talk to me. | Donald Kichline | 11/30/22 12:41 AM
| @don.kichline@penske.com @hugo.scavino@penske.com Understood, thank you | Yvette Urso | 11/30/22 2:24 AM
Row 169 | Need to determine resource for this application - was notified by @hugo.scavino@penske.com we may not have anyone to work this app. | Yvette Urso | 11/22/22 2:41 AM
Row 170 | @rajesh.haravde@penske.com , the status modified as App Deployed. But looking at above comments it is still in Maven review. Also, no bamboo deployments happened. Please check and let us know whether the updated status correct or not. @yvette.urso@penske.com | Gayam | 10/06/23 5:51 PM
Row 170 | Web.xml file was not configured properly. Please take prod version and check other conf files as well | Narsimhamurthy | 08/30/23 7:36 AM
| @narsimhamurthy.peddoju@penske.com , Do you mean copy web.xml and other conf files from trageted/prod folder? | Gayam | 08/30/23 10:52 PM
Row 170 | Bamboo build job has to create | Narsimhamurthy | 08/17/23 9:10 PM
| @narsimhamurthy.peddoju@penske.com , once the review completes and you merge the code, you can provide a comment to onboard to bamboo. Is the review completed? | Gayam | 08/18/23 12:56 AM
Row 170 | @rajesh.haravde@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/PTLCORP/repos/safetydata-web/pull-requests/3/overview | Gayam | 06/16/23 4:02 AM
Row 170 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 170 | On Secrete with respect to Safety data, we are not implementing any code change at this time. please take forward as it is. | Rajesh | 04/26/23 8:02 PM
Row 170 | Secrets: @rajesh.haravde@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:34 AM
Row 170 | @rajesh.haravde@penske.com confirmed following URL for web application. Web project URL : https://svn.penske.com/svn/webprojects/corp/safety/ branches/dev_gh/ | Gayam | 02/10/23 3:10 AM
Row 170 | @rajesh.haravde@penske.com , Both web and Batch bamboo plan is connecting to same repo. Not sure whether that is correct or are we missing nay info. Usually web and batch projects should be separate..right? @mathumala.nachiappan@penske.com | Gayam | 12/09/22 1:57 AM
| Safetydata and safetydata.war are same project. here the info as requested. Please find details of repo and bamboo build for QA environment. Repo: https://svn.penske.com/svn/webprojects/corp/safety/ Branch : branches/dev_gh/ Bamboo Build : https://bamboo.penske.com/browse/SAF-SAFQA | Rajesh | 12/12/22 10:26 PM
| @hugo.scavino@penske.com , Both web and batch projects related to this app have same repository. Not sure how it is going as we have to have separate bamboo builds and repos in mavanization. Could you please suggest. Thanks. @rajesh.haravde@penske.com | Gayam | 01/26/23 12:03 AM
Row 170 | Changed status to AO Bamboo | Yvette Urso | 12/15/22 2:54 AM
Row 170 | @rajesh.haravde@penske.com - Issue with Folder structure. Pls. share the folder reference to start the log4J changes. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:12 PM
| what do you mean by folder reference ?please schedule team call to take it forward thanks. | Rajesh | 12/01/22 9:52 PM
| @rajesh.haravde@penske.com , Web and Batch both source code, configuration files commit in single SVN repo....So they are used same repo to both WEB and Batch build plan... It is required to separate the source code, configuration files for Web and Batch. https://svn.penske.com/svn/webprojects/corp/safety/ and same branch "branches/dev_gh/ " but artifact generation is different for both @mathumala.nachiappan@penske.com | Gayam | 12/08/22 3:10 AM
| SafetyData QA : https://bamboo.penske.com/browse/SAF-SAFQA SafetyData PROD: | Rajesh | 12/09/22 1:36 AM
| https://bamboo.penske.com/browse/SAF-SAFPROD | Rajesh | 12/09/22 1:36 AM
Row 171 | App deployed to PROD on 08/22/2023 | Sreekanth | 08/23/23 7:35 PM
Row 171 | @veronique.labeille@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:29 AM
| @praneeth.gayam@penske.com I've provided the source as https://bitbucket.penske.com/projects/PTLCORP/repos/hvut-web/browse The shared secrets looks something different and the excel file doesn't has the source path. We don't have the below file in the bitbucket source "src/main/liberty/config/server.xml" which is part of the secret. Please clarify. @veronique.labeille@penske.com | Sreekanth | 02/25/23 2:34 AM
| @sreekanth.kancharla@penske.com , In the file we have inserted 2 columns Columns B & C. These 2 columns are from the Log4j team's review. Column B gives the info about whether it is a True/False positive. Column C gives the info about why it is a False or True positive. For the current issue, we provided the reason 'The file is not available,It is from the commit history'. Secrets scanning tool gives the secrets even if the commit history contains any secrets. Please check and let us know if you have any more questions. | Gayam | 02/27/23 11:43 PM
| @praneeth.gayam@penske.com Thank you for the clarification. We've made small change in this application and yet to be deployed to PROD. The code is not yet merged to master branch and still available in develop only. I'll have the code merged to master branch, so your team can work on log4j migration. | Sreekanth | 03/04/23 3:02 AM
| Thanks @sreekanth.kancharla@penske.com . Are these changes as part of secrets mitigation or something else? Also, please let us know once you merge your chagnes to develop branch. | Gayam | 03/07/23 12:17 AM
| @praneeth.gayam@penske.com These changes are not part of secrets. We are making changes as part of ongoing projects. The changes are merged to develop branch and yet to merge with master. | Sreekanth | 03/07/23 12:37 AM
| @sreekanth.kancharla@penske.com once your changes are deployed to production, are you planning to merge the develop_log4j to develop branch? develop_log4j contains the log4j team's changes | Gayam | 03/08/23 12:03 AM
| @praneeth.gayam@penske.com Sure, we'll take care of merging the log4j changes from develop_log4j to develop post prod deployment of current changes. | Sreekanth | 03/08/23 3:02 AM
| @praneeth.gayam@penske.com FYI, we've scheduled the PROD deployment with our changes today 04/11/2023. All the code is merged to master branch and develop branch. Could you please create PR from develop_log4j to develop branch tomorrow? | Sreekanth | 04/11/23 11:42 PM
| Sure @sreekanth.kancharla@penske.com | Gayam | 04/12/23 1:11 AM
| @praneeth.gayam@penske.com FYI, the deployment to PROD is completed. You are good to create PR for log4j changes to develop branch. | Sreekanth | 04/12/23 8:26 PM
| @sreekanth.kancharla@penske.com , Created PR https://bitbucket.penske.com/projects/PTLCORP/repos/hvut-web/pull-requests/41/overview | Gayam | 04/13/23 12:26 AM
| @praneeth.gayam@penske.com The PR has conflict. Could you please resolve and push the changes. | Sreekanth | 04/13/23 12:47 AM
| @praneeth.gayam@penske.com I've merged both the PR. We are good now. We'll continue testing the changes in local and use the existing Bamboo plan https://bamboo.penske.com/browse/HVUTBP-HVUTW itself to deploy to DEV and test once we are good with local testing. @veronique.labeille@penske.com | Sreekanth | 04/14/23 8:03 PM
| @praneeth.gayam@penske.com We've started testing this application in local & DEV. Please change the "App Status" accordingly. | Sreekanth | 04/19/23 9:17 PM
| @praneeth.gayam@penske.com We've tested this app in QA & got signoff from Users as well. Please update the "App Status". | Sreekanth | 05/22/23 8:50 PM
| @sreekanth.kancharla@penske.com , Changed the status. | Gayam | 05/22/23 10:13 PM
Row 171 | @veronique.labeille@penske.com , We couldn't find the SVN location and Bamboo build for this application. Could you please provide the requested info. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/18/23 2:09 AM
| @praneeth.gayam@penske.com This application is redesigned with a new name and the artifact name is "hvutirsforms.war". hvutirsforms is already in bitbcket. https://bitbucket.penske.com/projects/PTLCORP/repos/hvut-web/browse @mathumala.nachiappan@penske.com @veronique.labeille@penske.com | Sreekanth | 01/27/23 10:06 PM
| Thanks @sreekanth.kancharla@penske.com . From which branch you want us to create log4j branch. Also, please provide the bamboo location. | Gayam | 01/27/23 10:11 PM
| @praneeth.gayam@penske.com master branch is good to use for migration. Bamboo: https://bamboo.penske.com/browse/HVUTBP-HVUTW | Sreekanth | 01/27/23 10:17 PM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (Cap)Log4j | Gayam | 02/01/23 12:35 AM
Row 171 | @veronique.labeille@penske.com Testing Email | Yvette Urso | 01/25/23 1:25 AM
Row 171 | @yvette.urso@penske.com - To confirm this application to be taken by CAP for Modernization activity. CC: @brian.hug@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:40 AM
Row 171 | hi @yvette.urso@penske.com - as per the previous communication, modernization will be taken care by the Fleet services team. from the latest update of yours, is it moved under CAP scope for modernization? | Mathumala Nachiappan | 12/08/22 3:50 PM
Row 171 | @mathumala.nachiappan@penske.com this will remain where it it per @veronique.labeille@penske.com - I moved to (Cap) Analysis. Please move to the correct status per your work. | Yvette Urso | 12/02/22 12:15 AM
Row 171 | @veronique.labeille@penske.com @mathumala.nachiappan@penske.com @praneeth.gayam@penske.com - Veronique, can you please confirm this application is no longer a part of Corp App Group and it should be moved to fall under the Fleet Services Team? Thank you | Yvette Urso | 12/01/22 8:39 PM
| @yvette.urso@penske.com , It is part of Fleet Services which is under CORP systems | Veronique Labeille | 12/01/22 9:20 PM
Row 171 | Scope is moved to Fleet services Team. CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com and @april.ottey@penske.com | Mathumala Nachiappan | 12/01/22 8:10 PM
Row 172 | App deployed to PROD on 09/14/2023 | Sreekanth | 09/15/23 6:41 PM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 09/16/23 12:19 AM
Row 172 | Review: @sreekanth.kancharla@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/PTLCORP/repos/scorecard-batch/pull-requests/3/overview | Gayam | 05/03/23 2:13 AM
| @praneeth.gayam@penske.com Added review comment to the PR. please check and do the need. | Sreekanth | 05/08/23 10:58 PM
| @praneeth.gayam@penske.com I could the review comment is taken care. I've merged the PR. Please proceed with further process. | Sreekanth | 05/09/23 7:12 PM
| @sreekanth.kancharla@penske.com , Onboarded develop branch to Bamboo--------https://bamboo.penske.com/browse/CBP-CEFLEETB0 Please deploy to QA. | Gayam | 05/11/23 11:22 PM
| @praneeth.gayam@penske.com We've started validating the changes in our local environment, post that we'll deploy this to QA. Hope the "App Status" needs to be changed to AO team. | Sreekanth | 05/22/23 8:42 PM
| Yes @sreekanth.kancharla@penske.com . I already kept this app in (AO)Bamboo Review status. | Gayam | 05/22/23 10:09 PM
Row 172 | @veronique.labeille@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:29 AM
| @praneeth.gayam@penske.com Apart from 1 secret related to "src/conf/DB.properties" no other required any mitigation. For "src/conf/DB.properties", as per my analysis, this file seems unused. Please proceed with log4j changes. While testing this application, we'll remove the "src/conf/DB.properties" and test. Post testing, we'll remove this file and corresponding changes in the code. | Sreekanth | 04/12/23 12:02 AM
| Sure @sreekanth.kancharla@penske.com . Thanks | Gayam | 04/12/23 1:18 AM
Row 172 | Thanks @yvette.urso@penske.com . Following is the repo and bamboo details for this project. Batch: - https://svn.penske.com/svn/webprojects/corp/cefleetBatch/trunk/cefleetBatch Bamboo: https://bamboo.penske.com/browse/CBP | Gayam | 02/01/23 2:54 AM
Row 172 | @praneeth.gayam@penske.com I created a Batch and Web for Scorecard. Moved the status to (Cap) Analysis - please update the status to the right one from here. Thank you | Yvette Urso | 02/01/23 2:24 AM
Row 173 | App deployed to PROD on 09/14/2023 | Sreekanth | 09/15/23 6:41 PM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 09/16/23 12:19 AM
Row 173 | @praneeth.gayam@penske.com We've received confirmation from Manager that we'll continue with "scorecard" name. With this, we'll have to change the artifact name to "cefleetservices" in pom.xml as that is the context root of the application. We'll make this code change from our end. The other change should be in bamboo deploy plan(s) variable "appname" should also be as "cefleetservices" along with this, please delete the old deploy plan https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=140509192 | Sreekanth | 05/09/23 7:17 PM
| @sreekanth.kancharla@penske.com , Changed variable Appname from 'scorecard' to 'cefleetservices' in the deploy spec. Also, deleted the old deploy plans and run feature branch according to deleted deploy plans. https://bamboo.penske.com/browse/CBP-CEFLEETW/deployments https://bamboo.penske.com/deploy/config/configureEnvironmentVariables.action?environmentId=142802994 | Gayam | 05/11/23 11:21 PM
| @praneeth.gayam@penske.com Seems still the app is not deploying fine and I could see somewhere the name of the war is still scorecard.war & scorecard.tgz but we've changed that to cefleetservices.war and the same is available in target folder of artifact in bamboo. Please check below deployment logs and do the need. https://bamboo.penske.com/deployment-download/142802994/build_logs/142737427-142802994-141069075.log | Sreekanth | 05/12/23 6:49 PM
| @sreekanth.kancharla@penske.com , We observed following things. Changes for artifact id has done in "feature/FS-132-Log4j2-Testing" .But recently 2 more branches were created and artifact id is still "scorecard" . So need to make changes in those 2 branches pom file . https://bamboo.penske.com/deployment-download/142802994/build_logs/142737427-142802994-141068843.log - Deployment with "feature/FS-132-Log4j2-Testing" https://bamboo.penske.com/deployment-download/142802994/build_logs/142737427-142802994-141069010.log - Deployment with "develop-log4j-ao-testing" Could you please check. | Gayam | 05/15/23 11:33 PM
| @praneeth.gayam@penske.com We kept the artifact id as "scorecard" to have no change artifactory folder path but we've changed the final-name to "cefleetservices". Even then the artifact name is creating as scorecard-2.0.0-feature-sree-peer-review-20230515.190735-7.war Is that based on the artifactId attribute from pom file, if so then we've no choice other than making the artifactId to "scorecard" so the path in artifactory also would be as com/penske/cefleetservices instead of com/penske/scorecard Since the correct app name is scorecard we wanted to have the same everywhere except the artifact name as "cefleetservices" Hope you understand, please suggest on this. | Sreekanth | 05/16/23 2:19 AM
| @sreekanth.kancharla@penske.com , Theoretically it is possible but this has to be discussed with the broad team as environment has multiple steps to deploy to the server like build, deployment to artifactory, deployment to /opt location and a websphere script deploys to desire websphere server. | Gayam | 05/17/23 3:06 AM
| We've changed the artifact id in pom file to "cefleetservices" only so artifact name also will be the same. | Sreekanth | 05/22/23 8:41 PM
Row 173 | Review: @sreekanth.kancharla@penske.com , this app is ready for review. https://bitbucket.penske.com/projects/PTLCORP/repos/scorecard-web/pull-requests/3/overview | Gayam | 03/18/23 1:11 AM
| @praneeth.gayam@penske.com Added review comments. Please check. | Sreekanth | 04/11/23 11:53 PM
| @sreekanth.kancharla@penske.com , As discussed we implemented the review comments. Please check and merge. Thanks | Gayam | 04/15/23 12:44 AM
| @praneeth.gayam@penske.com The PR is merged. Please proceed with further steps. | Sreekanth | 04/15/23 12:55 AM
| Thanks @sreekanth.kancharla@penske.com . We will onboard to bamboo and deploy to Dev | Gayam | 04/19/23 3:26 AM
| @sreekanth.kancharla@penske.com , Bamboo build onboarding completed. Dev deployment done using develop branch. Please verify. Thanks. https://bamboo.penske.com/browse/CBP-CEFLEETW | Gayam | 04/20/23 2:05 AM
| @praneeth.gayam@penske.com Thank you for the update. We'll start testing this app in DEV. | Sreekanth | 04/24/23 8:35 PM
| @praneeth.gayam@penske.com If possible, please change the name of the plan in Bamboo from "scorecard-Web" to "scorecard-web" to maintain the consistency between Bamboo & Bitbucket. | Sreekanth | 04/24/23 11:41 PM
| Sure @sreekanth.kancharla@penske.com . we will let you know once the change implemented. | Gayam | 04/25/23 1:11 AM
| @sreekanth.kancharla@penske.com , changes are completed. Please verify. | Gayam | 04/27/23 2:12 AM
| @praneeth.gayam@penske.com Thank you for making the naming corrections as same as bitbucket repo name for both build & deploy plans. Started using new deploy plan. Please delete old deploy plan. | Sreekanth | 04/27/23 7:01 PM
Row 173 | @praneeth.gayam@penske.com No remediation required for the shared secrets. @veronique.labeille@penske.com | Sreekanth | 02/25/23 2:36 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to Cap Maven | Gayam | 02/27/23 11:45 PM
Row 173 | @praneeth.gayam@penske.com The status is as (AO). Please remind us in case you are waiting on something from us. CC: @veronique.labeille@penske.com | Sreekanth | 02/22/23 8:40 PM
| @sreekanth.kancharla@penske.com , Secrets need to be confirmed. I will share all the secrets of new corp apps. Thanks. | Gayam | 02/23/23 3:29 AM
| @veronique.labeille@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:29 AM
Row 173 | @praneeth.gayam@penske.com I created a Batch and Web for Scorecard. Moved the status to (Cap) Analysis - please update the status to the right one from here. Thank you | Yvette Urso | 02/01/23 2:24 AM
Row 173 | @veronique.labeille@penske.com , We couldn't find the SVN location and Bamboo build for this application. Could you please provide the requested info. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/18/23 2:08 AM
| @praneeth.gayam@penske.com This application has 2 projects. Web - https://svn.penske.com/svn/webprojects/corp/cefleet/trunk/cefleetservices Batch: - https://svn.penske.com/svn/webprojects/corp/cefleetBatch/trunk/cefleetBatch Bamboo: https://bamboo.penske.com/browse/CBP Not sure why we've only 1 application in this file. @mathumala.nachiappan@penske.com @veronique.labeille@penske.com | Sreekanth | 01/27/23 10:09 PM
| @sreekanth.kancharla@penske.com , Please let us know whether we need to modernize both batch and war applicaitons for this app. If yes, @yvette.urso@penske.com please insert 1 more column for batch app. @mathumala.nachiappan@penske.com | Gayam | 01/27/23 10:17 PM
Row 173 | @yvette.urso@penske.com - To confirm this application to be taken by CAP for Modernization activity. CC: @brian.hug@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:40 AM
Row 173 | hi @yvette.urso@penske.com - as per the previous communication, modernization will be taken care by the Fleet services team. from the latest update of yours, is it moved under CAP scope for modernization? | Mathumala Nachiappan | 12/08/22 3:51 PM
Row 173 | @mathumala.nachiappan@penske.com this will remain where it it per @veronique.labeille@penske.com - I moved to (Cap) Analysis. Please move to the correct status per your work. | Yvette Urso | 12/02/22 12:15 AM
Row 173 | @veronique.labeille@penske.com @mathumala.nachiappan@penske.com @praneeth.gayam@penske.com - Veronique, can you please confirm this application is no longer a part of Corp App Group and it should be moved to fall under the Fleet Services Team? Thank you | Yvette Urso | 12/01/22 8:39 PM
| @yvette.urso@penske.com , It is part of Fleet Services which is under CORP systems | Veronique Labeille | 12/01/22 9:24 PM
Row 173 | Scope is moved to Fleet services Team. CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com and @april.ottey@penske.com | Mathumala Nachiappan | 12/01/22 8:11 PM
Row 174 | @don.kichline@penske.com is looking further into what this application does. | Yvette Urso | 09/13/23 7:29 PM
Row 174 | @shane.myers@penske.com , For this jar we changed the scope of log4j jars from provided to compile. Please check and merge the code to develop branch. PR is https://bitbucket.penske.com/projects/ARPROJ/repos/security-author-filter/pull-requests/6/overview | Gayam | 05/22/23 9:11 PM
Row 174 | I have reviewed the changes. I had to decline the pull request. That was an accident on my part. I did take the changes and eventually merged them into the develop branch. Please proceed to the Bamboo step. Recall the final step for this JAR is artifactory. | Hugo Scavino | 02/10/23 10:55 PM
| @hugo.scavino@penske.com , Bamboo onboarding is completed. https://bamboo.penske.com/browse/SECUTIL-AUTHOR Could you please check. | Gayam | 02/13/23 11:32 PM
Row 174 | dependency with security_util.jar | Mathumala Nachiappan | 12/02/22 5:32 PM
| @yvette.urso@penske.com - This is just an update. Dependency is mentioned in #76. And Hugo is already tagged and the App status is updated | Mathumala Nachiappan | 12/12/22 4:50 PM
| @mathumala.nachiappan@penske.com let's re-mention the dependency here so the AO does not have to hunt or the details. Thanks | Yvette Urso | 12/15/22 2:42 AM
| @hugo.scavino@penske.com , After adding the latest security_util dependency, this app is getting following issue. security-author-filter/src/main/java/com/penske/security/filter/AuthorFilter.java:[57,65] constructor SecurityDesign in class com.penske.security.factory.SecurityDesign cannot be applied to given types; required: no arguments found: no arguments reason: SecurityDesign() has protected access in com.penske.security.factory.SecurityDesign SecurityDesign is from securityutil.jar and the constructor is a protected method. That is the reason we are seeing the above issue. | Gayam | 02/03/23 1:13 AM
| That is my fault. I will repair this. | Hugo Scavino | 02/03/23 2:57 AM
| Completed02 Feb 2023, 4:35:43 PM – < 1 second ago Please attempt the build. | Hugo Scavino | 02/03/23 3:06 AM
| Thanks @hugo.scavino@penske.com . We will check and update you. | Gayam | 02/03/23 11:45 PM
Row 174 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:28 AM
Row 174 | @hugo.scavino@penske.com | Yvette Urso | 12/09/22 1:02 AM
| @yvette.urso@penske.com - The dependent jar has to be cleared first. Presently no action required from Hugo now. | Mathumala Nachiappan | 12/12/22 4:49 PM
Row 175 | Thanks @hugo.scavino@penske.com for your support. This is perfectly fine now for the team to proceed on the dependent application. Can we update the status to deploy done? CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 02/15/23 10:22 AM
| Yes, this is done as the JAR is now in artifactory. | Hugo Scavino | 02/15/23 10:25 AM
| Thanks @hugo.scavino@penske.com . Changed the status to (AO)App Deploy Done. | Gayam | 02/16/23 1:16 AM
Row 175 | Team, great job. I repaired an issue with a unit test and we have another JAR ready for downstream clients. This JAR should be used for new mavenization <groupId>com.penske.architecture</groupId> <artifactId>security-util</artifactId> <version>2.0.0-develop_log4j-SNAPSHOT</version> https://bamboo.penske.com/browse/SECUTIL-SEUTL0/history | Hugo Scavino | 01/31/23 4:40 AM
Row 175 | I have completed the peer review and adding required unit tests. I remved the other branches and only have develop now. https://bitbucket.penske.com/projects/ARPROJ/repos/security_util/branches Next step is to create the Bamboo project for this one. The old Bambo project https://bamboo.penske.com/browse/SECUTIL | Hugo Scavino | 01/25/23 3:21 AM
| Sure @hugo.scavino@penske.com . We will create and let you know. Thanks. @haribabu.challa@penske.com @mathumala.nachiappan@penske.com | Gayam | 01/25/23 11:33 PM
| @hugo.scavino@penske.com , Bamboo is onboarded for this application. Location is https://bamboo.penske.com/browse/SECUTIL-SEUTL We only onboarded master. If we onboard develop branch, it builds and deploys to artifactory. That is the reason we did not onboard develop yet. @haribabu.challa@penske.com | Gayam | 01/31/23 2:15 AM
Row 175 | I am going to rename the bitbucket repo to security_util from security_util_batch to match the name of the JAR | Hugo Scavino | 01/19/23 8:31 PM
Row 175 | @hugo.scavino@penske.com | Yvette Urso | 12/15/22 2:59 AM
Row 175 | @hugo.scavino@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:17 AM
Row 176 | @praneeth.gayam@penske.com what will happen in this case? as in this case dependant project is not getting updated? | Rajesh | 07/05/23 8:24 PM
| @rajesh.haravde@penske.com , We sent an email about Utimage long time back but no response. Either Utimage has to be manually uploaded to artifactory or it needs to be modernized. AO needs to decide what way we need to go. Thanks. | Gayam | 07/06/23 3:15 AM
| Sent an email to Brian. This app is blocked until Utimage issue gets resolved. | Gayam | 08/17/23 1:50 AM
| Utimage service jar is uploaded to artifactory. | Gayam | 10/19/23 7:46 AM
Row 176 | @rajesh.haravde@penske.com , Sellsheet is ready for your review. Please check the PR and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/sellsheet-batch/pull-requests/2/overview | Gayam | 10/19/23 7:45 AM
Row 176 | Praneeth did you hear anything from Utimage team . | Rajesh | 04/26/23 8:03 PM
| No @rajesh.haravde@penske.com . | Gayam | 04/28/23 2:00 AM
Row 176 | On Secrete with respect to Safety data, we are not implementing any code change at this time. please take forward as it is. | Rajesh | 04/14/23 12:07 AM
| Thanks @rajesh.haravde@penske.com . Changed the status to Blocker as this app depends on Utimageclient.jar | Gayam | 04/14/23 12:21 AM
Row 176 | Secrets: Adding to above questions, sent the secrets in the email. Please check and respond. | Gayam | 03/18/23 12:56 AM
Row 176 | Also the dependant JAR utimageservice.jar needs to be added to artifactory. I created the maven pom.xml with a local version but this cannot be the final solution. | Hugo Scavino | 01/31/23 3:04 AM
| @hugo.scavino@penske.com , We found a Bamboo build and repo for utimageservice.jar. Following are the details. Do you want us to modernize this application also? Bamboobuild: https://bamboo.penske.com/browse/USEDTRUCKS-UTIMAGECLIENT BB Repo: https://bitbucket.penske.com/projects/EBUT/repos/ut-image-service/browse | Gayam | 02/10/23 1:18 AM
| for UTImageClient jar please contact @Joseph, Brian (Penske). | Rajesh | 02/17/23 2:48 AM
Row 176 | Sure @hugo.scavino@penske.com . We will do the required things and let you know. | Gayam | 02/01/23 12:10 AM
Row 176 | Please move this to bitbucket. The AO still needs to perform regression and spot checking. It would be worth the effort to create unit tests. see below for examples https://bitbucket.penske.com/projects/ARPROJ/repos/security_util/browse/src/test/java/com/penske/security | Hugo Scavino | 01/31/23 3:01 AM
Row 176 | I migrated this project to log4j2, maven and redacted some passwords where are used by local development. I did not find any issues with JDK 1.6 or 1.8 https://svn.penske.com/svn/fieldsys/maintenance/fleetnet/branches/sellsheet_modernization/ | Hugo Scavino | 01/31/23 2:57 AM
Row 176 | I am reviewing. I created a SVN branch https://svn.penske.com/svn/fieldsys/maintenance/fleetnet/branches/sellsheet_modernization | Hugo Scavino | 01/31/23 1:42 AM
Row 176 | @hugo.scavino@penske.com will review this | Yvette Urso | 01/24/23 3:42 AM
Row 176 | @hugo.scavino@penske.com assisting with this issue. | Yvette Urso | 12/15/22 2:55 AM
Row 176 | @rajesh.haravde@penske.com , This application is using commondatasource class . Upto java 1.6 its working fine. From java1.7 the commondatasource class having the getParentLogger() abstractmethod , the app should implement the method as we are upgrading java version to 1.8. Could you please check this. | Gayam | 11/29/22 1:56 AM
| @krishna.tanga@penske.com | Yvette Urso | 12/01/22 8:33 PM
| @rajesh.haravde@penske.com / @krishna.tanga@penske.com , Adding to above question, please provide existing bamboo build for this project. @mathumala.nachiappan@penske.com | Gayam | 12/08/22 11:02 PM
| Can you please provide the repo details to take forward. Thanks | Rajesh | 12/12/22 10:28 PM
| @rajesh.haravde@penske.com , Repo details provided above. Please check. @mathumala.nachiappan@penske.com | Gayam | 12/13/22 12:42 AM
Row 176 | @april.ottey@penske.com, @rajesh.haravde@penske.com confirmed the sellsheet svn location in the email. https://svn.penske.com/svn/fieldsys/maintenance/fleetnet/branches/offshore_standalone/sellsheet | Gayam | 11/29/22 1:55 AM
Row 176 | @april.ottey@penske.com / @veronique.labeille@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:35 AM
Row 177 | Kalrav is not familiar with this app but will ask his offshore team. | Yvette Urso | 05/11/23 12:59 AM
Row 177 | Per Kathy Marko - As indicated in my previous email, this application can be retired. I believe this would fall under Steve McMullen and/or Kalrav to retire the application as I am just the business process owner. Thank you, Kathy | Yvette Urso | 05/11/23 12:14 AM
Row 177 | Changing owner of this application and need to work with April to determine who to work with for this application. | Yvette Urso | 05/01/23 9:12 PM
Row 177 | @scott.bortzel@penske.com , For this application SVN repo available https://svn.penske.com/svn/webprojects/admin/SEM/. But Bamboo plan is not available. We need production branch confirmation for log4j-Migration and without existing bamboo build we could not find this. Could you please let us know what is the latest production branch. Thanks. | Gayam | 01/14/23 1:03 AM
| @scott.bortzel@penske.com , Could you please provide the response to above question. Thanks. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 03/24/23 10:53 PM
Row 178 | I made corrections proper property files names, placement of configuration of xml files as well as pom spring setting updates. I was able to get the servicenet batch application to run in QA environment and logging is working too. | Dale Porter | 09/25/23 7:15 PM
| Thanks @dale.porter@penske.com | Gayam | 09/26/23 1:00 AM
Row 178 | @praneeth.gayam@penske.com Please check this and let us know. We are having same issues with all of our batch. I think you have addressed for Parts PO. Can you please address this issue ASAP. This is impacting our testing | Stella george | 09/08/23 8:15 PM
| @stella.george@penske.com , we followed the same process for all the batch apps and it is difficult to debug the issue without running the app in local. Please run in local and check. Thanks. | Gayam | 09/09/23 2:41 AM
| @praneeth.gayam@penske.com It is not working let us know how we can proceed? | Stella george | 09/21/23 10:39 PM
| @stella.george@penske.com , After including batchconfig-qa.properties there was no build and deployment happened. We built and deployed. It is working fine. Please check. | Gayam | 09/23/23 2:09 AM
Row 178 | I see a build was run on Sept. 6th around 3:07 pm by Sireesha. The tgz was deployed to QA but when it then ran, it did not start up correctly and is not processing like it should. When I stopped it and restarted it, I saw the same log4j errors warning as noted above. Because QA team needs this to be running in QA for testing, I had to deploy the SVN version of the app so it can run again in qa. This is not resolved, can the log4j issue be resolved for the modernized version? Thank you. | Dale Porter | 09/08/23 7:07 PM
Row 178 | @dale.porter@penske.com , build plan onboarded and deployment to artifactory is successful. Deploy plan onboarding is also successful. Please deploy to QA and test it. Thanks. Build plan: https://bamboo.penske.com/browse/SERVICENETBATCH-SVCNETB0 Deploy Plan: https://bamboo.penske.com/browse/SERVICENETBATCH-SVCNETB/deployments | Gayam | 08/03/23 12:49 AM
| HI all, I ran the deploy to QA but it did not place the tgz file of the build in the /var/tmp of the qa deploymanager (clelx150ptlge). I included url of qa build log, thank you https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151196764 | Dale Porter | 08/05/23 1:07 AM
| @dale.porter@penske.com , we will check and get back to you. | Gayam | 08/08/23 1:05 AM
| @dale.porter@penske.com , issue got fixed. Qa deployment done and tgz file generated in clelx150ptlge. Thank you | Gayam | 08/11/23 12:18 AM
| I just ran QA build for develop branch and it shows completed. However, I am not finding the servicenetbatch.tgz file in /var/tmp of the qa deployment/batch manager (clelx150ptlge). I included the url to the build log for the deployment. https://bamboo.penske.com/download/SERVICENETBATCH-SVCNETB0-DTA/build_logs/SERVICENETBATCH-SVCNETB0-DTA-5.log | Dale Porter | 08/16/23 2:08 AM
| @dale.porter@penske.com , I have verified the /apps/servicenetbatch location of QA server and jar is deployed yesterday. Please check. | Gayam | 08/17/23 1:29 AM
| That build is one I did with the old QA build using SVN for getting a change we had to test. I just ran the develop branch build and after it "completed", I do not see the servicenetbatch.tgz file in /var/tmp. Included build log reference. https://bamboo.penske.com/browse/SERVICENETBATCH-SVCNETB0-DTA-6/log | Dale Porter | 08/17/23 9:10 AM
| @dale.porter@penske.com , It looks like you only run the build but you need to run the deploy plan also. If you want to deploy to QA, you need to run the QA deploy plan and for prod need to run the prod deploy plan. | Gayam | 08/18/23 8:00 PM
| I ran the build and it did place a servicenetbatch.tgz file on /var/tmp However, when it deployed I see that the servicenetbatch.jar file is dated 8/9 not the date 8/24 of the bamboo build so the compiled code is not included. Before looking into the log4 j issue noted next, Can someone please take a look at reason for why old code from days prior is only being packaged. Thank you. Build log https://bamboo.penske.com/deployment-download/151912586/build_logs/151814174-151912586-151200180.log | Dale Porter | 08/26/23 7:36 AM
| @dale.porter@penske.com , QA webservices deploy job runs every hour which copies the jar from var/tmp to targeted location. I am seeing the servicenetbatch.jar in the targeted location with the 08/25 date. Please check. | Gayam | 08/28/23 10:35 PM
| Made a small java code change in the logger comment (do not effect application) however, the packaged tgz file did not include a recently built class files. Including the "UnitAttachment.java" that I changed in develop branch. The bamboo build can be found at https://bamboo.penske.com/browse/SERVICENETBATCH-SVCNETB0-7/log | Dale Porter | 08/30/23 8:35 AM
| I ran the full deploy to pickup the new build and it included the updated class files. However, issue is that application does not run in QA. Is not processing data. Also there is no logger and I see an immediate error message when starting the program as follows: [600013879@clelx150ptlge servicenetbatch]$ log4j:WARN No appenders could be found for logger (com.penske.architecture.batchframework.config.PropertiesConfigurator). log4j:WARN Please initialize the log4j system properly. log4j:WARN See http://logging.apache.org/log4j/1.2/faq.html#noconfig for more info. | Dale Porter | 09/06/23 2:24 AM
Row 178 | Review: @dale.porter@penske.com , this app is ready for your review. Please check and merge the PR. https://bitbucket.penske.com/projects/MAIN/repos/servicenet-batch/pull-requests/3/overview | Gayam | 07/27/23 11:50 PM
| I reviewed and merged the code. Thank you. | Dale Porter | 07/28/23 1:48 AM
| will onboard to bamboo. | Gayam | 07/31/23 2:32 AM
Row 178 | @stella.george@penske.com / @dale.porter@penske.com , This application dependent on servicenet-models.jar. This jar is not available in artifactory Could you please provide your approval to upload it to artifactory in the below location. GroupId: com.penske.apps ArtifactId: servicenet-models Version:default Location: common-mvn-development-local | Gayam | 06/30/23 12:56 AM
| Yes, please upload the servcienet-models.jar to the Penske artifactory. | Dale Porter | 07/07/23 12:54 AM
| Thanks @dale.porter@penske.com . We have uploaded the dependency jar to artifactory. | Gayam | 07/10/23 11:36 PM
Row 178 | Had a discussion with @dale.porter@penske.com and confirmed that we need to use the latest prod reference branch as base brach for modernization changes. | Gayam | 06/29/23 3:11 AM
Row 178 | Query: @stella.george@penske.com , Adding to secrets, we have a query on this app. This application dependent on servicenet-models.jar. This jar is not available in artifactory Could you please provide your approval to upload it to artifactory in the below location. GroupId: com.penske.apps ArtifactId: servicenet-models Version:default Location: common-mvn-development-local | Gayam | 06/15/23 2:02 AM
| @dale.porter@penske.com , Please provide your response for above query. Thanks. | Gayam | 06/21/23 1:06 AM
| @dale.porter@penske.com , Could you please respond to above query. | Gayam | 06/27/23 3:31 AM
Row 178 | It will be deploy later for production, please use the branch as instructed. Thank you. | Dale Porter | 06/24/23 12:44 AM
| Thanks @dale.porter@penske.com . We will use the following as base branch as instructed. https://svn.penske.com/svn/fieldsys/maintenance/batch/servicenetbatch/branches/servicenetbatch_Log4jChanges | Gayam | 06/27/23 3:28 AM
Row 178 | I have merged prior code changes we have in QA that are planned to deploy in future and do not want to lose in the bit bucket migration to the branch https://svn.penske.com/svn/fieldsys/maintenance/batch/servicenetbatch/branches/servicenetbatch_Log4jChanges | Dale Porter | 06/23/23 12:41 AM
| @dale.porter@penske.com , Do we need wait until you confirm your changes goes to production? or let us know what is the step we need to take? | Gayam | 06/23/23 11:46 PM
Row 178 | I have removed the test user User name and secret for the iBMI connection in the applicationContext.xml file and checked in the change in SVN. The other files were not senstive data (just false positives). Thank you. | Dale Porter | 06/16/23 3:02 AM
| @dale.porter@penske.com , We are seeing your changes in the dev_gh branch. Also, we are seeing latest commits in this branch. https://svn.penske.com/svn/fieldsys/maintenance/batch/servicenetbatch/branches/dev_gh But we took the https://svn.penske.com/svn/fieldsys/maintenance/batch/servicenetbatch/tags/prod/20230309 as base branch. Bamboo prod build is pointing to this branch. Which one we need to consider as base branch and start doing log4j changes? | Gayam | 06/21/23 1:05 AM
Row 178 | Secrets: @stella.george@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:52 AM
Row 179 | @subramanian.vennimalayan@penske.com / @sarath.mani@penske.com , I sent the secrets file of this app in the email. Please check. Thanks. | Gayam | 08/05/23 12:23 AM
| @praneeth.gayam@penske.com these are false alert. Please move forward. | Stella george | 08/16/23 12:02 AM
| Thanks @stella.george@penske.com . Changed to Cap maven | Gayam | 08/17/23 1:54 AM
Row 179 | @praneeth.gayam@penske.com The status shows "Waiting on AO" for this app. Could you please let us know if you need more information. | Subramanian | 07/28/23 2:10 AM
| Changed to Cap Analysis | Gayam | 07/31/23 2:45 AM
Row 179 | @david.long@penske.com , Log4j team started working on modernizing this application. When we verified the old production bamboo build we are seeing following 2 repositories mentioned in the build. SERVICEREQBATCH_PROD - https://svn.penske.com/svn/fieldsys/maintenance/batch/servicerequestbatch/tags/prod/PROD_20220428 DICTIONARYJAR_PROD (Jar repo) - https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/Jar/PROD/ I am expecting 2nd one is a dependency jar for the first repo. Is that correct? If yes, we need to do the log4j and mavanization for the dependency jar also. Could you please check and confirm. Thanks. FYI: @shane.myers@penske.com | Gayam | 05/18/23 1:22 AM
| @praneeth.gayam@penske.com Yes that is a dependency Jar. but that should be covered under Servicereqsvc,war. this jar will be used by edvir.war, servicereqbatch and servicereqweb | Stella george | 06/14/23 1:49 AM
| @stella.george@penske.com , So Servicereqsvc,war, edvir.war, servicereqbatch and servicereqweb are depending on serviceRequestUtility.jar. The source code available under https://svn.penske.com/svn/fieldsys/maintenance/service-request-service | Gayam | 06/14/23 3:29 AM
| @praneeth.gayam@penske.com we need to use the source code available in serviceRequestUtility folder for serviceRequestUtility.jar. FYI: @stella.george@penske.com | Subramanian | 06/27/23 7:53 PM
Row 180 | Review & Query: @subramanian.vennimalayan@penske.com / @stella.george@penske.com / @subramanian.vennimalayan@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/MAIN/repos/servicereqsvc/pull-requests/3/overview Query: Please check the servicereqsvcbuilder build.xml file. Currently it is building different artifacts depends on the environment and each build is using their respective properties files. These values are getting populated ibm-web-ext.xmi.ant which is then copied to ibm-web-ext.xmi. But in environment agnostic build there will be only 1 build and it can be deployed to different environments. Code needs to be chagned to satisfy environment agnostic build. Could you please check this. | Gayam | 09/21/23 12:42 AM
Row 180 | Secrets: @subramanian.vennimalayan@penske.com / @stella.george@penske.com , I ahve sent the secrets of this app in the email. Could you please check the file and let us know whether this app requires any code changes to mitigate the secrets. | Gayam | 09/14/23 1:43 AM
| @stella.george@penske.com confirmed that no changes required for secrets. Pushing the status to next step. | Gayam | 09/15/23 6:59 AM
Row 180 | @david.long@penske.com , This application having multiple src folders . We are expecting that service-request-service folder is the original source which builts servicereqsvc.war and other folder(serviceRequestUtility) is the dependency jar. SVN Location: https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/tags/prod/PROD_2023-04-06 Servicerequestutility jar build plan: https://bamboo.penske.com/browse/SVCRQ-UTILPROD servicereqsvc.war application build plan: https://bamboo.penske.com/browse/SVCRQ-SRSPROD Following are the 2 suggestions. 1. Build a new repo for serviceRequestUtility folder and mavanize and create a new bamboo plan which builds the jar and uploads to artifactory. Then servicereqsvc.war application uses that jar as a dependency in pom. 2. If serviceRequestUtility folder is not a shared jar then AO can include that folder inside the servicereqsvc.war application. Then no need of separate repo and bamboo plan for the serviceRequestUtility . Please verify and confirm. Thanks. @shane.myers@penske.com | Gayam | 06/01/23 1:49 AM
| @praneeth.gayam@penske.com Service Request utility is jar used by multiple applications. We should go with option 1. | Stella george | 06/14/23 1:52 AM
| Thanks @stella.george@penske.com | Gayam | 06/14/23 3:20 AM
Row 181 | @praneeth.gayam@penske.com , I don't have access to the specified bamboo path hence took help from @sarath.mani@penske.com did the bamboo build and verified the artifact. Everything looks good with the jar. | Subramanian | 09/06/23 1:35 AM
| Thanks @subramanian.vennimalayan@penske.com | Gayam | 09/07/23 1:27 AM
Row 181 | @praneeth.gayam@penske.com we have verified the changes and merged the PR | Subramanian | 08/31/23 8:13 PM
| Thanks @subramanian.vennimalayan@penske.com . We will onboard to Bamboo and upload the jar to artifactory. | Gayam | 08/31/23 11:42 PM
| @subramanian.vennimalayan@penske.com , we have onboarded the app to bamboo and deploy to artifactory. Please verify. https://bamboo.penske.com/browse/SVCRQ-SVCREQUTIL0 | Gayam | 09/02/23 4:15 AM
Row 181 | @praneeth.gayam@penske.com I have verified the pull request and it looks like the source has been taken from https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/tags/prod/PROD_2023-04-06 we did two more prod deploy after that tag. Could you please use the below tag and add the changes. https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/tags/prod/PROD_2023-06-27 | Subramanian | 07/28/23 2:35 AM
| @subramanian.vennimalayan@penske.com , Are there any changed made in the servicerequestutility folder? Also, are you planning any more prod deployments or code changes? | Gayam | 07/31/23 2:48 AM
| @praneeth.gayam@penske.com We are good with 2023-04-06 tag. please move forward. | Stella george | 08/19/23 12:12 AM
| Thanks @stella.george@penske.com . In that case, please review the PR and merge. https://bitbucket.penske.com/projects/MAIN/repos/servicerequestutility/pull-requests/2/overview | Gayam | 08/21/23 9:50 PM
Row 181 | @stella.george@penske.com , This app is ready for review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/servicerequestutility/pull-requests/2/overview | Gayam | 07/07/23 1:08 AM
Row 181 | Secrets: @stella.george@penske.com , I sent the secrets in the email. Please verify and let us know whether this app requires code changes. | Gayam | 06/28/23 12:45 AM
| @stella.george@penske.com confirmed there are no code chagnes required for this app. | Gayam | 07/06/23 3:36 AM
Row 182 | Review and Query: @subramanian.vennimalayan@penske.com / @stella.george@penske.com , We have completed the mavanization with an open query. PR: https://bitbucket.penske.com/projects/MAIN/repos/servicereq-web/pull-requests/3/overview Query: By checking servicereqweb build.xml file we can confirm that it is building different artifacts depends on the environment and each build is using their respective properties files. These values are getting populated in web.xml.ant which is then copied to ibm-web-ext.xmi.ant. But in environment agnostic build there will be only 1 build and it can be deployed to different environments. Code needs to be chagned to satisfy environment agnostic build. Could you please check this. | Gayam | 09/21/23 4:12 AM
Row 182 | @praneeth.gayam@penske.com I think the pull request mentioned here is created for servicereqsvc(row id -213 in this sheet). | Subramanian | 09/20/23 12:53 AM
| @subramanian.vennimalayan@penske.com , Yes you are correct. Sorry for this. Removing the above comment | Gayam | 09/21/23 12:41 AM
Row 182 | Secrets: @subramanian.vennimalayan@penske.com / @stella.george@penske.com , I have sent the secrets of this app in the email. Could you please check the file and let us know whether this app requires any code changes to mitigate the secrets. | Gayam | 09/14/23 1:44 AM
| @stella.george@penske.com confirmed that no changes required for secrets. Pushing the status to next step. | Gayam | 09/15/23 6:59 AM
Row 182 | @praneeth.gayam@penske.com ServiceReqApp the SVN URL you are having is worng. the latest build is from below URL> https://svn.penske.com/svn/fieldsys/other/service-request/tags/prod/PROD_BUILD_2021-11-09. the second one is a dependency jar, but that will be covered under Service REq Service.war. 3 one also dependency, but we are going make code change to invoke their REST API. will be removing this jar from application. 4th attachment service jar will be done by Penske Team. | Stella george | 06/16/23 10:08 PM
| Thanks @stella.george@penske.com for the confirmation of the dependencies and correct branch of ServiceReApp. Regarding the 3rd point, locationservice dependency, you said that you are trying to remove this dependency from servicereweb.war application. So do we need to wait to do the modernization until you complete the coding? | Gayam | 06/19/23 8:15 PM
| @praneeth.gayam@penske.com https://svn.penske.com/svn/fieldsys/other/service-request/dev/dev_gh use above URL. we have removed location service dependency. Thanks. | Stella george | 08/18/23 11:48 PM
Row 182 | @david.long@penske.com , Log4j team started working on modernizing this application. When we verified the old production bamboo build we are seeing following 4 repositories mentioned in the build. SERVICEREQAPP_PROD - https://svn.penske.com/svn/fieldsys/other/service-request/tags/prod/PROD_BUILD_2019-07-16 DICTIONARYJAR_PROD (Jar repo)- https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/Jar/PROD LOCATIONSERVICE_PROD (Jar repo) - https://svn.penske.com/svn/fieldsys/rental/services/locationmaintainence/trunk/LOCATIONMAINT_LIBS/client-jar/ ATTACHMENTSVC_PROD (Jar repo) - https://svn.penske.com/svn/fieldsys/other/attachment-service/Jar/prod/ I am expecting 2nd, 3rd and 4th are the dependency jars for the first repo. Is that correct? If yes, we need to do the log4j and mavanization for the dependency jars also. Could you please check and confirm. Thanks. FYI: @shane.myers@penske.com | Gayam | 05/18/23 1:24 AM
Row 183 | @sivagamasundari.suresh@penske.com deployed this app to production on 9/26/2023. This app is complete. | David Graf | 09/27/23 5:17 PM
| Thanks @david.w.graf@penske.com | Gayam | 09/28/23 12:49 AM
Row 183 | @praneeth.gayam@penske.com Hi Praneeth, I deployed release branch to QA. "Release-Ess-38-modernization". Same issue as before, Project compilation error or so. Though logs say "Success", .war file is not deployed to var/tmp Here is the link for logs: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151200584 Please take a look at this. Thanks! | Sivagamasundari Suresh | 08/29/23 7:06 PM
| @sivagamasundari.suresh@penske.com , As discussed we will check and update you. | Gayam | 08/29/23 11:14 PM
| @sivagamasundari.suresh@penske.com , As discussed in the teams, war file is moving to var/tmp and further getting deployed to targeted location. I believe there may be timing issue when you are checking. Thanks. | Gayam | 08/30/23 6:29 PM
Row 183 | @praneeth.gayam@penske.com Please provide an update on this Bamboo plan issue for sessionmgmtsvc. Here is the logs link again: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151198753 Thanks! | Sivagamasundari Suresh | 08/22/23 7:38 PM
| @sivagamasundari.suresh@penske.com , Team is checking on this issue. We will update as soon as we fix the issue. | Gayam | 08/22/23 9:05 PM
| @sivagamasundari.suresh@penske.com , My team resolved the issue and deployed to QA var/tmp location successfully. Could you please verify. | Gayam | 08/22/23 11:37 PM
| @praneeth.gayam@penske.com It deployed and I validated the logging changes. Looks good!!. Thanks so much!! | Sivagamasundari Suresh | 08/26/23 12:55 AM
| @sivagamasundari.suresh@penske.com , Thanks for the update. When are you planning to move this to production? | Gayam | 08/26/23 1:06 AM
| @praneeth.gayam@penske.com Hi Praneeth, There are few minor changes that needs to be reviewed by David. After approval, these changes can be pushed to QA and Tested. I will update here once it is done!. Thanks! | Sivagamasundari Suresh | 08/26/23 1:19 AM
Row 183 | @praneeth.gayam@penske.com , I attempted to deploy the changes in develop -Build #12 release to QA Env, qa_was8_deploy. It was not deployed...logs show that there are JTest issues in Deploy plan. (Compilation errors or so) Here is the link for the logs: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151198753 Please check this and let me know | Sivagamasundari Suresh | 08/21/23 8:59 PM
| @sivagamasundari.suresh@penske.com , If there are test case failures please fix them. Hope that resolves your issue. Thanks. | Gayam | 08/21/23 10:04 PM
| @praneeth.gayam@penske.com Please look at this again. JTest is not a unit test, it is the dtp static analysis process. If it isn't running as part of the build then there is something missing in the build plan. The other issue is that the artifact was not delivered to the var/tmp directory. The deploy was not successful, the build shows green but it is not telling the truth. | David Graf | 08/21/23 11:07 PM
Row 183 | @praneeth.gayam@penske.com , I tested the application in DEV and checked the logs. In Develop branch, committed a small change in "Timestamp pattern" - pattern layout in log4j2.xml file. and merged the changes that created Build #3. I tried to deploy the release for this Build #3 to DEV env. This caused an error. dev_was8_deploy failed. Please find the screen shot as .png image | Sivagamasundari Suresh | 07/27/23 7:43 PM
| Sure @sivagamasundari.suresh@penske.com . We will check and get back to you. | Gayam | 07/27/23 10:46 PM
| @sivagamasundari.suresh@penske.com , Deployment issue is resolved. Please check. | Gayam | 08/01/23 12:40 AM
| Thank you!. I checked it and though the dev deployment was success, I was not able to find the deployed .war in the DEV server. I searched through folders (WInSCP). Reached out to @raghuramredd.thummalapalli@penske.com . It is resolved now. I could view changes in the logs of sessionmgmtsvc app. | Sivagamasundari Suresh | 08/04/23 9:56 PM
| Thanks @sivagamasundari.suresh@penske.com | Gayam | 08/08/23 1:03 AM
Row 183 | Develop Branch Repaired : Thank you for letting my know. I repaired the branch and Bamboo plan now runs. Also this is an API so there are no front end resources so there is no tgz required. | Hugo Scavino | 02/10/23 11:03 PM
| @hugo.scavino@penske.com , dev deployment is completed for this app. Could you please verify. Thanks. | Gayam | 03/28/23 12:35 AM
Row 183 | Bamboo: Please create a secure bamboo plan for this application. No secrets issues. All mavenized | Hugo Scavino | 02/09/23 2:50 AM
| @hugo.scavino@penske.com , There is no parent declaration in pom and bin.xml is not defined. Do you want us to take care of thise? Also, jtests are getting failed. | Gayam | 02/10/23 10:38 PM
Row 183 | @mathumala.nachiappan@penske.com @hugo.scavino@penske.com This is not blocked. Changed status to Secrets Scanning | Yvette Urso | 12/09/22 12:54 AM
Row 183 | @hugo.scavino@penske.com - Secret scanning resulted with True positives. But the respective statements are not available in the current code. For your secret analysis once. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 7:33 PM
Row 183 | @yvette.urso@penske.com - There are other related testing activities by Brad from webservices team. @hugo.scavino@penske.com to confirm to move to QA | Mathumala Nachiappan | 12/02/22 5:22 PM
Row 183 | @mathumala.nachiappan@penske.com Can you update where this is in the process? ie.. what has been complete and what is pending. | Yvette Urso | 11/30/22 12:34 AM
Row 183 | Update from Hugo - This app is available in Dev. @hugo.scavino@penske.com will move to QA | Mathumala Nachiappan | 11/23/22 3:45 AM
Row 184 | This application has been retired | William | 08/25/23 8:33 PM
Row 184 | @praneeth.gayam@penske.com this application testing completed move this Deploy/Test | Mahipal | 05/17/23 12:00 AM
| @mahipal.podduturi@penske.com , Changed to QA Deploy/Test | Gayam | 05/17/23 1:56 AM
Row 184 | I deployed dev and qa and tested as well | Mahipal | 05/16/23 11:48 PM
Row 184 | I will check and let you know | Mahipal | 04/03/23 9:47 PM
Row 184 | @mahipal.podduturi@penske.com , this app is onboarded to Bamboo. Please review and let us know whether we can deploy to Dev. | Gayam | 03/23/23 11:06 PM
Row 184 | @praneeth.gayam@penske.com i am goof with PR you can star next steps | Mahipal | 03/22/23 9:15 AM
Row 184 | @praneeth.gayam@penske.com looks good to me the POM changes | Mahipal | 03/15/23 6:35 PM
| @mahipal.podduturi@penske.com , If you complete the review, can you merge the code to develop branch . https://bitbucket.penske.com/projects/ARPROJ/repos/shoptalkreg-web/pull-requests/4/overview | Gayam | 03/15/23 10:39 PM
Row 184 | @praneeth.gayam@penske.com updated the comments https://bitbucket.penske.com/projects/ARPROJ/repos/shoptalkreg-web/pull-requests/4/diff#pom.xml | Mahipal | 03/09/23 7:33 PM
| @mahipal.podduturi@penske.com , We have implemented the suggestions mentioned in the comment. Please check. | Gayam | 03/12/23 9:42 PM
Row 184 | @shane.myers@penske.com , Could you please review this app at https://bitbucket.penske.com/projects/ARPROJ/repos/shoptalkreg-web/pull-requests/4/overview | Gayam | 03/07/23 6:35 AM
Row 184 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:31 AM
Row 184 | @shane.myers@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 3:46 AM
Row 185 | Review: @kenneth.french@penske.com , This app is ready for your review. Please verify andmerge. https://bitbucket.penske.com/projects/EBS/repos/shorturlservice/pull-requests/5/overview | Gayam | 10/11/23 2:37 AM
Row 185 | @praneeth.gayam@penske.com these are false positives, please proceed with the modernization | Kenneth | 09/15/23 8:06 PM
| Thanks @kenneth.french@penske.com . Pushing the app to next step. | Gayam | 09/16/23 12:10 AM
Row 185 | Secrets: @kenneth.french@penske.com / @sree.gopal@penske.com / @frank.d'angelo@penske.com , I have sent the secrets of this app in the email. Could you please verify and let us know whether it requires any code changes to mitigate the secrets. Thanks. | Gayam | 09/14/23 1:59 AM
Row 185 | Sounds good, just want to get ahead of any development we may need to do for git leaks. thanks | Gianfranco | 08/30/23 3:45 AM
Row 185 | @praneeth.gayam@penske.com , this is the 2nd app in the Not Started bucket. Can we get these into Cap Analysis and start to do the scans? | Gianfranco | 08/29/23 6:17 PM
| @frank.d'angelo@penske.com , My team already started analyzing. But completing the modernization may takes some times as team is busy with lot of apps. | Gayam | 08/30/23 2:33 AM
Row 186 | Per Rafiq on 11/18/22 - Obsolete. There are other sics war/batch active | Yvette Urso | 11/19/22 12:50 AM
Row 187 | Deployed app to PROD on 08/17/2023 | Sreekanth | 08/18/23 7:47 AM
| @sreekanth.kancharla@penske.com , Thanks for the update. | Gayam | 08/18/23 8:18 PM
Row 187 | Post reverting the dlink_filter changes, we've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD. | Sreekanth | 07/05/23 7:32 PM
Row 187 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD but waiting on dlink-filter.jar PROD deployment by Architect team. | Sreekanth | 06/08/23 11:24 PM
Row 187 | @praneeth.gayam@penske.com As per the naming convention, all the apps in bitbucket follow a standard and the same name being used in bamboo plan as well. If possible, please change the name from "sic" to "sics-web" for https://bamboo.penske.com/browse/SCSBP-SICSW | Sreekanth | 04/24/23 8:43 PM
| @sreekanth.kancharla@penske.com , we completed the change for all the apps. Please verify. Thanks. | Gayam | 04/27/23 2:13 AM
| @praneeth.gayam@penske.com Thank you for making the naming corrections as same as bitbucket repo name for both build & deploy plans. Started using new deploy plan. Please delete old deploy plan. | Sreekanth | 04/27/23 7:01 PM
| @praneeth.gayam@penske.com We've started using the new deploy plan and good to delete the old deploy plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=132710402 | Sreekanth | 05/03/23 8:00 PM
| @sreekanth.kancharla@penske.com , Not sure whether deleting the old plans part of Log4j project. But I will check and confirm. | Gayam | 05/04/23 12:17 AM
| @sreekanth.kancharla@penske.com , Deleted the old deploy plan. | Gayam | 05/08/23 10:13 PM
Row 187 | @praneeth.gayam@penske.com We started testing this application and had some issues with dlinkfilter. The issue was resolved with the help of @hugo.scavino@penske.com by removing unwanted dependency "dom.jar". Post that we are getting issue with sessionvalidationfilter which @hugo.scavino@penske.com will be working on common solution. Only then we can resume the testing. The pending sessionvalidationfilter change does applies for all the web applications to proceed with environment agnostic web.xml. @kalrav.khamar@penske.com | Sreekanth | 03/20/23 9:12 PM
| @praneeth.gayam@penske.com The latest dlinkfilter changes are working fine for this app in DEV server. Once we complete the application-level testing, we'll post update. Meanwhile we are waiting on confirmation from @hugo.scavino@penske.com to deploy the changes to QA for further testing. | Sreekanth | 04/06/23 11:59 PM
Row 187 | @praneeth.gayam@penske.com The PR is merged to develop. CC: @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 2:26 AM
| Thanks @sreekanth.kancharla@penske.com . Could you please confirm the secrets too. | Gayam | 01/26/23 8:19 PM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. Most of the files are jsp & js. The 2 files that has password as a word are CPMApplication.java & CPUReportServlet.java In both these files the code is commented and not used. You are good to proceed with next steps. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 12:33 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (Cap)Maven | Gayam | 01/27/23 2:45 AM
| @sreekanth.kancharla@penske.com , There is a small change in the artifactid. So we changed and created the PR. Could you please merge. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/sics-web/pull-requests/5/overview | Gayam | 02/02/23 11:57 PM
| Thanks @sreekanth.kancharla@penske.com for merging the code. Can we go for the next step which is build & deploy plans onboarding and Dev deployment? | Gayam | 02/03/23 12:12 AM
| @praneeth.gayam@penske.com Sure, please proceed with dev plan build & deployment. @kalrav.khamar@penske.com | Sreekanth | 02/03/23 2:15 AM
| @sreekanth.kancharla@penske.com , Dev deployment is completed for this application Could you please verify. Thanks. @haribabu.challa@penske.com | Gayam | 02/07/23 2:13 AM
| @praneeth.gayam@penske.com Dev deployment completed means, was that through Bamboo? Please share the bamboo plan as I couldn't find any new plan for SICS under existing project https://bamboo.penske.com/browse/SCSBP | Sreekanth | 02/15/23 3:06 AM
| @sreekanth.kancharla@penske.com Following is the Bamboo plan. https://bamboo.penske.com/browse/SCSBP-SICSW yes. It is deployed through Bamboo. | Gayam | 02/16/23 2:47 AM
| @praneeth.gayam@penske.com We'll wait till we get the access to Bamboo plans. Meanwhile we are getting below issue when we access the DEV application. Error: Error 500: javax.servlet.ServletException: Filter [CPUSessionValidationFilter]: com.penske.apps.sics.ui.CPUSessionValidationFilter was found, but is corrupt: URL: https://web3dev.penske.com/sics/entry/ApplicationEntry?LoginUserID=600123805 | Sreekanth | 02/18/23 12:05 AM
| @sreekanth.kancharla@penske.com , for sics.war RBAC roles are updated. Please check the access now. | Gayam | 02/18/23 12:37 AM
| @praneeth.gayam@penske.com I'm still unable to view the new plans in bamboo under https://bamboo.penske.com/browse/SCSBP | Sreekanth | 02/22/23 8:42 PM
| @sreekanth.kancharla@penske.com , Following thing mentioned by @kalrav.khamar@penske.com in the email. "PTL-Admin-Development = Can execute Build Plans Once we’ve BB-Admin role, we will add eligible developers to this role." Because of this no one added to above roles. I am expecting this is the issue. @haribabu.challa@penske.com / @balu.mohan@penske.com | Gayam | 02/23/23 3:19 AM
| @praneeth.gayam@penske.com My name is also available under BB-Admin role but still I'm unable to view the bamboo plan. If admin doesn't have the access, how can he/she provide access to developers. | Sreekanth | 02/23/23 3:32 AM
| @sreekanth.kancharla@penske.com , As discussed BB-Admin role is only bitbucket projects. We sent an email to respective person to add the provided users to the requested role. We will let you know once it is completed. | Gayam | 02/25/23 12:17 AM
| @praneeth.gayam@penske.com We got access to new bamboo plans but we are unable to add a "Plan branch". Please check and do the need. | Sreekanth | 03/13/23 10:14 PM
Row 187 | @kalrav.khamar@penske.com / @sreekanth.kancharla@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:57 AM
Row 187 | @rafiq.melath@penske.com / @sreekanth.kancharla@penske.com, This is a web application but when we check the targeted folder it contains jee-resources and batchconfig properties files for each environment. Usually these 2 files are exist for batch apps only. Could you please check and clarify us whether these are required or not. Also, there is a extra file sicsbatch.properties in targeted folder. Please check whether this file is required. Thanks. @mathumala.nachiappan@penske.com / @hugo.scavino@penske.com | Gayam | 12/17/22 2:05 AM
| @praneeth.gayam@penske.com All the 3 files jee-resources, batchconfig properties, sicsbatch.properties are not required. CC: @kalrav.khamar@penske.com @rafiq.melath@penske.com | Sreekanth | 12/22/22 12:12 AM
| Thanks @sreekanth.kancharla@penske.com . We will make the changes accordingly. @mathumala.nachiappan@penske.com | Gayam | 12/22/22 3:04 AM
Row 187 | @mathumala.nachiappan@penske.com Moved to CAP Bitbucket status - Did you create a Footprints ticket for the Bitbucket Team (plus @hugo.scavino@penske.com ) | Yvette Urso | 12/15/22 2:17 AM
| @yvette.urso@penske.com - CAP is able to rectify this issue and this is in Maven stage now.. So moving to (Cap) Maven. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/15/22 10:14 AM
Row 187 | facing SVN to BB migration issue @kalrav.khamar@penske.com . Looking forward to discuss with Architecture team regd. permission issues from SVN or BB. Planned for Monday. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:45 PM
Row 188 | Deployed app to PROD on 08/17/2023 | Sreekanth | 08/18/23 7:47 AM
| @sreekanth.kancharla@penske.com , Thanks for the update. | Gayam | 08/18/23 8:18 PM
Row 188 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD. | Sreekanth | 07/05/23 7:32 PM
Row 188 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD but waiting on dlink-filter.jar PROD deployment by Architect team. | Sreekanth | 06/08/23 11:24 PM
Row 188 | @praneeth.gayam@penske.com As per the naming convention, all the apps in bitbucket follow a standard and the same name being used in bamboo plan as well. If possible, please change the name from "sicsbatch" to "sics-batch" for https://bamboo.penske.com/browse/SCSBP-SICSB | Sreekanth | 04/24/23 8:42 PM
| Sure @sreekanth.kancharla@penske.com , We will check and get back to you. | Gayam | 04/25/23 1:17 AM
| @praneeth.gayam@penske.com I do see the changes made in bamboo plans. Thank you. Appreciate if you could make similar changes to deploy plans as well for all 3 SICS apps. | Sreekanth | 04/25/23 6:17 PM
| Sure @sreekanth.kancharla@penske.com . We are in the process of doing all the changes. | Gayam | 04/26/23 1:21 AM
| @sreekanth.kancharla@penske.com , we completed the change for all the apps. Please verify. Thanks. | Gayam | 04/27/23 2:14 AM
| @praneeth.gayam@penske.com Thank you for making the naming corrections as same as bitbucket repo name for both build & deploy plans. Started using new deploy plan. Please delete old deploy plan. | Sreekanth | 04/27/23 7:01 PM
| @praneeth.gayam@penske.com We've started using the new deploy plan and good to delete the old deploy plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=132710401 | Sreekanth | 05/03/23 8:03 PM
| @sreekanth.kancharla@penske.com , Deleted the old deploy plan. | Gayam | 05/08/23 10:14 PM
Row 188 | @praneeth.gayam@penske.com This application is deployed in QA and verified the logs. The logs are printing fine. We'll continue the integration testing of SICS Web, Service & Batch apps and post update. @kalrav.khamar@penske.com | Sreekanth | 04/07/23 12:00 AM
Row 188 | @sreekanth.kancharla@penske.com , As the PR merged we onboarded this application to bamboo. Following is the URL. https://bamboo.penske.com/browse/SCSBP-SICSB Please run the 'develop' branch to onboard the deploy plan. We can't onboard the deploy plan because if we onboard it automatically deploys it to QA as this is the batch app there is no Dev environment. As per Hugo, Log4j team can't deploy to QA. Thanks. | Gayam | 02/04/23 12:44 AM
| @praneeth.gayam@penske.com Thank you. We can't deploy the application to QA. Since no DEV environment for batch app, we need to test the changes in local first. @kalrav.khamar@penske.com | Sreekanth | 02/04/23 3:48 AM
| Sure @sreekanth.kancharla@penske.com . Changed the status to (AO)Bamboo Review. We will wait for your confirmation. | Gayam | 02/07/23 12:01 AM
| @praneeth.gayam@penske.com We've no access to bamboo plan. Please grant the access. | Sreekanth | 02/15/23 3:11 AM
| @sreekanth.kancharla@penske.com , We sent an email to AO Manager and other team to get the details about whom we need to add different Admin RBAC groups. Devops team decided that they are not going to provide the individual accesses. So could you please respond to that email. Once we add the team members to different RBAC groups, depends on the permissions members will see the build plans. | Gayam | 02/15/23 7:02 AM
| @praneeth.gayam@penske.com Please provided access to have Add Plan branch option on all the new bamboo plans. We don't have access to the plans created as part of this log4j migration. For any other new apps, we are getting the access to add the Plan branch by default. Please check with Architect team on this and do the need. | Sreekanth | 03/16/23 12:57 AM
| There is a discussion going on this in the email. | Gayam | 03/17/23 3:00 AM
Row 188 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:58 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. Most of the files are mybatis files. We are good to proceed with next steps. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 12:35 AM
Row 188 | @praneeth.gayam@penske.com - Changing the status to (AO) Maven as the PR is raised | Mathumala Nachiappan | 12/19/22 8:23 PM
| @praneeth.gayam@penske.com The PR is merged to develop. CC: @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 2:27 AM
| Thanks @sreekanth.kancharla@penske.com . Could you please check the secrets and confirm. | Gayam | 01/26/23 8:11 PM
Row 188 | @rafiq.melath@penske.com / @kalrav.khamar@penske.com , Log4j and maven changes are completed by log4j team. Could you please review the below PR and merge. https://bitbucket.penske.com/projects/ITFIS/repos/sics-batch/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/16/22 3:11 AM
Row 189 | Deployed app to PROD on 08/17/2023 | Sreekanth | 08/18/23 7:47 AM
| @sreekanth.kancharla@penske.com , Thanks for the update. | Gayam | 08/18/23 8:18 PM
Row 189 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD. | Sreekanth | 07/05/23 7:32 PM
Row 189 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD but waiting on dlink-filter.jar PROD deployment by Architect team. | Sreekanth | 06/08/23 11:24 PM
Row 189 | @praneeth.gayam@penske.com As per the naming convention, all the apps in bitbucket follow a standard and the same name being used in bamboo plan as well. If possible, please change the name from "sicssvc" to "sics-service" for https://bamboo.penske.com/browse/SCSBP-SICSSVCP | Sreekanth | 04/24/23 8:43 PM
| @sreekanth.kancharla@penske.com , we completed the change for all the apps. Please verify. Thanks. | Gayam | 04/27/23 2:14 AM
| @praneeth.gayam@penske.com Thank you for making the naming corrections as same as bitbucket repo name for both build & deploy plans. Started using new deploy plan. Please delete old deploy plan. | Sreekanth | 04/27/23 7:01 PM
| @praneeth.gayam@penske.com We've started using the new deploy plan and good to delete the old deploy plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=129728520 | Sreekanth | 05/03/23 7:59 PM
| @sreekanth.kancharla@penske.com , Deleted the old deploy plan. | Gayam | 05/08/23 10:14 PM
Row 189 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:58 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 12:36 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (AO)Maven as MR is already created and provided in above comment. | Gayam | 01/27/23 2:47 AM
| @praneeth.gayam@penske.com The MR is merged and good to proceed with next steps. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 7:43 PM
| Thanks @sreekanth.kancharla@penske.com . We will onboard to Bamboo and will deploy to dev. Please confirm whether you are ok for the Dev deployment. @mathumala.nachiappan@penske.com | Gayam | 01/27/23 8:01 PM
| @praneeth.gayam@penske.com We should be good with the Dev deployment of this application. Please share the Bamboo plan details once it is available. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 8:11 PM
| @sreekanth.kancharla@penske.com , Dev deployment is completed. Following is the Bamboo URL. https://bamboo.penske.com/browse/SCSBP-SICSSVCP Please validate dev. Thanks. | Gayam | 02/04/23 12:36 AM
| @praneeth.gayam@penske.com Seems we need to access to the new bamboo plans. Please grant the access. | Sreekanth | 02/04/23 3:49 AM
| @sreekanth.kancharla@penske.com , You need to be added to one of the admin RBAC group. I sent an email to admin group few days back whom to be added to the different groups. Waiting fthe response. | Gayam | 02/06/23 11:49 PM
Row 189 | @rafiq.melath@penske.com / @kalrav.khamar@penske.com , Log4j team completed log4j and maven changes. Could you please review them in below PR and merge. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/sics-service/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/17/22 3:05 AM
Row 190 | Review: @shawn.mcmurtry@penske.com , This app is ready for your review. Pelase check and merge. https://bitbucket.penske.com/projects/MAIN/repos/smsbatch/pull-requests/3/overview | Gayam | 10/13/23 8:48 AM
Row 190 | Secrets: @shawn.mcmurtry@penske.com , I have sent the secrets of this app in the email. Could you please check the file and let us know whether this app requires any code changes to mitigate the secrets. | Gayam | 09/14/23 1:45 AM
| Thanks @shawn.mcmurtry@penske.com . As you updated in the email, there are no coding changes required for the secrets. Pushing the status to Cap Maven. | Gayam | 09/26/23 12:48 AM
Row 190 | @praneeth.gayam@penske.com path is correct: tags/_T_PROD_20210510 . smsserviceutility.jar is part of the smsservice repo. Once the smsservice is modernized that should include the smsserviceutility.jar | Shawn | 08/10/23 8:24 PM
| Thanks @shawn.mcmurtry@penske.com. Looks like smsserviceutility is used in multiple applications. So it should be created as a separate jar and needs to be uploaded into artifactory. We will extract smsserviceutility to a separate repo and will modernize and create a separate bamboo plan to upload to artifactory. Thanks. | Gayam | 08/11/23 12:15 AM
Row 190 | @shawn.mcmurtry@penske.com / @dave.kost@penske.com , For this app's bamboo prod build mentioned build branch name is differed with branch path. Following are the details. Could you please confirm whether the path is correct. Svn url:https://svn.penske.com/svn/architecture/general/sms-batch/ Branch name: _T_PROD_20131104 Branch Path: tags/_T_PROD_20210510 (latest commit done by shane) This app also dependent on smsserviceutility.jar. Do we need to modernize this jar? Following are the details of this dependency jar. bamboo:https://bamboo.penske.com/chain/admin/config/editChainRepository.action?buildKey=SMSBATCHBP-UTILPROD Svn url:https://svn.penske.com/svn/architecture/general/sms-service/ branch path:tags/_T_PROD_20210510 | Gayam | 07/31/23 3:15 AM
Row 191 | Secrets: @shawn.mcmurtry@penske.com , I have sent the secrets of this app in the email. Could you please check the file and let us know whether this app requires any code changes to mitigate the secrets. | Gayam | 09/14/23 1:45 AM
| Thanks @shawn.mcmurtry@penske.com . As you updated in the email, there are no coding changes required for the secrets. Pushing the status to Cap Maven. | Gayam | 09/26/23 12:48 AM
Row 191 | @praneeth.gayam@penske.com Path is correct: tags/_T_PROD_20210510 | Shawn | 08/10/23 8:19 PM
| Thanks @shawn.mcmurtry@penske.com | Gayam | 08/10/23 11:49 PM
Row 191 | @shawn.mcmurtry@penske.com / @dave.kost@penske.com , For this app's bamboo prod build mentioned build branch name is differed with branch path. Following are the details. Could you please confirm whether the path is correct. SVN url: https://svn.penske.com/svn/architecture/general/sms-service/ Branch name:_T_PROD_20131112 Branch Path: tags/_T_PROD_20210510 | Gayam | 07/31/23 3:17 AM
Row 192 | @praneeth.gayam@penske.com PR has been reviewed and merged. | Shawn | 09/05/23 9:10 PM
| Thanks @shawn.mcmurtry@penske.com . we will onboard to bamboo and deploy to artifactory. | Gayam | 09/06/23 12:58 AM
| @shawn.mcmurtry@penske.com , smsserviceutility is successfully uploaded in artifactory through bamboo. Maven dependency: <groupId>com.penske.maintenance</groupId> <artifactId>smsserviceutility</artifactId> <version>2.0.0-develop-20230906.072026-1</version> | Gayam | 09/07/23 12:48 AM
Row 192 | @shawn.mcmurtry@penske.com , Modernization completed and following is the PR. Please review and merge. https://bitbucket.penske.com/projects/MAIN/repos/smsserviceutility/pull-requests/2/overview | Gayam | 08/30/23 9:58 PM
Row 193 | Decision is to retire these applications | Yvette Urso | 05/01/23 9:17 PM
Row 193 | @scott.bortzel@penske.com / @scott.pemrick@penske.com , For this application both SVN and Bamboo are not available. Could you please let us know the SVN and Bamboo details. Thanks. | Gayam | 01/14/23 1:06 AM
| @scott.bortzel@penske.com / @scott.pemrick@penske.com , Could you please provide the response to above question. Thanks. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 03/24/23 10:51 PM
Row 194 | . | Sreenivasa | 10/16/23 8:57 PM
Row 194 | I verified in QA, will plan for prod deployment | Sreenivasa | 10/11/23 1:33 AM
Row 194 | changes looks good. we can deploy into QA and test | Sreenivasa | 09/25/23 8:41 PM
| Sure @sreenivasa.papannagari@penske.com | Gayam | 09/26/23 12:59 AM
| @sreenivasa.papannagari@penske.com , This app is deployed to QA. Please verify. | Gayam | 09/27/23 12:45 AM
Row 194 | @sreenivasa.papannagari@penske.com , Onboarded to bamboo and deployed to dev. Pelase check. https://bamboo.penske.com/browse/SOSSBP-SOSW1/deployments | Gayam | 09/22/23 12:09 AM
Row 194 | Reviewed and merged. | Sreenivasa | 09/20/23 12:00 AM
| Thanks @sreenivasa.papannagari@penske.com . We will onboard to Bamboo. | Gayam | 09/20/23 12:34 AM
Row 194 | looks good for me.. please go ahead with further steps | Sreenivasa | 09/16/23 1:42 AM
| @sreenivasa.papannagari@penske.com , We completed all the changes in develop_log4j branch. Can you merge the chagnes to develop branch. https://bitbucket.penske.com/projects/MAIN/repos/sos-web/pull-requests/3/overview So that we can onboard the develop branch to bamboo. Thanks | Gayam | 09/19/23 12:50 AM
Row 194 | reviewed and gave one comment ... please check and confirm | Sreenivasa | 09/14/23 8:36 PM
| Thanks @sreenivasa.papannagari@penske.com . We will check on this. | Gayam | 09/15/23 7:24 AM
| @sreenivasa.papannagari@penske.com , Narendra modified the configuration as recommended in confluence documentation. Please verify. Thanks | Gayam | 09/16/23 12:43 AM
Row 194 | @praneeth.gayam@penske.com , I made the changes to align with environment agnostic. Please review and approve the pull request- https://bitbucket.penske.com/projects/MAIN/repos/sos-web/pull-requests/4/overview | Sreenivasa | 08/25/23 5:25 PM
| @sreenivasa.papannagari@penske.com , I merged the code to develop_log4j branch. We continue the next set of work and will provide for your review. Thanks. | Gayam | 08/26/23 1:05 AM
| Review: @sreenivasa.papannagari@penske.com , Please review the total modernization changes in below PR. https://bitbucket.penske.com/projects/MAIN/repos/sos-web/pull-requests/3/overview | Gayam | 09/13/23 11:09 PM
Row 194 | Working on code changes to align with environment agnostic. will update you by this Wednesday. | Sreenivasa | 08/21/23 7:32 PM
Row 194 | Query: @sreenivasa.papannagari@penske.com , In this application build folder having sos_specificbuild.xml. The build is including dispatcher-servlet.xml on environment basis. how to implement this in environment agnostic build as we don't have separate builds for each environment. | Gayam | 07/25/23 12:06 AM
Row 194 | @shawn.mcmurtry@penske.com , This app depends on the sosutility.jar . Sosutility having the svn repo . Can we continue to migrate sosutility also ? https://svn.penske.com/svn/fieldsys/other/sos-service/tags/prod/2023-05-04/SosUtility/ There are other apps soservice.war and 24*7custnotify also depend on Sosutility jar. | Gayam | 05/18/23 10:57 PM
| @david.long@penske.com confirmed to create a separate repo and Bamboo plan for sosutility. We will take up this app for migration once Sosutiloity work completed. Thanks. | Gayam | 06/12/23 7:42 AM
Row 194 | I have validated the secretes , looks good for me ... except these 3 build_script/prod.properties build_script/dev.properties build_script/qa.properties. Remaining all are not secrets. | Sreenivasa | 06/09/23 7:30 PM
| Thanks @sreenivasa.papannagari@penske.com . We will remove build_script folder while doing the mavanization. | Gayam | 06/12/23 7:37 AM
Row 194 | Secrets: @shawn.mcmurtry@penske.com , adding to above question, I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:53 AM
Row 195 | yes I am able to see logs in local | Sreenivasa | 10/17/23 6:37 PM
Row 195 | application is not up in DEV, even I don't see any logs in the dev. | Sreenivasa | 10/11/23 1:57 AM
| @praneeth.gayam@penske.com - tagging you to make sure you saw Sreeni's response. | Patel | 10/11/23 2:02 AM
| @sreenivasa.papannagari@penske.com / @falgun.patel@penske.com , We will check whether anything missed in the modernization process. Also, @sreenivasa.papannagari@penske.com is this app genrated logs in local? | Gayam | 10/12/23 7:13 AM
Row 195 | @praneeth.gayam@penske.com - just making sure you received the confirmation from @sreenivasa.papannagari@penske.com to move forward. | Patel | 10/06/23 6:30 PM
| @sreenivasa.papannagari@penske.com / @falgun.patel@penske.com , Dev deployment is completed. Please verify. Thanks. | Gayam | 10/10/23 12:08 AM
Row 195 | looking good .. please proceed with next steps | Sreenivasa | 10/04/23 7:31 PM
Row 195 | changes looks good, please go ahead with further steps | Sreenivasa | 09/27/23 7:00 PM
| Sure @sreenivasa.papannagari@penske.com | Gayam | 09/28/23 12:45 AM
| @sreenivasa.papannagari@penske.com , Onboarded develop_log4j branch to bamboo - https://bamboo.penske.com/browse/SOSP-SOSPCW1/ Please check. | Gayam | 10/03/23 1:38 AM
Row 195 | Please make log4j changes as like sos.war | Sreenivasa | 09/16/23 1:49 AM
| Sure @sreenivasa.papannagari@penske.com | Gayam | 09/19/23 12:51 AM
| @sreenivasa.papannagari@penske.com , Changes are completed. Pelase verify the PR. | Gayam | 09/21/23 12:54 AM
Row 195 | yes all changes completed .. please go ahead with further steps | Sreenivasa | 09/09/23 1:18 AM
| Sure @sreenivasa.papannagari@penske.com | Gayam | 09/11/23 10:31 PM
| Review: @sreenivasa.papannagari@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/MAIN/repos/sospcard-web/pull-requests/4/overview | Gayam | 09/15/23 7:38 AM
Row 195 | Hi Praneeth, I made the changes to align with environment agnostic and created a pull request to your branch - https://bitbucket.penske.com/projects/MAIN/repos/sospcard-web/pull-requests/2/overview. Please review and merge the changes | Sreenivasa | 09/08/23 7:12 PM
| Thanks @sreenivasa.papannagari@penske.com . Are your changes completed? If yes, we will take it forward. | Gayam | 09/09/23 12:36 AM
Row 195 | Need to do code changes, will update you on this by Friday. | Sreenivasa | 08/21/23 7:43 PM
Row 195 | Query: @sreenivasa.papannagari@penske.com / @stella.george@penske.com , We have following queries in this application. 1.Targeted folder contains different sosProperties.properties files for different environments. These properties are referred in web.xml and InitializationServlet. The main difference is upload path Production UploadPath = \\GRNHILLS/ROOT/applications/pcard/ Qa UploadPath = \\QAGH/ROOT/applications/pcard/) 2.Targeted folder contains different web.xml files for different environments. In environment agnostic build there will be no separate builds for each environment. But it seems above files are environement specific. Could you please check and resolve this issue. Thanks. | Gayam | 07/25/23 12:16 AM
Row 195 | Verified the secrets, I don't see any PI data hardcoded in the code.. most of them are getting from back end(DB). So we should be ok with it. | Sreenivasa | 06/15/23 10:56 PM
| Thank you. | Gayam | 06/16/23 1:13 AM
Row 195 | @stella.george@penske.com / @sreenivasa.papannagari@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:52 AM
Row 196 | Still working on deploying this. A release was created and pushed to PROD, but it failed. Currently working with Architect team to figure out what issue is happening | David | 10/09/23 11:20 PM
Row 196 | @david.long@penske.com , This app is ready for review. Please check and merge the PR. https://bitbucket.penske.com/projects/MAIN/repos/sosservice/pull-requests/3/overview | Gayam | 08/08/23 11:25 PM
| @praneeth.gayam@penske.com Reviewed and merged :) | David | 08/15/23 6:18 PM
| Thanks @david.long@penske.com . Onboarding to bamboo. | Gayam | 08/17/23 1:39 AM
| @david.long@penske.com Bamboo onboarding completed. Please check https://bamboo.penske.com/browse/SOSSBP-SOSSW0. | Gayam | 08/18/23 12:18 AM
| @praneeth.gayam@penske.com the build and deploy looks to be working but I can't validate until tomorrow. the dev wsv instance is currently down and I can't test the build just yet. | David | 08/18/23 2:18 AM
| @praneeth.gayam@penske.com validated that I'm able to get a response from Dev now. Deploying to QA and will check tomorrow | David | 08/18/23 2:31 AM
| @david.long@penske.com , Thanks for the update. | Gayam | 08/18/23 8:22 PM
| @praneeth.gayam@penske.com I was able to confirm that it is logging and is working on QA | David | 08/23/23 8:38 PM
| Thanks @david.long@penske.com | Gayam | 08/24/23 3:46 AM
Row 196 | Responded to the email! THanks! | David | 07/18/23 2:19 AM
| Thanks @david.long@penske.com | Gayam | 07/18/23 9:56 PM
Row 196 | Secrets: @david.long@penske.com , @falgun.patel@penske.com , I sent the secrets file of this app in an email. Please check and confirm. Thank you. | Gayam | 07/18/23 1:29 AM
Row 196 | @praneeth.gayam@penske.com Yes please create a separate repo and bamboo plan for sos utility. I believe this also addresses some other wars that were pending this question. | David | 06/09/23 6:20 PM
| Sure @david.long@penske.com . I will request @yvette.urso@penske.com to create new line item in smartsheet for sosutility jar. Thanks. | Gayam | 06/10/23 1:49 AM
Row 196 | @shawn.mcmurtry@penske.com , In this application prod reference in Bamboo is having 2 folder sos-service and sos-utility folders. Expecting sos-utility is a dependency jar and sos-service is the orginal application. Following are the 2 folders. Could you please check and confirm whether our expectation is correct or not. https://svn.penske.com/svn/fieldsys/other/sos-service/tags/prod/2023-05-04/sos-service/ https://svn.penske.com/svn/fieldsys/other/sos-service/tags/prod/2023-05-04/SosUtility/ | Gayam | 05/10/23 11:15 PM
| @praneeth.gayam@penske.com That is correct. sos-service is the original application, and the sos-utility is a dependency jar containing objects for sos service. | David | 06/06/23 10:09 PM
| Thanks @david.long@penske.com for the response. Not only sosservice but also 24x7custnotif, sos.war apps are depend on SosUtility jar. Can we extract SosUtility and create separate repo and bamboo plan? | Gayam | 06/07/23 3:33 AM
| Yes, but I would investigate the nature of the sos utility jar first among the other apps. I checked the 24x7 cust notif batch and the only place it uses the sosUtility jar is to call the spring remoting method: getRoadReportPDF. The batch does not make use of any objects from the utility. So, if the getRoadReportPDF was updated to a restful method in sos service, the batch would only need to call the restful service and we would be able to remove the sos utility jar as a dependency for the 24x7 cust notif batch | David | 06/07/23 4:49 AM
| Sure @david.long@penske.com . Let us know whether we need to create a separate repo and bamboo plan for sosutility. | Gayam | 06/08/23 7:55 AM
Row 197 | Just to not it's not DONE as in deployed to PROD, but DONE as in it's working and now Penske needs to promote to PROD. Thanks, | David | 08/25/23 12:36 AM
Row 197 | @praneeth.gayam@penske.com I found the Bitbucket build, but I don't have access to it, so I'm getting access and then will confirm that it's up on artifactory | David | 07/11/23 1:31 AM
| @david.long@penske.com , We referred a different source repo for this app. We are reworking on this app as each application's prod reference have different sosutility folders. Trying to compare all these and we will ask the question if there are any differences. Thanks. Changing the status of the app to Cap. | Gayam | 07/11/23 6:53 AM
| Thanks for the update @praneeth.gayam@penske.com Keep me posted if there are any questions | David | 07/11/23 7:30 PM
| @david.long@penske.com , All the changes are completed and deployed to artifactory. Following is the bamboo build. https://bamboo.penske.com/chain/viewChain.action?planKey=SOSSBP-SOSUTIL | Gayam | 07/13/23 2:12 AM
| Hey @praneeth.gayam@penske.com my apologies for the big delay. I am still unable to view the plan and I need to contact qa team in order to give me access. no update on this at this time. | David | 08/15/23 6:11 PM
| @david.long@penske.com , as per configuration you should see view and build. | Gayam | 08/17/23 1:37 AM
| @praneeth.gayam@penske.com Hey there! I was able to validate that the build is working and deploying to artifactory | David | 08/23/23 8:34 PM
| @david.long@penske.com , Thank you. Can i change the status to Done as this is just a dependency jar and not going to be deployed into production. | Gayam | 08/24/23 3:45 AM
| @praneeth.gayam@penske.com yes you can mark as Done | David | 08/24/23 6:54 PM
Row 197 | @david.long@penske.com , This is onboarded to Bamboo and deployed to artifactory. Please check and confirm. Thanks. | Gayam | 07/07/23 1:34 AM
| Sorry for the delay. What's the bamboo build URL? I can't seem to find it @praneeth.gayam@penske.com | David | 07/11/23 1:26 AM
Row 197 | Review: @david.long@penske.com / @falgun.patel@penske.com , This app is ready for your review. Please check and merge. https://bitbucket.penske.com/projects/MAIN/repos/sosutility/pull-requests/2/overview | Gayam | 06/28/23 2:53 AM
| @praneeth.gayam@penske.com I reviewed the PR and merged it into the develop branch! Thanks! | David | 07/04/23 2:51 AM
| Thanks @david.long@penske.com . We will onboard to bamboo and let you know. | Gayam | 07/06/23 3:10 AM
Row 197 | No secrets found on this jar. So changing the status to Cap Maven | Gayam | 06/23/23 12:16 AM
Row 197 | Hi Yvette, I wanted to bring to your attention that the shared jar "sosutility" requires a new repository and a bamboo build. This jar is utlized by three Maintenance apps: 24x7custnotif, sosservice and sos.war. David has confirmed the need to create a separate repository and Bamboo build for "sosutility" and it also requires to implement all modernization steps. Therefore I kindly request you to include a new line item "sosutility" in the smartsheet. Thanks, Praneeth | Yvette Urso | 06/12/23 9:11 PM
Row 198 | Review: @sarath.mani@penske.com , This application ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/spellingservice/pull-requests/3/overview | Gayam | 10/18/23 8:16 AM
Row 198 | they are false positives and no code change is required, please proceed. | Vaddi Mani | 07/31/23 8:39 PM
| Thank you | Gayam | 08/01/23 12:36 AM
Row 198 | Secrets: @dale.porter@penske.com / @sarath.mani@penske.com , I sent secrets file in an email. Please verify. Thanks. | Gayam | 07/21/23 10:48 PM
Row 198 | I checked the last production build and see it was part of that release. Yes, it needs to be modernized as well Thank you. | Dale Porter | 06/24/23 1:01 AM
| Thanks @dale.porter@penske.com . | Gayam | 06/27/23 3:43 AM
Row 198 | @stella.george@penske.com / @dale.porter@penske.com , This application having multiple src folders . We are expecting that Penske-spelling-service folder is the original source which builts spellingservice.war and other folder(Penske_Spelling_Utility) is the dependency jar. SVN Location: https://svn.penske.com/svn/fieldsys/maintenance/Penske-Spelling-Service/tags/prod/prod_2012-08-14/ penske_spellingutility jar build plan: https://bamboo.penske.com/browse/PNSKESPLNGBP-PNSKESPLINGUTLYPROD spellingservice.war application bamboo : -https://bamboo.penske.com/browse/PNSKESPLNGBP-PNSKESPLINGSVCPROD Following are the 2 suggestions. 1. Build a new repo for penske_spellingutility folder and mavanize and create a new bamboo plan which builds the jar and uploads to artifactory. Then spellingservice.war application uses that jar as a dependency in pom. 2. If penske_spellingutility folder is not a shared jar then AO can include that folder inside the spellingservice.war application. Then no need of separate repo and bamboo plan for the penske_spellingutility . Please verify and confirm. Thanks. @shane.myers@penske.com | Gayam | 06/03/23 12:35 AM
| @praneeth.gayam@penske.com Pensk_spellingutility is a shared jar. you should go with option1 | Stella george | 06/14/23 2:01 AM
| Thanks @stella.george@penske.com . We are also seeing another folder Penske_Spelling_ClientJar and the bamboo build for this is https://bamboo.penske.com/browse/PNSKESPLNGBP-PNSKESPLINGPROD Is this dependency also needs to modernized? | Gayam | 06/21/23 2:23 AM
Row 199 | @praneeth.gayam@penske.com , we have confirmed that SSO Service is not used. We are going to mark it for retirement | Gianfranco | 08/28/23 9:47 PM
Row 199 | @praneeth.gayam@penske.com , we are not seeing any usage. We are going to turn this off in QA and see if there is any impact to applications. We will keep this as Waiting on AO, but we may be retiring this application. | Gianfranco | 08/23/23 2:07 AM
| @frank.d'angelo@penske.com , thanks for the update. | Gayam | 08/23/23 8:06 AM
Row 199 | @praneeth.gayam@penske.com NEEDS RESEARCH - Multiple configuration files (for each env) a lot of our applications use this approach. I will need to check, but maybe architecture has a solution for this as this style of setup is used by many Penske apps. Is the expectation that the Penske team needs to remediate existing builds that are not environment agnostic? | Gianfranco | 08/14/23 11:39 PM
| @frank.d'angelo@penske.com , Cap Log4j team will create a new bamboo build and deploy plan. But to go that step, application needs to be written in a way that one build version can be deployed to all environments. | Gayam | 08/14/23 11:48 PM
Row 199 | @jeremiah.ashway@penske.com / @frank.d'angelo@penske.com , This application's resources folder has different xml files for each environment and virtual-host name variable is different in prod, qa ibm-web-bnd.xml files. As modernization involves environment agnostic build which means 1 build needs to be deployed to different environments. In this case, we can't use different xml files for diff environments. Could you please check how to resolve this issue. Thanks. | Gayam | 08/01/23 1:08 AM
Row 200 | @nicolas.hernandez@penske.com , There is a small update in log4j2.xml. Please check and merge the PR. Thanks. https://bitbucket.penske.com/projects/PBTFUEL/repos/ssptktportal-web/pull-requests/13/overview | Gayam | 10/10/23 1:08 AM
Row 200 | issue with code delivered after mavernizing. waiting on architect team to troubleshoot. | Rafiq Melath | 08/15/23 11:46 PM
Row 200 | @praneeth.gayam@penske.com There's an issue with the reuse jar or another dependencies when trying to access the dev application. I Have sent you some screens. | Hernandez | 08/15/23 1:13 AM
| @nicolas.hernandez@penske.com , We can't resolve the application specific run time issues as we don't have any idea about the application. Please let us know whether the application is missing any dependency. Usually, app will throw compilation issues if it misses any required dependencies. Thanks | Gayam | 08/15/23 2:13 AM
Row 200 | @praneeth.gayam@penske.com SSPTKTPORTAL seems to have some misconfiguration when running in DEV server and LOCAL. Could you verify? | Hernandez | 08/14/23 10:38 PM
| @nicolas.hernandez@penske.com , Could you please elaborate the issue. We are seeing the deployment in successful in bamboo. | Gayam | 08/15/23 1:03 AM
Row 200 | @praneeth.gayam@penske.com Can you please deploy suspended ticket portal on Dev | Venkatesh | 08/03/23 2:53 AM
| @venkatesh.hossalinever@penske.com , looks like dev deployment is completed yesterday. Please check. https://bamboo.penske.com/browse/SUSP-SSPT0/deployments | Gayam | 08/04/23 12:57 AM
Row 200 | Web Dev looking good with Log4j & Maven changes. We will proceed with QA deployment and keep you posted. | Nayum | 07/19/23 6:47 PM
Row 200 | @praneeth.gayam@penske.com @venkatesh.hossalinever@penske.com Retrofitted Recent PBT-567 (deployed) Changes to Develop_Log4J branch. I've submitted a pull request to push to develop branch. | Hernandez | 07/10/23 11:45 PM
| @nicolas.hernandez@penske.com , I believe changes are application specific and not related to modernization project. Do you want to deploy your changes and modernization changes to prod together? If yes, please review with your peer. Thanks. | Gayam | 07/11/23 11:37 PM
| @praneeth.gayam@penske.com Yes, we are intending to push the changes from PBT-567 with the modernization changes. | Hernandez | 07/13/23 1:44 AM
| Sure @nicolas.hernandez@penske.com . Please work with your team and merge the PR. | Gayam | 07/13/23 3:07 AM
Row 200 | @shilpaashok.rane@penske.com , Build plan and deploy plan of this app onboarded successfully. Also, deployment to dev is completed. Pelase verify. Thanks. | Gayam | 06/13/23 2:09 AM
Row 200 | Review: @shilpaashok.rane@penske.com This app is ready for AO review. Please check at https://bitbucket.penske.com/projects/ARPROJ/repos/ssptktportal-web/pull-requests/3/overview Thanks. | Gayam | 04/25/23 1:07 AM
| @praneeth.gayam@penske.com Code changes has been merged. Please deploy the application on dev. | Venkatesh | 06/08/23 8:02 PM
| We will onboard to Bamboo and will let you know. | Gayam | 06/09/23 1:38 AM
Row 200 | We have verified the secrets shared in the email, some are key events in jsp and js files. Some of the values used in UI. And they are not secret or confidential info. So no change required. | Rane | 04/10/23 6:06 PM
| Thanks @shilpaashok.rane@penske.com . We will work on the next step. | Gayam | 04/11/23 8:39 AM
Row 200 | Secrets: @dylan.price@penske.com / @william.spohn@penske.com , I have shared the secrets in the email. Please check and confirm. | Gayam | 03/24/23 12:05 AM
Row 200 | the bamboo build for this is https://bamboo.penske.com/browse/SUSP-SUSPPROD and the repo is https://svn.penske.com/svn/webprojects/admin/suspendedticketsportal/trunk/STP_Web | Dylan | 03/07/23 2:05 AM
| Thank you. Changed the app status to Cap Log4j | Gayam | 03/08/23 12:06 AM
Row 200 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 200 | Moved to AO Bamboo status | Yvette Urso | 12/15/22 2:49 AM
Row 200 | Hi @sam.skelding@penske.com - we couldnt trace the Bamboo key and the Repo url for this applicaiton. Pls. share those details. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 12:01 PM
Row 201 | We have prepared documents to deploy this on 08/03/2023 | Dylan | 08/02/23 7:10 PM
| Thanks @dylan.price@penske.com . Please let me know once it is deployed. i will change the status to Done. | Gayam | 08/03/23 12:42 AM
Row 201 | Hi @praneeth.gayam@penske.com Nicolas will be deploying his changes for StopBilling with Maven/log4j2. There is no other work for Capgemini team that needs completed. Thank you! | Dylan | 07/10/23 8:22 PM
Row 201 | @praneeth.gayam@penske.com I pushed my changes to dev. everything in develop looks good on my end. Are you able to build develop? | Hernandez | 05/22/23 6:43 PM
| @nicolas.hernandez@penske.com , Develop branch build is successful and it is deployed to dev environment. https://bamboo.penske.com/browse/STOPBILLINGBP-STOPBILL0/deployments Please verify in Dev. | Gayam | 05/22/23 10:03 PM
| @praneeth.gayam@penske.com I am not seeing the changes made from old log4j in dev. I made changes and merged to 'develop' branch. | Hernandez | 05/22/23 10:51 PM
| @nicolas.hernandez@penske.com , Could you please verify now. We changed the artifactid to stopbilling. Hope it works now. Thanks. | Gayam | 05/24/23 1:28 AM
| @praneeth.gayam@penske.com I've verified the changes are now on dev. Thank you. Is QA bamboo plan ready? | Hernandez | 05/24/23 2:17 AM
| @nicolas.hernandez@penske.com , QA deploy plan is already ready. | Gayam | 05/25/23 2:42 AM
Row 201 | @praneeth.gayam@penske.com , There are two changes I made to the XML file to get log4j2 running: 1. Added a <Loggers> tag and added <Root> tag inside (Error in console gone) 2. SMTP Apender syntax error (Error in console) Also noticed that log4j2 is creating a new log file after each mvn clean build. Is that happening on your end? We can setup a discussion for further details. I made code changes to the application to remove old log4j properties and configuration. Please Review | Hernandez | 05/18/23 6:54 PM
Row 201 | @praneeth.gayam@penske.com Thanks. Nicolas validated changes in his local and he is not able to see the logs getting generated in his local. Also on dev server the logs are not rolling when he tested the changes. Error from his local system: [5/15/23 15:13:25:015 EDT] 0000004f SystemOut O 2023-05-15 15:13:25,015 server.startup : 0 ERROR Unknown object "Root" of type org.apache.logging.log4j.core.config.LoggerConfig is ignored: try nesting it inside one of: ["Appenders", "Loggers", "Properties", "Scripts", "CustomLevels"]. [5/15/23 15:13:25:017 EDT] 0000004f SystemOut O 2023-05-15 15:13:25,016 server.startup : 0 WARN No Loggers were configured, using default. Is the Loggers element missing? | Venkatesh | 05/16/23 12:45 AM
| @venkatesh.hossalinever@penske.com , As discussed in the call, one of the log4j team member able to build the app successfully in local using billing settings. | Gayam | 05/18/23 1:02 AM
Row 201 | @praneeth.gayam@penske.com We will using ARPROJ repo. Please deploy develop_log4j changes on dev environment. | Venkatesh | 05/10/23 1:06 AM
| @venkatesh.hossalinever@penske.com We will do that and will let you know. | Gayam | 05/11/23 6:41 AM
| @venkatesh.hossalinever@penske.com , Onboarded develop_log4j to bamboo and deployed to Dev. Please verify https://bamboo.penske.com/browse/STOPBILLINGBP-STOPBILL1/deployments | Gayam | 05/11/23 11:23 PM
Row 201 | @venkatesh.hossalinever@penske.com / @mark.weaver@penske.com , We observed there is a new repo created for stopbilling recently. Following is the repo details. https://bitbucket.penske.com/projects/PBJB/repos/stopbilling-web/browse?at=refs%2Fheads%2Ffeature%2FPBT-141-Cancel-Code-Feature But we already create a repo for this application and mavanized. Repo which we created is https://bitbucket.penske.com/projects/ARPROJ/repos/stopbilling-web/browse?at=refs%2Fheads%2FDevelop_Log4j Do you know why there is a new repo created? | Gayam | 04/07/23 12:02 AM
Row 201 | Review: @venkatesh.hossalinever@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/stopbilling-web/pull-requests/3/overview | Gayam | 03/18/23 1:08 AM
Row 201 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 2:02 AM
| Thank you. Changed the status to Cap Maven | Gayam | 03/02/23 2:02 AM
Row 201 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 201 | @rafiq.melath@penske.com / @mark.weaver@penske.com , We completed the secrets scanning on this application and found that all are false positives. I will send the sheet to you in the email. Could you please check and confirm. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/10/23 12:39 AM
Row 202 | This application is no longer needed and no modernization effort is required on this. | Sherin | 04/21/23 12:09 AM
Row 202 | @sherin.basheer@penske.com , There are no secrets found in this app. So we completed log4j/maven work. Please review at https://bitbucket.penske.com/projects/ARPROJ/repos/synchghdbc-batch/pull-requests/3/overview | Gayam | 03/02/23 3:11 AM
Row 202 | production source code is decompiled and checked in to svn. Branch prod should be used for new changes. | Sherin | 02/18/23 12:42 AM
| Thanks @sherin.basheer@penske.com . Changing the status to (Cap)Log4j | Gayam | 02/18/23 1:03 AM
| @sherin.basheer@penske.com , As discussed in the chat, we are are making SqlMapClientCallback empty args and this.val$emplist will be replaced with emplist. Also, we will provide this info in Reamdeme file. Thanks. | Gayam | 02/22/23 3:20 AM
Row 202 | I will get back to you on the question on which branch to work on. | Sherin | 02/14/23 12:47 AM
Row 202 | This application can go under Architecture commons. https://bitbucket.penske.com/projects/ARPROJ. Bamboo plan should match application name. | Sherin | 02/14/23 12:44 AM
Row 202 | @sherin.basheer@penske.com , Unable to find bamboo build plans. Bamboo build plans required for prod reference. Following are the Svn and respective branches info. https://svn.penske.com/svn/architecture/general/synchghdbc/ dev_gh/ offshore_pol/ (This is the Latest branch. Last modifications done in May-6-2014 ) qa/ @mathumala.nachiappan@penske.com | Gayam | 11/26/22 1:59 AM
| @sherin.basheer@penske.com , Adding to above question, as there is no existing bamboo build, under which project we need to create new bamboo specs? | Gayam | 01/11/23 9:25 AM
| Yes application is very old and there is no bamboo plan existing for this. Please create new one. | Sherin | 02/01/23 12:53 AM
| Question: @sherin.basheer@penske.com , We have 2 questions on this application. 1. There is no old bamboo build. So we are not sure what is the latest branch deployed to production. Could you please let us know on what branch we need start working on modernization. 2. For the new build plans in Bamboo, do you want to create a new project. If so please suggest the name. Or do you want us to create under any other Arch project? If so, under which project we need to create? Thanks. @haribabu.challa@penske.com @mathumala.nachiappan@penske.com | Gayam | 02/02/23 11:15 PM
Row 202 | @mathumala.nachiappan@penske.com moved to AO Bamboo Review. | Yvette Urso | 12/15/22 2:38 AM
Row 203 | @ravi.daram@penske.com / @krishna.tanga@penske.com , We sent a secret file to you for this app and it looks like all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:41 PM
Row 204 | I'll be looking at this next. Hope to have an update soon. | David Graf | 02/09/23 12:01 AM
Row 204 | @praneeth.gayam@penske.com per @david.w.graf@penske.com - he will work on this when he returns to the office. Please keep status as is. | Yvette Urso | 01/24/23 8:20 PM
Row 204 | Moved to AO Code Work | Yvette Urso | 12/15/22 2:38 AM
Row 204 | I am hoping to work on this next week. | David Graf | 12/09/22 1:39 AM
Row 204 | @praneeth.gayam@penske.com @mathumala.nachiappan@penske.com Moved to Cap Blocked since Capgemini is blocked from moving forward, not the AO. | Yvette Urso | 12/01/22 8:42 PM
| yes @yvette.urso@penske.com . Thanks! | Mathumala Nachiappan | 12/02/22 5:50 PM
Row 204 | @david.w.graf@penske.com - Hope you progressed on this. Pls. share the present status | Mathumala Nachiappan | 11/30/22 3:17 PM
| I have not made progress since my last update. I'm working on a production deploy and will resume this after I am finished. | David Graf | 11/30/22 7:27 PM
Row 204 | I attempted to confirm the dev deploy but ran into an issue with the datasource. This is something that I need to work on from my end. | David Graf | 11/17/22 1:33 AM
Row 205 | This application has been retired. | William | 08/25/23 8:33 PM
Row 205 | @praneeth.gayam@penske.com it is already on boarded bambboo now is Faling build as well https://bamboo.penske.com/browse/TLMSBP-TLMS2-BLD-1 | Mahipal | 05/16/23 7:56 PM
| @mahipal.podduturi@penske.com , The PR is not yet merged. That is the reason it is failing. Please review and merge. https://bitbucket.penske.com/projects/ARPROJ/repos/telematicssvc-web/pull-requests/4/overview | Gayam | 05/17/23 2:10 AM
Row 205 | can you do | Mahipal | 05/16/23 7:48 PM
Row 205 | yes | Mahipal | 05/16/23 7:48 PM
Row 205 | @praneeth.gayam@penske.com can you mark this to complete | Mahipal | 05/04/23 7:13 PM
| @mahipal.podduturi@penske.com , Do you mean go to next step which is Bamboo onboarding? | Gayam | 05/05/23 6:15 AM
Row 205 | tested the application working as excepted. | Mahipal | 05/04/23 7:12 PM
Row 205 | @praneeth.gayam@penske.com can you deploy the devlop_log4j branch to dev | Mahipal | 04/03/23 10:02 PM
| @mahipal.podduturi@penske.com , telematicssvc.war - build & Deploy plan onboarding completed and dev deployment done from develop_log4j branch. Please verify. https://bamboo.penske.com/browse/TLMSBP-TLMS/deployments | Gayam | 04/04/23 11:19 PM
Row 205 | PR for this is https://bitbucket.penske.com/projects/ARPROJ/repos/telematicssvc-web/pull-requests/4/overview | Gayam | 04/03/23 9:41 PM
Row 205 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:31 AM
Row 205 | @shane.myers@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 3:50 AM
Row 206 | @sreekanth.kancharla@penske.com , Could you please merge the below PR. https://bitbucket.penske.com/projects/ITFIS/repos/tririga-integrations-batch/pull-requests/2/overview Then review the below PR. https://bitbucket.penske.com/projects/ITFIS/repos/tririga-integrations-batch/pull-requests/3/overview | Gayam | 07/13/23 8:53 AM
| @praneeth.gayam@penske.com Both PRs are merged. Please proceed with Bamboo plan configuration. | Sreekanth | 07/13/23 7:21 PM
| Sure @sreekanth.kancharla@penske.com . Thanks | Gayam | 07/14/23 12:34 AM
| @sreekanth.kancharla@penske.com , It is onboarded to Bamboo. Please deploy to QA. https://bamboo.penske.com/browse/TRGBP-TRIGBCH/deployments | Gayam | 07/15/23 1:34 AM
| @praneeth.gayam@penske.com Thank you. We'll work on promoting this to QA and test. Meanwhile, could you please change the deploy plan names as "Staging-Deploy" & "Prod-Deploy" as this is a batch application. | Sreekanth | 08/30/23 6:27 PM
| @sreekanth.kancharla@penske.com , Yes, the deploy names are meaning less as these are batch apps. But for all batch apps CICD team did same thing. I need to check with the team whether those can be changed for all. | Gayam | 08/30/23 10:47 PM
| @praneeth.gayam@penske.com Please share incase of any update on above request in changing the deploy plan names. | Sreekanth | 09/07/23 12:46 AM
| @sreekanth.kancharla@penske.com , Code CICD team said that it is difficult to change the name now. | Gayam | 09/07/23 1:28 AM
Row 206 | Question: @sreekanth.kancharla@penske.com , In this application TestMain.java has the main method. But the batchconfig file in this application referred to trinity.jar and the main class which is referred in batchconfig file exist in this jar. Could you please check and let us know which main class we need to use. Thanks. | Gayam | 06/16/23 3:04 AM
| @praneeth.gayam@penske.com I've checked the PROD deployed batchconfig.properties & it has the main class as "class=com.tririga.integration.InterfaceController" Please use the same. | Sreekanth | 06/26/23 6:37 PM
| Sure. Thank you. | Gayam | 06/27/23 3:15 AM
Row 206 | @sreekanth.kancharla@penske.com , this application has dependecy on following jars and need to upload them in artifactory 1.TririgaCustomTask.jar (groupid: com.tririga.pub, artifactid:TririgaCustomTask ) 2.trinity-dep.jar (after com which folder can i take) 3.trinity.jar (groupid: com.tririga, artifactid: trinity ) 4.PENSKE-test.jar (there is no folder structure to find the group id) PENSKE-test.jar, trinity-dep.jar groupid details. Could you please help us to get the groupid. All these jars are availabe in https://svn.penske.com/svn/webprojects/admin/Tririga_Batch/branches/qagh/Tririga/lib/ | Gayam | 02/01/23 1:20 AM
| @praneeth.gayam@penske.com 2.trinity-dep.jar (this jar has apache logger package, spring util package and others) This has all the dependencies which trinity.jar requires. We need to see whether we can eliminate this jar and include the dependencies such as log4j, spring etc. explicitly. If that works with no compiler errors, then we can test in QA. If application works with no issues, then we can remove this jar so no need to have any dependency. We can't create 1 group id for this jar as it has many packages in it. 4.PENSKE-test.jar - This jar does not have any files. By taking this out from build path, no compiler errors, so hope we can rid of this jar and that can be confirmed only after testing this application in QA. | Sreekanth | 02/01/23 3:41 AM
| Thanks @sreekanth.kancharla@penske.com . So are you going to work on eliminating both jars from the application? What about other jars? are you ok to upload? | Gayam | 02/01/23 3:45 AM
| @praneeth.gayam@penske.com We don't have any plans to remove the dependencies now. Can't that be taken care by your team and check for compiler errors. If we don't get any compiler errors, then we can deploy that app in QA and test later. We don't have DEV as this is batch app. | Sreekanth | 02/01/23 3:58 AM
| @sreekanth.kancharla@penske.com , We removed the dependencies and facing several issues in different files. There are approx 10-11 java files which are having error related to import statement. All import statement are from trinity.jar Following are sample 3 files. 1.FileTransferActivity.java 2.FTPActivity.java 3.FiletoDbtoApiActivity.java | Gayam | 02/03/23 12:56 AM
| @praneeth.gayam@penske.com Didn't we add trinity.jar (groupid: com.tririga, artifactid: trinity) to artifactory as you previously stated. | Sreekanth | 06/08/23 6:44 PM
| @sreekanth.kancharla@penske.com , Based on our previous discussions, I'm uncertain if we actually uploaded trinity jar to artifactory. I will debug with my team to check what is the status on this. Thanks. | Gayam | 06/09/23 1:34 AM
| @praneeth.gayam@penske.com Thank you, please change the "App Status" accordingly. | Sreekanth | 06/09/23 7:14 PM
| @sreekanth.kancharla@penske.com , let me summarize the required dependency jars from above chat. 1.TririgaCustomTask.jar (groupid: com.tririga.pub, artifactid:TririgaCustomTask ) 2.trinity.jar (groupid: com.tririga, artifactid: trinity ) 3. Ftp4j-1.9jar Please provide your approval to upload above jars to artifactory? | Gayam | 06/10/23 2:09 AM
| @praneeth.gayam@penske.com Please proceed. | Sreekanth | 06/13/23 2:14 AM
Row 206 | @charles.csoky@penske.com / @steve.mcmullen@penske.com , We completed the secrets scanning on this app and we found that there are true positives. I will send the file in the email. Could you please check and let us know whether you are planning mitigate the secrets. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 3:03 AM
| @praneeth.gayam@penske.com a. The password related secrets are fine as the properties file is being referred from specific location in QA & PROD servers which admins only can access. b. The file People_Inbound.xml – the provided secret is not available in QA & PROD code. CC: @mathumala.nachiappan@penske.com, @charles.csoky@penske.com | Sreekanth | 01/25/23 3:13 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the App Status to (Cap) Maven | Gayam | 01/25/23 11:27 PM
Row 206 | @mathumala.nachiappan@penske.com Moved to the AO Log4j Status. | Yvette Urso | 12/15/22 2:18 AM
Row 206 | @charles.csoky@penske.com - Log4J1 dependency. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:08 PM
Row 207 | Hi @manish.sisodiya@penske.com - Is this app duplicated with line # 122? CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 11:57 AM
Row 208 | @praneeth.gayam@penske.com please create bamboo plan the same as bill_avobatch | Dylan | 09/12/23 1:26 AM
| @dylan.price@penske.com , develop_log4j branch onboarded to bamboo and tasks are modified as like bill_avobatch. https://bamboo.penske.com/browse/PBSBP-TRSEXC | Gayam | 09/13/23 12:53 AM
Row 208 | Review: @dylan.price@penske.com , This app is ready for your review. Please check and merge. https://bitbucket.penske.com/projects/PBTCBOS/repos/trs-extract-batch/pull-requests/3/overview | Gayam | 07/10/23 11:45 PM
Row 208 | hi @praneeth.gayam@penske.com I will update the property file when I merge my changes with develop_log4j like I have done for other applications. Could you please start on log4j/maven changes? | Dylan | 06/13/23 5:17 PM
| Sure @dylan.price@penske.com | Gayam | 06/14/23 2:44 AM
Row 208 | @praneeth.gayam@penske.com found a violation with passwords in properties file. Will work on a solution to avoid these visible passwords. | Dylan | 03/30/23 9:27 PM
Row 208 | Secrets: @dylan.price@penske.com , secrets are shared in the email. Please check and confirm. Thanks. | Gayam | 03/24/23 12:00 AM
Row 208 | The trs_extract and trs_extract.jar are the same aplication. Please delete out the duplicate. | Dylan | 03/07/23 2:07 AM
| Thanks @dylan.price@penske.com . We will start working on it | Gayam | 03/07/23 11:48 PM
Row 208 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 208 | @dylan.price@penske.com - Have you checked for this? | Mathumala Nachiappan | 12/19/22 8:47 PM
Row 208 | Hi @manish.sisodiya@penske.com / @dylan.price@penske.com - There are 2 entries with the same name trs_extract. One is named as trs_extract and another is trs_extract.jar. Could you please check whether these 2 are same? @mathumala.nachiappan@penske.com , @yvette.urso@penske.com | Gayam | 12/16/22 12:19 AM
Row 208 | @mathumala.nachiappan@penske.com moved to Backlog due to missing comments with no information | Yvette Urso | 12/15/22 2:50 AM
Row 209 | @praneeth.gayam@penske.com - I discussed this with @david.long@penske.com . Yes, we would like you to manually upload the coversheet jar to artifactory. We do not want to change any existing logic \ dependencies. | Patel | 08/15/23 2:32 AM
| Thanks @falgun.patel@penske.com . Changing the status to Cap Maven | Gayam | 08/15/23 8:43 PM
Row 209 | @praneeth.gayam@penske.com , As the jar is currently being referenced by existing application, let's keep that jar in the build for now. | Patel | 07/28/23 12:47 AM
| @falgun.patel@penske.com , That mean do you want us to maually upload the coversheet jar to artifactory? | Gayam | 07/31/23 2:24 AM
Row 209 | Question: @david.long@penske.com , There is a coversheet jar in the lib folder of this app but without that jar also build is getting successful. Do you want us to upload this jar to artifactory and include that dependency in pom? | Gayam | 07/19/23 3:31 AM
Row 209 | Query: @david.long@penske.com , This application dependent on attachservice-client.jar(shared jar) latest version but the latest version is not available in artifactory. Old version is available in artifactory which is used by several other apps. The latest jar build is done by you from the below branch. SVN-URL: https://svn.penske.com/svn/fieldsys/other/attachment-service/ tags/qa/_T_QA-2022-06-16 Can we upload latest version to artifactory? | Gayam | 07/06/23 4:27 AM
| That may be a question for @stella.george@penske.com and @subramanian.vennimalayan@penske.com as they work with attachment service more than I do. I built that last year, but I'm sure some things have been changed since then | David | 07/06/23 7:27 PM
| @stella.george@penske.com / @subramanian.vennimalayan@penske.com , Could you please check the above comment and provide your response. Thanks. | Gayam | 07/07/23 12:16 AM
| @praneeth.gayam@penske.com please use the latest jar for attachment artifactory. | David | 07/11/23 1:28 AM
Row 209 | @praneeth.gayam@penske.com Emailed you back. no code changes are required as all secrets found were false positives. | David | 07/03/23 11:21 PM
| Thanks @david.long@penske.com . Chaning the status to Cap Maven. | Gayam | 07/03/23 11:23 PM
Row 209 | @david.long@penske.com / @falgun.patel@penske.com , I sent the secrets to you in the email. Please analyze and let me know wether this requires any code changes. Thanks. | Gayam | 07/03/23 11:14 PM
Row 209 | @praneeth.gayam@penske.com This is still in the "waiting on AO" status. Is there something I need to address? yea the attach svc client jar may already be in artifactory. | David | 06/09/23 6:21 PM
| @david.long@penske.com , Do we need to modernize the UnitJacket_ATTACHSVCCLIENT_JAR (Jar repo)- https://svn.penske.com/svn/fieldsys/other/attachment-service/Jar/prod too? | Gayam | 06/10/23 2:06 AM
| I don't think you need to. To my knowledge the attachment svc client jar is already on artifactory which means it should be running on maven, but I'm not totally sure. If it's not, then yes the attach svc client jar would need to be modernized | David | 06/15/23 1:33 AM
| Sure @david.long@penske.com . We will check and come back to you. | Gayam | 06/15/23 1:50 AM
| @david.long@penske.com , We found the dependency in artifactory. We will use this dependency in unitjkt. <dependency> <groupId>com.penske.mis.common.sharedlib</groupId> <artifactId>attachservice-client</artifactId> <version>1.0.0-20210310.061729-1</version> </dependency> | Gayam | 06/16/23 1:06 AM
| @david.long@penske.com , As indicated in the comment of 'servicereqweb.war' app, the penske team is doing the modernization of attachservice-client jar. So, we will be including the following dependency in the unitjkt.war. <dependency> <groupId>com.penske.mis.common.sharedlib</groupId> <artifactId>attachservice-client</artifactId> <version>1.0.0-20210310.061729-1</version> </dependency> | Gayam | 06/19/23 7:59 PM
| Sounds good thank you @praneeth.gayam@penske.com | David | 06/21/23 7:55 PM
Row 209 | @yojando.drullard@penske.com , Log4j team started working on modernizing this application. When we verified the old production bamboo build we are seeing following 2 repositories mentioned in the build. UnitJacket_PROD - https://svn.penske.com/svn/fieldsys/maintenance/unit-jacket/tags/prod/20220623/unitjkt UnitJacket_ATTACHSVCCLIENT_JAR (Jar repo)- https://svn.penske.com/svn/fieldsys/other/attachment-service/Jar/prod I am expecting 2nd one is a dependency jar for the first repo. Is that correct? If yes, we need to do the log4j and mavanization for the dependency jar also. Could you please check and confirm. Thanks. FYI: @shane.myers@penske.com | Gayam | 05/18/23 1:16 AM
| @praneeth.gayam@penske.com Yojando is no longer an employee at Penske. You are correct that the 2nd one is the dependency jar. The jar supports attachments in unit jacket. The attach svc client jar is already in artifactory i believe. I am not sure on the status of log4j for attach service | David | 06/06/23 10:30 PM
| @david.long@penske.com . Thanks for the info. we need to modernize the attach svc client jar also. @yvette.urso@penske.com , Could you please add one line in smartsheets for UnitJacket_ATTACHSVCCLIENT_JAR. | Gayam | 06/07/23 3:37 AM
Row 210 | Review & Query: @shweta.gupta@penske.com , Modernization is completed with an open query. Following is the PR. https://bitbucket.penske.com/projects/EBMS/repos/updlatlong-batch/pull-requests/7/overview Query: The application having the env based resource folders and there are some differences in application.yml file in prod and qa folders. These have to be handled in the code to satisfy the environment agnostic build. Please check. | Gayam | 10/18/23 7:38 AM
Row 210 | @frank.d'angelo@penske.com , We did complete our analysis on this application. The log4j branches are created by ebusiness team only and it looks like log4j upgrdataion and mavanization already completed. We are trying to complete any missed configurations in mavanization. But we got a query which I mentioned above. But as you suggested in the email we will complete all the remaining configurations and will give you the PR along with the query. Thanks. | Gayam | 09/21/23 1:12 AM
Row 210 | @praneeth.gayam@penske.com Is it fair to say that any application that already is using maven and has a pom.xml file will require our team to make changes before you are able to proceed? | Gianfranco | 09/07/23 8:42 PM
| yes @frank.d'angelo@penske.com . If it is already mavanized then implementing the changes by your team is the best step before we pick up the app. | Gayam | 09/08/23 12:21 AM
Row 210 | @praneeth.gayam@penske.com Sent via email (be much easier to read on Outlook): For Notification Batch and UpdLatLong, we have been discussing the approach for the environment agnostic build in the Smartsheet. You have been asking us to analyze the folders and tell you which properties file to use. I believe what you are actually asking us to do is to externalize our configurations into a database and make application changes to a single folder structure so that we can ultimately have 1 artifact. We are asking that the team take a different approach, one that we have gotten approved already through the architecture code review process. This would allow for consistency in applications that are already set up with the multiple folder structure and should only require minor changes to get the properties based on environment. This also meets the end goal of a single artifact. Eventually, we will be looking to leverage Spring Cloud Config Server once we are able to use it. I am providing an example that has already been completed and approved, Location API, for the team to use to review the approach. Folder Structure: https://bitbucket.penske.com/projects/EBCE/repos/locations-api/browse/src/main/resources/environment?at=refs%2Fheads%2Fdevelop EnvironmentType.Java - Line number 19/20 based on system properties, environment variables are set: https://bitbucket.penske.com/projects/EBCE/repos/locations-api/browse/src/main/java/com/penske/ce2/locations/configuration/web/EnvironmentType.java?at=develop WebApplication.Java - Line number 31 based on environment the Spring profiles are set: https://bitbucket.penske.com/projects/EBCE/repos/locations-api/browse/src/main/java/com/penske/ce2/locations/configuration/web/WebApplication.java?at=develop ApiConfig.Java - Line number 36 it dynamically loads specific environment property file: https://bitbucket.penske.com/projects/EBCE/repos/locations-api/browse/src/main/java/com/penske/ce2/locations/configuration/spring/ApiConfig.java?at=refs%2Fheads%2Fdevelop WebApplication.Java - Line 22 and line 43 for loading env specific log4j file: https://bitbucket.penske.com/projects/EBCE/repos/locations-api/browse/src/main/java/com/penske/ce2/locations/configuration/web/WebApplication.java?at=refs%2Fheads%2Fdevelop | Gianfranco | 09/06/23 4:05 AM
| Yes @frank.d'angelo@penske.com . That is a good approach. Thanks. Please let us know once your team complete the changes. We will do the next set of work. Thanks | Gayam | 09/07/23 1:38 AM
Row 210 | Query: @frank.d'angelo@penske.com / @shweta.gupta@penske.com , this application have the environment based resource folders and there is some differences in application.yml file between each environment. Which one we need to use? In environment agnostic build we can't use 2 separate yml files as it requires 2 separate builds. | Gayam | 08/25/23 12:45 AM
Row 210 | @praneeth.gayam@penske.com https://bamboo.penske.com/browse/MSP-UPLATLON | Gianfranco | 08/15/23 1:16 AM
| Thanks @frank.d'angelo@penske.com . Chaning the status to Cap analysis. | Gayam | 08/15/23 2:16 AM
Row 210 | @shweta.gupta@penske.com / @frank.d'angelo@penske.com , We found the BB repo for this app but not Bamboo build. Could you please let us know the production branch which we need to use as base branch for modernization work. https://bitbucket.penske.com/projects/EBMS/repos/updlatlong-batch/browse | Gayam | 08/03/23 1:11 AM
Row 211 | @praneeth.gayam@penske.com , I have gone ahead and updated | Gianfranco | 08/25/23 1:49 AM
Row 211 | @shweta.gupta@penske.com , Do we consider this application as duplicate and make the necessary changes in UpdLatLong? | Gianfranco | 08/24/23 8:25 PM
| The UpdateTimeZone only exists in IT contacts, so yes we can mark that as duplicate and continue with UpdLatLong. I'll work on retiring the Update Time Zone from IT contacts. | Gupta | 08/24/23 10:35 PM
| Thanks @frank.d'angelo@penske.com U @shweta.gupta@penske.com . Can I change this one as duplicate? | Gayam | 08/25/23 12:03 AM
Row 211 | The code repo BB and bamboo build is same as UpdLatLong. https://confluence.penske.com/pages/viewpage.action?pageId=19620789 This build is special. It builds two application artifacts from the same source: updlatlong.tgz This is the geocoder. It looks for changed Agent locations that have an address change updtimezon.tgz. This is the timezoner. It takes all active locations and checks for timezone changes. This was created for the explicit fact that jobs cannot be scheduled with a parameter. It has a special startup class in its manifest that contains the timezone parameter The deploy script pushes both artifacts as well. Both apps would need to be deployed for a coding change. | Gianfranco | 08/15/23 1:19 AM
| @frank.d'angelo@penske.com / @shweta.gupta@penske.com , I believe you are changing the code and running the bamboo build to create 2 separate artifacts. In that case, can we create separate bitbucket projects and bamboo builds for each app? | Gayam | 08/15/23 2:30 AM
| @praneeth.gayam@penske.com After research I found out that it's one build and one code repo. To run the timezone piece of code we have code in our service only. it doesn't require any special build. So, we can keep Update Lat Long and Update Time Zone in obe repo and build. Please let me know if you have any questions. | Gupta | 08/16/23 12:56 AM
| @shweta.gupta@penske.com , Do you want us to create only 1 repo and 1 build for both updtimezon and updlatlong apps? In that case what is the repo name should be and what is the final build file we need to mention in pom.xml? | Gayam | 08/17/23 1:08 AM
| @praneeth.gayam@penske.com We do not a new repo. We can proceed with the one which is existing for UpdatLatLong. Please let me know if you have concerns. | Gupta | 08/24/23 5:57 PM
Row 211 | @shweta.gupta@penske.com / @frank.d'angelo@penske.com , We couldn't find Bamboo and code repo for this app. Could you please help us to find them. Thanks. | Gayam | 07/27/23 11:43 PM
Row 212 | see attahced | Brian | 10/17/23 7:03 AM
| @brian.joseph@penske.com We will work on top of feature/email-fix branch and will provide the PR asap. Thanks. | Gayam | 10/17/23 11:52 PM
Row 212 | current branch in prod is this... https://bitbucket.penske.com/projects/EBUT/repos/used-trucks-admin/browse?at=refs%2Fheads%2Ffeature%2Femail-fix | Brian | 10/17/23 7:02 AM
Row 212 | Left a comment in the pull request.. | Brian | 10/13/23 7:51 PM
| @brian.joseph@penske.com , We will check and respond. | Gayam | 10/14/23 2:06 AM
Row 212 | Review: @brian.joseph@penske.com , We have completed the work on this app. Please review and merge. Thanks. https://bitbucket.penske.com/projects/EBUT/repos/used-trucks-admin/pull-requests/3/overview | Gayam | 10/13/23 8:43 AM
Row 212 | Hi @Praneeth Gayam we need to update the imports in UT Admin. This app did not get the latest jar when we migrated a few years ago. com.penske.apps.usedtrucks.imageservice.domain.Image. Please update any references to domain package under imageservice. | Brian | 10/11/23 2:54 AM
| Sure @brian.joseph@penske.com | Gayam | 10/12/23 7:41 AM
Row 212 | UT-Image Build -- https://bamboo.penske.com/browse/USEDTRUCKS-UTIMAGECLIENT | Brian | 10/03/23 1:25 AM
| Thanks @brian.joseph@penske.com . Changing the status to Cap Maven as log4j team needs to work on this further. | Gayam | 10/04/23 1:31 AM
| @brian.joseph@penske.com , We have uploaded usedtruckpdfcreator to artifactory. Regarding utimageservice.jar, We have uploaded to artifactory by given bamboo build. But the given utimageservice repo missing some classes when compared to the jar available in lib folder of UsedTruckAdmin. Because of this UsedTruckAdmin app is facing compilation issues in below class with given imports. classname : UploadImageForUnitAction import statements : import com.penske.apps.usedtrucks.domain.Image; Could you please check whether the given utimageservice is correct or not. Thanks. | Gayam | 10/11/23 2:10 AM
Row 212 | Review & Query: We have completed mavanization of this app with couple of open queries. https://bitbucket.penske.com/projects/EBUT/repos/used-trucks-admin/pull-requests/3/overview Query 1: This application has environment specific application.properties file. QA and prod properties file has a difference campaignServerPath variable. Web.xml file of qa and prod is same but there is some differences in dev file apart from dummyfilter at line no 230. Also there is a difference in environment-specific-config.xml between qa , prod and dev . qa and prod files are same but dev is different. Query 2: Below two jars are required for this application but these are not available in artifactory . used-trucks-image-service.jar: Bamboo - https://bamboo.penske.com/browse/USEDTRUCKS-UTIMAGECLIENT Bitbucket - https://bitbucket.penske.com/projects/EBUT/repos/ut-image-service/browse usedtruckspdfcreator.jar: BitBucket- https://bitbucket.penske.com/projects/EBUT/repos/usedtruckspdfcreator/browse , Bamboo -https://bamboo.penske.com/browse/USEDTRUCKS-PCA Do you want us to modernize the above 2 jars too or manually upload them to artifactory? Please check above 2 queries. Thanks. | Gayam | 09/28/23 1:49 AM
| Query 1: This should be fine as long as everything works in QA. The environment-specific-config.xml is only different in Dev. I dont think this will be an issues as long as QA works. Query 2: PDF Creator will need to be pushed to Artifactory .. As long as it can be downloaded in a pom with no modernization, then we only need to push to artifcatory. If we have issues calling it, we will need to modernize it. UT Image Service is in this branch, which is Maven modernization, it needs to be pushed to artifcatory. The build needs to be updated to accept maven. https://bitbucket.penske.com/projects/EBUT/repos/ut-image-service/browse?at=refs%2Fheads%2FMaven_2023 | Brian | 10/01/23 12:39 AM
| @brian.joseph@penske.com , Query 1: We will replace the files with prod/qa ones in resources folder. It will not work in dev. Query 2: We will upload PDF creator jar to artifactory. What is the bamboo build for UT Image service? | Gayam | 10/03/23 1:06 AM
Row 212 | @praneeth.gayam@penske.com , I am changing the App Status to CAP MAVEN. I have a management report out Monday morning and want to show the most current status for applications. | Gianfranco | 08/26/23 6:19 PM
Row 212 | @praneeth.gayam@penske.com thanks @brian.joseph@penske.com . Team may proceed with next steps | Gianfranco | 08/25/23 1:49 AM
Row 212 | HI I did not see any outstanding issues. The false positives are correct. | Brian | 08/25/23 1:13 AM
Row 212 | @brian.joseph@penske.com , I sent secrets in an email. Could you please verify it. Thanks. | Gayam | 08/05/23 12:35 AM
Row 213 | User Lookup deployed on 9/28 to production. Thank you for your support. | David Graf | 09/29/23 11:29 PM
| Thanks for the update @david.w.graf@penske.com | Gayam | 10/05/23 1:26 AM
Row 213 | I attempted the Prod deployment in bamboo which was a success. Changing status. | David Graf | 07/05/23 10:54 PM
Row 213 | if maven hasn't already been signed off on. This message is sign off for maven. | David Graf | 06/30/23 6:59 PM
Row 213 | Soon, I will attempt to run Prod deployment. This will complete the bamboo testing. | David Graf | 06/30/23 6:58 PM
Row 213 | confirmed, looks good; thanks | David Graf | 06/30/23 6:56 PM
Row 213 | We deployed to QA without issue continuing testing to run Prod deploy, but first can you clean up the two deployments? I see two: userlookup-svc-deploy userlookup-web-deploy | David Graf | 06/28/23 7:31 PM
| Sure @david.w.graf@penske.com . we will remove userlookup-web-deploy | Gayam | 06/29/23 2:35 AM
| @david.w.graf@penske.com , Deleted userlookup-web-deploy. | Gayam | 06/30/23 1:23 AM
Row 213 | @praneeth.gayam@penske.com another thing that we might have to check is the deploy pattern that it is using. If it was originally set up was a web deploy then that could be the reason that it is including a tgz with the war. The Web Services scripts only expects the war and so far the tgz has been left in the var/tmp directory each time we build. My suggestion is to have the deploy use a service implementation instead of web deploy implementation which should only deliver the war to var/tmp. | David Graf | 06/14/23 7:34 PM
| @david.w.graf@penske.com , For web applications, the tgz file contains only static content and it should be copied to the location /opt/webcontent/<instance>/<app>/. Is there anything different for this application? | Gayam | 06/15/23 12:43 AM
| this is not a web application. It is a service (svc) that deploys on wsv which has no need for static content. | David Graf | 06/16/23 4:38 PM
| Sure @david.w.graf@penske.com . We will fix the issue and will deploy the war to /var/tmp. | Gayam | 06/16/23 10:16 PM
| @david.w.graf@penske.com , WE removed the assembly configuration which generates the tgz file with static content. Please check the changes in below PR. https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-svc/pull-requests/5/overview | Gayam | 06/19/23 7:36 PM
Row 213 | @praneeth.gayam@penske.com The bamboo build plan is incorrectly labeled as userlookup-web but it should be userlookup-svc. I think @ankita.tiwary@penske.com created a footprint ticket that requests the same. Please let us know when the bamboo is fixed to have svc. | David Graf | 06/12/23 7:56 PM
| Sure @david.w.graf@penske.com . We will work on it. | Gayam | 06/13/23 1:28 AM
| @david.w.graf@penske.com , We changed the build plan name to userlookup-svc. https://bamboo.penske.com/browse/ULSBP-USELO/ Do you want us to change the deploy plan name too? | Gayam | 06/14/23 3:48 AM
| yes, please change the deploy name too. And can you link to the spec and template for this app in Bitbucket? so that I may confirm | David Graf | 06/14/23 5:12 PM
| @david.w.graf@penske.com , Deploy name changed to userlookup-svc-deploy. Please deploy to dev and qa. We will delete old deploy plan once you confirm the new deploy plans. | Gayam | 06/16/23 2:52 AM
Row 213 | we overcame an issue with logging this morning and hope to continue with dev deployment soon. | David Graf | 06/12/23 7:54 PM
Row 213 | @david.w.graf@penske.com , We did complete the mavanization on this app. But Hugo took over to add the unit tests. Latest code is in the branch https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-web/commits?until=refs%2Fheads%2Fdevelop_log4j&merges=include Bamboo plan is https://bamboo.penske.com/browse/ULSBP-USELO/ Please let us know if you are looking for any other info. Thanks | Gayam | 04/21/23 1:32 AM
Row 213 | looks like even web-inf is in svn. So during modernization it may not be needed because maven may create those directories from scratch. | David Graf | 04/20/23 6:46 PM
Row 213 | Hugo provided SVN location: https://svn.penske.com/svn/architecture/general/userlookup/branches/dev_gh/ | David Graf | 04/20/23 6:45 PM
Row 213 | shouldn't this bitbucket be userlookup-svc? https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-web/browse the app does not have a front end and is deployed to wsv instance. I'm not sure it needs a web-inf directory either. Where is the SVN archive location to refer to? | David Graf | 04/20/23 6:30 PM
Row 213 | @hugo.scavino@penske.com @sherin.basheer@penske.com We are tasking Ankita with this modernization work. Please let me know if you have any issues with that. @praneeth.gayam@penske.com let us know where this left off | David Graf | 04/20/23 5:28 PM
Row 213 | @hugo.scavino@penske.com , userlookup - build & Deploy plan onboarding completed and Dev deployment done. Please verify. https://bamboo.penske.com/browse/ULSBP-USELO/ | Gayam | 04/04/23 11:14 PM
Row 213 | Sure @hugo.scavino@penske.com . Can you also verify the secrets which we sent earlier and let us know whether any code changes required. Thanks. | Gayam | 02/10/23 12:56 AM
Row 213 | Bamboo (CAP) - I have completed my peer review and unit tests. Please proceed with the Bamboo build using the develop branch. https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-web/branches | Hugo Scavino | 02/09/23 10:06 PM
Row 213 | I will review project. It requires a new unit and integration test before deploying to DEV https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-web/browse?at=refs%2Fheads%2Fdevelop_log4j | Hugo Scavino | 01/31/23 9:49 PM
Row 213 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:28 AM
Row 213 | @hugo.scavino@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 3:51 AM
Row 214 | Query: @stella.george@penske.com / @karthikeyan.srinivasan@penske.com , Need to mitigate following issues to satisfy the environment agnostic build. Could you please check. 1.This application has LocalTestAuthenticationFilter.java file under targeted/dev foder only which is getting used in the application for dev build. 2.There are environment based propertiy files. Dev and qa folders have testing.properties and prod has production.properties . 3.There is UserMaintWebService.wsdl file is available under targeted folder . This is different for each environment . | Gayam | 09/20/23 12:49 AM
Row 214 | Secrets: @karthikeyan.srinivasan@penske.com / @stella.george@penske.com , I have sent the secrets of this app in the email. Could you please check the file and let us know whether this app requires any code changes to mitigate the secrets. | Gayam | 09/14/23 1:46 AM
| @stella.george@penske.com confirmed that no changes required for secrets. Pushing the status to next step. | Gayam | 09/15/23 7:00 AM
Row 214 | Question: @karthikeyan.srinivasan@penske.com / @sarath.mani@penske.com / @stella.george@penske.com , Based on bamboo the prod ref is https://svn.penske.com/svn/fieldsys/maintenance/usermaint/tags/_T_PROD_BUILD_2016-12-13/ But looks like the tag is moved to here https://svn.penske.com/svn/fieldsys/maintenance/usermaint/tags/old_tags/_T_QA_BUILD_2016-12-13 We need a confirmation on the branch? Could you please check it. Thanks. Bamboo: https://bamboo.penske.com/chain/viewChain.action?planKey=USERMAINTBP-USERMAINTPROD | Gayam | 06/27/23 5:37 AM
| @praneeth.gayam@penske.com here is the last prod tag. https://svn.penske.com/svn/fieldsys/maintenance/usermaint/tags/old_tags/_T_PROD_BUILD_2018-07-18 | Stella george | 08/15/23 2:56 AM
| Thanks @stella.george@penske.com . Updated the status to Cap Analysis. | Gayam | 08/15/23 8:48 PM
Row 215 | Hi Praneeth, verified for production and its looks good and I see that tgz is generating. I will create the FP to remove the old Bamboo plans.Thanks! cc: @david.w.graf@penske.com | Sama | 10/18/23 12:27 AM
Row 215 | Hi @praneeth.gayam@penske.com we are confirming that QA and QA2 is working fine. Please continue the change the instance name of production.Thanks! cc: @david.w.graf@penske.com | Sama | 10/16/23 8:32 PM
| Sure @bhagya.sama@penske.com | Gayam | 10/17/23 1:03 AM
| @bhagya.sama@penske.com , Prod plan instance value changed to external. | Gayam | 10/17/23 11:48 PM
Row 215 | @praneeth.gayam@penske.com I am checking on clex150ptlge(batch) server. | Sama | 10/06/23 8:06 PM
| @bhagya.sama@penske.com , What I know is above server is for batch apps. But usermgmt is a web app. | Gayam | 10/10/23 12:10 AM
| all artifacts are deployed to var/tmp on the batch server. I think that is what Laxmi is saying. | David Graf | 10/10/23 7:51 PM
| @david.w.graf@penske.com , this is a war application and tgz supposed to be pushed to apache server and war supposed to be deployed to QA was servers. Let us check on this and get back to you. | Gayam | 10/11/23 1:05 AM
| What you are describing is the step performed by Web Services to deploy the WAR into WebSphere. We are testing that the WAR and TGZ is available in the var/tmp and webcontent directory. And Laxmi and I have not seen the TGZ on the server with the recent build for QA2. Our test is to confirm the artifacts are available for the Web Services scripts. | David Graf | 10/11/23 5:26 PM
| @david.w.graf@penske.com / @bhagya.sama@penske.com , Instance name of QA and QA2 plans mentioned as internal. That was the reason it is not working. Now it is changed to 'external' and QA2 deployment is working fine. usermgmt2.tgz is deployed to /opt/webcontent/external/ location. Once you comfirm, we will change the instance name of production plan to 'external'. Thanks. | Gayam | 10/13/23 9:08 AM
Row 215 | @praneeth.gayam@penske.com I try deploying to QA2 and see that war file generating with out any issues but I don't see the tgz file under /opt/webcontent/external/usermgmt2. Can you please check on this? cc: @david.w.graf@penske.com | Sama | 10/05/23 10:56 PM
| @bhagya.sama@penske.com , Please let us know on which server you are checking. | Gayam | 10/06/23 12:54 AM
Row 215 | Still confirming if we can deploy to QA2 and Prod from the new Bamboo plan. | David Graf | 09/27/23 1:32 AM
| @david.w.graf@penske.com , We have modified the QA2 plan. Please check it. https://bamboo.penske.com/deploy/viewEnvironment.action?id=151912535 | Gayam | 09/28/23 12:59 AM
| I see that the variables for QA and QA2 do not match. The variables for QA2 seem to match Prod. Please confirm this is correct before we attempt to deploy. | David Graf | 10/02/23 11:40 PM
| @david.w.graf@penske.com , CICD team fixed the QA2 variables. COuld you please check now. | Gayam | 10/04/23 1:53 AM
Row 215 | I see the plan but running into issues with the intial deployment: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=147554384 | David Graf | 07/07/23 4:56 PM
| @david.w.graf@penske.com , We will check and get back to you. | Gayam | 07/10/23 11:29 PM
| @david.w.graf@penske.com issue is resolved. Please check. instancetype was missing initally. | Gayam | 07/12/23 1:44 AM
Row 215 | @praneeth.gayam@penske.com Please add a third deployment for QA 2 which will deploy an artifacts called usermgmt2.war and usermgmt2.tgz. | David Graf | 06/30/23 9:20 PM
| @david.w.graf@penske.com , I am not sure about the ask here. Build needs to be environment agnostic..right? One build and same war/tgz needs to be deployed to all environments. Could you please let me know whether I am missing anything. | Gayam | 07/01/23 1:34 AM
| it is the same agnostic artifact, the name of the artifact needs to change to usermgmt2 so that the QA server can host it using the usermgmt2 scripts. | David Graf | 07/03/23 4:39 PM
| I see there was an attempt to create a branch which alters the pom. I don't think that is the best way to proceed. The pom will support prod by default so it should be usermgmt. For usermgmt2, there should be a bamboo tasked added after the jar was pulled from artifactory which renames it with a 2 at the end (ex: usermgmt2) | David Graf | 07/05/23 7:30 PM
| @david.w.graf@penske.com , That is what I suggested to team. CICD team is looking into this. | Gayam | 07/06/23 3:11 AM
| @david.w.graf@penske.com , We have created another deploy plan 'qa2_was8-deploy' to satisfy the given requirement. Please check. Thanks. https://bamboo.penske.com/browse/USRMGMT-UMGMT/deployments | Gayam | 07/07/23 1:36 AM
Row 215 | @praneeth.gayam@penske.com Here are some details: User Management has the following Deployments: QA, QA2, Prod There is no DEV and QA2 deploys to the sam location as QA but the artifact is called usermgmt2.war. Currently the user-management build plan has two deployments and that should be fixed to only be one: https://bamboo.penske.com/browse/USRMGMT-UMGMT/deployments | David Graf | 06/29/23 1:30 AM
| @david.w.graf@penske.com We will delete the usermgmt-deploy plan and retain the user-management-deploy plan that has a matching name with the bitbucket project. | Gayam | 06/30/23 12:46 AM
| confirmed, looks good. Thanks. | David Graf | 06/30/23 6:57 PM
Row 215 | @praneeth.gayam@penske.com we have deployed changes succesfully to production on 05/09 so we can close this app. | Sama | 05/17/23 2:04 AM
| Thanks @bhagya.sama@penske.com . Changed the status to Done. | Gayam | 05/17/23 3:12 AM
| @bhagya.sama@penske.com , Do the log4j and maven changes are deployed to production? | Gayam | 06/06/23 9:51 AM
| @praneeth.gayam@penske.com log4j and maven changes are in production. However, we had to use the old bamboo build ALL_BUILD plan to deploy. We are starting the Bamboo effort back up. So that it can be completed. | David Graf | 06/29/23 1:15 AM
Row 215 | after that we will have to return to the bamboo plan. @hugo.scavino@penske.com @bhagya.sama@penske.com | David Graf | 04/11/23 12:16 AM
Row 215 | we have a deploy scheduled for 4/18 which contains all of the changes placed in develop_log4j. | David Graf | 04/11/23 12:14 AM
Row 215 | @bhagya.sama@penske.com - QA Deployment done on 16th Nov | Mathumala Nachiappan | 11/23/22 3:53 AM
Row 216 | we are going to be starting this effort back up. We will be doing the Dev deploy test. | David Graf | 06/29/23 1:31 AM
Row 216 | As per @hugo.scavino@penske.com , RBAC updates for usermgmtsvc.war are working fine and provided approval for reonboarding RBAC updates for all other arch apps. @mathumala.nachiappan@penske.com @balu.mohan@penske.com @haribabu.challa@penske.com | Gayam | 02/16/23 3:23 AM
Row 216 | I'm going to delete the branch that you created for me for javadoc after I transfer what I've learned to a different app. | David Graf | 01/18/23 11:31 PM
Row 216 | @david.w.graf@penske.com , As requested for javadoc changes we created following branch. https://bitbucket.penske.com/projects/AR-SEC/repos/usermgmtsvc/branches?base=refs%2Fheads%2Ffeature%2Fjavadoc_implementaion FYI: @hugo.scavino@penske.com , @mathumala.nachiappan@penske.com | Gayam | 12/08/22 11:14 PM
| how do I run the JavaDoc creation locally? I want to see the errors preventing JavaDoc creation. | David Graf | 01/18/23 8:52 PM
| I used intelliJ to generate and there were some errors and warnings but the javadoc generated. "C:\Program Files\Amazon Corretto\jdk1.8.0_322\bin\javadoc.exe" -protected -splitindex -d C:\PTL_MIS\git\usermgmtsvc\javadoc @C:\Users\600212113\AppData\Local\Temp\javadoc_args | Hugo Scavino | 01/18/23 9:36 PM
| I remember having talked to someone about this and that I could run it from the command line. I think that doing a mvn install was sufficient. I was able to see it fail miserably with this app due to javadoc errors. I'm thinking about maybe putting this one the ebs client jar instead of this service which should be well documented through swagger instead of javadocs. But a shared library jar the ebs client would be perfect for javadoc. | David Graf | 01/18/23 11:29 PM
Row 216 | Now that we have a valid bamboo plan. I was able to make minor changes. The appilcation was deployed to DEV and is logging at /logs/apps/usermgmtsvc as expected. Once QA is available we can regression test there. | Hugo Scavino | 01/13/23 3:07 AM
| Thanks @hugo.scavino@penske.com . We will deploy the app to QA and will let you know. @haribabu.challa@penske.com | Gayam | 01/13/23 9:42 AM
| @hugo.scavino@penske.com , usermgmtsvc Qa deployment done but jtest reports are not published in DTP server. @haribabu.challa@penske.com is checking on this. | Gayam | 01/14/23 12:21 AM
Row 216 | @hugo.scavino@penske.com , Secret scanning is completed on this application and in our analysis all are false positives. I will send the sheet in the email. Could you please check and confirm. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/10/23 12:03 AM
Row 216 | Sure @hugo.scavino@penske.com . @praneeth.gayam@penske.com - Pls. note this for the changes | Mathumala Nachiappan | 12/02/22 5:42 PM
Row 216 | The project should be here https://bamboo.penske.com/browse/USRMGMT and NOT https://bamboo.penske.com/browse/CSP-USM Thank you | Hugo Scavino | 12/01/22 3:24 AM
Row 216 | @praneeth.gayam@penske.com and @mathumala.nachiappan@penske.com I opened a ticket to moderize the Bamboo project for usermgmtsvc. There is an issue in QA and I would rather solve it with a newer branch and code - FYI FP - 1758286 | Hugo Scavino | 12/01/22 3:23 AM
Row 216 | @praneeth.gayam@penske.com - To confirm the Maven rework | Mathumala Nachiappan | 11/23/22 3:55 AM
Row 217 | @sherin.basheer@penske.com , Please review the below PR. https://bitbucket.penske.com/projects/AR-SEC/repos/userstoreclient-rest/pull-requests/3/overview | Gayam | 02/16/23 2:09 AM
Row 217 | @mathumala.nachiappan@penske.com This is not blocked. I picked AO Final Testing - but please find the proper stage you are in. @sherin.basheer@penske.com can you work with Mathu on what is needed for this? Thank you | Yvette Urso | 12/09/22 12:58 AM
Row 217 | @praneeth.gayam@penske.com - Pls. follow up with Hari on the Artifact upload process | Mathumala Nachiappan | 12/02/22 5:29 PM
Row 217 | @yvette.urso@penske.com - Deployment is not required for these jars. Can we have this as one of the deliverables as Needed/Not Needed? | Mathumala Nachiappan | 11/23/22 3:57 AM
Row 217 | @praneeth.gayam@penske.com - To upload artifacts to Artifactory. No Deployment Required | Mathumala Nachiappan | 11/23/22 3:56 AM
Row 218 | @yvette.urso@penske.com These wars are probably going to be retired. Need to migrate reuse first before working on these. These will be LAST in the enterprise with reuse. | Donald Kichline | 09/12/23 11:49 PM
Row 218 | I have reviewed the secrets and cOnfirming secrets are false positives. | Sherin | 06/20/23 11:33 PM
| Thanks @sherin.basheer@penske.com . Could you please provide the response for the question asked above. | Gayam | 06/21/23 12:57 AM
Row 218 | Question: @sherin.basheer@penske.com , adding to secrets mitigation, targeted folder of this app contains dev/prod/qa subfolders and each have multiple xsd and wsld files. Do we need to include them in the build path? If yes, which folder files we need to include them because different env files have diff data. | Gayam | 02/03/23 1:03 AM
Row 218 | Secrets Mitigation: @sherin.basheer@penske.com , We completed the secrets scanning of this app and in my team's analysis all are false positives. I will send the secrets in an email. Please verify and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/19/23 11:59 PM
Row 218 | @sherin.basheer@penske.com - Modernized version of Penskesso.jar is uploaded to artifactory. This application is good to proceed for further changes, CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/13/22 5:46 PM
Row 218 | penskesso.jar is awaiting for PR review. | Mathumala Nachiappan | 12/02/22 5:30 PM
| @yvette.urso@penske.com - This is just an update tracked for this app. No action required presently for this Application. 'CAP is blocked' as the dependency Penskess.jar is not progressed. And that is in #71. | Mathumala Nachiappan | 12/12/22 4:48 PM
Row 218 | @mathumala.nachiappan@penske.com this is not blocked. Please specify who you are requesting to review and at what stage. Thank you | Yvette Urso | 12/09/22 1:00 AM
Row 218 | Missing denendency not available in artifactory-->penskesso.jar | Mathumala Nachiappan | 11/23/22 3:59 AM
Row 219 | sorry about that confusion, merge is complete | David Graf | 06/01/23 1:31 AM
| Thanks @david.w.graf@penske.com . We will onboard feature/maven branch to bamboo. | Gayam | 06/03/23 12:16 AM
| @david.w.graf@penske.com , feature/maven branch is onbaorded to Bamboo. Please check. https://bamboo.penske.com/browse/UCSVC-USRSVCCLT1/ | Gayam | 06/10/23 2:12 AM
Row 219 | @praneeth.gayam@penske.com I don't want to merge to develop. That isn't mandatory is it? I would prefer to leave develop as close to production as possible so that I can deploy a change if I need to. | David Graf | 05/25/23 5:33 AM
| Sure @david.w.graf@penske.com . You don't have to merge to develop. But can you merge the PR. https://bitbucket.penske.com/projects/AC/repos/usrcreationsvc-client/pull-requests/4/overview This is merging to feature/maven branch which is the base branch all of lo4j team's changes. | Gayam | 05/26/23 12:01 AM
Row 219 | maven is confirmed please move to Bamboo stage. | David Graf | 05/24/23 5:10 PM
| @david.w.graf@penske.com , PR is still in open status. Could you please merge. Also, once you merge the below, I think need to merge feature/maven branch to develop. Then we will onboard the develop branch to Bamboo. https://bitbucket.penske.com/projects/AC/repos/usrcreationsvc-client/pull-requests/4/overview | Gayam | 05/25/23 2:41 AM
Row 219 | @praneeth.gayam@penske.com please enter the needed and not needed information into the analysis columns for this app. | David Graf | 05/03/23 5:19 PM
| Review: @david.w.graf@penske.com / @mahendra.kalyan@penske.com , Log4j team completed the required changes and created PR. Please check. https://bitbucket.penske.com/projects/AC/repos/usrcreationsvc-client/pull-requests/4/overview | Gayam | 05/04/23 12:14 AM
Row 219 | Mahendra reviewed the secrets and they are all false positives. Please move to next step. | David Graf | 05/02/23 5:24 PM
Row 219 | @mahendra.kalyan@penske.com Sent secrets in the email. Please check and confirm. | Gayam | 04/26/23 1:49 AM
Row 219 | @praneeth.gayam@penske.com complete your analysis, and don't trust that the mavenization was done to the Security Modernization standards. I expect there to be changes in the pom and also the need for new bamboo builds. | David Graf | 04/21/23 4:32 PM
| Sure @david.w.graf@penske.com . We will verify and complete the requested work. | Gayam | 04/22/23 2:08 AM
Row 219 | changed status to CAP analysis. Mahendra will do work after the analysis stage is over. | David Graf | 04/19/23 5:11 PM
| @david.w.graf@penske.com , Are you expecting any work on this. It looks like already mavanized. | Gayam | 04/21/23 1:49 AM
Row 219 | @sherin.basheer@penske.com , It looks like this is already mavanized by AO. https://bitbucket.penske.com/projects/AC/repos/usrcreationsvc-client/browse?at=feature%2Fmaven Is this needs any more work? FYI: @yvette.urso@penske.com , @hugo.scavino@penske.com | Gayam | 04/19/23 3:15 AM
Row 219 | @praneeth.gayam@penske.com Per Arch Team this is a companion Jar to usrcreationsvc.war. I added this new today. | Yvette Urso | 04/14/23 8:54 PM
| Thanks @yvette.urso@penske.com . We will check. | Gayam | 04/18/23 3:05 AM
Row 220 | We testing in QA and test is passing with logs being created. | David Graf | 06/19/23 5:10 PM
Row 220 | @praneeth.gayam@penske.com We attempted to test this morning and found that the build plan is missing some configuration or security for myself and Mahendra. We cannot create a plan branch the button is missing. We cannot test without using our plan branch. | David Graf | 06/13/23 5:17 PM
| @david.w.graf@penske.com , I will check with CICD team and let you know. | Gayam | 06/14/23 2:48 AM
| @david.w.graf@penske.com , Ritesh added your id as admin for this app and you can create plan branches now. | Gayam | 06/15/23 12:53 AM
| I think the branches that I need have been created but the admin setting must have been temporary. Because this morning I do not see the add branch button. | David Graf | 06/16/23 4:39 PM
Row 220 | Please create bamboo for the service | David Graf | 04/13/23 5:31 PM
| Sure @david.w.graf@penske.com . we will onboard to bamboo and will let you know. | Gayam | 04/13/23 11:22 PM
| @david.w.graf@penske.com usrcreationsvc dev deployment is completed from develop_log4j branch. Please verify. https://bamboo.penske.com/browse/UCSVC-USRSVC/deployments | Gayam | 04/15/23 12:35 AM
Row 220 | we cannot go to dev because bamboo is ant so we will move to Bamboo stage. | David Graf | 04/13/23 5:30 PM
Row 220 | Last step for mavenization from AO is to deploy using old bamboo into Dev and test. Then we will move to next step. | David Graf | 04/11/23 5:31 PM
Row 220 | https://jira.penske.com/browse/WRPSUP-148 Mahendra is working on this. | Sherin | 03/10/23 9:26 PM
Row 220 | @mathumala.nachiappan@penske.com this is not blocked - moved to AO Secrets Mitigation | Yvette Urso | 12/09/22 1:00 AM
| Got it @yvette.urso@penske.com | Mathumala Nachiappan | 12/12/22 4:48 PM
Row 220 | @sherin.basheer@penske.com - In Secret scanning, found hardcoded href links and hardcoded credentials. Pls. check it for redaction. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 7:47 PM
Row 220 | @sherin.basheer@penske.com , We have completed log4j/maven changes. Please revie and merge them. https://bitbucket.penske.com/projects/AR-SEC/repos/usrcreationsvc/pull-requests/10/overview | Gayam | 12/07/22 10:25 AM
Row 220 | Pending for the modernization of usrcreationservice-client.jar | Mathumala Nachiappan | 12/02/22 5:31 PM
Row 221 | has any of these apps be deployed to dev or QA? or has it all been local testing? | Brian | 10/16/23 10:00 PM
| @brian.joseph@penske.com , Log4j/migration is in progress for both usedtrucksadmin and sellsheet. But the apps are geeting compiled successfully once we did the changes which you are suggested. | Gayam | 10/17/23 11:58 PM
Row 221 | Botha apps usedtrucksadmin and sellsheet are working fine after changing the imports. @brian.joseph@penske.com , Can we change the status of this app to Done as it is uploaded artifactory? | Gayam | 10/14/23 2:20 AM
Row 221 | SellSheet will need to update to the new imports same with UT Admin. | Brian | 10/11/23 2:55 AM
| Thanks @brian.joseph@penske.com | Gayam | 10/12/23 7:42 AM
Row 221 | @brian.joseph@penske.com provided following repo and bamboo build in usedtruckadmin app's comments. Updated us to run the below bamboo build to upload utimage into artifactory. But when we use utimage dependecy from this bamboo build, both usedtruckadmin and sellsheet application are getting compilation issues. Bamboo - https://bamboo.penske.com/browse/USEDTRUCKS-UTIMAGECLIENT Bitbucket - https://bitbucket.penske.com/projects/EBUT/repos/ut-image-service/browse | Gayam | 10/11/23 2:17 AM
Row 221 | @hugo.scavino@penske.com @praneeth.gayam@penske.com Hugo - and you look at this open item - whether utimageservice should be taken into log4j/mavan upgradation. | Yvette Urso | 03/29/23 12:57 AM
Row 221 | Sellsheet application depends on this jar. Sellsheet is a corp app. But utimageservice's owner is Brian Joseph. | Yvette Urso | 03/29/23 12:56 AM
Row 222 | I confirmed there is no change record for the deploy and the changed timestamp for vdrfilebatch in prod is 6/21/2021 which I confirmed from the Manifest was deployed from SVN. FYI: @praneeth.gayam@penske.com | David Graf | 08/25/23 7:58 PM
| Thanks @david.w.graf@penske.com . I am seeing prod deployment in bamboo ran in June. That is the reason I asked. https://bamboo.penske.com/deploy/viewEnvironment.action?id=113344514 | Gayam | 08/26/23 12:56 AM
| We probably performed the prod deployment during Bamboo Review. FYI, that is our strategy to ensure that prod deployment is working. Instead of waiting until right before the production deploy. | David Graf | 09/18/23 11:19 PM
| Thanks @david.w.graf@penske.com | Gayam | 09/19/23 12:52 AM
Row 222 | I will try to get you an answer on this tomorrow. | David Graf | 08/25/23 6:02 AM
Row 222 | @david.w.graf@penske.com , Looks like this app is deployed to production with modernization changes. Please confirm. So that we can change the status to Done. | Gayam | 08/24/23 11:10 PM
Row 222 | @praneeth.gayam@penske.com Shouldn't log4j scope be updated? | Sherin | 06/24/23 2:03 AM
| @sherin.basheer@penske.com , Not getting you. Please elaborate. | Gayam | 06/27/23 3:11 AM
Row 222 | Tested in QA and got signoff from users | Sherin | 06/24/23 12:00 AM
Row 224 | Confirmed by @sherin.basheer@penske.com | Mathumala Nachiappan | 11/23/22 4:02 AM
Row 225 | @rajesh.haravde@penske.com , Build is already successful on develop_log4j branch. Please deploy to QA. | Gayam | 07/10/23 11:31 PM
Row 225 | log4j commits not merged into main develop branch. develop branch is failing to build. But log4j_develop branch is getting successfully build. please guide. | Rajesh | 07/07/23 11:38 PM
Row 225 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:09 AM
| @rajesh.haravde@penske.com , PR is not yet merged. But we will onboard the develop_log4j branch to bamboo for you to validate. Once validation completes, please merge. | Gayam | 06/09/23 1:45 AM
| @rajesh.haravde@penske.com , develop_log4j branch is onboarded successfully and build is successful. Please verify. | Gayam | 06/13/23 2:11 AM
Row 225 | pom.xml not found , please look look into it. | Rajesh | 05/16/23 6:51 PM
| @rajesh.haravde@penske.com , Develop_log4j branch has pom.xml. | Gayam | 05/17/23 3:31 AM
Row 225 | Review: @rajesh.haravde@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/PTLCORP/repos/vehicleimageupdate-batch/pull-requests/4/overview | Gayam | 05/02/23 2:04 AM
Row 225 | We are not going to implement any code change at this moment. please take it forward the source as it with maven and bitbucket upgradation efforts. Thank you. | Rajesh | 04/14/23 12:10 AM
| Thanks @rajesh.haravde@penske.com . Changed the status to Cap Maven. | Gayam | 04/14/23 12:22 AM
Row 225 | @april.ottey@penske.com / @veronique.labeille@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:36 AM
| @krishna.tanga@penske.com | Yvette Urso | 12/01/22 8:33 PM
| @rajesh.haravde@penske.com updated the svn url in the email. https://svn.penske.com/svn/fieldsys/maintenance/fleetnet/branches/offshore_standalone/vehicleimageupdate Rajesh, could you please provide the existing bamboo plan too. Thanks. @mathumala.nachiappan@penske.com | Gayam | 12/08/22 11:04 PM
| There is not bamboo plan for this one. this are get deployed on JDK box as JAR. I will verify with previous lead and get back to you if any. but as of now no bamboo plan available for this one. | Rajesh | 12/12/22 11:54 PM
| @rajesh.haravde@penske.com , As there is no existing bamboo build, under which project we need to create new bamboo specs for this app? | Gayam | 01/11/23 9:28 AM
| As discussed with @rajesh.haravde@penske.com , log4j team needs to create a new Bamboo project for vehicleimageupdate. Changing the status to (Cap)Log4j | Gayam | 02/21/23 4:56 AM
| Created the project in Bamboo https://bamboo.penske.com/browse/VIGBP | Gayam | 03/02/23 2:19 AM
Row 225 | Secrets: @rajesh.haravde@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:34 AM
Row 225 | Changed status to AO Bamboo | Yvette Urso | 12/15/22 2:56 AM
Row 225 | @krishna.tanga@penske.com can you assist Mathu with the Bamboo Plan for this app? | Yvette Urso | 12/09/22 1:04 AM
Row 226 | @dale.porter@penske.com , You just need to verify whether the bamboo built correctly and jar is deployed to artifactory. This is just a dependency jar and not going to deployed to any server. Thanks. | Gayam | 08/10/23 1:00 AM
| I ran a build and see in Jfrog artifactory the new artifacts "vehicleinformationutility" added. Look good, thank you | Dale Porter | 08/26/23 2:53 AM
| Thanks @dale.porter@penske.com . Closing the app. | Gayam | 08/28/23 10:16 PM
Row 226 | Thanks @dale.porter@penske.com . We will onboard to Bamboo. | Gayam | 07/07/23 10:42 PM
| The jar is onboarded to bamboo and uploaded to artifactory. Following is the dependency. <dependency> <groupId>com.penske.maintenance</groupId> <artifactId>vehicleinformationutility</artifactId> <version>2.0.0-develop-20230710.062023-1</version> </dependency> | Gayam | 07/10/23 11:12 PM
| Hi @praneeth.gayam@penske.com , please let me know if you are waiting on me for update as I am not sure what to do next. thanks | Dale Porter | 08/10/23 12:02 AM
Row 226 | thank you | Dale Porter | 07/17/23 10:58 PM
Row 226 | Review: @stella.george@penske.com / @dave.kost@penske.com , This utility app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/vehicleinformationutility/pull-requests/3/overview | Gayam | 06/24/23 12:22 AM
Row 226 | Review: @Stell | Gayam | 06/24/23 12:22 AM
Row 226 | There are no secrets exist for this application. So changing the status of this app to Cap Maven. | Gayam | 06/23/23 12:14 AM
Row 227 | @sarath.mani@penske.com / @dale.porter@penske.com , I sent a secret file of this app in email. Please verify. | Gayam | 07/25/23 9:34 PM
| Hi, I checked the secrets referenced in the excel file and in the SVN repository. I did not see any issues as no "actual" password or key value secrets security wise are found. You can move forward with the modernization process, thank you. | Dale Porter | 07/28/23 2:49 AM
| Sure @dale.porter@penske.com . thanks. | Gayam | 07/31/23 2:50 AM
Row 227 | Hi all, these changes are not deployed yet to production and I was not sure if I was supposed to merge new changes to the logr4j branch. I know understand that I should not have. Can you please use the last production release like you originally branched from and disregard the changes I checked in as I will have to do a feature Jira tasks once this is moved to bitbucket (git) and then I can have the latest changes merged then. Thank you. | Dale Porter | 07/17/23 7:23 PM
| Thanks @dale.porter@penske.com | Gayam | 07/19/23 1:06 AM
Row 227 | @dale.porter@penske.com , We observed that you committed some of your changes to log4j branch. But this branch is specifically for log4j migration. Are you planning to implement any new application specific changes for this app? Log4j branch: https://svn.penske.com/svn/fieldsys/maintenance/vehicle-information-service/branches/vehicleinfosvc_Log4jChanges/ | Gayam | 07/12/23 2:52 AM
Row 227 | Question: @dale.porter@penske.com , This app is having multiple src folders. We are expecting vehicle-information-service folder is the vehicleinfosvc.war application and the other folder(vehicleInformationUtility) is the dependency jar. SVN location(vehicleinfosvc): https://svn.penske.com/svn/fieldsys/maintenance/vehicle-information-service/tags/prod/1.0_20220809 Bamboo for vehicleInformationUtility. https://bamboo.penske.com/browse/VEHICLEINFO-VICPROD As we are modernizing the application, we have 2 choices for the vehicleInformationUtility fodler. 1. If vehicleInformationUtility is not used by any other application then this folder can be included inside the vehicleinfosvc app's source. It requires work from AO. Or 2. Need to extract the vehicleInformationUtility folder and create separate repo and bamboo build. Use this jar as a dependency in vehicleinfosvc app. It doesn't require work from AO. Please let us know which route you want to take. Thanks. @shane.myers@penske.com | Gayam | 06/13/23 1:58 AM
| @praneeth.gayam@penske.com VehicleInformationUtility.jar is a sharded jar used by different application. you need to go with option#2 | Stella george | 06/14/23 2:01 AM
| Thanks @stella.george@penske.com . I will ask @yvette.urso@penske.com to add one more line item for vehicleInformationUtility | Gayam | 06/14/23 2:18 AM
Row 227 | Confirmed in PC2 and SVN, The last production tag in SVN is https://svn.penske.com/svn/fieldsys/maintenance/vehicle-information-service/tags/prod/1.0_20220809 | Dale Porter | 06/06/23 6:58 AM
| Thanks @dale.porter@penske.com | Gayam | 06/06/23 8:32 AM
Row 227 | @yojando.drullard@penske.com , In bamboo, prod reference to "https://svn.penske.com/svn/fieldsys/maintenance/vehicle-information-service/tags/prod/1.0_20190620" But this path doesn't exist in svn. Could you please help us to find the correct prod reference. | Gayam | 05/10/23 11:12 PM
Row 228 | @praneeth.gayam@penske.com @stella.george@penske.com This is being deployed to PROD tomorrow night (October 3rd, 2023) | David | 10/03/23 3:32 AM
Row 228 | @praneeth.gayam@penske.com so the vendor dvir batch isn't logging and doesn't seem to actually be running after it's deployed. Need to contact architecture or webservices. | David | 08/29/23 2:45 AM
| @david.long@penske.com , i think it is not daemon application which runs always. You may need to trigger manually. | Gayam | 08/30/23 2:31 AM
| @praneeth.gayam@penske.com We are seeing below error when i start batch. same error happens for ServiceNet batch also. [600114230@clelx150ptlge ~]$ sudo -u apps /apps/vendordvir/vendordvir.sh [sudo] password for 600114230: stopping vendordvir [600114230@clelx150ptlge ~]$ log4j:WARN No appenders could be found for logger (com.penske.architecture.batchframework.config.PropertiesConfigurator). log4j:WARN Please initialize the log4j system properly. log4j:WARN See http://logging.apache.org/log4j/1.2/faq.html#noconfig for more info. | Stella george | 09/06/23 1:46 AM
| @stella.george@penske.com , We added a file batchconfig-qa.prop file. Please deploy and check again. | Gayam | 09/07/23 11:58 PM
| @praneeth.gayam@penske.com @stella.george@penske.com When I go to run the batch I still don't see any logs and have no indicator that the batch is actually running... | David | 09/13/23 1:33 AM
Row 228 | @praneeth.gayam@penske.com the logging is incorrect so I just did a quick fix on develop. Testing it out after 5pm qa deploy | David | 08/29/23 1:47 AM
Row 228 | @praneeth.gayam@penske.com build is working and running deploy scripts now. Everything looks good from a build perspective. Will test if the batch works at 5pm. | David | 08/18/23 1:42 AM
| @praneeth.gayam@penske.com I need to build the project again since the threads in the batch need to be turned on individually. I did notice however, that the logs are going to the wrong folder. It looks like there is an extra directory lower than where it should log... I'm seeing for example the path is /apps/logs/vendordvir/vendordvir/rootlog. when it should be /apps/logs/vendordvir/rootlog | David | 08/23/23 8:40 PM
| @praneeth.gayam@penske.com I can confirm the build is working though :) | David | 08/23/23 8:41 PM
Row 228 | Review: @david.long@penske.com / @payel.ganguly@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/MAIN/repos/vendordvir-batch/pull-requests/3/overview | Gayam | 07/21/23 10:55 PM
| @praneeth.gayam@penske.com reviewed and merged :) | David | 08/15/23 6:19 PM
| Thanks @david.long@penske.com . Changed to Cap Bamboo | Gayam | 08/17/23 1:56 AM
| @david.long@penske.com , Bamboo onboarding completed. Please verify https://bamboo.penske.com/browse/VDBP-VENDV0 | Gayam | 08/18/23 12:19 AM
Row 228 | @david.long@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:53 AM
| AO confirmed no changes required for secrets. | Gayam | 06/16/23 10:32 PM
| Thank you for the update @praneeth.gayam@penske.com I am included on this app as one of it's contacts, but as you saw in our email chain for secrets, Stella and her team will be taking care of this mostly. Thanks again :) | David | 06/21/23 7:56 PM
Row 228 | @praneeth.gayam@penske.com Is there any update on this batch? | David | 06/13/23 7:54 PM
| @david.long@penske.com , We have started working on this applciation. | Gayam | 06/14/23 2:50 AM
Row 230 | @praneeth.gayam@penske.com can you create the build and deploy job | Mahipal | 05/30/23 8:05 PM
| @mahipal.podduturi@penske.com , If your review completes, can you merge the code to develop branch. https://bitbucket.penske.com/projects/ARPROJ/repos/bill-apprunner-batch/pull-requests/8/overview | Gayam | 05/31/23 12:59 AM
Row 230 | @mahipal.podduturi@penske.com | Sherin | 05/25/23 8:42 PM
Row 230 | @sherin.basheer@penske.com - This app is available for your final review. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/02/22 5:46 PM
| @sherin.basheer@penske.com , This is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/vendorreg-web/pull-requests/3/overview | Gayam | 03/03/23 1:15 AM
Row 230 | @praneeth.gayam@penske.com - To review Maven changes | Mathumala Nachiappan | 11/23/22 4:02 AM
Row 231 | @rajesh.haravde@penske.com , There is no old bamboo plan for this app. So no existing bamboo project. Do you want us to create a new bamboo project and onboard the plans? | Gayam | 09/26/23 1:39 AM
Row 231 | Maven looks good. we are waiting on bamboo plan to take it forward. | Rajesh | 09/22/23 7:27 PM
| Thanks @rajesh.haravde@penske.com , We will onboard to bamboo and will let you know. | Gayam | 09/22/23 11:31 PM
Row 231 | Praneet, i already added messaged on 8/23, we don't need secret mitigation for this project. please take it to next step without delay. | Rajesh | 09/05/23 8:21 PM
| Sure @rajesh.haravde@penske.com . We already started working on this app. Will change the status. | Gayam | 09/05/23 8:26 PM
| @olukemi.olaewe@penske.com / @rajesh.haravde@penske.com , Modernization is completed on this app. Please verify. https://bitbucket.penske.com/projects/PTLCORP/repos/vfjexcel-batch/pull-requests/3/overview | Gayam | 09/07/23 1:10 AM
Row 231 | Secrets: @venkata.bobba@penske.com , I sent a secret file in the email. Please check and confirm. Thanks | Gayam | 08/30/23 9:26 PM
Row 231 | @praneeth.gayam@penske.com we got current proudction information on this project we will start validation on or before monday. Venakta will reach out to you please guide as and when needed. SVN URL https://svn.penske.com/svn/ecomm/webprojects/vfjexcelupload/branches/dev_gh/vfjexcel/ | Rajesh | 08/23/23 11:00 PM
| Thanks @rajesh.haravde@penske.com . We will wait until @venkata.bobba@penske.com confirms. | Gayam | 08/24/23 3:57 AM
Row 231 | we can't change the status. Capgemini need to take it forward | Narsimhamurthy | 08/23/23 11:05 PM
Row 231 | No Secrea Mitigation NOT needed. | Rajesh | 08/23/23 11:01 PM
Row 231 | We are not supporting this project anymore. it belongs to different team. | Rajesh | 02/10/23 2:59 AM
| @rajesh.haravde@penske.com - Can you share the reference if you have? CC: @yvette.urso@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 02/10/23 11:14 AM
| @yvette.urso@penske.com - As this app belongs to different team, Pls. help us with the new AO for this. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 02/14/23 10:33 AM
| @yvette.urso@penske.com , Rajesh mentioned that this app belongs to a different team. Could you please help us to find the new AO and team details. @balu.mohan@penske.com | Gayam | 02/24/23 1:09 AM
| @rajesh.haravde@penske.com mentioned following in the email. "You can keep that project on my name currently. Here is the svn url information : https://svn.penske.com/svn/ecomm/webprojects/vfjexcelupload/branches/dev_gh/vfjexcel it’s a java batch will get more information in coming days on if we need bamboo, maven and log4j or not. It’s a OLD project, last modification happened in 2019 as per email notes. Let me verify and get back to you on it." So Log4j team is waiting for the confirmation from Rajesh. @yvette.urso@penske.com | Gayam | 02/27/23 11:51 PM
Row 231 | @krishna.tanga@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:36 AM
| @rajesh.haravde@penske.com , Could you please check above comment and provide your response. @mathumala.nachiappan@penske.com | Gayam | 12/16/22 12:21 AM
Row 231 | @praneeth.gayam@penske.com moved status to AO Bamboo | Yvette Urso | 12/15/22 2:56 AM
Row 232 | @praneeth.gayam@penske.com added comment in bitbucket push request | Dylan | 05/03/23 9:18 PM
| @dylan.price@penske.com We will check and provide the response. | Gayam | 05/04/23 12:20 AM
| @dylan.price@penske.com , I responded in the PR. Please check. thanks. | Gayam | 05/06/23 2:58 AM
Row 232 | @venkatesh.hossalinever@penske.com , This app is ready for your review. Please verify in below PR. https://bitbucket.penske.com/projects/ARPROJ/repos/viewpdf-web/pull-requests/3/overview | Gayam | 03/30/23 11:33 PM
Row 232 | Completed reviewing the log4j secrets - there are no coding changes required. | Venkatesh | 02/27/23 10:09 PM
| Thanks @venkatesh.hossalinever@penske.com. Updated the status to (Cap)Maven | Gayam | 02/27/23 11:31 PM
Row 232 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 232 | @dylan.price@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:49 AM
Row 233 | @david.long@penske.com , I see that you have already merged the code to develop branch. But we have an open query in this application. In the ant build, application.properties file is replaced by application.properties.build .This file contains app.version=@DEPLOYMENT_INSTANCE@ and this variable value is injected based on environment. This needs to be corrected to satisfy the environment agnostic build. Please check. Thanks. | Gayam | 09/27/23 1:40 AM
| So Virtual Pay already has been pushed to PROD. I was able to fix this build issue. The app doesn't need the property files anymore, as it's able to get the server environment through a websphere variable. Based on this value, the app is able to set the environment and handle if the user should go through the local test filter or the dlink filter. | David | 10/03/23 3:32 AM
| Thanks @david.long@penske.com | Gayam | 10/04/23 1:49 AM
Row 233 | @shane.myers@penske.com | Yvette Urso | 09/25/23 10:51 PM
| @praneeth.gayam@penske.com please verify the mavenization was completed successfully - once you confirm, I will investigate further. | William | 09/25/23 10:57 PM
Row 233 | @yvette.urso@penske.com @praneeth.gayam@penske.com I'm currently running into issues with Virtual Pay. It seems whenever someone tries to access it, it goes to the test auth filter instead of the dlinks filter. I compared the project to sos-web and other web apps and virtual pay doesn't have any configurations like them when starting up the app...this was "mavenized" but I still see ant build things in the app, so I question if this is actually done. | David | 09/25/23 10:39 PM
| Hi David. Shane and Praneeth should be able to direct you technically. | Yvette Urso | 09/25/23 10:51 PM
Row 233 | @david.long@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/virtualpay-web/pull-requests/3/overview | Gayam | 07/07/23 1:16 AM
| @praneeth.gayam@penske.com merged! :) | David | 07/11/23 1:29 AM
| @david.long@penske.com , onboarded to bamboo and deployed to dev. Please verify. Deployment link: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151192149 build & Deploy plan: https://bamboo.penske.com/browse/VIR-VIRPW | Gayam | 07/13/23 1:04 AM
| @praneeth.gayam@penske.com my apologies on this. Will try to validate that today. | David | 08/23/23 8:41 PM
| @praneeth.gayam@penske.com I am building qa for the 2pm deploy window. However I think I'm not in the correct group to update the build plan, because I can't seem to be able to configure the virtual pay build plan and look at values | David | 08/23/23 9:00 PM
| @praneeth.gayam@penske.com Virtual Pay is working on QA | David | 08/24/23 1:35 AM
| Thanks @david.long@penske.com | Gayam | 08/24/23 3:54 AM
Row 233 | @david.long@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:53 AM
| AO confirmed that all secrets are false positives. No code changes required. | Gayam | 06/16/23 1:14 AM
Row 233 | @praneeth.gayam@penske.com I believe that wsdl can be removed from the project. | David | 06/06/23 10:31 PM
| @david.long@penske.com , We will remove that wsdl and let you know whether we are facing any problems. Thanks. | Gayam | 06/07/23 3:39 AM
Row 233 | @david.long@penske.com , We are facing following issue in this app. Could you please check. Thank you. The application having error in one file under conf folder - AccessOnlineWebServices.wsdl . Its look like application error. Error message : - The part 'userNameToken' has an invalid value 'userNameToken' defined for its element. Element declarations must refer to valid values defined in a schema. | Gayam | 05/25/23 3:26 AM
Row 233 | @David | Gayam | 05/25/23 3:25 AM
Row 234 | @praneeth.gayam@penske.com After the web.xml update, the logging is working in DEV & QA. Attached the screenshot. | Vaddi Mani | 09/26/23 7:05 AM
| Thanks @sarath.mani@penske.com . We have deployed the latest code. | Gayam | 09/27/23 12:39 AM
Row 234 | @praneeth.gayam@penske.com Give us update on this | Stella george | 09/23/23 2:14 AM
| @stella.george@penske.com , we will check and get back to you. | Gayam | 09/23/23 2:33 AM
Row 234 | Logging is not working in both DEV & QA. Please look at the web.xml file, it's still pointing to old log4j reference. Please update the web.xml and let me know and I will test both in DEV & QA environments. Thanks. | Vaddi Mani | 09/23/23 12:58 AM
Row 234 | Latest file is copied to DEV. But, the logging is not working. Looks like in web.xml, it's still pointing to old log4j. | Vaddi Mani | 09/05/23 8:40 PM
Row 234 | Checking now. | Vaddi Mani | 09/05/23 7:44 PM
Row 234 | Deployed to DEV and I still see the old file. Attached the screenshot. | Vaddi Mani | 09/01/23 2:39 AM
| @sarath.mani@penske.com , We fixed the issue. Now dev server showing latest files. | Gayam | 09/02/23 5:17 AM
Row 234 | Working on it. | Vaddi Mani | 09/01/23 2:07 AM
Row 234 | @sarath.mani@penske.com , Build and Deploy plans are onboarded and deployment to artifactory is successful. plan onboarding is also successful. Dev deployment completed. Please verify. Thanks. Build plan: https://bamboo.penske.com/browse/VOICEPMSVC-VOICPMABLD0 Deploy Plan: https://bamboo.penske.com/browse/VOICEPMSVC-VOICPMABLD/deployments | Gayam | 08/03/23 12:47 AM
Row 234 | @stella.george@penske.com / @sarath.mani@penske.com , This app is ready for your review. Please verify and merge. Thanks. https://bitbucket.penske.com/projects/MAIN/repos/voicepmsvc/pull-requests/3/overview | Gayam | 07/20/23 11:17 PM
| I reviewed and merged the code. Thank you. | Vaddi Mani | 07/28/23 2:04 AM
| Will onboard to bamboo and deploy to dev. | Gayam | 07/31/23 2:37 AM
Row 234 | @praneeth.gayam@penske.com I didn't get any email yet. | Vaddi Mani | 06/15/23 10:28 PM
| Just sent now. Please check | Gayam | 06/16/23 1:46 AM
| AO confirmed no changes required for secrets. | Gayam | 06/16/23 10:32 PM
Row 234 | @stella.george@penske.com / @sarath.mani@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:54 AM
Row 235 | @venkatesh.hossalinever@penske.com , As requested we onboarded the app to bamboo. https://bamboo.penske.com/browse/WAMB-WAMBA But please look into the open quesiton asked above. I believe app will not work properly without resolving that issue. Thanks. | Gayam | 09/27/23 12:44 AM
Row 235 | @praneeth.gayam@penske.com Please deploy the maven/log4j changes on QA and let us know. we will validate and confirm. Note: There is no dev environment for batch application. | Venkatesh | 09/25/23 11:10 PM
| @venkatesh.hossalinever@penske.com , Did you update the code to resolve the query asked above? If not, application will not run properly. | Gayam | 09/26/23 1:03 AM
Row 235 | Review & Question: @dylan.price@penske.com , this app is completed. Please check. https://bitbucket.penske.com/projects/PB/repos/wambea-batch/pull-requests/3/overview Question: jdbc configuration mentioned in applicationcationcotext.xml have different properties depends on environment. All these values are mentioned in different environment properties file. Currently, the build is environment dependendent but after modernization it is going to be environment agnostic. Could you please check this issue and modiy the code accordingly. Thanks. | Gayam | 09/12/23 12:03 AM
Row 235 | Hi @praneeth.gayam@penske.com this is also in the BillingUtility jar that was mentioned in the cmns application. I believe we should build BillingUtility out into its own application so we can deploy into Artifactory. Could you please set that up? We will then use that jar for this application. Thank you! | Dylan | 06/13/23 7:59 PM
| Thanks @dylan.price@penske.com . Can we take the source code of billingutility from below folder. https://svn.penske.com/svn/fieldsys/other/billing-service/trunk/BillingUtility | Gayam | 06/14/23 2:54 AM
| Hi @praneeth.gayam@penske.com yes that location looks great | Dylan | 06/14/23 5:17 PM
| sure @dylan.price@penske.com | Gayam | 06/15/23 12:48 AM
Row 235 | @manish.sisodiya@penske.com , we are experiencing following issue in this app. We are getting errors in below import statements. import com.penske.cns.maintenance.exceptions.EmailNotSentException; import com.penske.cns.maintenance.services.CustomerNotificationService; We couldn't find the dependent jar for these errors in ptlcommon or project's library. Could you please help us to find the correct jar | Gayam | 03/10/23 11:36 PM
Row 235 | please use the url https://svn.penske.com/svn/fieldsys/other/customer-rolodex-service/tags/prod/1.0.3_20140806/Wambea/src/ as the source for this application | Dylan | 03/07/23 2:09 AM
Row 235 | @sam.skelding@penske.com / @manish.sisodiya@penske.com , This applications in SVN contains multiple src folders. Ideally each application should have only 1 src folder. Could you please check and clarify us. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 1:31 AM
Row 236 | all environments we no need the database.propeties | Mahipal | 09/12/23 10:49 PM
| Yes @mahipal.podduturi@penske.com . But in agnostic build these should be handled in a way that 1 build can satisfy all the environments. | Gayam | 09/13/23 1:05 AM
Row 236 | Q2 Ans: use QA for now but we need to check how to implement to get the Prod based on the environment | Mahipal | 05/25/23 10:49 PM
| Thanks @mahipal.podduturi@penske.com . What about 3rd? | Gayam | 05/25/23 11:57 PM
Row 236 | @praneeth.gayam@penske.com Q1 Ans: yes no dev for batch | Mahipal | 05/25/23 10:47 PM
Row 236 | @praneeth.gayam@penske.com | Mahipal | 05/25/23 10:46 PM
Row 236 | @mahipal.podduturi@penske.com , We have following queries on this app. Q1:This application have the dev folder in the targeted folder. But this is a batch app and batch apps do not have dev environment.Could you please clarify this. Q2: In the settings.xml there is email.properties and settings.properties configured. But all 3 environment folders under targeted folder have these 2 files. Which one we need to use? Q3: In all the environment folders under targeted folder we have settings.properties which have database.properties config. But we have databse.properties only in dev folder. Please confirm whether we can use this database.proprties file for all environments? | Gayam | 05/25/23 2:59 AM
Row 236 | @praneeth.gayam@penske.com I am not seeing develop branch https://bamboo.penske.com/browse/BUILWLSDEV-WCHLT | Mahipal | 05/17/23 1:58 AM
| @mahipal.podduturi@penske.com , We will onboard develop branch to Bamboo and will let you know. In the mean time could you please review and merge below PR. https://bitbucket.penske.com/projects/WL/repos/watchlistbatch/pull-requests/9/overview This is recent change as per Hugo's suggestions, log4j2 scope should be compile. | Gayam | 05/17/23 2:05 AM
| @mahipal.podduturi@penske.com , Onboarding develop branch to bamboo is completed. | Gayam | 05/18/23 12:42 AM
Row 236 | @mahipal.podduturi@penske.com , This app is onboarded to bamboo. Please deploy to QA and verify. Thanks. https://bamboo.penske.com/browse/BUILWLSDEV-WCHLT0/deployments | Gayam | 03/30/23 12:50 AM
Row 236 | @praneeth.gayam@penske.com yes you can start the next step | Mahipal | 03/09/23 1:03 AM
Row 236 | @david.w.graf@penske.com , the new bamboo plans not yet on boarded. Once AO reviews the changes and provides the approval for the changes then we are going for the next step which is Bamboo onboarding and build. @mahipal.podduturi@penske.com , It looks like you already completed the review, so can we go for the next step? | Gayam | 03/04/23 12:15 AM
Row 236 | I don't see any builds. Are we sure we should have merged that? | David Graf | 03/03/23 8:30 PM
Row 236 | reviewed the PR and merged | Mahipal | 03/03/23 7:45 PM
Row 236 | @shane.myers@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/WL/repos/watchlistbatch/pull-requests/4/overview | Gayam | 03/03/23 1:19 AM
Row 236 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:31 AM
Row 236 | @shane.myers@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:03 AM
Row 237 | @praneeth.gayam@penske.com I have checked develop branch . i am not seen any rest changes you can create and Merage log4j changes | Mahipal | 10/10/23 10:54 PM
| @mahipal.podduturi@penske.com , there are several commits in 2022 in develop branch. But master doesn't have these commits. Are these deployed to production? Do you want us to work on top of develop branch? Currently we created develop_log4j branch from master. | Gayam | 10/11/23 1:11 AM
Row 237 | @praneeth.gayam@penske.com changes looks good to me. Please proceed for further steps.Thanks! | Sama | 03/25/23 12:57 AM
| Thanks @bhagya.sama@penske.com . @mahipal.podduturi@penske.com , I am seeing that you are doing some changes in develop branch. But we did the log4j and maven changes in develop_log4j branch which is created from master branch. But we can't merge to master unless it is deployed to production. So to verify the changes we have to merge to develop branch. But develop have your changes. So could you please change develop branch name to related to your changes. So that I will create a develop branch from master and merge log4j changes to develop. | Gayam | 03/27/23 11:47 PM
Row 237 | Sure @david.w.graf@penske.com . Maven chagnes also completed on this app. Please review https://bitbucket.penske.com/projects/WL/repos/watchlistservice/pull-requests/37/overview | Gayam | 03/02/23 1:37 AM
Row 237 | can we consider the secrets step finished and move to Maven step? | David Graf | 03/01/23 7:47 PM
Row 237 | It is odd how I don't see the value in SVN either. I guess there are no secrets then but I'm not sure where that row came from. | David Graf | 02/24/23 2:36 AM
| I believe this secret from commit history. That is the reason we are unable see the mentioned secret in the current branch. | Gayam | 02/25/23 12:49 AM
Row 237 | I found a Bitbucket Repo for watchlistsvc.war. I'm not sure which is correct but the Bitbucket repo does not have the secret. Can you compare the two repos and try to figure out which one was used for the last prod deploy? https://bitbucket.penske.com/projects/WL/repos/watchlistservice/browse | David Graf | 02/24/23 2:28 AM
Row 237 | @david.w.graf@penske.com - In secret scanning, one entry with hardcoded credential is found. Pls. check it for redaction. CC: @praneeth.gayam@penske.com @yvette.urso@penske.com - Pls. update the AO as David | Mathumala Nachiappan | 12/08/22 7:49 PM
Row 237 | @yvette.urso@penske.com - New app Owner is @david.w.graf@penske.com . Pls. update. @david.w.graf@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:06 AM
Row 238 | @praneeth.gayam@penske.com We can see the logs successfully after adding policy to RolingFile configuration(PURGEFILE & MFCFILE). What is the need of old log4j.xml, this is not required looks like. Please confirm are these changes proper? | Venkatesh | 09/30/23 1:01 AM
| We don't need to keep the old log4j.xml. But as per the recommendation from the starting of the project and for back up purpose, we are keeping old log4j.xml | Gayam | 10/03/23 1:09 AM
Row 238 | @praneeth.gayam@penske.com we are still getting the same errors ERROR StatusConsoleListener The parameter is null: policy ERROR StatusConsoleListener Could not create plugin of type class org.apache.logging.log4j.core.appender.RollingFileAppender for element RollingFile org.apache.logging.log4j.core.config.ConfigurationException: Arguments given for element RollingFile are invalid: field 'policy' has invalid value 'null' can you please look into it. cc: @prashant.prabhakar@penske.com | Venkatesh | 09/29/23 2:28 AM
Row 238 | @venkatesh.hossalinever@penske.com , We made some modifications to resolve the above mentioned issue in develop_log4j branch. Please check. Thanks | Gayam | 09/27/23 12:59 AM
| @venkatesh.hossalinever@penske.com , Onboarded develop_log4j to bamboo - https://bamboo.penske.com/browse/WBMUSERNOTIFIERBP-WBMUSERB1/deployments | Gayam | 09/28/23 12:56 AM
Row 238 | @praneeth.gayam@penske.com Please deploy the maven/log4j changes on QA and let us know. we will validate and confirm. Note: There is no dev environment for batch application. | Venkatesh | 09/25/23 11:10 PM
Row 238 | @praneeth.gayam@penske.com Please confirm is this the correct dependency . <dependency> <groupId>org.apache.logging.log4j</groupId> <artifactId>log4j-slf4j-impl</artifactId> <version>${log4j2-version}</version> <scope>${log4j2-scope}</scope> </dependency> After updating artifact ID to log4j-slf4j2-impl. we are getting the error ERROR StatusConsoleListener The parameter is null: policy ERROR StatusConsoleListener Could not create plugin of type class org.apache.logging.log4j.core.appender.RollingFileAppender for element RollingFile org.apache.logging.log4j.core.config.ConfigurationException: Arguments given for element RollingFile are invalid: field 'policy' has invalid value 'null' cc: @prashant.prabhakar@penske.com | Venkatesh | 09/21/23 2:17 AM
| @venkatesh.hossalinever@penske.com , we will check and get back to you. | Gayam | 09/21/23 4:02 AM
Row 238 | @praneeth.gayam@penske.com Can you please use the production branch and integrate the changes. SVN code base: https://svn.penske.com/svn/webprojects/admin/mileagereporting/wbmusernotifier/branches/dev_gh_log4j2 | Venkatesh | 08/23/23 2:23 AM
| @venkatesh.hossalinever@penske.com , Do you want us to ignore all the previous changes and start modernizing on top of above mentioned branch? | Gayam | 08/24/23 3:40 AM
| hi @praneeth.gayam@penske.com yes please. We will retrofit our changes on top of your log4j2/maven changes | Dylan | 08/24/23 9:41 PM
| @dylan.price@penske.com , Modernization is completed for this app. https://bitbucket.penske.com/projects/PB/repos/wbmusernotifier-batch/pull-requests/3/overview Please review. Also, we have a query on this app. Applciationcontext.xml is different for both prod and qa. That is the reason we did not delete those files. It should be rectified to satisfy the environment agnostic build. Thanks. | Gayam | 09/12/23 12:40 AM
Row 238 | Hi @praneeth.gayam@penske.com, can you please prcoeed with log4j migration and use the following source code. https://svn.penske.com/svn/webprojects/admin/mileagereporting/wbmusernotifier/branches/dev_gh | Venkatesh | 08/03/23 12:55 AM
| @venkatesh.hossalinever@penske.com , Do you want us to ignore the changes which we have completed previously and start from above source code again? | Gayam | 08/04/23 1:00 AM
Row 238 | Review: @venkatesh.hossalinever@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/wbmusernotifier-batch/pull-requests/3/overview | Gayam | 03/04/23 1:21 AM
Row 238 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 2:03 AM
| Thanks you. Changed the status to Cap Maven | Gayam | 03/02/23 1:59 AM
Row 238 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 238 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:55 AM
Row 239 | @praneeth.gayam@penske.com We see some pull request today, But log4j changes has been already deployed to production successfully. cc: @mark.weaver@penske.com | Venkatesh | 10/04/23 9:57 PM
| @venkatesh.hossalinever@penske.com , it is deployed from develop_log4j branch. Because still the above PR is open and code is not merged to develop branch. | Gayam | 10/05/23 1:23 AM
Row 239 | @praneeth.gayam@penske.com Any update on log4j changes, can you please share it soon. | Venkatesh | 09/14/23 8:37 PM
| @venkatesh.hossalinever@penske.com , Please review the PR https://bitbucket.penske.com/projects/PB/repos/webmileagesvc/pull-requests/3/overview | Gayam | 09/15/23 7:25 AM
Row 239 | @praneeth.gayam@penske.com Can you please start the log4j migration. Use the following SVN code base. https://svn.penske.com/svn/webprojects/admin/webmileagesvc/branches/dev_gh_log4j2 cc: @mark.weaver@penske.com | Venkatesh | 08/24/23 1:45 AM
| Thanks @venkatesh.hossalinever@penske.com | Gayam | 08/24/23 4:02 AM
Row 239 | please modernize this jar, and add it into artifactory. thank you! also, i do not see any secrets files that need updated. | Dylan | 03/07/23 2:12 AM
| @dylan.price@penske.com Thanks for your response on secrets. Could you please also provide the response for the question asked above. | Gayam | 03/07/23 6:19 AM
| We are working on the changes on this application, please wait for sometime. | Venkatesh | 03/24/23 8:56 PM
Row 239 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 239 | @mark.weaver@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:56 AM
Row 239 | Question: @rafiq.melath@penske.com / @mark.weaver@penske.com , Following things are we observed in this application. Please check and provide your response. The lib folder contains following jars. servicenetsvc-client.jar serviceRequestUtility.jar. While mavanizing it build is getting successful with out adding these dependencies into pom. Let us know whether we need add these dependencies. If yes, serviceRequestUtility.jar is available in artifactory. So, we can add this dependency. But servicenetsvc-client.jar is not available in artifactory. Please let us know whether we can upload this jar into artifactory. Also we found the bamboo build plan for this jar. The link for this jar is https://bamboo.penske.com/browse/SVCN-SNSVCPROD . Please check it and let us know whether we need to modernize and upload to artifactory. Thanks. @mathumala.nachiappan@penske.com | Gayam | 12/17/22 2:15 AM
Row 240 | WRP was successfully deployed last Thursday and the Oracle HR changes completed the deploy testing and signoff. Thanks for everyone's help. CC: @praneeth.gayam@penske.com | David Graf | 08/25/23 6:00 AM
| Thanks @david.w.graf@penske.com for the update. | Gayam | 08/26/23 12:57 AM
Row 240 | This app is scheduled to be deployed on 8/24 and by Friday we should have signoff that the application has completed modernization. | David Graf | 08/23/23 8:17 PM
Row 240 | @praneeth.gayam@penske.com Please ignore last message. I had a mistyped password during the last attempt. Just confirmed that the webrptportal.war is on the var/tmp in prod batch box. It is working. | David Graf | 08/16/23 10:52 PM
Row 240 | @praneeth.gayam@penske.com Still couldn't get the prod build to be successful: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151198338 although maybe it is a different issue. | David Graf | 08/16/23 9:45 PM
Row 240 | We ran into an issue when running the PROD deploy. Please investigate: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151197905 @praneeth.gayam@penske.com | David Graf | 08/12/23 2:18 AM
| @david.w.graf@penske.com , My team analyzed and compared with all other prod builds. They found that the branch which you used to create the snapshot version is missing in the bamboo. That is the reason prod build is failing. They onboarded that branch. Plese check now. Thanks. | Gayam | 08/16/23 6:51 PM
Row 240 | we confirm that QA deploy was successful. | David Graf | 04/06/23 5:21 PM
Row 240 | Confirming that artifact is in Artifactory and then announcing a QA deploy. | David Graf | 03/17/23 5:44 PM
Row 240 | Dev deploy is confirmed with develop_log4j branch | David Graf | 03/17/23 5:23 PM
Row 240 | yes please deploy to dev environment | David Graf | 03/09/23 6:23 PM
Row 240 | Maven and log4j changes have been confirmed. Moving this app to the next step which is Bamboo. | David Graf | 02/28/23 6:29 PM
| Thanks @david.w.graf@penske.com . We will let you know once we onbaord the app to Bamboo | Gayam | 02/28/23 11:45 PM
| @david.w.graf@penske.com , We onboarded the app to Bamboo. https://bamboo.penske.com/browse/WRP-WEBRP Can we deploy to Dev? | Gayam | 03/02/23 2:17 AM
Row 240 | I am assigning Amit, from WRP development team, to start the review. | David Graf | 02/22/23 7:25 PM
Row 240 | @david.w.graf@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:07 AM
Row 241 | App deployed to PROD on 09/19/2023 | Sreekanth | 09/20/23 6:24 PM
Row 241 | Deployment: @sreekanth.kancharla@penske.com , Dev deployment is completed for this app. Please check. | Gayam | 03/17/23 2:49 AM
| @sreekanth.kancharla@penske.com , Please merge https://bitbucket.penske.com/projects/ITFIS/repos/wje-web/pull-requests/5/diff#pom.xml The changes are for making log4j2 scope to compile. Thank you. | Gayam | 05/30/23 8:58 AM
| @praneeth.gayam@penske.com Merge completed. | Sreekanth | 06/01/23 12:09 AM
| Thanks @sreekanth.kancharla@penske.com . Build is already completed | Gayam | 06/01/23 10:44 PM
Row 241 | Review: @sreekanth.kancharla@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ITFIS/repos/wje-web/pull-requests/3/overview | Gayam | 03/09/23 1:19 AM
| @praneeth.gayam@penske.com PR is merged. Please proceed with further steps. | Sreekanth | 03/13/23 10:19 PM
| Thanks @sreekanth.kancharla@penske.com . We will onboard the app to Bamboo. | Gayam | 03/13/23 11:03 PM
Row 241 | Secrets: @sreekanth.kancharla@penske.com / @kalrav.khamar@penske.com / @james.minisce@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/24/23 1:57 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/24/23 2:37 AM
| Thanks @sreekanth.kancharla@penske.com . Changing the status to (Cap)Maven | Gayam | 02/25/23 12:19 AM
Row 241 | @sreekanth.kancharla@penske.com , In this app, same db.prop file exist in dev and prod folders under targeted folder but different db.prop file exist for QA. Could you please check and clarify us. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/wje-web/browse?at=develop_log4J | Gayam | 02/14/23 12:44 AM
| @praneeth.gayam@penske.com The difference in QA is not required as the hard coded credentials are removed from prod file itself. Please keep the same db.prop for QA as well. Since there is no change between dev & prod specific files and we are going to keep the qa also the same. With this, hope we don't need to maintain this file in targeted folder at all. | Sreekanth | 02/15/23 3:03 AM
| @praneeth.gayam@penske.com Sreekanth has replied to you. Can you change the 'App Status'? | Kalrav | 02/18/23 12:43 AM
| Thanks @kalrav.khamar@penske.com . Changing the status (Cap)Log4j | Gayam | 02/18/23 12:59 AM
Row 241 | @sreekanth.kancharla@penske.com Can you address the app logger replacement query? Thank you. | James | 12/15/22 2:19 AM
| @sreekanth.kancharla@penske.com Did you address the app logger replacement question from 12/09? I think this is still outstanding. | James | 01/25/23 2:22 AM
| @james.minisce@penske.com I've replied already on 12/14. No further questions from the team. | Sreekanth | 01/25/23 7:00 AM
Row 241 | @james.minisce@penske.com - errors on fileappender configuration. @praneeth.gayam@penske.com to follow up | Mathumala Nachiappan | 12/01/22 8:47 PM
| Please be specific as to what you need from me to remove this block. | James | 12/09/22 5:52 PM
| @james.minisce@penske.com , in this app, logger classes are getting created with custom configuration using fileappender(getallappender) and simplelayout . Not able to configure using the slf4j and log4j2. providing link for class file. https://svn.penske.com/svn/webprojects/admin/wje/trunk/wje_prod/JavaSource/com/penske/ebus/journal/filter/DummySecurityFilter.java Could you please check whether these logger classes can be replaced. As we don't have enough info of athe application we can't modify other than what requested. @mathumala.nachiappan@penske.com | Gayam | 12/10/22 12:45 AM
| @praneeth.gayam@penske.com DummySecurityFilter.java is used only for DEV application. I do see in other class files also, the custom logger is implemented. This application is very old application. If these can be replaced with slf4j & log4j2, we are good. Please proceed with changes. | Sreekanth | 12/15/22 3:18 AM
Row 241 | Changed Status | Yvette Urso | 12/15/22 2:19 AM
Row 242 | @praneeth.gayam@penske.com PR looks good can start the next steps | Mahipal | 03/22/23 9:17 AM
| @mahipal.podduturi@penske.com , PR is still in open status. Could you please lerge. https://bitbucket.penske.com/projects/WL/repos/watchlistweb/pull-requests/17/overview | Gayam | 05/22/23 11:51 PM
Row 242 | @mahipal.podduturi@penske.com , this app is onboarded to Bamboo. Please check and let us know whether you are ok to deploy to Dev? | Gayam | 03/23/23 11:07 PM
Row 242 | https://bitbucket.penske.com/projects/WL/repos/watchlistweb/pull-requests/17/diff#pom.xml | Mahipal | 03/15/23 6:45 PM
| Sure @mahipal.podduturi@penske.com . We will check and fix them | Gayam | 03/15/23 11:38 PM
| @mahipal.podduturi@penske.com , We implemented the changes. Could you please check. Thanks. | Gayam | 03/21/23 1:40 AM
Row 242 | @praneeth.gayam@penske.com update the POM with comments | Mahipal | 03/15/23 6:45 PM
Row 242 | Maven Review: @shane.myers@penske.com , We have completed the modernization work on this application. Could you please review in the below PR and provide your approval for the next step. https://bitbucket.penske.com/projects/WL/repos/watchlistweb/pull-requests/17/overview Thanks. | Gayam | 03/01/23 12:19 AM
Row 242 | @shane.myers@penske.com, We completed the secrets scanning for this application and in my team's analyzation all are false positives. But could you please check them and confirm. I will send the sheet in the email. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 3:09 AM
| Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:32 AM
Row 243 | I'm changing the status to Major Blocker. This action cannot move forward until thdpaymentsvc goes through Security Modernization. We stopped before deploying into the dev environment. | David Graf | 06/06/23 12:54 AM
Row 243 | nvm, the log4j changes are already in develop so I completed the merge. | David Graf | 06/06/23 12:52 AM
Row 243 | the target is the develop branch but we aren't merging there yet. Please advise. | David Graf | 06/06/23 12:50 AM
Row 243 | @david.w.graf@penske.com , Changed the scope of log4j2 jars from provided to compile. Could you please merge the code. https://bitbucket.penske.com/projects/AC/repos/ws-authorizationfilter/pull-requests/8/overview | Gayam | 05/24/23 2:29 AM
Row 243 | I just noticed that the bitbucket repo is in Architecture-Project but since this repo is for a shared library jar it should reside in Architecture-Commons. Pleas advise: @praneeth.gayam@penske.com | David Graf | 04/28/23 8:00 PM
| Sure @david.w.graf@penske.com . We will push to commons. | Gayam | 04/29/23 1:49 AM
| @david.w.graf@penske.com , this app is moved from Architecture-Project to Architecture-Commons and corresponding Bamboo plans also changed. | Gayam | 05/04/23 12:01 AM
Row 243 | @david.w.graf@penske.com , This app is deployed to ptlcommon_1 folder in dev region. Please check. Thanks. https://bamboo.penske.com/browse/WBPA-WSAUTHZ0/deployments | Gayam | 03/30/23 1:02 AM
Row 243 | @praneeth.gayam@penske.com did you get your answer from Hugo? | David Graf | 03/24/23 5:19 PM
| @david.w.graf@penske.com , if we keep the instanceType variable as shared in bamboo script then app will be deployed to ptlcommon folder. We started working on onboarding to Bamboo. | Gayam | 03/24/23 5:44 PM
| Thanks | David Graf | 03/27/23 7:03 PM
Row 243 | To help with clarifications 1) All WARs, JAR, EAR builds use artifactory as their binary repository. The result of these builds is uploaded to artifactory. 2) Some "JARs" are shared within or amongst teams. This way, teams do not copy JARs but add them to their maven dependency. There is nothing special in artifactory to denote these as shared. 3) Then a subset of these JARs are copied to ./ptlcommmon_1 on each WAS and BATCH server that IBM has called "SHAREDLIBS." Some JARs are third-party, like log4j, and some are Penske proprietary, like reuse. Unfortunately, these JARs do not have the version number as part of the filename, which is the maven standard. But that is another problem. These JARs have an additional deployment step beyond artifactory which is to deploy to the shared library (aka ../ptlcommon_1) directory. See dlinks authentication and reuse for examples. HAppy to discuss more | Hugo Scavino | 03/21/23 6:31 PM
| So @hugo.scavino@penske.com , is webservices script going to deploy to ./ptlcommmon_1 if we provide the instanceType variable value as 'shared' in Bamboo? | Gayam | 03/22/23 12:15 AM
Row 243 | @david.w.graf@penske.com , Shared Library jar means, is it needs to upload only to antifactory? | Gayam | 03/21/23 1:28 AM
| @hugo.scavino@penske.com please straighten out this confusion around the term Shared Library. CC: @yvette.urso@penske.com Shared Library jars are deployed to WebSphere instances and so they are not bundled with application war. That means there need to be a deployment task for each environment (DEV, QA, and PROD) | David Graf | 03/21/23 4:43 AM
Row 243 | @praneeth.gayam@penske.com please see my last message. | David Graf | 03/20/23 5:21 PM
Row 243 | please revisit the bamboo template, this is a Shared Library jar and needs deployments to the environment. | David Graf | 03/17/23 5:46 PM
Row 243 | Confirming that artifact is in Artifactory and then announcing a QA deploy. | David Graf | 03/16/23 5:25 PM
| ignore this for ws_auth it was meant for wrp. | David Graf | 03/17/23 5:44 PM
Row 243 | @david.w.graf@penske.com , Log4j team is not supposed to do the QA deployment as per the instructions from Hugo. AO needs to do the QA deployment. So changed the status to AO QA Deploy/Test. Thank you. | Gayam | 03/17/23 3:06 AM
Row 243 | Dev environment confirmed. | David Graf | 03/16/23 5:26 PM
Row 243 | @hugo.scavino@penske.com / @david.w.graf@penske.com , this is onbaorded to Bamboo. https://bamboo.penske.com/browse/WBPA-WSAUTHZ Please run the develop branch to deploy the artifacts to artifactory | Gayam | 03/02/23 2:18 AM
Row 243 | Ankita confirmed the Maven and now we are moving to the Bamboo stage. | David Graf | 02/24/23 6:27 PM
Row 243 | https://bitbucket.penske.com/projects/ARPROJ/repos/ws-authorizationfilter/browse/src/main/filters/com/penske/ws/filter/WSAuthorizationFilter.java?at=refs%2Fheads%2Fdevelop_log4j | Hugo Scavino | 01/31/23 10:01 PM
Row 243 | This project is a single filter. This will require a single unit test and then ultimate promotion to artifactory. | Hugo Scavino | 01/31/23 10:01 PM
Row 243 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:28 AM
Row 243 | @hugo.scavino@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:20 AM
Sheet | @praneeth.gayam@penske.com Please use the folder with bodyshop6 | Subramanian | 06/15/23 1:25 AM

## Summary
Capgemini App Summary | Capgemini Migration
Field 2 | 2023-02-01
Total Apps Not Started | 0
Total Apps Capgemini is Working on | 32
Total Apps AO is Working on | 109
Grand Total of All Apps/All Status Levels | 243
Total Apps Done | 58
Total Apps Retire/Duplicate | 44
Billing - Not Started | 0
Billing - Total In Progress | 34
Billing - Done | 7
Billing - Retire/Duplicate | 11
Finance & Biz Auto - Not Started | 0
Finance & Biz Auto - Total In Progress | 4
Finance & Biz Auto - Done | 18
Finance & Biz Auto - Retire/Duplicate | 4
Architect - Not Started | 0
Architect - Total In Progress | 40
Architect - Done | 12
Architect - Retire/Duplicate | 9
Fleet Services - Not Started | 0
Fleet Services - Total In Progress | 10
Fleet Services - Done | 12
Fleet Services - Retire/Duplicate | 3
Cust Digital Engineer - Not Started | 0
Cust Digital Engineer - Total In Progress | 21
Cust Digital Engineer - Done | 0
Cust Digital Engineer - Retire/Duplicate | 10
HR - Not Started | 0
HR - Total In Progress | 5
HR - Done | 0
HR - Retire/Duplicate | 0
Web - Not Started | 0
Web - Total In Progress | 1
Web - Done | 0
Web - Retire/Duplicate | 2
Maintenance - Not Started | 0
Maintenance - Total In Progress | 26
Maintenance - Done | 9
Maintenance - Retire/Duplicate | 3
Savvion - Retire/Duplicate | 1
Security - Retire/Duplicate | 1
Oldest AO Waiting Date | 50.4
Blank | \
Total In Progress | 141