## Capgemini Migration - Java Sec
Health | Redeploy w/log4j2 Complete? | Original Scope | Redeploy Needed? | Application | Dependency | App Status | App Group | Department Directors | AO Manager | AO Assigned | AO Assigned Email | File Total Count | Bamboo JDK8 Compliant? | Log4j? | Secrets? | Bamboo Plan is Java v1.8? REQUIRED (AO) | Bamboo? | BitBucket? | Maven? | Module (Not Confirmed) | Cap Contacts | Project Completion Date | CAP Migration (y/n) | Start Date for Major Blocker | Start Date for Waiting On AO | Start Date for (AO) Log4J | Start Date of (AO) Secrets Mitigation | Start Date for (AO) BitBucket | Start Date for (AO) Maven | Start Date for (AO) Bamboo | Start Date for (AO) QA Deploy | Start Date for (AO) App Deployed
|  | No |  | 24x7custnotif |  | Waiting on AO | Maintenance | David Kost | Patel-Falgun | Long-David, Patel-Falgun | David, Patel | [13 empty] | 2023-07-20
|  | No |  | vehicleInformationUtility.jar | vehicleinfosvc,football.war depend on this utility. | 5.2 (AO)Bamboo Review | Maintenance | David Kost |  | George-Stella | Dale Porter, Vaddi Mani | [17 empty] | 2023-06-23 | 2023-07-10
|  | No |  | serviceRequestUtility.jar | Servicereqsvc,war, edvir.war, servicereqbatch, servicereqweb, webmileagesvc.war and unitjkt.war are depends on this utility | 4.2 (AO)Maven | Maintenance | David Kost |  | George-Stella | Stella george, Subramanian | [15 empty] | 2023-06-27 |  | 2023-07-06
Green |  | Yes | No | ach.war |  | 6.2 (AO)QA Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 131 |  | Needed | Not Needed |  | Needed | Needed | Needed | Customer File | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [6 empty] | 2023-03-30
Green |  | Yes | No | achbatch |  | 6.2 (AO)QA Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 44 |  | Needed | Not Needed |  | Needed | Needed | Needed | Cash Application | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-02-06 | Yes - Capgemini | [5 empty] | 2023-03-01 | 2023-03-29
Green |  | Yes | No | achsvc.war |  | 6.2 (AO)QA Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 26 |  | Needed | Not Needed |  | Needed | Needed | Needed | Customer File | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | b2busercreation.war |  | 4.2 (AO)Maven | Architect | Victor Chelladurai | Don Kichline | Sama Bhagya | Sama, Sherin |  |  | Needed |  | Yes | Needed | Needed | Needed | B2B User Creation | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-04-17 |  | 2023-02-24 |  | 2023-05-22
Green |  | Yes | No | bbupload.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 120 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Blue Book Upload | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-02-15 | 2023-06-08
Green |  | Yes | No | bill_apprunner |  | 6.1 (Cap/AO)Dev Deploy/Test | Billing | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | 15 |  |  | Needed |  |  |  |  | PBS - CBOS - Invoice Job | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-05-18 |  |  |  | 2023-04-17
Green |  | Yes | No | bill_avobatch |  | 6.2 (AO)QA Deploy/Test | Billing | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | 20 |  |  | Needed |  |  |  |  | PBS - CBOS - Avo Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-06-02 |  |  |  | 2023-04-14 | 2023-06-15
Green |  | Yes | No | bill_rpginvoker |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | 12 |  |  | Needed |  |  |  |  | PBS - CBOS - RPG Invoker | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-20 |  | 2023-05-12 |  | 2023-06-29
Green |  | Yes | No | bill_xmlloader_mp |  | 5.2 (AO)Bamboo Review | Billing | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  |  | Needed |  |  |  |  | PBS - CBOS - Invoice XML Generator | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-06-13 |  |  |  | 2023-05-10 | 2023-06-15
Green |  | Yes | No | bill_xmlloader_st |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | PBS - CBOS - Invoice XML Generator | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  |  |  | 2023-04-18 |  | 2023-07-13
Green |  | Yes | No | billingcommons.jar |  | Waiting on AO | Customer Digital Engineer (eBusiness) | Michael Hintenach | Frank D'Angelo | Shweta Gupta | shweta.gupta@penske.com | [8 empty] | Billing Commons | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-03-24
Green |  | Yes | No | billingservice.war |  | Waiting on AO | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed |  |  | Needed | Needed | Needed | WSV - Billing Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-01-04
|  |  |  | penske_spellingutility.jar | spellingservice.war depends on this utility. | 5.2 (AO)Bamboo Review | Maintenance | David Kost |  | George-Stella | [18 empty] | 2023-06-23 | 2023-07-11
|  | No |  | bodyshop.war |  | 4.1 (Cap)Maven | Maintenance | David Kost | Patel-Falgun | Vennimalayan-Subramanian, Patel-Falgun | Patel, Subramanian | [13 empty] | 2023-05-10 |  |  |  | 2023-07-20
Green |  | Yes | No | bos.war |  | 2.2 (AO)Secrets Mitigate | HR Systems | David Kost | Tim Fox | Vinay Ramanand | Satish, Vinay Ramanand | [8 empty] | BOS - Breach of Security | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  |  |  | 2023-03-09
Green |  | Yes | No | buzonebatch |  | 5.2 (AO)Bamboo Review | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | PBS - LBS - Buzone Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-01-19 |  |  |  | 2023-04-02 | 2023-06-08
Green |  | Yes | No | cbosdbmonitor |  | Retire App | Billing | Stephen McMullen | Rafiq Melath | Sreenivasulu Mupparaju | Sreenivasulu | [8 empty] | CCMS | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-06-07 |  | 2023-05-12
Green |  | Yes | No | ccms.war |  | Dup App | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh |  |  | Not Needed | Not Needed | Yes | Not Needed | Not Needed | Not Needed | CCMS - Arch Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | Yes | ccms.war (Web Application) |  | 5.2 (AO)Bamboo Review | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 152 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | CCMS | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-05-30 | 2023-06-14
Green |  | Yes | No | ccmsservice.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 35 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | CCMSSERVICE | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-02-15 | 2023-05-31
Green |  | Yes | Yes | ccmsxservice.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 50 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | CCMS - Extranet Services | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-02-15 | 2023-06-09
Green |  | Yes | No | cds.war |  | 2.2 (AO)Secrets Mitigate | HR Systems | David Kost | Tim Fox | Vinay Ramanand | Satish | [8 empty] | CDS E-Learning | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  |  |  | 2023-03-09
Green |  | Yes | No | cmns.war | billingutility.jar | 4.1 (Cap)Maven | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | manish sisodiya |  |  | Needed |  |  | Needed | Needed | Needed | CE - Customer Maintenance Notification System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-06-09
|  | No |  | cmns.war |  | Dup App | Maintenance | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-05-09
Green |  | Yes | No | cmsplus.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Mark Weaver | 310 |  | Needed | Not Needed |  | Needed | Needed | Needed | Collection Management Systems Enhanced | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | 2023-02-15 | 2023-05-11 |  |  |  | 2023-07-19 | 2023-07-24
|  | No |  | cns.war |  | Waiting on AO | Maintenance | David Kost | McMurtry-Shawn | McMurtry-Shawn | Shawn | [13 empty] | 2023-07-18 |  | 2023-06-14
Green |  | Yes | No | cnsmailer | BillingUtility.jar | 4.1 (Cap)Maven | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | manish sisodiya |  |  | Needed |  |  | Needed | Needed | Needed | CMNS - CNSMAILER | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-06-09
Green |  | Yes | No | cntxfrmwrk |  | Dup App | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Not Needed | Not Needed | Yes | Not Needed | Not Needed | Not Needed | Connection Mangement Framework | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed |  | Yes - Capgemini
Green |  | Yes | No | connectionmaint.war |  | 5.2 (AO)Bamboo Review | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Needed | Yes | Needed | Needed | Needed | Connection Maintenance | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [6 empty] | 2023-02-09
Green |  | Yes | No | contextframework |  | 5.2 (AO)Bamboo Review | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Connection Mangement Framework | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [6 empty] | 2023-07-09
Green |  | Yes | No | contribreport |  | 6.2 (AO)QA Deploy/Test | Architect | Victor Chelladurai | Shane Myers | Shane Myers | David Graf, Shane Myers | 50 |  | Needed |  | Yes | Needed | Needed | Needed | Contribution Reports | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-02-16 |  |  |  | 2023-03-15
Green |  | Yes | No | csar.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf | [8 empty] | CSAR - Computer Security Access Request | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | csb.war |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  |  | Not Needed |  |  |  |  | PBS - Contract Support Billing (Lease) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-03-24 |  |  |  | 2023-07-13
Green |  | Yes | Yes | cvi.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 179 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | IT Docs Lease/Cmaint Vehicle Installation | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-03-02 | 2023-06-09
Green |  | Yes | No | cyclops.war |  | Retire App | Web Services | Scott Pemrick | Scott Bortzel | Scott Pemrick | Scott Pemrick | [8 empty] | 3rd Party SSO Utility | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-03-24
Green |  | Yes | No | da.war |  | Dup App | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Not Needed | Not Needed | Yes | Not Needed | Not Needed | Not Needed | Delegated Admin | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | darptbatch |  | 2.2 (AO)Secrets Mitigate | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Needed | Yes | Needed | Needed | Needed | Delegated Admin - Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  |  |  | 2023-07-16
Green |  | Yes | No | dasservice.war |  | Dup App | Architect | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | dasservice.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Document Archive | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
|  | No |  | digitech.war |  | Waiting on AO | Maintenance | David Kost | George-Stella | Obst-Gregg | Gregg, Vaddi Mani | [13 empty] | 2023-07-13 |  | 2023-06-01
Green |  | Yes | No | dlinkappremoval |  | 6.2 (AO)QA Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Not Needed | Dlinks Application Removal | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-05-22
Green |  | Yes | No | dlinks.war |  | 6.2 (AO)QA Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf, Sama |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | Dlinks | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-05-01 | 2023-04-12
Green |  | Yes | No | dlinks_filter.jar |  | 6.1 (Cap/AO)Dev Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed |  | Yes | Needed | Not Needed | Needed | DLinks Authentication Filter | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
|  | No |  | domicileservice.jar |  | 4.2 (AO)Maven | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga |  | Rajesh Harvade | Rajesh | [15 empty] | 2023-04-14 |  | 2023-04-24
Green |  | Yes | No | domservice.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 46 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Domicile Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  |  |  |  | 2023-02-15 | 2023-02-16 | 2023-06-08
Green |  | Yes | No | ebill |  | Dup App | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth |  |  | Needed |  |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-06-05
Green |  | Yes | No | ebs.war |  | Waiting on AO | Architect | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf, Sama |  |  | Needed |  | Yes | Needed | Needed | Needed | EBS - Email Broadcast System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-03-17
Green |  | Yes | No | ebsadmin.war |  | Waiting on AO | Architect | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf, Sama |  |  | Needed |  | Yes | Needed | Needed | Needed | EBS - Admin | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-03-17
Green |  | Yes | No | ebsservice.war |  | 4.2 (AO)Maven | Architect | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf, Sama |  |  | Needed |  | Yes | Needed | Not Needed | Needed | WSV - EBSservice | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  |  |  | 2023-02-22 |  | 2023-03-03
|  | No |  | ebsserviceclient.jar |  | 4.2 (AO)Maven | Architect | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf, Sama | [17 empty] | 2023-06-13
Green |  | No | No | ebsworkerbatch |  | DONE - (AO)App Deployed | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed |  | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [8 empty] | 2023-03-20
Green |  | Yes | No | ecm.war |  | 6.2 (AO)QA Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 180 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | e-Credit Memo | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | edi_encryption |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Brian Hug | Sreenivasulu Mupparaju | Sreenivasulu |  |  | Needed | Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-04-12
Green |  | Yes | No | edibatch |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Sreenivasulu Mupparaju | Sreenivasulu |  |  |  | Not Needed |  |  |  |  | EDI Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-05-12
Green |  | Yes | No | edicbos.war |  | 5.2 (AO)Bamboo Review | Billing | Stephen McMullen | Rafiq Melath | Sreenivasulu Mupparaju | Sreenivasulu |  |  |  | Not Needed |  |  |  |  | EDI/CBOS | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-05-17 | 2023-07-27
Green |  | Yes | No | edipostclient |  | 5.2 (AO)Bamboo Review | Billing | Stephen McMullen | Rafiq Melath | Sreenivasulu Mupparaju | Sreenivasulu |  |  |  | Not Needed |  |  |  |  | EDI Post Client Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-01-10 |  |  |  | 2023-05-09 | 2023-05-17
|  | No |  | edvir.war |  | 4.1 (Cap)Maven | Maintenance | David Kost | George-Stella | George-Stella | Stella george, Vaddi Mani | [13 empty] | 2023-05-17 |  | 2023-06-27
Green |  | Yes | No | efuel.war |  | 6.2 (AO)QA Deploy/Test | Billing | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn |  |  |  | Not Needed |  |  |  |  | eFuel | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-04-18 | 2023-04-18
Green |  | Yes | No | efueladmin.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Billing | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn |  |  |  | Not Needed |  |  |  |  | eFuel Admin | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-08 |  |  |  | 2023-06-19
|  | No |  | employeemasterbatch |  | 6.2 (AO)QA Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | [15 empty] | 2023-06-06 |  |  |  | 2023-06-27
Green |  | Yes | No | eram.war |  | DONE - (AO)App Deployed | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 50 |  | Needed |  | Yes | Needed | Needed | Needed | eRam | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-02-28 | 2023-03-10
Green |  | Yes | No | esr.war |  | 5.2 (AO)Bamboo Review | Finance & Business Process Automation (Admin) | Stephen McMullen | Steve McMullen | Charles Csoky | Charles Csoky | 72 |  | Needed | Not Needed |  | Needed | Needed | Needed | Environmental Self Review | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-01-31 |  |  |  |  | 2023-06-12
Green |  | Yes | Yes | esrbatch |  | 6.2 (AO)QA Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Steve McMullen | Charles Csoky | Charles Csoky | 31 |  | Needed | Needed |  | Needed | Needed | Needed | Environmental Self Review - Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-02-16 | 2023-03-29
|  | No |  | etimeservice.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Maintenance | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [15 empty] | 2023-06-01 |  | 2023-06-23
Green |  | Yes | No | fbwatermark |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - CBOS - Watermark | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-20 |  | 2023-03-23 |  | 2023-06-16
Green |  | Yes | No | fbwatermark.jar |  | Dup App | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - CBOS - Watermark | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | fedexrental.war |  | Waiting on AO | Customer Digital Engineer (eBusiness) | Michael Hintenach | Frank D'Angelo | Frank D'Angelo | Frank D'Angelo | [8 empty] | Federated SSO | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-02-14
Green |  | Yes | No | fixedasset.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 14 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Fixed Assets (Web) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-06-08 | 2023-05-17
Green |  | Yes | No | Flex Billing |  | Dup App | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - CBOS - Invoice and Profile Control | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-01-09
Green |  | Yes | No | flex_billing_acl.jar |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Flex Billing Account Context Loader (not in PC2) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-04-17 |  |  |  | 2023-07-06
Green |  | Yes | No | flexbilling |  | Dup App | Billing | Stephen McMullen | Rafiq Melath | Elliott Eames | Elliott | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-01-09
Green |  | Yes | No | flexbilling.war |  | Waiting on AO | Billing | Stephen McMullen | Rafiq Melath | Elliott Eames | Elliott | [8 empty] | PBS - CBOS - Profile Maintenance | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-06-12 |  | 2023-05-12
Green |  | Yes | No | fmea.war |  | 4.1 (Cap)Maven | Web Services | Gary Galyas | Gary Galyas | Gary Galyas | [9 empty] | FMEA | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-06-12 |  | 2023-06-01
|  | No |  | football.war |  | Waiting on AO | Maintenance | David Kost | George-Stella | Obst-Gregg | Gregg, Vaddi Mani | [13 empty] | 2023-06-22 |  | 2023-06-01
Green |  | Yes | No | fuelbatch |  | 4.1 (Cap)Maven | Billing | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn | [8 empty] | FuelNet - Fuel Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-05-23 |  | 2023-05-04
Green |  | Yes | No | fuelcardsplit.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Billing | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Truckstop Fuel | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-05-22
Green |  | Yes | No | fuelnet |  | Dup App | Billing | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-05-03 |  | 2023-05-12
Green |  | Yes | No | fuelnetsvc.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Billing | Stephen McMullen | Rafiq Melath | Bill Spohn | William Spohn |  |  | Needed | Not Needed |  | Needed | Needed | Not Needed | FuelNet - Web Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-03-03 | 2023-06-07
Green |  | Yes | No | fuelpricing.war |  | 5.2 (AO)Bamboo Review | Billing | Stephen McMullen | Rafiq Melath | Bill Spohn | Elliott |  |  | Needed | Needed |  | Needed | Needed | Needed | Fuel Purchasing - Fuel Pricing | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-01-10 |  |  |  | 2023-04-04 | 2023-06-23
Green |  | Yes | Yes | fuelpromos.war |  | 2.2 (AO)Secrets Mitigate | Billing | Stephen McMullen | Rafiq Melath | Elliott Eames | Elliott | [8 empty] | Fuel Promotion Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-01-09 |  | 2023-07-17
Green |  | Yes | No | fuelrecptbatch |  | DONE - (AO)App Deployed | Architect | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | CE - Fuel Receipt Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | No | No | fuelrecptbatch |  | DONE - (AO)App Deployed | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | gewebcash |  | 6.1 (Cap/AO)Dev Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Srinivasan Narayanan | Sreekanth, Srinivasan Narayanan |  |  | Needed | Not Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [6 empty] | 2023-03-23
Green |  | Yes | No | High Radius |  | 6.2 (AO)QA Deploy/Test | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | invarcbatch-sftp | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-07 |  | 2023-03-23 |  | 2023-06-29
Green |  | Yes | No | hrcc.war |  | 6.2 (AO)QA Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 83 |  | Needed | Not Needed |  | Needed | Not Needed | Needed | HRCC Highradius Collection Cloud | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-04-18
Green |  | Yes | No | hrldapcomparision |  | 6.1 (Cap/AO)Dev Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Shane Myers | David Graf, Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | HRLDAP Comparison | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | hvutefile |  | 4.2 (AO)Maven | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Veronique Labeille | Veronique Labeille | Sreekanth, Veronique Labeille |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-05-24 |  | 2023-02-24 |  | 2023-07-09
Green |  | Yes | No | ias-broker |  | 2.2 (AO)Secrets Mitigate | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | IASBATCHBROKER (not in PC2) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-13 |  | 2023-06-27
Green |  | Yes | No | ias-invoiceimage |  | Waiting on AO | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | invoiceimagebatch (not in PC2) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | 2023-06-29 | 2023-08-08 |  | 2023-05-12
Green |  | Yes | No | ias-lbs |  | Waiting on AO | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - LBS - Logistics Billing System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-06-15 |  | 2023-03-23
Green |  | Yes | No | ias.war |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Invoice Archive System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-06-15
Green |  | Yes | No | iasarchiver |  | 2.2 (AO)Secrets Mitigate | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | IASARCHIVER (not in PC2) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-13 |  | 2023-05-12
Green |  | Yes | No | iasinvservice.war |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  | Needed | Not Needed |  | Needed | Needed | Needed | WSV - IASInvService | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-04-05
Green |  | Yes | No | international.war |  | 6.2 (AO)QA Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf, Sama |  |  | Needed | Needed | Yes | Needed | Needed | Needed | ASP - International Link (eLearning) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-04-11 |  |  |  | 2023-02-22
Green |  | Yes | No | invarcbatch |  | Dup App | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | [8 empty] | PBS - Invoice Archive Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-15 |  | 2023-05-12
Green |  | Yes | No | invarcbatch |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | PBS - Invoice Archive Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-15 |  | 2023-04-18 |  | 2023-06-29
Green |  | Yes | Yes | irm.war |  | Waiting on AO | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 208 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | IRM Prism / Web Application | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-07-12 |  |  |  |  | 2023-04-17
Green |  | Yes | No | irmbatch |  | 6.1 (Cap/AO)Dev Deploy/Test | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 110 |  | Needed | Not Needed | Yes | Needed | Needed | Needed | IRM Prism / Savvion Transfer | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-02-16 | 2023-06-08
|  | No |  | IRS Dependency Jar Here |  | Dup App | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Veronique Labeille | Sreekanth Kancharla | Kancharla, Sreekanth (Penske, Capgemini) <Sreekanth.Kancharla@penske.com>
|  | Yes |  | irs.jar |  | 5.2 (AO)Bamboo Review | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Veronique Labeille | Sreekanth Kancharla | Kancharla, Sreekanth (Penske, Capgemini) <Sreekanth.Kancharla@penske.com> | [13 empty] | 2023-05-02 |  |  |  | 2023-06-23 | 2023-08-01
Green |  | Yes | No | iseriessavvionwebserviceclient |  | Retire App | Savvion | Stephen McMullen | Peter MacMahon | Peter MacMahon | Peter | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-03-24
Green |  | Yes | No | itcontact.war |  | 2.2 (AO)Secrets Mitigate | HR Systems | David Kost | Tim Fox | Sathish Polubothu | Satish | [8 empty] | IT Contact Information | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  |  |  | 2023-03-09
Green |  | Yes | No | javapostop |  | 4.2 (AO)Maven | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | Sherin |  |  | Needed | Needed | Yes | Needed | Needed | Needed | JAVAPOSTOP | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-04-05 |  |  |  | 2023-07-13
Green |  | Yes | No | lbs.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | PBS - LBS - Logistics Billing System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-06-05
Green |  | Yes | No | ldapismgr |  | DONE - (AO)App Deployed | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | Sherin |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | ldapismgr | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-04-06
Green |  | Yes | No | mailreader_1_0 |  | Waiting on AO | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth |  |  | Needed |  |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-08-03
Green |  | Yes | No | mailreader_2_0 |  | 5.2 (AO)Bamboo Review | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth |  |  | Needed | Not Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-05-01 | 2023-05-09
|  | No |  | maintconfig.war |  | Waiting on AO | Maintenance | David Kost | Patel-Falgun | Mani-Sarath, Patel-Falgun | Patel, Vaddi Mani | [13 empty] | 2023-07-25 |  | 2023-06-27
Green |  | Yes | No | mileageforecast.war |  | Retire App | Billing | Stephen McMullen | Rafiq Melath | Dylan Price |  |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Iron Mountain Excel upload (Mileage Forecast) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-03-23
Green |  | Yes | No | mileagereporting.war |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | Web Mileage Entry | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-04-05
|  | No |  | openrepairsumm |  | 6.2 (AO)QA Deploy/Test | Maintenance | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-05-31 |  |  |  | 2023-07-16 | 2023-07-19
Green |  | Yes | No | oracle2ldap |  | 6.2 (AO)QA Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Needed | Yes | Needed | Needed | Needed | Oracle2LDAP | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-04-19 | 2023-04-13
Green |  | Yes | No | oraemail |  | Retire App | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | OraEmail | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
|  | No |  | partspo |  | 4.2 (AO)Maven | Maintenance | David Kost | George-Stella | Karthik | Karthikeyan, Vaddi Mani | [15 empty] | 2023-06-01 |  | 2023-06-29
Green |  | Yes | No | pcc |  | Waiting on AO | HR Systems | David Kost | Tim Fox | Sathish Polubothu | Satish | [8 empty] | PC2- Penske Change Control Batch App | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-03-24
Green |  | Yes | No | pcc.war |  | Waiting on AO | HR Systems | David Kost | Tim Fox | Sathish Polubothu | Satish | [8 empty] | PCÂ² - Penske Change Control | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-03-24
Green |  | No | No | penske-secure-logger-1.0.0.jar |  | DONE - (AO)App Deployed | Architect | Victor Chelladurai | Don Kichline | David Graf | Don Kichline |  |  | Needed |  | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [8 empty] | 2023-04-14
Green |  | No | No | penske-watchlist-client jar |  | 4.2 (AO)Maven | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Not Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | penskesso-ws-client.jar |  | Waiting on AO | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Not Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-03-17 |  |  |  | 2023-02-14
Green |  | No | No | penskesso.jar |  | DONE - (AO)App Deployed | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [8 empty] | 2023-04-14
|  | No |  | peoplenetbatch |  | 4.2 (AO)Maven | Maintenance | David Kost | George-Stella | George-Stella | Stella george, Vaddi Mani | [15 empty] | 2023-06-01 |  | 2023-07-19
Green |  | Yes | No | pettycash.war |  | DONE - (AO)App Deployed | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Srinivasan Narayanan | Sreekanth, Srinivasan Narayanan | 72 |  | Needed | Needed |  | Needed | Needed | Needed | AP Petty Cash | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  |  |  | 2023-02-24 |  |  | 2023-03-10
Green |  | Yes | No | pextfl |  | 6.1 (Cap/AO)Dev Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 9 |  | Needed | Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-07-26
|  | No |  | phonesvc.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Maintenance | David Kost | Patel-Falgun | Long-David, Patel-Falgun | David, Patel | [15 empty] | 2023-06-01 |  | 2023-07-11
|  | No |  | pmmailer |  | Waiting on AO | Maintenance | David Kost | Patel-Falgun | Porter-Dale, Patel-Falgun | Dale Porter, Patel | [13 empty] | 2023-07-13 |  | 2023-06-01
|  | No |  | pmscheduling.war |  | 4.1 (Cap)Maven | Maintenance | David Kost | Patel-Falgun | McMurtry-Shawn, Patel-Falgun | Patel, Shawn | [15 empty] | 2023-06-14
Green |  | Yes | No | pops.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 300 |  | Needed |  |  | Needed | Needed | Needed | POPS - Penske On-Line Payment System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-02-24 |  |  |  | 2023-03-16
Green |  | Yes | No | pops_batch |  | 6.2 (AO)QA Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 85 |  | Needed |  |  | Needed | Needed | Needed | POPS - Batch Process | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-02-27 |  |  |  | 2023-03-15
Green |  | Yes | No | printapp |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Needed |  | Needed | Needed | Needed | PRINTAPP | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-03-30
|  | No | No | psndmail |  | 5.2 (AO)Bamboo Review | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | [15 empty] | 2023-02-23 |  | 2023-03-01 | 2023-03-20
Green |  | Yes | No | ptldao.jar |  | DONE - (AO)App Deployed | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Was Needed - AO Done | Was Needed - AO Done | Yes | Not Needed | Was Needed - AO Done | Was Needed - AO Done | PTL DAO | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | queryrunner |  | DONE - (AO)App Deployed | Architect | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed |  | Yes | Needed | Needed | Needed | need to create one | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | [6 empty] | 2023-02-22 |  |  |  | 2023-05-16
Green |  | Yes | No | rentalnet.war |  | Retire App | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver | 1050 |  | Needed |  |  | Needed | Needed | Needed | PBS - Contract Support Billing (RentalNet/VAR) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-01-23 |  | 2023-05-12
Green |  | Yes | No | restfilter.jar |  | 4.2 (AO)Maven | Architect | Victor Chelladurai | Don Kichline | Sama Bhagya | Sama |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | reuse-changemode |  | Retire App | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Not Needed | Not Needed | Yes | Not Needed | Not Needed | Not Needed | Reusable Web Code | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed
Green |  | Yes | No | reuse.jar |  | 6.1 (Cap/AO)Dev Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Needed | Yes | Needed | Needed | Needed | Reusable Web Code | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | roforms.war |  | 6.2 (AO)QA Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | ASP - RO Forms | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
|  | No |  | rsareviewloop.war |  | 4.1 (Cap)Maven | Maintenance | David Kost | Patel-Falgun | Long-David, Patel-Falgun | David, Patel | [15 empty] | 2023-06-27
Green |  | Yes | Yes | rsi.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 84 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | IT DOCS Rental Vehicle Installation | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-02-15 | 2023-06-08
Green |  | Yes | No | safetydata |  | Dup App | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Non-Critical | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-02-16 |  |  |  | 2023-02-15
Green |  | Yes | Yes | safetydata.war |  | 4.2 (AO)Maven | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh |  | No | Needed | Not Needed | Yes | Needed | Needed | Needed | Insurance Safety Data | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-26 |  | 2023-02-24 |  | 2023-06-15
Green |  | Yes | No | schedule1reprint |  | 6.2 (AO)QA Deploy/Test | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Veronique Labeille | Veronique Labeille | Sreekanth, Veronique Labeille |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  |  |  | 2023-02-24 |  | 2023-04-14
Green |  | No | No | scorecard - Batch |  | 6.2 (AO)QA Deploy/Test | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Veronique Labeille | Veronique Labeille | Sreekanth, Veronique Labeille | [15 empty] | 2023-02-24 |  | 2023-05-02 | 2023-05-11
Green |  | Yes | No | scorecard - Web |  | 6.2 (AO)QA Deploy/Test | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Veronique Labeille | Veronique Labeille | Sreekanth, Veronique Labeille |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  |  |  | 2023-02-19 |  | 2023-03-17
Green |  | No | No | security_author_filter.jar |  | 5.2 (AO)Bamboo Review | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  |  |  | 2023-02-08 |  |  | 2023-02-13
Green |  | No | No | security_util.jar |  | DONE - (AO)App Deployed | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [8 empty] | 2023-02-15
Green |  | Yes | No | sellsheet |  | Waiting on AO | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 26 |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | 2023-04-13 | 2023-08-08
Green |  | Yes | No | sem.war (aka Security Exception Maintenance) |  | Retire App | Security | Scott Bortzel | Scott Bortzel <scott.bortzel@penske.com> | [10 empty] | Security Exception Maintenance | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-03-24
|  | No |  | servicenetbatch |  | 6.2 (AO)QA Deploy/Test | Maintenance | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-06-20 |  | 2023-06-14 |  | 2023-07-27
|  | No |  | servicereqbatch |  | 2.2 (AO)Secrets Mitigate | Maintenance | David Kost | George-Stella | Vennimalayan-Subramanian | Subramanian, Vaddi Mani | [13 empty] | 2023-05-17 |  | 2023-08-04
|  | No |  | servicereqsvc.war | serviceRequestUtility.jar | 1.1 (Cap)Log4j | Maintenance | David Kost | George-Stella | Vennimalayan-Subramanian | Subramanian, Vaddi Mani | [13 empty] | 2023-05-31
|  | No |  | servicereqweb.war |  | Waiting on AO | Maintenance | David Kost | George-Stella | Vennimalayan-Subramanian | Subramanian, Vaddi Mani | [13 empty] | 2023-05-17
Green |  | Yes | Yes | sessionmgmtsvc.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Sivagamasundari Suresh | David Graf |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | Session Management Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | shoptalkreg.war |  | 6.2 (AO)QA Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Shane Myers | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Shop Talk Registration | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [6 empty] | 2023-03-23
Green |  | Yes | No | sics |  | Retire App | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | NA |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed
Green |  | Yes | No | sics.war |  | 6.2 (AO)QA Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 204 |  | Needed | Not Needed |  | Needed | Needed | Needed | SICS - Sales Incentives Commission System | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | sicsbatch |  | 6.2 (AO)QA Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 108 |  | Needed | Not Needed |  | Needed | Needed | Needed | SICS Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | sicssvc.war |  | 6.2 (AO)QA Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Kalrav Khamar | Kalrav, Sreekanth | 83 |  | Needed | Not Needed |  | Needed | Needed | Needed | SICS Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | smvendors |  | Retire App | Web Services | Scott Pemrick | Scott Bortzel | Scott Pemrick | Scott Pemrick | [9 empty] | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-03-24
|  | No |  | sos.war |  | Waiting on AO | Maintenance | David Kost | Patel-Falgun | Papannagari-Sreenivasa, George-Stella | Patel, Sreenivasa | [13 empty] | 2023-07-24 |  | 2023-06-01
|  | No |  | sospcard.war |  | Waiting on AO | Maintenance | David Kost | Patel-Falgun | Papannagari-Sreenivasa, George-Stella | Patel, Sreenivasa | [13 empty] | 2023-07-24 |  | 2023-06-14
|  | No |  | sosservice.war | sosutility.jar | 4.2 (AO)Maven | Maintenance | David Kost | Patel-Falgun | Long-David | David, Patel | [13 empty] | 2023-05-10 |  | 2023-07-17 |  | 2023-08-08
|  |  |  | sosutility | sosservice,sos.war,24x7custnotif depend on this utlity. | 5.2 (AO)Bamboo Review | Maintenance | David Kost | Patel-Falgun | Long-David, Patel-Falgun | David, Patel, Sreenivasa | [17 empty] | 2023-06-27 | 2023-07-12
|  | No |  | spellingservice.war | penske_spelling_Client | 4.1 (Cap)Maven | Maintenance | David Kost | George-Stella | George-Stella, Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-06-20 |  | 2023-07-21
Green |  | Yes | No | ssptktportal.war |  | 6.2 (AO)QA Deploy/Test | Billing | Stephen McMullen | Rafiq Melath | Spohn-Bill | William Spohn | [8 empty] | Fuel Reconciliation-Suspended Tkts Portal | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-07 |  | 2023-03-23 |  | 2023-04-24 | 2023-06-12
Green |  | Yes | No | stopbilling.war |  | 6.2 (AO)QA Deploy/Test | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed | Not Needed |  | Needed | Needed | Needed | IT Docs - Stop Billing | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-05-11
Green |  | Yes | No | synchghdbc |  | Retire App | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed |  | Yes | Needed | Needed | Needed | SynchGHDBC | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-15 |  |  |  | 2023-03-01
Green |  | Yes | No | taebatch |  | 2.2 (AO)Secrets Mitigate | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Ravi Daram | Ravi | 60 | No | Needed | Not Needed | Yes | Needed | Needed | Needed | T&E Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | techchallenge.war |  | Waiting on AO | Architect | Victor Chelladurai | Don Kichline | Sama Bhagya | David Graf, Sama |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | ASP - Tech Challenge | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-11-16
Green |  | Yes | No | telematicssvc.war |  | 4.2 (AO)Maven | Architect | Victor Chelladurai | Don Kichline | Myers-Shane | Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Telematics Service (eDTR) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | tririga_integrations |  | 5.2 (AO)Bamboo Review | Finance & Business Process Automation (Admin) | Stephen McMullen | Steve McMullen | Charles Csoky | Charles Csoky | 30 |  | Needed |  |  | Needed | Needed | Needed | Tririga- Integrations | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-06-15 |  |  |  | 2023-07-12 | 2023-07-14
Green |  | Yes | No | trs_extract |  | Dup App | Billing | Stephen McMullen | Rafiq Melath | Manish Sisodiya | manish sisodiya | [8 empty] | Trust Extract | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | trs_extract.jar |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan | [8 empty] | Trust Extract | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-14 |  | 2023-03-23 |  | 2023-07-10
|  | No |  | unitjkt.war |  | Waiting on AO | Maintenance | David Kost | Patel-Falgun | Long-David | David, Patel | [13 empty] | 2023-07-18 |  | 2023-07-03
Green |  | Yes | No | userlookup.war |  | 6.2 (AO)QA Deploy/Test | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf, Sherin |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | User Lookup Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-06-19 | 2023-06-30
|  | No |  | usermaint.war |  | Waiting on AO | Maintenance | David Kost | George-Stella | Srinivasan-Karthikeyan | Karthikeyan, Vaddi Mani | [13 empty] | 2023-06-26
Green |  | Yes | No | usermgmt.war |  | 5.2 (AO)Bamboo Review | Architect | Victor Chelladurai | Don Kichline | Bhagya Sama | David Graf, Sama |  |  | Needed | Was Needed - AO Done | Yes | Needed | Not Needed | Needed | User Management | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [6 empty] | 2023-06-30 |  | 2023-05-16
Green |  | Yes | Yes | usermgmtsvc.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | User Management Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  |  |  | 2023-02-08
Green |  | Yes | No | userstoreclient_rest.jar |  | 4.2 (AO)Maven | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | User Store Client - Rest | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-02-15
Green |  | Yes | No | userstoresvcjws.war |  | Waiting on AO | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | Userstore Service - jax-ws | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-06-20
|  | No |  | usrcreationsvc-client.jar |  | 5.2 (AO)Bamboo Review | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf | [13 empty] | 2023-04-18 |  | 2023-04-25 |  | 2023-05-24 | 2023-06-09
Green |  | Yes | No | usrcreationsvc.war |  | 6.2 (AO)QA Deploy/Test | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Needed | Yes | Needed | Not Needed | Needed | User Creation Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-04-11
|  | No |  | utimageservice.jar |  | Waiting on AO | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga |  | Brain Joseph | [14 empty] | 2023-03-30
Green |  | Yes | No | vdrfilebatch |  | 6.2 (AO)QA Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | VDR File Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | vdrfilesvc.war |  | 6.2 (AO)QA Deploy/Test | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | VDR File SVC | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | vehicledatarepo |  | Retire App | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf |  |  | Needed |  | Yes | Needed | Needed | Needed | Vehicle Data Repository Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed
Green |  | Yes | No | vehicleimageupdate |  | 5.2 (AO)Bamboo Review | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Rajesh Haravde | Rajesh | 13 |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-02-16 |  | 2023-02-24 |  | 2023-05-01 | 2023-07-10
|  | No |  | vehicleinfosvc.war |  | 4.1 (Cap)Maven | Maintenance | David Kost | George-Stella | Porter-Dale | Dale Porter, Vaddi Mani | [13 empty] | 2023-07-11 |  | 2023-07-25
|  | No |  | vendordvir |  | 4.2 (AO)Maven | Maintenance | David Kost | George-Stella | Long-David, Ganguli-Payel | David, Ganguly, Vaddi Mani | [15 empty] | 2023-06-14 |  | 2023-07-21
Green |  | Yes | No | vendorinfo.war |  | Retire App | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | Narayanan-Srinivasan | Srinivasan Narayanan |  |  | Not Needed | Not Needed |  | Not Needed | Not Needed | Not Needed
Green |  | Yes | No | vendorreg.war |  | 4.2 (AO)Maven | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | Mahipal, Sherin |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed | vendorregistration | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini
Green |  | Yes | No | vfjexcel |  | Waiting on AO | Fleet Services & Asset Mngmt (Corp) | Krishna Tanga | Krishna Tanga | Krishna Tanga | Rajesh |  |  | Needed |  |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-26
Green |  | Yes | No | viewpdf.war |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Dylan Price | Dylan |  |  | Needed | Not Needed |  | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-05-05
|  | No |  | virtualpay.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Maintenance | David Kost | Patel-Falgun | Long-David | David, Patel | [13 empty] | 2023-05-24 |  | 2023-06-14 |  | 2023-07-06
|  | No |  | voicepmsvc.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Maintenance | David Kost | George-Stella | Mani-Sarath | Vaddi Mani | [15 empty] | 2023-06-14 |  | 2023-07-20
|  | No |  | penske_spelling_Client | spellingservice.war | 5.2 (AO)Bamboo Review | Maintenance | Dale Porter |  |  | Dale Porter | [13 empty] | 2023-07-05 |  |  |  | 2023-07-26 | 2023-08-02
Green |  | Yes | No | wambea | BillingUtility.jar | 1.1 (Cap)Log4j | Billing | Stephen McMullen | Rafiq Melath | Manish Sisodiya | manish sisodiya |  |  | Needed |  |  | Needed | Needed | Needed | CMNS - WAMBEA | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-06-13 |  | 2023-05-12
Green |  | Yes | No | watchlistbatch |  | Waiting on AO | Architect | Victor Chelladurai | Don Kichline | Mahipal Podduturi | David Graf, Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Needed | Watch List Batch | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-11-29 | Yes - Capgemini |  | 2023-05-24
Green |  | Yes | Yes | watchlistsvc.war |  | Waiting on AO | Architect | Victor Chelladurai | Don Kichline | Sama Bhagya | Sama |  |  | Needed | Needed | Yes | Needed | Not Needed | Needed | Watch List Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-05-29 |  |  |  | 2023-03-01
Green |  | Yes | No | wbmusernotifier |  | 4.2 (AO)Maven | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  |  | Not Needed |  |  |  |  | WSV - wbmuserservice | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-03-03
Green |  | Yes | No | webmileagesvc.war |  | Waiting on AO | Billing | Stephen McMullen | Rafiq Melath | Mark Weaver | Mark Weaver |  |  | Needed |  |  | Needed | Needed | Needed | Web Mileage Service | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2022-12-16
|  | No |  | billingutility.jar | cmns, cnsmailer and wambea depends on this utility | 4.2 (AO)Maven | Billing | Stephen McMullen |  | Dylan Price | [18 empty] | 2023-06-27
Green |  | Yes | No | webrptportal.war |  | 6.2 (AO)QA Deploy/Test | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf, Sama |  |  | Needed | Needed | Yes | Needed | Not Needed | Not Needed | Web Report Portal | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [6 empty] | 2023-03-01
Green |  | Yes | No | wje.war |  | 6.1 (Cap/AO)Dev Deploy/Test | Finance & Business Process Automation (Admin) | Stephen McMullen | Kalrav Khamar | James Minisce | James Minisce, Sreekanth | 67 |  | Needed |  |  | Needed | Needed | Needed | Web Journal Entry | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini |  | 2023-02-13 |  | 2023-02-23 |  | 2023-03-08
Green |  | Yes | No | wlstandalone.war |  | 4.2 (AO)Maven | Architect | Victor Chelladurai | Don Kichline | Mahipal Podduturi | David Graf, Shane Myers |  |  | Needed | Not Needed | Yes | Needed | Not Needed | Not Needed | FBI Watch List (Web) | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | [5 empty] | 2023-05-22 | 2023-03-23
Green |  | Yes | No | ws_authorizationfilter.jar |  | Waiting on AO | Architect | Victor Chelladurai | Don Kichline | David Graf | David Graf |  |  | Needed | Not Needed | Yes | Needed | Needed | Needed |  | Mathumala Nachiappan, Praneeth Gayam, Rafeeq Ahamed | 2023-09-15 | Yes - Capgemini | 2023-06-05 | 2023-08-08 |  |  |  |  | 2023-03-01
|  | No |  | captchabatchjob |  | Waiting on AO | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal-Sree | Joseph-Brian | Brian | [13 empty] | 2023-07-27
|  | No |  | captchaservice.war |  | 4.1 (Cap)Maven | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal-Sree | Joseph-Brian | Brian
|  | No |  | cedabatchjob |  | Waiting on AO | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | [5 empty] | In Progress |  | Was Needed - AO Done | [6 empty] | 2023-08-02
|  | No |  | cedanotifybatch |  | Not Started | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | [5 empty] | In Progress |  | Was Needed - AO Done
|  | No |  | cookie.war |  | Waiting on AO | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Possible retirement | [13 empty] | 2023-07-27
|  | No |  | emetrics.war |  | Not Started | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Possible retirement |  |  |  |  | In Progress |  | Was Needed - AO Done
|  | No |  | etservice.war |  | Not Started | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal-Sree | French-Kenneth
|  | No |  | fcservice.war |  | Not Started | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal-Sree | Devarapally-Sravani |  |  |  |  | Was Needed - AO Done |  |  | Was Needed - AO Done
|  | No |  | fdtypes |  | 2.2 (AO)Secrets Mitigate | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | [7 empty] | Was Needed - AO Done | [8 empty] | 2023-08-09
|  | No |  | fimigration |  | Waiting on AO | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Possible retirement | [6 empty] | Was Needed - AO Done | [6 empty] | 2023-07-26
|  | No |  | fuelcalc.war |  | 2.2 (AO)Secrets Mitigate | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal-Sree | Devarapally-Sravani |  |  |  |  | Was Needed - AO Done | Was Needed - AO Done |  | Was Needed - AO Done | [8 empty] | 2023-08-09
|  | No |  | fuelcalcadmin.war |  | 2.2 (AO)Secrets Mitigate | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal-Sree | Devarapally-Sravani |  |  |  |  | Was Needed - AO Done | Was Needed - AO Done |  | Was Needed - AO Done | [8 empty] | 2023-08-04
|  | No |  | intsecuritysvc.war |  | 4.1 (Cap)Maven | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Elanchezhian |  |  |  |  | In Progress |  | Was Needed - AO Done
|  | No |  | ldapcompanybatch |  | 2.2 (AO)Secrets Mitigate | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | [5 empty] | In Progress |  | Was Needed - AO Done | [8 empty] | 2023-08-09
|  | No |  | locationfinder.war |  | Not Started | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | Possible retirement |  |  |  |  | Was Needed - AO Done |  | Was Needed - AO Done
|  | No |  | locationsearch |  | Waiting on AO | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | [5 empty] | Was Needed - AO Done |  | Was Needed - AO Done | Was Needed - AO Done | [5 empty] | 2023-07-31
|  | No |  | locrulesrv.war |  | Waiting on AO | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal-Sree | Ochathevan-Elanchezhian |  |  |  |  | Was Needed - AO Done | Was Needed - AO Done |  | Was Needed - AO Done | [6 empty] | 2023-07-27
|  | No |  | mapadmin.war |  | Not Started | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal-Sree | French-Kenneth |  |  |  |  | Was Needed - AO Done | Was Needed - AO Done |  | Was Needed - AO Done
|  | No |  | mapservice.war |  | 2.2 (AO)Secrets Mitigate | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal-Sree | French-Kenneth |  |  |  |  | Was Needed - AO Done | Was Needed - AO Done |  | Was Needed - AO Done | [8 empty] | 2023-08-04
|  | No |  | smsbatch |  | 1.1 (Cap)Log4j | Maintenance | David Kost | McMurtry-Shawn | McMurtry-Shawn | [14 empty] | 2023-07-30
|  | No |  | smsservice.war |  | 1.1 (Cap)Log4j | Maintenance | David Kost | McMurtry-Shawn | McMurtry-Shawn | [14 empty] | 2023-07-30
|  | No |  | mfaservice |  | Waiting on AO | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal-Sree | French-Kenneth |  |  |  |  | Was Needed - AO Done | Was Needed - AO Done |  | Was Needed - AO Done | Was Needed - AO Done | [5 empty] | 2023-08-02
|  | No |  | modifyuserdaemon |  | 2.2 (AO)Secrets Mitigate | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Possible retirement |  |  |  |  | In Progress |  | Was Needed - AO Done | [8 empty] | 2023-08-04
|  | No |  | notificationbatch |  | Not Started | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Ashway, Jeremiah | [5 empty] | In Progress |  | Was Needed - AO Done
|  | No |  | reconcilebatch |  | 2.2 (AO)Secrets Mitigate | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Possible retirement |  |  |  |  | In Progress |  | Was Needed - AO Done | [8 empty] | 2023-08-04
|  | No |  | rentaladmin.war |  | Not Started | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal-Sree | French-Kenneth |  |  |  |  | Was Needed - AO Done | Was Needed - AO Done |  | Was Needed - AO Done
|  | No |  | shorturlservice |  | Not Started | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal, Sree | Ochathevan, Elanchezhian |  |  |  |  | Was Needed - AO Done | Was Needed - AO Done |  | Was Needed - AO Done | Was Needed - AO Done
|  | No |  | ssoservice.war |  | Waiting on AO | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Ashway-Jeremiah | Possible retirement |  |  |  |  | In Progress |  | Was Needed - AO Done | [6 empty] | 2023-07-31
|  | No |  | updlatlong |  | Waiting on AO | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | [5 empty] | Was Needed - AO Done |  | Was Needed - AO Done | Was Needed - AO Done | [5 empty] | 2023-08-02
|  | No |  | updtimezon |  | Waiting on AO | Customer Digital Engineer (eBusiness) | Michael Hintenach | D'Angelo-Frank | Gupta-Shweta | [14 empty] | 2023-07-27
|  | No |  | usedtrucksadmin.war |  | 2.2 (AO)Secrets Mitigate | Customer Digital Engineer (eBusiness) | Michael Hintenach | Gopal-Sree | Joseph-Brian | [16 empty] | 2023-08-04
|  | No |  | docserviceclient.jar |  | 4.2 (AO)Maven | Architect | Victor Chelladurai | Don Kichline | Sherin Basheer | David Graf | [17 empty] | 2023-07-20

## Comments
Row 1 | @david.long@penske.com , The jdbc configuration is configured in applicationcontext.xml file and depends on the environment the respective configuration loaded from different properties files. But when we modernize the app, the build is going to be environment agnostic. Means one build should be deployed to all environments. So, the current way of implementation doesn't work for jdbc configuration. Same issue exist in pmmailer app also. Could you please check with Architecture team to resolve this issue. Thanks. | Gayam | 07/20/23 11:08 PM
Row 1 | @praneeth.gayam@penske.com I checked out the secrets in the 24x7 cust notif batch and there are none. All secrets are stored in the encrypted table. Yes you may move the velocity jar to artifactory! Thanks! | David | 06/09/23 6:19 PM
| Thanks @david.long@penske.com . Regarding an email you sent about the branches, we took the base reference branch https://svn.penske.com/svn/fieldsys/other/24x7-customer-notifications/tags/PROD/2023-02-02/24x7CustomerNotifications for log4j/maven changes. This branch corresponds to the latest prod deployment in Bamboo. Kindly inform us whether we should utilize the dev_24x7_threads branch instead of the above branch? Thanks. | Gayam | 06/10/23 1:43 AM
| @praneeth.gayam@penske.com Please use the PROD tag, as the dev threads branch is current on dev and qa, but that will not be pushed to PROD for some time. Best to do what's on PROD vs what's on dev | David | 06/13/23 2:25 AM
| Sure @david.long@penske.com . Thanks | Gayam | 06/14/23 2:05 AM
Row 1 | Thanks @praneeth.gayam@penske.com | Yvette Urso | 06/08/23 8:05 PM
Row 1 | @yvette.urso@penske.com I now have access to the smart sheet. What's the item waiting on AO? Is there someone actively working on this migration? | David | 06/06/23 8:06 PM
| @david.long@penske.com we are waiting for following 2 things. 1. Secrets confirmation 2. This app depends on the velocity-dep jar but this is not available in artifactory. Could you please provide your approval to upload to artifactory in the below provided location. <groupid>org.apache.velocity</groupid> <artifactid>velocity-1.7-dep</artifactid> <version>Default</version> | Gayam | 06/08/23 2:47 AM
Row 1 | This is my reply @falgun.patel@penske.com | Yvette Urso | 06/03/23 1:47 AM
Row 1 | @david.long@penske.com @falgun.patel@penske.com @yvette.urso@penske.com testing | Yvette Urso | 06/03/23 1:43 AM
Row 1 | @falgun.patel@penske.com - test comment | Patel | 06/02/23 8:34 PM
Row 1 | Secrets: @shawn.mcmurtry@penske.com , adding to above question, I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:53 AM
Row 1 | @shawn.mcmurtry@penske.com , This app depends on the velocity-dep jar but this is not available in artifactory. Could you please provide your approval to upload to artifactory in the below provided location. <groupid>org.apache.velocity</groupid> <artifactid>velocity-1.7-dep</artifactid> <version>Default</version> | Gayam | 05/13/23 2:58 AM
Row 2 | @dale.porter@penske.com , You just need to verify whether the bamboo built correctly and jar is deployed to artifactory. This is just a dependency jar and not going to deployed to any server. Thanks. | Gayam | 08/10/23 1:00 AM
Row 2 | Thanks @dale.porter@penske.com . We will onboard to Bamboo. | Gayam | 07/07/23 10:42 PM
| The jar is onboarded to bamboo and uploaded to artifactory. Following is the dependency. <dependency> <groupId>com.penske.maintenance</groupId> <artifactId>vehicleinformationutility</artifactId> <version>2.0.0-develop-20230710.062023-1</version> </dependency> | Gayam | 07/10/23 11:12 PM
| Hi @praneeth.gayam@penske.com , please let me know if you are waiting on me for update as I am not sure what to do next. thanks | Dale Porter | 08/10/23 12:02 AM
Row 2 | thank you | Dale Porter | 07/17/23 10:58 PM
Row 2 | Review: @stella.george@penske.com / @dave.kost@penske.com , This utility app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/vehicleinformationutility/pull-requests/3/overview | Gayam | 06/24/23 12:22 AM
Row 2 | Review: @Stell | Gayam | 06/24/23 12:22 AM
Row 2 | There are no secrets exist for this application. So changing the status of this app to Cap Maven. | Gayam | 06/23/23 12:14 AM
Row 3 | @praneeth.gayam@penske.com I have verified the pull request and it looks like the source has been taken from https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/tags/prod/PROD_2023-04-06 we did two more prod deploy after that tag. Could you please use the below tag and add the changes. https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/tags/prod/PROD_2023-06-27 | Subramanian | 07/28/23 2:35 AM
| @subramanian.vennimalayan@penske.com , Are there any changed made in the servicerequestutility folder? Also, are you planning any more prod deployments or code changes? | Gayam | 07/31/23 2:48 AM
Row 3 | @stella.george@penske.com , This app is ready for review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/servicerequestutility/pull-requests/2/overview | Gayam | 07/07/23 1:08 AM
Row 3 | Secrets: @stella.george@penske.com , I sent the secrets in the email. Please verify and let us know whether this app requires code changes. | Gayam | 06/28/23 12:45 AM
| @stella.george@penske.com confirmed there are no code chagnes required for this app. | Gayam | 07/06/23 3:36 AM
Row 4 | Ready to be tested in QA. | Sreekanth | 07/05/23 7:35 PM
| @sreekanth.kancharla@penske.com , QA deployment needs to complete by AO only. Please deploy and test. Thanks. | Gayam | 07/06/23 3:16 AM
Row 4 | @sreekanth.kancharla@penske.com : this app is deployed to dev. https://bamboo.penske.com/browse/ACH-ACHW/deployments | Gayam | 04/13/23 11:43 PM
Row 4 | @james.minisce@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @sreekanth.kancharla@penske.com | Gayam | 01/24/23 10:19 AM
| @praneeth.gayam@penske.com No remediations required for the shared secrets as all are valid. CC: @james.minisce@penske.com | Sreekanth | 01/26/23 1:29 AM
| Thanks @sreekanth.kancharla@penske.com. Changing back to (AO)Maven status. Please review the MR when you get a chance. MR provide above. | Gayam | 01/26/23 2:03 AM
| @praneeth.gayam@penske.com The PR is not yet merged. I've added comments. Please provide clarification. https://bitbucket.penske.com/projects/ITFIS/repos/ach-web/pull-requests/3/overview | Sreekanth | 02/16/23 8:46 PM
| @sreekanth.kancharla@penske.com , I have responnded in the PR. Please check. | Gayam | 02/17/23 1:22 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 03/24/23 5:50 PM
| Thanks @sreekanth.kancharla@penske.com . We will let you know once onboarding to Bamboo and deploymnet to Dev completed. | Gayam | 03/24/23 11:06 PM
| @sreekanth.kancharla@penske.com , this app is onboarded to Bamboo. But the build was failing. For that reason we had to change version of one dependency. Could you please approve and merge the below PR for this change. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/ach-web/pull-requests/5/overview | Gayam | 03/30/23 11:29 PM
| @praneeth.gayam@penske.com The latest PR was merged on 03/30/2023 | Sreekanth | 04/12/23 7:18 AM
Row 4 | @rafiq.melath@penske.com / @james.minisce@penske.com / @sreekanth.kancharla@penske.com , Log4j, Mavne changes are completed for this app. Please review in the below PR and merge. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/ach-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/13/22 2:58 AM
| @praneeth.gayam@penske.com I've added comment to PR. Please check and reply back to take further action. @mathumala.nachiappan@penske.com @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 3:00 AM
Row 4 | @praneeth.gayam@penske.com What is the plan once the changes are reviewed and merged ? Hope we may've to have a new Bamboo plan with latest CICD approach to deploy this app in DEV/QA for testing. | Sreekanth | 12/20/22 4:33 AM
| Yes @sreekanth.kancharla@penske.com . We will build and deploy the application to dev/qa with the new build plan. | Gayam | 12/20/22 4:54 AM
Row 5 | Ready to be tested in QA. | Sreekanth | 07/05/23 7:35 PM
| @sreekanth.kancharla@penske.com , QA deployment needs to complete by AO only. Please deploy and test. Thanks. | Gayam | 07/06/23 3:16 AM
Row 5 | @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: achbatch-deploy New deployment project name: ach-batch-deploy Thank you. | Gayam | 05/14/23 9:15 PM
| @praneeth.gayam@penske.com Perfect! Thank you! | Sreekanth | 05/24/23 9:07 PM
Row 5 | @sreekanth.kancharla@penske.com , This app is onboarded to bamboo. Please deploy to QA and test. Thanks. https://bamboo.penske.com/browse/ACH-ACHBAP1/deployments | Gayam | 03/30/23 12:40 AM
Row 5 | @rafiq.melath@penske.com / @james.minisce@penske.com / @sreekanth.kancharla@penske.com , We have completed the secrets scanning on this application and found that there is 1 true positive and all others are false positives. I will share the excel report in the email. Could you please check and remediate the secrets. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/06/23 1:01 AM
| @sreekanth.kancharla@penske.com , Is there a standard process/practice already in place to remediate these finding(s)? | James | 01/06/23 2:06 AM
| @praneeth.gayam@penske.com No remediation is required for all False positives as those are Connection Framework setup related files as per the Penske standard. The 1 True positive seems in offshore branch only and not in DEV/QA/Trunk branches. We are not sure whether offshore branch has latest code. To make any changes, we always refer the trunk branch and then either create a new branch from trunk (OR) work with DEV branch if the source is in sync with Trunk branch. With this, hope we don't need to make any remediation for the shared secrets. Please let us know in case any further clarifications required. CC: @mathumala.nachiappan@penske.com @james.minisce@penske.com | Sreekanth | 01/06/23 2:41 AM
| Thanks @sreekanth.kancharla@penske.com . We will do the next step which is Mavanizing the application. @james.minisce@penske.com | Gayam | 01/07/23 12:50 AM
| @sreekanth.kancharla@penske.com , As discussed PR is already merged to develop branch. Could you please check and provide your approval for the Bamboo stage. | Gayam | 03/02/23 2:49 AM
| @praneeth.gayam@penske.com Please proceed with further steps. @james.minisce@penske.com | Sreekanth | 03/04/23 2:54 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to Cap Bamboo | Gayam | 03/07/23 12:19 AM
Row 6 | Ready to be tested in QA. | Sreekanth | 07/05/23 7:35 PM
| @sreekanth.kancharla@penske.com , QA deployment needs to complete by AO only. Please deploy and test. Thanks. | Gayam | 07/06/23 3:16 AM
| @praneeth.gayam@penske.com Yes. Just updated the status for information. | Sreekanth | 07/06/23 7:50 PM
Row 6 | @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: achsvc-deploy New deployment project name: ach-service-deploy Thank you. | Gayam | 05/14/23 9:15 PM
| @praneeth.gayam@penske.com Thank you! | Sreekanth | 05/24/23 9:07 PM
Row 6 | @sreekanth.kancharla@penske.com , Dev deployment of this app is completed. Please check. Thank you. | Gayam | 03/23/23 11:45 PM
Row 6 | @james.minisce@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @sreekanth.kancharla@penske.com | Gayam | 01/24/23 10:20 AM
| @praneeth.gayam@penske.com No remediations required for the shared secrets as all are valid. CC: @james.minisce@penske.com | Sreekanth | 01/26/23 1:30 AM
| Thanks @sreekanth.kancharla@penske.com. Changing back to (AO)Maven status. Please review the MR when you get a chance. MR provide above. | Gayam | 01/26/23 2:05 AM
| @praneeth.gayam@penske.com - Still i see the status is (Cap) Bamboo.. Missing anything here? And is that PR? | Mathumala Nachiappan | 01/27/23 10:51 AM
| @mathumala.nachiappan@penske.com , Sreekanth already merged the code and provided the update above. I changed the status to Cap Bamboo. Please check | Gayam | 01/27/23 7:30 PM
Row 6 | @rafiq.melath@penske.com / @james.minisce@penske.com / @sreekanth.kancharla@penske.com , Log4j team completed log4j and maven changes. Please review them in below PR and merge. https://bitbucket.penske.com/projects/ITFIS/repos/ach-service/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/09/22 6:48 AM
| @sreekanth.kancharla@penske.com Please review the log4j changes in the link above and merge if there are no issues. Thank you. | James | 12/09/22 5:54 PM
| @praneeth.gayam@penske.com PR is merged. @mathumala.nachiappan@penske.com @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 3:12 AM
| Thanks @sreekanth.kancharla@penske.com . We will create the Bamboo for this and will deploy to Dev and let you know. Please confirm whether you are ok for Dev deployment. Thanks. Changed the status to (AO)Bamboo. | Gayam | 01/26/23 8:59 PM
Row 7 | Hi @praneeth.gayam@penske.com As discussed over the teams we are seeing issues with while upgrading to spring4 so I am working on that.Thanks! | Sama | 05/19/23 7:56 PM
Row 7 | Hi @praneeth.gayam@penske.com As discussed I found the issue that spring jar dependency is missing: org.springframework.remoting.httpinvoker.CommonsHttpInvokerRequestExecutor so please let us know if this is happening because of the upgrade or something else so that we will check our side. | Sama | 05/15/23 11:00 PM
| @bhagya.sama@penske.com , we will check this issue. Also, as per @hugo.scavino@penske.com 's suggestions we are changing the log4j2 scope to compile from provided. So changed this and merged to develop branch. Thank you. | Gayam | 05/16/23 12:20 AM
| @bhagya.sama@penske.com , we added the dependency and raised the PR. https://bitbucket.penske.com/projects/ARPROJ/repos/b2busercreation-web/pull-requests/10/overview Please check. | Gayam | 05/18/23 1:48 AM
Row 7 | Hi @praneeth.gayam@penske.com dev deployment looks good so please proceed to deploy to QA. | Sama | 05/09/23 8:05 PM
| @bhagya.sama@penske.com , Log4j team is not supposed to do the QA deployments per instructions from management. AO need to take care of it. | Gayam | 05/09/23 10:29 PM
Row 7 | Hi @praneeth.gayam@penske.com I merged the code to develop branch. | Sama | 05/03/23 6:46 PM
| @bhagya.sama@penske.com Develop branch is deployed to Dev. Please verify. Thanks | Gayam | 05/05/23 6:13 AM
Row 7 | @bhagya.sama@penske.com , this app is deployed to dev using develop_log4j branch - https://bamboo.penske.com/browse/BBUC-BBUCT1/deployments Please check and also please merge the code to develop branch. https://bitbucket.penske.com/projects/ARPROJ/repos/b2busercreation-web/pull-requests/6/overview | Gayam | 04/28/23 12:20 AM
Row 7 | @praneeth.gayam@penske.com I have done the changes and committed to develop_log4j branch. Please deploy to the DEV. | Sama | 04/10/23 11:09 PM
| Thanks @bhagya.sama@penske.com . We will take up the next step. | Gayam | 04/11/23 8:34 AM
| @bhagya.sama@penske.com , When we check the old bamboo builds, this app doesn't have dev environment. Could you please check and let us know whether it needs to be deployed to Dev. If so, can we deploy to ghlx008ptlge server and also we need instance type. Could you please check and update us. Thanks. | Gayam | 04/18/23 3:02 AM
| @bhagya.sama@penske.com confirmed that the instanceType is external as per documentation https://confluence.penske.com/display/ATSD/B2B+User+Creation | Gayam | 04/27/23 1:29 AM
Row 7 | Hi @praneeth.gayam@penske.com I am working on it and will update once I am done with it.Thanks! | Sama | 03/30/23 8:21 PM
Row 7 | Question: @sherin.basheer@penske.com , Adding to above secrets question, there is a header.jspf file which is different for both prod and qa exist under targeted folder. Could you please check and let us know whether we can use prod one. Thanks. | Gayam | 03/03/23 1:09 AM
| Hi @praneeth.gayam@penske.com I have checked the files in both qa and prod, we have to pick the file based on the environment. | Sama | 03/20/23 7:34 AM
| Hi @bhagya.sama@penske.com , Are you making the code changes to pick the file depends on environment? Thanks. | Gayam | 03/20/23 11:46 PM
| Hi @praneeth.gayam@penske.com Can you use env variable in the file like ${sys:srvenv}] ,this should give you the environment QA/PROD | Sama | 03/25/23 12:28 AM
| @bhagya.sama@penske.com , As per instructions we are not supposed to do any code changes other than log4j and maven changes. Also, to verify the changes we don't know how to run the app in local. So could you please complete the changes on top of log4j branch. Thanks. @hugo.scavino@penske.com | Gayam | 03/27/23 11:36 PM
Row 7 | Secrets: @sherin.basheer@penske.com , adding to above question we sent the secret file of this app to you in the email. Could you please check whether this app requires any code changes on secrets part. Thanks | Gayam | 02/24/23 1:51 AM
| Hi @praneeth.gayam@penske.com I have taken the secret file from Sherin and verified, it's does not require code changes. | Sama | 03/20/23 7:35 AM
Row 7 | @sherin.basheer@penske.com , As per @hugo.scavino@penske.com penske-secure-logger is not getting migrated to log4j2 and there is no modernization for that jar. But b2busercreation.war using loggers from penske-seucre-logger jar which is using log4j1. Do you want us to replace the loggers from penske-secure jar with log4j2 loggers in b2busercreation app? | Gayam | 02/23/23 12:28 AM
| Yes you can replace with log4j2 loggers. Thank you. | Sherin | 02/24/23 9:37 PM
| Thank you. Changing the status (AO)Secrets Mitigation | Gayam | 02/25/23 12:59 AM
Row 7 | Blocker: penske-secure-logger-1.0.0.jar | Yvette Urso | 02/01/23 8:29 PM
Row 7 | @sherin.basheer@penske.com Can you assist @mathumala.nachiappan@penske.com with this blocker? | Yvette Urso | 12/09/22 12:46 AM
Row 7 | Hi @yvette.urso@penske.com - Once this dependent jar modernization is complete, this parent application can be progressed. | Mathumala Nachiappan | 12/02/22 5:24 PM
Row 7 | @mathumala.nachiappan@penske.com Can you clarify this blocker? | Yvette Urso | 11/30/22 12:36 AM
Row 7 | <Mathu> Dependent with penske-secure-logger-1.0.0.jar | Mathumala Nachiappan | 11/23/22 3:11 AM
Row 8 | @praneeth.gayam@penske.com After disabling the test cases & jtest results. we are getting following issue while executing bamboo build as requested. 12-Jun-2023 14:04:45 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:04:45 [INFO] BUILD FAILURE 12-Jun-2023 14:04:45 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:04:45 [INFO] Total time: 9.394 s 12-Jun-2023 14:04:45 [INFO] Finished at: 2023-06-12T14:04:45-04:00 12-Jun-2023 14:04:45 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:04:45 [ERROR] Failed to execute goal org.apache.maven.plugins:maven-surefire-plugin:3.0.0-M4:test (unit-tests) on project bbupload: There are test failures. 12-Jun-2023 14:04:45 [ERROR] | Rajesh | 06/12/23 11:43 PM
| @rajesh.haravde@penske.com , Still seeing test failures. Let me check with my CICD team on this. | Gayam | 06/13/23 1:36 AM
| @rajesh.haravde@penske.com , unit tests are disabled and build got success https://bamboo.penske.com/browse/BBUPLOADBP-BBULD0 | Gayam | 06/14/23 3:45 AM
Row 8 | Please confirm if we can validate the bamboo script for this project and which branch | Rajesh | 06/08/23 11:16 PM
| @rajesh.haravde@penske.com , This app is already onboarded to Bamboo. Please check. https://bamboo.penske.com/browse/BBUPLOADBP-BBULD0/ | Gayam | 06/09/23 1:22 AM
Row 8 | PR been executed please take it forward. Thanks for guidance on process Praneeth appreciated. | Rajesh | 05/18/23 1:50 AM
| Sure @rajesh.haravde@penske.com . We will let you know once we deploy to dev. | Gayam | 05/18/23 10:47 PM
| @rajesh.haravde@penske.com , Test cases are failing in this application. Please check the build at https://bamboo.penske.com/browse/BBUPLOADBP-BBULD1-UTEST-3 Could you please work with your team to fix them. Thanks. | Gayam | 05/22/23 9:27 PM
Row 8 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/bbupload-web/pull-requests/3/overview Thanks. | Gayam | 02/16/23 11:01 PM
Row 8 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:44 PM
Row 8 | WAR is building now | Hugo Scavino | 01/19/23 3:14 AM
Row 8 | I moved the XML files from source and test source to the appropriate resources folder to follow maven conventions. XML files should not be the src/main/java directory. Added simple console log4j into test resources. Please see the below comment I added in one of the tests. Application Owner should review. Test was failing and I made a more generic test but would prefer their test if possible. // TODO This test was failing because the recordset1 was not the same argument. Should be resolved. | Hugo Scavino | 01/19/23 3:14 AM
Row 8 | @rajesh.haravde@penske.com , I provided the response above. Please check. | Gayam | 01/18/23 9:13 PM
Row 8 | We updated Praneeth and waiting on response. | Rajesh | 01/18/23 8:20 PM
Row 8 | BBUpload failed its maven build, so I couldn’t test it. These are the main errors that came up. | Rajesh | 01/18/23 8:20 PM
Row 8 | @rajesh.haravde@penske.com , This is ragarding the issues you posted in the email. Maven build is failing when we run the tests but without tests it is getting successful. @hugo.scavino@penske.com | Gayam | 01/14/23 12:29 AM
Row 8 | @krishna.tanga@penske.com / @yogesh.sinha@penske.com , Please review the log4j/maven changes in below MR and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/bbupload-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 11/28/22 9:02 AM
Row 9 | Hi @praneeth.gayam@penske.com looks like I am not able to publish the local version of my bill-apprunner to artifactory. Getting 403 error. [ERROR] Failed to execute goal org.apache.maven.plugins:maven-deploy-plugin:2.8.2:deploy (default-deploy) on project bill-apprunner: Failed to deploy artifacts: Could not transfer artifact com.penske.billing:bill-apprunner:jar:2.0.0-20230601.150206-1 from/to billing-development (https://artifactory.penske.com/artifactory/billing-mvn-development-local): Access denied to https://artifactory.penske.com/artifactory/billing-mvn-development-local/com/penske/billing/bill-apprunner/2.0.0-SNAPSHOT/bill-apprunner-2.0.0-20230601.150206-1.jar. Error code 403, Forbidden -> [Help 1] | Dylan | 06/01/23 8:34 PM
| looks like it should only deploy when we run bamboo. Going to move the code from develop_log4j to develop | Dylan | 06/01/23 8:46 PM
| Thanks @dylan.price@penske.com . Build is successfully completed and as mentioned deployed to Dev server ghlx006ptlge. Could you please check and let us know whether it is working without any issues. Thanks. | Gayam | 06/01/23 10:55 PM
Row 9 | Hi @praneeth.gayam@penske.com I have created a generic unit test to satisfy bamboo. Could you please try again? | Dylan | 05/26/23 1:48 AM
| Hi @dylan.price@penske.com , develop_log4j build is successful. Could you please merge the code develop branch. https://bitbucket.penske.com/projects/ARPROJ/repos/bill-apprunner-batch/pull-requests/8/overview | Gayam | 05/31/23 12:50 AM
| Hi @praneeth.gayam@penske.com looks like the repos are being built for our team. I no longer have access to bill-apprunner-batch path on bitbucket. I will let you know as soon as the repo is moved to a billing repo and I can merge the develop_log4j changes into develop branch. | Dylan | 05/31/23 5:19 PM
| Sure @dylan.price@penske.com . Thanks | Gayam | 05/31/23 11:52 PM
Row 9 | @praneeth.gayam@penske.com thank you! I have merged the pull request into develop branch. Can you please move onto bamboo for this application? | Dylan | 05/17/23 5:33 PM
| Sure @dylan.price@penske.com . We will let you know once it is onboarded to Bamboo. | Gayam | 05/18/23 12:39 AM
| @dylan.price@penske.com , The following question we asked above but didn't get the response. Could you please check it and provide your response. "This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application." | Gayam | 05/18/23 10:40 PM
| Hi @praneeth.gayam@penske.com this application is an internal application. It will deploy to a separate server though outside of the original batch box. It will deploy as an internal batch application to ghlx006ptlge.penske.com | Dylan | 05/24/23 11:52 PM
| @dylan.price@penske.com , We onboarded this app to Bamboo but unit tests are getting failed. Could you please check. https://bamboo.penske.com/browse/PBSBP-BILAP2 | Gayam | 05/25/23 8:41 PM
| Hi @praneeth.gayam@penske.com yes there are no test cases so the check is failing. Let me create a feature and fix this issue. I will merge it into the develop branch. I will let you know here when that is completed. | Dylan | 05/25/23 10:32 PM
Row 9 | @praneeth.gayam@penske.com is there a way we could move this application off of the architecture repo and into https://bitbucket.penske.com/projects/PBJB ? | Dylan | 05/24/23 11:53 PM
| Yes @dylan.price@penske.com . We can do that. There is an email going on between billing team and Yvette to decide on Billing project. Is it decided to move all billing repos under PBJB or only this bill_apprunner needs to be moved under PBJB? | Gayam | 05/25/23 2:35 AM
Row 9 | @praneeth.gayam@penske.com Hi Praneeth I have created a pull request to move some code into your develop_log4j branch. Once you confirm, I will accept the pull request you have out there for me. | Dylan | 05/16/23 11:47 PM
| @dylan.price@penske.com , You can merge as you are the AO. | Gayam | 05/17/23 2:09 AM
Row 9 | @praneeth.gayam@penske.com added comment in bitbucket push request | Dylan | 05/03/23 9:18 PM
| @dylan.price@penske.com , I just replied to your questions. Please check and let me know if you have any other question. Thanks. | Gayam | 05/04/23 12:09 AM
Row 9 | Hi @praneeth.gayam@penske.com getting following error when I try to run through my local: [INFO] Scanning for projects... [ERROR] [ERROR] Some problems were encountered while processing the POMs: [FATAL] Non-resolvable parent POM for com.penske.billing:bill-apprunner:2.0.0-SNAPSHOT: com.penske.mis.common:batch-parent:pom:1.0.0-DJ-BAT-18-04d91b2 was not found in https://repo.maven.apache.org/maven2 during a previous attempt. This failure was cached in the local repository and resolution is not reattempted until the update interval of central has elapsed or updates are forced and 'parent.relativePath' points at wrong local POM @ line 10, column 10 @ [ERROR] The build could not read 1 project -> [Help 1] [ERROR] [ERROR] The project com.penske.billing:bill-apprunner:2.0.0-SNAPSHOT (C:\ptl_mis\AvolentSource\bill-apprunner\pom.xml) has 1 error [ERROR] Non-resolvable parent POM for com.penske.billing:bill-apprunner:2.0.0-SNAPSHOT: com.penske.mis.common:batch-parent:pom:1.0.0-DJ-BAT-18-04d91b2 was not found in https://repo.maven.apache.org/maven2 during a previous attempt. This failure was cached in the local repository and resolution is not reattempted until the update interval of central has elapsed or updates are forced and 'parent.relativePath' points at wrong local POM @ line 10, column 10 -> [Help 2] [ERROR] [ERROR] To see the full stack trace of the errors, re-run Maven with the -e switch. [ERROR] Re-run Maven using the -X switch to enable full debug logging. [ERROR] [ERROR] For more information about the errors and possible solutions, please read the following articles: [ERROR] [Help 1] http://cwiki.apache.org/confluence/display/MAVEN/ProjectBuildingException [ERROR] [Help 2] http://cwiki.apache.org/confluence/display/MAVEN/UnresolvableModelException | Dylan | 04/11/23 8:36 PM
| @dylan.price@penske.com , You need to use the Billing groups settings.xml in your .m2 location. Please check and let me know whether you are facing same issue. | Gayam | 04/12/23 1:05 AM
Row 9 | Hi @praneeth.gayam@penske.com looks like I do not have the correct privileges to merge your pull request. I will work with Architecture to get this access. In the meantime I will clone the repo down to my local machine and start testing the maven changes. | Dylan | 04/06/23 11:30 PM
Row 9 | @praneeth.gayam@penske.com we are scheduling this to be tested in April 2023 | Dylan | 03/30/23 9:20 PM
Row 9 | @venkatesh.hossalinever@penske.com , Maven changes are completed. Please review the app at https://bitbucket.penske.com/projects/ARPROJ/repos/bill-apprunner-batch/pull-requests/3/overview | Gayam | 03/02/23 3:01 AM
Row 9 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 2:07 AM
| Thank you @venkatesh.hossalinever@penske.com . Could you please provide the response which I asked above. | Gayam | 03/02/23 1:31 AM
Row 9 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:26 AM
Row 9 | @dylan.price@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:50 AM
Row 9 | @sam.skelding@penske.com / @dylan.price@penske.com , This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:57 AM
Row 10 | Updated bamboo plan and I am seeing the bill-avobatch.jar file successfully deployed out in DEV. The user is not correct, so I have made the changes in the QA deploy and will test after the 5pm deploy window. If this works, I will do the same for all the "bill_" applications and start testing them in QA next week. | Dylan | 08/04/23 1:23 AM
Row 10 | @praneeth.gayam@penske.com this looks great! Can you please create this for a dev bamboo build off the develop branch? | Dylan | 06/01/23 10:30 PM
| Sure @dylan.price@penske.com . We will let you know once it is onboarded to Bamboo. | Gayam | 06/01/23 10:58 PM
| @dylan.price@penske.com , Do you have idea how this app is currently getting deployed to CBOS batch box? | Gayam | 06/02/23 11:37 PM
| Hi @praneeth.gayam@penske.com it gets packaged in the "CBOS_PROD_PACKAGE" and gets moved to /var/tmp on the CBOS servers | Dylan | 06/06/23 12:51 AM
| @dylan.price@penske.com , bill_apprunner is successfully deployed to Dev instance ghlx006ptlge. I believe ghlx006ptlge is a CBOS server. You mentioned bill_avobatch should be deployed to ghlx097ptlge server. But getting bamboo fails to connect to ghlx097ptlge server. Bamboo did not face this issue while connecting to ghlx006ptlge server. Could you please check and guide us whether the ghlx097ptlge server is correct or not. https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=141072739 | Gayam | 06/13/23 2:23 AM
| Hi @praneeth.gayam@penske.com I am sorry! you are correct -- ghlx006ptlge is the correct server. This will be the same for bill_xmlloader_mp | Dylan | 06/14/23 5:13 PM
| Sure @dylan.price@penske.com | Gayam | 06/15/23 12:44 AM
| @dylan.price@penske.com , Dev hostname changed to ghlx006 and deploy plan re onboarded. Dev deployment also successful. Please verify. | Gayam | 06/16/23 2:36 AM
Row 10 | @praneeth.gayam@penske.com I have merged my changes in with "develop_log4j". Could you please merge this into the "develop" branch and start with bamboo testing? | Dylan | 05/26/23 6:19 PM
Row 10 | Review: @dylan.price@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/bill-avo-batch/pull-requests/5/overview | Gayam | 04/15/23 1:13 AM
Row 10 | @praneeth.gayam@penske.com No issues with the database property passwords. It is being excluded in the build script. Please proceed with log4j changes | Dylan | 03/30/23 9:19 PM
Row 10 | @sam.skelding@penske.com / @dylan.price@penske.com , This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:57 AM
| This application is an internal CBOS batch application and deploys to ghlx097ptlge (our CBOS batch box). Not sure how you would mark this in your artifactory -- wondering if CBOS should have its own instance type. | Dylan | 03/06/23 6:45 PM
| @hugo.scavino@penske.com / @balu.mohan@penske.com , Could you please check @dylan.price@penske.com question above and provide your response. Thanks. | Gayam | 03/06/23 11:57 PM
Row 10 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 10 | @dylan.price@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:50 AM
Row 11 | Review: @dylan.price@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/PBTCBOS/repos/bill-rpginvoker-batch/pull-requests/3/overview | Gayam | 06/30/23 1:19 AM
Row 11 | Hi @praneeth.gayam@penske.com we will remove the properties file and have it moved to /apps/conf on the server. Could you please continue with your log4j/maven changes? As soon as develop_log4j is up to date with both changes I will pull down and take care of the property files | Dylan | 05/26/23 6:36 PM
| Sure @dylan.price@penske.com . We will let you know once we complete the mavanization. | Gayam | 05/30/23 9:41 AM
Row 11 | @sam.skelding@penske.com / @mark.weaver@penske.com , This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:55 AM
| This application is an internal CBOS batch application and deploys to ghlx097ptlge (our CBOS batch box). Not sure how you would mark this in your artifactory -- wondering if CBOS should have its own instance type. | Dylan | 03/06/23 6:45 PM
| @hugo.scavino@penske.com , Could you please check @dylan.price@penske.com question above and provide your response. Thanks. @balu.mohan@penske.com | Gayam | 03/06/23 11:56 PM
Row 11 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 11 | @mark.weaver@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:52 AM
Row 12 | Hi @praneeth.gayam@penske.com this application has been merged into "develop" branch. Please create the bamboo plan for DEV | Dylan | 06/02/23 12:44 AM
| Thanks @dylan.price@penske.com . We will let you know once we onboard to Bamboo. | Gayam | 06/02/23 11:40 PM
| @dylan.price@penske.com , Onboarded the build and deploy plan successfully but dev deployment to cbos server ghlx097ptlge getting failed. It's look like that deployment is failing because it can't connect to host server(ghlx097ptlge@penske.com). Same issue we are facing in bill-avo-batch. Could you please check and guide us whether the ghlx097ptlge server is correct or not. | Gayam | 06/14/23 3:50 AM
| Hi @praneeth.gayam@penske.com I am sorry! you are correct -- ghlx006ptlge is the correct server. This will be the same for bill_avobatch | Dylan | 06/14/23 5:14 PM
| @dylan.price@penske.com , Dev hostname changed to ghlx006 and deploy plan re onboarded. Dev deployment also successful. Please verify. | Gayam | 06/16/23 2:35 AM
Row 12 | Review: @dylan.price@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/ARPROJ/repos/bill-xmlloader-mp-batch/pull-requests/4/overview | Gayam | 05/10/23 11:32 PM
Row 12 | @praneeth.gayam@penske.com No issues with the database property passwords. It is being excluded in the build script. Please proceed with log4j changes | Dylan | 03/30/23 9:22 PM
Row 12 | @sam.skelding@penske.com / @dylan.price@penske.com , This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:56 AM
| This application is an internal CBOS batch application and deploys to ghlx097ptlge (our CBOS batch box). Not sure how you would mark this in your artifactory -- wondering if CBOS should have its own instance type. | Dylan | 03/06/23 6:45 PM
| @hugo.scavino@penske.com , Could you please check @dylan.price@penske.com question above and provide your response. Thanks. @balu.mohan@penske.com | Gayam | 03/06/23 11:55 PM
Row 12 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 12 | @dylan.price@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:50 AM
Row 13 | Review: This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/PBTCBOS/repos/bill-xmlloader-st-batch/pull-requests/3/overview | Gayam | 07/14/23 6:40 AM
Row 13 | Hi @praneeth.gayam@penske.com the secrets file on this application is fine. it will be hidden behind a configuration file that only webmasters have access to. Could you please start maven/log4j changes? | Dylan | 06/02/23 12:50 AM
| Thanks @dylan.price@penske.com . we will do the changes and will let you know. | Gayam | 06/02/23 11:44 PM
Row 13 | Secrets: @dylan.price@penske.com , secrets are shared in the email. Please check and confirm. Thanks. | Gayam | 02/21/23 5:49 AM
Row 13 | @sam.skelding@penske.com / @dylan.price@penske.com , This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:57 AM
| Adding to above question, @hugo.scavino@penske.com , While doing the svn to bb migration we are facing the issue "Software caused connection abort: Error running context: ". I believe this is because of timeout issue. Could you please increase the timeout in svn server. Thanks. | Gayam | 01/20/23 1:13 AM
| @praneeth.gayam@penske.com please share the SVN branch name. I can try from local PC and in the alternative from an onprem linux server like the Arch Server | Hugo Scavino | 01/26/23 8:36 PM
| @hugo.scavino@penske.com , My team is working with CICD team to resolve this issue. I will let you know incase if we need help from you. @haribabu.challa@penske.com | Gayam | 01/26/23 8:54 PM
| @hugo.scavino@penske.com , CICD team also unable to resolve the issue. Could you please look into it. Following are the details. https://svn.penske.com/svn/avolent/ptl_customization/billing/standalone/bill_xmlloader_st/ Branch: trunk | Gayam | 02/01/23 3:40 AM
| @hugo.scavino@penske.com , I just want to update you that we are able to resolve the issue. | Gayam | 02/08/23 12:22 AM
Row 14 | @frank.d'angelo@penske.com - Per Frank please get with him prior to starting - this app may go away. | Yvette Urso | 01/25/23 2:54 AM
Row 14 | @frank.d'angelo@penske.com / @shweta.gupta@penske.com, For this application SVN repo available https://svn.penske.com/svn/ebusiness/extranet/billingcommons/. But Bamboo plan is not available. We need production branch confirmation for log4j-Migration and without existing bamboo build we could not find this. Could you please let us know what is the latest production branch. Thanks. @hugo.scavino@penske.com / @mathumala.nachiappan@penske.com | Gayam | 01/14/23 12:50 AM
Row 15 | @praneeth.gayam@penske.com Please proceed with log4j migration for billing service. you can use the source code from following location https://svn.penske.com/svn/fieldsys/other/billing-service/trunk/billing-service | Venkatesh | 08/03/23 12:48 AM
| @praneeth.gayam@penske.com Billing service we have active development, please keep log4j migration on hold. | Venkatesh | 08/03/23 9:27 PM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 08/04/23 12:53 AM
Row 15 | I am working on some of the changes, please wait for log4j and maven changes implementation. | Venkatesh | 03/17/23 7:51 PM
Row 15 | @sam.skelding@penske.com / @manish.sisodiya@penske.com , This application in SVN contains multiple src folders. Ideally each application should have only 1 src folder. Could you please check and clarify us. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 1:33 AM
| The src that should be used is https://svn.penske.com/svn/fieldsys/other/billing-service/trunk/billing-service/src/ | Dylan | 03/07/23 12:32 AM
| Thanks @dylan.price@penske.com . Is there any active development going on this app? Because we are seeing latest commits in the given src folder. | Gayam | 03/07/23 7:59 PM
Row 17 | @dale.porter@penske.com , onboarded to bamboo and deployed to artifactory. https://bamboo.penske.com/browse/PNSKESPLNGBP-PSUJ | Gayam | 07/12/23 1:40 AM
Row 17 | Sarath has approved and merged this back on June 28th in bitbucket. Thank you. | Dale Porter | 07/11/23 12:02 AM
Row 17 | Review: @stella.george@penske.com / @dave.kost@penske.com , This utility app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/penske_spellingutility/pull-requests/2/overview | Gayam | 06/24/23 12:25 AM
Row 17 | There are no secrets exist for this application. So changing the status of this app to Cap Maven. | Gayam | 06/23/23 12:13 AM
Row 18 | @praneeth.gayam@penske.com I have verified the code and it looks like you have taken the base code from https://svn.penske.com/svn/fieldsys/other/bodyshop/tags/_T_Prod_Build_2018-09-05, but we did one more deploy in November 2020 https://svn.penske.com/svn/fieldsys/other/bodyshop/tags/_T_Prod_Build_2020-11-22 and somehow bamboo is not showing this in the plan. I have merged the pull request to develop branch and while going through the history only I could able to find this issue in bamboo. Could you please take the base source code from https://svn.penske.com/svn/fieldsys/other/bodyshop/tags/_T_Prod_Build_2020-11-22 and create the pull request again. | Subramanian | 07/28/23 1:59 AM
| @subramanian.vennimalayan@penske.com , We need to rework on this app. Because I don't think pull from 2023-11-22 branch to mavanization branch may cause lot of problems as both have different folder structures. We will rework on this app. | Gayam | 08/01/23 1:21 AM
Row 18 | @falgun.patel@penske.com / @subramanian.vennimalayan@penske.com , This app is ready for your review. Please verify and merge. Thanks https://bitbucket.penske.com/projects/MAIN/repos/bodyshop-web/pull-requests/3/overview | Gayam | 07/20/23 11:15 PM
Row 18 | There are no secrets exist for this application. So changing the status of this app to Cap Maven. | Gayam | 06/23/23 12:11 AM
Row 18 | Copied Subramanian's comments @praneeth.gayam@penske.com Please use the folder with bodyshop6 | Patel | 06/15/23 1:35 AM
| Thanks | Gayam | 06/15/23 1:44 AM
Row 18 | @praneeth.gayam@penske.com the status is saying Waiting on AO. we did not see any comment or emails. | Stella george | 06/14/23 2:06 AM
| @stella.george@penske.com , Not sure what happened to the question I asked. But let me give you the question again. For this application prod reference in Bamboo build is pointed to https://svn.penske.com/svn/fieldsys/other/bodyshop/tags/_T_Prod_Build_2018-09-05 But this reference have two folders and both the folders have java source and webcontent folder in it. Need clarification which folder is correct. Following are the folders info. https://svn.penske.com/svn/fieldsys/other/bodyshop/tags/_T_Prod_Build_2018-09-05/bodyshop/ https://svn.penske.com/svn/fieldsys/other/bodyshop/tags/_T_Prod_Build_2018-09-05/bodyshop6/ | Gayam | 06/14/23 3:38 AM
Row 19 | @vinay.ramanand@penske.com , I sent the secrets in the email. Could you please verify them. | Gayam | 03/10/23 2:00 AM
Row 19 | Bamboo Project Setup 2/1/23 - Yvette sent Tim Fox the below question via email: Tim, We are submitting a request for a Bamboo Project and would like to know who to add from the HR team as the Admin of that Project? That person can then create what ever they need for other access and repositories, etc. | Yvette Urso | 02/01/23 8:53 PM
Row 19 | @hugo.scavino@penske.com , This is regarding log file size which needs to be mentioned in log4j2.xml for file appenders. You mentioned that it has to be maximum 1MB in confluence page. But for bos.war application's log4j.properties has the file size of 4096kb. In this case do we need to mention 4MB in log4j2.xml or 1MB only? | Gayam | 01/18/23 3:02 AM
| We should keep what they have had in the past. Let them know they are exceeding the recommendation but we should keep what they have when deploying to DEV. | Hugo Scavino | 01/18/23 9:38 PM
Row 20 | Hi @praneeth.gayam@penske.com develop_log4j branch has been merged with develop. Please start on the bamboo build for DEV. | Dylan | 06/06/23 11:47 PM
| Sure @dylan.price@penske.com | Gayam | 06/07/23 5:37 AM
| @dylan.price@penske.com ,Onboarded develop branch to Bamboo. Please deploy to QA. https://bamboo.penske.com/browse/BUZONEBBP-BUZBCH0 | Gayam | 06/09/23 2:03 AM
Row 20 | Review: @dylan.price@penske.com / @mark.weaver@penske.com , this app is ready for your review. Please verify in the below PR. https://bitbucket.penske.com/projects/ARPROJ/repos/buzone-batch/pull-requests/3/overview | Gayam | 04/03/23 2:52 AM
Row 20 | @praneeth.gayam@penske.com the MonetaryConversion.jar can be added to artifactory. We also have no code changes needed for the password file. | Dylan | 03/07/23 12:56 AM
Row 20 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 20 | @mark.weaver@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:52 AM
Row 20 | @rafiq.melath@penske.com / @mark.weaver@penske.com , For buzonebatch application, there is a dependency jar 'MonetaryConversion.jar' which is not available in artifactory. We need this in artifactory for mavanization. Could you please provide your approval to upload this jar to artifactory in the following location. Thanks. groupid : com.penske.util artifactid : MonetaryConversion version : Default @hugo.scavino@penske.com , @mathumala.nachiappan@penske.com , @swati.saxena@penske.com | Gayam | 01/20/23 12:53 AM
Row 21 | Hi @mathumala.nachiappan@penske.com I cannot find this application in our application list. Could you please remove this from the smart sheet? This application will not need moved over. | Dylan | 06/06/23 11:43 PM
| @dylan.price@penske.com , we can't find the repo or bamboo build for this app. Can I change the status to Reitre? @yvette.urso@penske.com | Gayam | 06/09/23 1:58 AM
| @praneeth.gayam@penske.com yes we can retire this application | Dylan | 06/13/23 1:24 AM
| @yvette.urso@penske.com , As per above conversation, we are retiring this application. Thanks. | Gayam | 06/13/23 1:33 AM
Row 21 | @mathumala.nachiappan@penske.com This application does not have a bamboo build. We may need to create one for it. I need to see where the codebase is for this application then get back to you | Dylan | 03/07/23 12:40 AM
Row 21 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 21 | @sreenivasulu.mupparaju@penske.com - For this App, we referred the bamboo key of 'PBSBP'. Got the project name as 'cbos'. But doesnt look related to this application. Pls. help us to clarify this CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 12:09 PM
| @sreenivasulu.mupparaju@penske.com - Pls. ignore the previous comment. Actual issue is we couldnt find the Bamboo build for this app. Pls. help us with the bamboo reference and the branch/folder to refer for modernization changes CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 02/10/23 11:16 AM
Row 21 | @mathumala.nachiappan@penske.com moved to AO Bamboo Status | Yvette Urso | 12/15/22 2:44 AM
Row 22 | @praneeth.gayam@penske.com can you please remove dupp apps. | Rajesh | 04/26/23 8:53 PM
| @yvette.urso@penske.com can help on removing dup apps. I am not authorized too delete them. @rajesh.haravde@penske.com | Gayam | 04/27/23 3:13 AM
Row 22 | validation work in progress. | Rajesh | 01/18/23 8:23 PM
Row 23 | Project got build issue while dev deployment with following Error: 13-Jun-2023 14:18:46 Connecting to ghlx008ptlge.penske.com on port: 22 13-Jun-2023 14:18:46 Uploading '/apps/bamboows/build-dir/142737482-142803182/ccms.tgz' to '${bamboo.static_ftpdir_service}/ccms'... 13-Jun-2023 14:18:46 Failed to upload file '/apps/bamboows/build-dir/142737482-142803182/ccms.tgz' 13-Jun-2023 14:18:46 net.schmizz.sshj.xfer.scp.SCPRemoteException: Remote SCP command had error: scp: ${bamboo.static_ftpdir_service}/ccms: No such file or directory 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPEngine.check(SCPEngine.java:73) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPEngine.sendMessage(SCPEngine.java:133) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPUploadClient.sendFile(SCPUploadClient.java:105) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPUploadClient.process(SCPUploadClient.java:84) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPUploadClient.startCopy(SCPUploadClient.java:76) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPUploadClient.copy(SCPUploadClient.java:54) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPUploadClient.copy(SCPUploadClient.java:47) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPUploadClient.copy(SCPUploadClient.java:43) 13-Jun-2023 14:18:46 at net.schmizz.sshj.xfer.scp.SCPFileTransfer.upload(SCPFileTransfer.java:55) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.plugins.scp.ScpTransport.transferFiles(ScpTransport.java:131) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.plugins.scp.ScpTask.execute(ScpTask.java:189) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.plugins.scp.ScpTask.run(ScpTask.java:62) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.plugins.scp.ScpTask.execute(ScpTask.java:49) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.task.TaskExecutorImpl.lambda$executeTasks$1(TaskExecutorImpl.java:319) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.task.TaskExecutorImpl.executeTaskWithPrePostActions(TaskExecutorImpl.java:258) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.task.TaskExecutorImpl.executeTasks(TaskExecutorImpl.java:319) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.task.TaskExecutorImpl.execute(TaskExecutorImpl.java:118) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.build.pipeline.tasks.ExecuteBuildTask.call(ExecuteBuildTask.java:73) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.v2.build.agent.DefaultBuildAgent.executeBuildPhase(DefaultBuildAgent.java:205) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.v2.build.agent.DefaultBuildAgent.build(DefaultBuildAgent.java:177) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.v2.build.agent.BuildAgentControllerImpl.lambda$waitAndPerformBuild$0(BuildAgentControllerImpl.java:169) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.variable.CustomVariableContextImpl.withVariableSubstitutor(CustomVariableContextImpl.java:118) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.v2.build.agent.BuildAgentControllerImpl.waitAndPerformBuild(BuildAgentControllerImpl.java:162) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.v2.build.agent.DefaultBuildAgent.lambda$start$0(DefaultBuildAgent.java:122) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.utils.BambooRunnables$1.run(BambooRunnables.java:48) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.security.ImpersonationHelper.runWith(ImpersonationHelper.java:26) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.security.ImpersonationHelper.runWithSystemAuthority(ImpersonationHelper.java:17) 13-Jun-2023 14:18:46 at com.atlassian.bamboo.security.ImpersonationHelper$1.run(ImpersonationHelper.java:41) 13-Jun-2023 14:18:46 at java.lang.Thread.run(Thread.java:748) 13-Jun-2023 14:18:46 Copy Failed. Some files were not uploaded successfully. 13-Jun-2023 14:18:46 '/apps/bamboows/build-dir/142737482-142803182/ccms.tgz' was not uploaded. 13-Jun-2023 14:18:46 Finished task 'SCP tgz' with result: Error 13-Jun-2023 14:18:46 Finalising the build... 13-Jun-2023 14:18:46 Stopping timer. 13-Jun-2023 14:18:46 Build 142737482-142803182-141073425 completed. 13-Jun-2023 14:18:46 Finished processing deployment result Deployment of '2.0.0-develop_log4j-SNAPSHOT-4' on 'dev_was8-deploy' | Rajesh | 06/13/23 11:50 PM
| We will check | Gayam | 06/14/23 3:06 AM
| @rajesh.haravde@penske.com , Issue got fixed. Please check. | Gayam | 06/15/23 12:54 AM
Row 23 | while executing build after disabling test cases requirement, though the project getting build successfully, but failing on missing pom.xml ARE WE MISSIGN ANY STEP HERE? PLEASE GUIDE. 12-Jun-2023 14:16:30 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:16:30 [INFO] BUILD FAILURE 12-Jun-2023 14:16:30 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:16:30 [INFO] Total time: 2.143 s 12-Jun-2023 14:16:30 [INFO] Finished at: 2023-06-12T14:16:30-04:00 12-Jun-2023 14:16:30 [INFO] ------------------------------------------------------------------------ 12-Jun-2023 14:16:30 [ERROR] Failed to execute goal org.codehaus.mojo:versions-maven-plugin:2.16.0:set (default-cli): Goal requires a project to execute but there is no POM in this directory (/apps/bamboows/build-dir/CCMS-CCMSW-BLD). Please verify you invoked Maven from the correct directory. -> [Help 1] 12-Jun-2023 14:16:30 [ERROR] | Rajesh | 06/12/23 11:47 PM
| @rajesh.haravde@penske.com , I am seeing that you ran the build on master branch. But the code is not yet merged to develop or master branch. You need to run the build on develop_log4j branch. | Gayam | 06/13/23 1:39 AM
Row 23 | Please confirm if we can validate the bamboo script for this project and which branch | Rajesh | 06/09/23 12:07 AM
| @rajesh.haravde@penske.com , this is also already onboarded . https://bamboo.penske.com/browse/CCMS-CCMSW0 | Gayam | 06/09/23 1:23 AM
Row 23 | We are getting maven build issue. following is the error messages: [4:37 PM] Peddoju, Narsimhamurthy (Penske) Error1: [ERROR] com.penske.ccms.service.impl.DefaultClientServiceTest.shouldUpdateContact Time elapsed: 0 s <<< ERROR! java.lang.IllegalStateException: Failed to load ApplicationContext Caused by: org.springframework.beans.factory.BeanDefinitionStoreException: Failed to parse configuration class [com.penske.ccms.configuration.ApplicationConfiguration]; nested exception is java.lang.NoSuchMethodError: org.slf4j.spi.LocationAwareLogger.log(Lorg/slf4j/Marker;Ljava/lang/String;ILjava/lang/String;Ljava/lang/Throwable;)V Caused by: java.lang.NoSuchMethodError: org.slf4j.spi.LocationAwareLogger.log(Lorg/slf4j/Marker;Ljava/lang/String;ILjava/lang/String;Ljava/lang/Throwable;)V error 2: [5/30/23 16:32:41:618 EDT] 0000005a webapp I com.ibm.ws.webcontainer.webapp.WebApp log SRVE0292I: Servlet Message - [ccms-web-git#ccms-web-git.war]:.Initializing Spring FrameworkServlet 'Dispatcher' @praneeth.gayam@penske.com [5/30/23 16:32:42:021 EDT] 0000005a ServletWrappe E com.ibm.ws.webcontainer.servlet.ServletWrapper init SRVE0271E: Uncaught init() exception created by servlet [Dispatcher] in application [ccms-web-git]: java.lang.NoSuchMethodError: org/slf4j/spi/LocationAwareLogger.log(Lorg/slf4j/Marker;Ljava/lang/String;ILjava/lang/String;Ljava/lang/Throwable;)V at org.apache.commons.logging.impl.SLF4JLocationAwareLog.debug(SLF4JLocationAwareLog.java:99) | Rajesh | 05/31/23 2:11 AM
| @rajesh.haravde@penske.com , Test cases are getting failed. Please check. | Gayam | 05/31/23 11:51 PM
Row 23 | @praneeth.gayam@penske.com can we proceed with "develop_log4j" branch for maven validation? | Rajesh | 05/30/23 10:45 PM
| Sure @rajesh.haravde@penske.com | Gayam | 05/31/23 1:02 AM
Row 23 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 23 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/ccms-web/pull-requests/3/overview Thanks. | Gayam | 02/16/23 11:05 PM
Row 23 | @rajesh.haravde@penske.com , we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:45 PM
Row 23 | validation work in progress. | Rajesh | 01/18/23 8:23 PM
Row 23 | @yvette.urso@penske.com - Its with CAP for Maven development changes | Mathumala Nachiappan | 12/15/22 10:26 AM
Row 23 | Moved to AO Maven status | Yvette Urso | 12/15/22 2:51 AM
Row 23 | Yes please upload it to Artifactory. as we are as per class path using this jar dependancy. | Rajesh | 12/12/22 10:10 PM
| Thanks @rajesh.haravde@penske.com . We will upload and will progress on ccms app. @mathumala.nachiappan@penske.com | Gayam | 12/13/22 12:01 AM
Row 23 | @krishna.tanga@penske.com , @rajesh.haravde@penske.com - SVN to BB Migration issue, mentioned previously is resloved now for ccms.war. We are looking for the update on the dependent jar. Here is the Artifactory details suggested for this jar from the package information. Pls. confirm this if you are fine to upload it to Artifactory. Group ID - com.penske.salessys Artifact ID - salessysutil Version - default CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 3:27 PM
Row 23 | @praneeth.gayam@penske.com - Adding the SVN to BB migration issue too | Mathumala Nachiappan | 12/01/22 9:13 PM
Row 23 | @krishna.tanga@penske.com / @yogesh.sinha@penske.com , ccms app depends on the jar salessysutil.jar. This jar is not available in SVN/BB repo and don't have bamboo build. Can we upload the jar into artifactory? @mathumala.nachiappan@penske.com | Gayam | 11/25/22 11:29 PM
Row 24 | In the build log. | Rajesh | 06/13/23 11:32 PM
| @rajesh.haravde@penske.com , Narsimha able to build from feature/maven branch and deployed to dev. | Gayam | 06/14/23 3:09 AM
Row 24 | @praneeth.gayam@penske.com please guide. Error 2-Jun-2023 14:19:17 Finished publishing of artifact Non required shared artifact: [Source], pattern: [src/**] in 19.73 ms 12-Jun-2023 14:19:17 Publishing an artifact: target 12-Jun-2023 14:19:17 Unable to publish artifact [target]: 12-Jun-2023 14:19:17 The artifact is required for down stream Stages and Jobs, build will now fail. 12-Jun-2023 14:19:17 The artifact hasn't been successfully published after 4.918 ms 12-Jun-2023 14:19:17 Publishing an artifact: XML 12-Jun-2023 14:19:17 Unable to publish artifact [XML]: 12-Jun-2023 14:19:17 The artifact is required for down stream Stages and Jobs, build will now fail. 12-Jun-2023 14:19:17 The artifact hasn't been successfully published after 5.120 ms 12-Jun-2023 14:19:17 Running post build plugin 'Artifactory Release Management Staging' 12-Jun-2023 14:19:17 Running post build plugin 'Artifactory Build Info Copier' 12-Jun-2023 14:19:17 Running post build plugin 'Artifactory Gradle Properties Info Copier' 12-Jun-2023 14:19:17 Running post build plugin 'npm Cache Cleanup' 12-Jun-2023 14:19:17 Running post build plugin 'NCover Results Collector' | Rajesh | 06/12/23 11:54 PM
| @rajesh.haravde@penske.com , where are you getting above error? | Gayam | 06/13/23 1:35 AM
Row 24 | @praneeth.gayam@penske.com can we proceed with "develop_log4j" branch for maven validation? | Rajesh | 05/30/23 10:46 PM
| Sure @rajesh.haravde@penske.com | Gayam | 05/31/23 1:01 AM
| @rajesh.haravde@penske.com , Onboard develop_log4j to bamboo and deploy to dev is completed. https://bamboo.penske.com/deploy/viewEnvironment.action?id=142802957 | Gayam | 06/01/23 12:08 AM
Row 24 | @rajesh.haravde@penske.com , Bamboo build for this app is https://bamboo.penske.com/browse/CCMS-CCMSSVVC | Gayam | 03/07/23 12:22 AM
Row 24 | GIT URL info: https://bitbucket.penske.com/scm/ptlcorp/ccmsservice-web.gitBranch :develop_log4J | Rajesh | 03/04/23 1:16 AM
Row 24 | Please build bamboo deployment script for development environment. | Rajesh | 03/04/23 1:11 AM
Row 24 | Thanks @rajesh.haravde@penske.com . Please review the below PR when you get a chance. https://bitbucket.penske.com/projects/PTLCORP/repos/ccmsservice-web/pull-requests/3/overview | Gayam | 02/16/23 10:44 PM
Row 24 | Its false positive please do the needful. no action needed at this time. | Rajesh | 02/16/23 3:43 AM
Row 24 | we do not want to address secrete mitigation at this movement. please move forward with project upgrade with respect to bitbucket, maven and log4j | Rajesh | 02/16/23 3:41 AM
Row 24 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:46 PM
Row 24 | validation work in progress. | Rajesh | 01/18/23 8:23 PM
Row 24 | @rajesh.haravde@penske.com / @krishna.tanga@penske.com , Log4j team completed log4j/maven changes on this app. Please review them in below MR and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/ccmsservice-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/10/22 3:29 AM
| We will do the needful as requested and get back to you the build result as early as possible. | Rajesh | 12/12/22 10:14 PM
Row 25 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:08 AM
| @rajesh.haravde@penske.com , develop_log4j branch is onboarded to Bamboo and build is failing because of test case failure. Please check. | Gayam | 06/10/23 1:38 AM
Row 25 | Getting following error, lava.lang.IllegalStateException: Failed to load ApplicationContext Caused by: org.springframework.beans.factory.UnsatisfiedDependencyException: Error creating bean with name 'customerContactService': Unsatisfied dependency expressed through field 'basicInformationDao'; nested exception is org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'basicInformationDao' defined in file [C:\Users\600224522\Workspaces\Git_Projects_workspace\ccmsxservice-git2\target\classes\com\penske\ccms\contact\basicinfo\BasicInformationDao.class]: Cannot resolve reference to bean 'primarySessionFactory' while setting bean property 'sqlSessionFactory'; nested exception is org.springframework.beans.factory.UnsatisfiedDependencyException: Error creating bean with name 'com.penske.ccms.configuration.PrimaryMapperConfiguration': Unsatisfied dependency expressed through field 'dataSource'; nested exception is org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'greenHillsDataSource' defined in com.penske.ccms.configuration.EmbeddedDataSourceConfiguration: Bean instantiation via factory method failed; nested exception is org.springframework.beans.BeanInstantiationException: Failed to instantiate [javax.sql.DataSource]: Factory method 'greenHillsDataSource' threw exception; nested exception is org.springframework.jdbc.datasource.init.CannotReadScriptException: Cannot read SQL script from class path resource [setup/create-ccms-database.sql]; nested exception is java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist Caused by: org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'basicInformationDao' defined in file [C:\Users\600224522\Workspaces\Git_Projects_workspace\ccmsxservice-git2\target\classes\com\penske\ccms\contact\basicinfo\BasicInformationDao.class]: Cannot resolve reference to bean 'primarySessionFactory' while setting bean property 'sqlSessionFactory'; nested exception is org.springframework.beans.factory.UnsatisfiedDependencyException: Error creating bean with name 'com.penske.ccms.configuration.PrimaryMapperConfiguration': Unsatisfied dependency expressed through field 'dataSource'; nested exception is org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'greenHillsDataSource' defined in com.penske.ccms.configuration.EmbeddedDataSourceConfiguration: Bean instantiation via factory method failed; nested exception is org.springframework.beans.BeanInstantiationException: Failed to instantiate [javax.sql.DataSource]: Factory method 'greenHillsDataSource' threw exception; nested exception is org.springframework.jdbc.datasource.init.CannotReadScriptException: Cannot read SQL script from class path resource [setup/create-ccms-database.sql]; nested exception is java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist Caused by: org.springframework.beans.factory.UnsatisfiedDependencyException: Error creating bean with name 'com.penske.ccms.configuration.PrimaryMapperConfiguration': Unsatisfied dependency expressed through field 'dataSource'; nested exception is org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'greenHillsDataSource' defined in com.penske.ccms.configuration.EmbeddedDataSourceConfiguration: Bean instantiation via factory method failed; nested exception is org.springframework.beans.BeanInstantiationException: Failed to instantiate [javax.sql.DataSource]: Factory method 'greenHillsDataSource' threw exception; nested exception is org.springframework.jdbc.datasource.init.CannotReadScriptException: Cannot read SQL script from class path resource [setup/create-ccms-database.sql]; nested exception is java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist Caused by: org.springframework.beans.factory.BeanCreationException: Error creating bean with name 'greenHillsDataSource' defined in com.penske.ccms.configuration.EmbeddedDataSourceConfiguration: Bean instantiation via factory method failed; nested exception is org.springframework.beans.BeanInstantiationException: Failed to instantiate [javax.sql.DataSource]: Factory method 'greenHillsDataSource' threw exception; nested exception is org.springframework.jdbc.datasource.init.CannotReadScriptException: Cannot read SQL script from class path resource [setup/create-ccms-database.sql]; nested exception is java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist Caused by: org.springframework.beans.BeanInstantiationException: Failed to instantiate [javax.sql.DataSource]: Factory method 'greenHillsDataSource' threw exception; nested exception is org.springframework.jdbc.datasource.init.CannotReadScriptException: Cannot read SQL script from class path resource [setup/create-ccms-database.sql]; nested exception is java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist Caused by: org.springframework.jdbc.datasource.init.CannotReadScriptException: Cannot read SQL script from class path resource [setup/create-ccms-database.sql]; nested exception is java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist Caused by: java.io.FileNotFoundException: class path resource [setup/create-ccms-database.sql] cannot be opened because it does not exist | Rajesh | 05/31/23 1:09 AM
| @narsimhamurthy.peddoju@penske.com , As discussed test cases are getting failed. Please check. Thanks. | Gayam | 06/01/23 12:27 AM
Row 25 | @praneeth.gayam@penske.com can we proceed with "develop_log4j" branch for maven validation? | Rajesh | 05/30/23 10:46 PM
| Sure @rajesh.haravde@penske.com | Gayam | 05/31/23 1:02 AM
Row 25 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 25 | we confirm its false positive. we do not want to address secrete mitigation at this movement. please move forward with project upgrade with respect to bitbucket, maven and log4j | Rajesh | 02/16/23 3:43 AM
| Thanks @rajesh.haravde@penske.com . Please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/ccmsxservice-web/pull-requests/3/overview Thanks. | Gayam | 02/16/23 11:20 PM
Row 25 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:46 PM
Row 25 | validation work in progress. | Rajesh | 01/18/23 8:24 PM
Row 25 | @krishna.tanga@penske.com / @yogesh.sinha@penske.com We have completed log4j, maven changes. Please review, merge and provide your approval for the deployment. https://bitbucket.penske.com/projects/PTLCORP/repos/ccmsxservice-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 11/29/22 7:15 AM
| We will do the needful and get back to you on build result with maven as requested. | Rajesh | 12/12/22 10:15 PM
Row 26 | @vinay.ramanand@penske.com , I sent the secrets in the email. Could you please verify them. | Gayam | 03/10/23 2:01 AM
Row 26 | Bamboo Project Setup 2/1/23 - Yvette sent Tim Fox the below question via email: Tim, We are submitting a request for a Bamboo Project and would like to know who to add from the HR team as the Admin of that Project? That person can then create what ever they need for other access and repositories, etc. | Yvette Urso | 02/01/23 8:53 PM
Row 27 | @praneeth.gayam@penske.com cmns application looks like it has a dependency on the "billingservice" application. The class "RepairOrderDetail" that you were looking for is inside the BIllingService application: https://svn.penske.com/svn/fieldsys/other/billing-service/trunk/BillingUtility/src/com/penske/cns/models/RepairOrderDetail.java NotificationContract object is also in there. | Dylan | 06/07/23 12:33 AM
| Thanks @dylan.price@penske.com . we will check and get back to you. | Gayam | 06/07/23 5:45 AM
| @dylan.price@penske.com , It looks like the java classes which you mentioned above are under BillingUtility. There is a jar under lib folder of cmns application with name BillingUtility. I believe this jar is created from the svn location which you mentioned above. So do we need to create a separate repo for BillingUtility and Bamboo build and modernize it. | Gayam | 06/10/23 2:30 AM
| We are modernizing billing utility as we got the approval in another app. So changing the status to Cap maven. | Gayam | 07/18/23 6:10 PM
Row 27 | @mark.weaver@penske.com / @dylan.price@penske.com , We are facing build issues with below import statements while doing initial setup in local. We are unable to find the dependent jar in ptlcommon or inside the project. class name ; RepairOrderReportPrint.java import com.penske.cns.models.RepairOrderDetail; Other imports causing issues import com.penske.cns.models.mailer.NotificationContact; Could you please check and provide the correct dependency jar to resolve these issues. Thanks. | Gayam | 03/14/23 11:34 PM
Row 27 | @praneeth.gayam@penske.com please use the following SVN url: https://svn.penske.com/svn/fieldsys/other/customer-notification-system/trunk/cns-web/ | Dylan | 03/07/23 12:43 AM
Row 27 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 27 | @manish.sisodiya@penske.com , This application has complex folder structure at https://svn.penske.com/svn/fieldsys/other/customer-notification-system/tags/prod/1.0.3_20170531/ We are not sure on which folder we need to start working on it. Could you please check and guide us. Thanks. | Gayam | 01/30/23 3:48 AM
Row 27 | @praneeth.gayam@penske.com - To discuss with AO on folder structure | Mathumala Nachiappan | 01/10/23 10:46 AM
Row 28 | @yvette.urso@penske.com , There is a app already under billing group with the same name 'cmns.war'. Is this duplicate or there is another app under Maintenance group with the same name? | Gayam | 05/10/23 1:08 AM
| @praneeth.gayam@penske.com This is a duplicate application. one under Billing is correct. | Stella george | 06/14/23 2:30 AM
Row 29 | @sreekanth.kancharla@penske.com , Onboarded to bamboo and dev deployment is done with develop branch. Please verify. Thanks. https://bamboo.penske.com/browse/CMSP-CMSPLP0/deployments | Gayam | 07/25/23 12:03 AM
Row 29 | @sreekanth.kancharla@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ITFIS/repos/cmsplus-web/pull-requests/3/overview | Gayam | 07/20/23 12:38 AM
| @praneeth.gayam@penske.com PR is merged. Please proceed with bamboo configuration. | Sreekanth | 07/20/23 7:16 PM
| Sure @sreekanth.kancharla@penske.com | Gayam | 07/20/23 10:51 PM
Row 29 | @praneeth.gayam@penske.com Please let me know in case any update on this application. | Sreekanth | 07/07/23 8:26 PM
Row 29 | Hugo suggests grabbing the prod jar and reuse in artifactory since Prod is the most current jar. Assigned to Kalrav | Yvette Urso | 05/12/23 12:54 AM
| @yvette.urso@penske.com / @praneeth.gayam@penske.com Please take the "dassupport.jar" & "iasservice-client.jar" from SVN location. https://svn.penske.com/svn/webprojects/admin/cmsplus/trunk/CMSplusPhaseIII/WebContent/WEB-INF/lib We are not using "IAS_Agent.jar" in CMSPlus application and not sure where we can get this jar. | Sreekanth | 06/08/23 11:21 PM
| @sreekanth.kancharla@penske.com , We required iasservice-client.jar and IAS_Agent.jar for this app. It doesn't require dassupport.jar. Without IAS_Agent.jar application is giving compilation issues and the jar exist at https://svn.penske.com/svn/webprojects/admin/cmsplus/trunk/CMSplusPhaseIII/targeted/prod/ Could you please check and provide your approval to upload the jar. | Gayam | 06/10/23 2:22 AM
| @praneeth.gayam@penske.com Yes, we can use the IAS_Agent.jar from the trunk branch. | Sreekanth | 06/13/23 2:13 AM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 06/13/23 2:29 AM
Row 29 | @dylan.price@penske.com confirmed that we can upload the 'iasservice-client.jar' to artifactory. This app depends on IAS_Agent.jar and dassupport.jar also. So could you please let us know whether we can upload these jars into artifactory. | Gayam | 04/03/23 2:47 AM
Row 29 | Thanks @yvette.urso@penske.com . @mark.weaver@penske.com - Pls. have a look on the previous discussions and confirm your approval to upload to artifactory. Suggested Artifactory details as per the package information iasservice-client.jar --------------------- Group ID - com.penske.ias.services Artifact ID - iasservice-client Version - Default IAS_Agent.jar --------------------- Group ID - com.penske.invoice Artifact ID - IAS_Agent Version - Default CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 3:31 PM
| @mark.weaver@penske.com , Could you please respond to above query. Thanks. | Gayam | 03/09/23 2:01 AM
Row 29 | This is blocked by Billing Team. Kalrav sent Rafiq the question on which Jar is needed for this Application. | Yvette Urso | 02/16/23 12:11 AM
Row 29 | @kalrav.khamar@penske.com - Hi Kalrav..Any update on this | Mathumala Nachiappan | 12/01/22 9:03 PM
| @mathumala.nachiappan@penske.com I'm working with Sreekanth.Kancharla@penske.com. He will contact you and after that will update here. | Kalrav | 12/01/22 9:21 PM
| @mathumala.nachiappan@penske.com IAS_Agent.jar and iasservice-client.jar both are provided by invoice archive systems. @mark.weaver@penske.com is application owner and he should be able to provide more details about these jar files. | Kalrav | 12/01/22 9:44 PM
| @mark.weaver@penske.com Can you update IAS_Agent.jar and iasservice-client.jar? It's been waiting for your response since long time. | Kalrav | 02/13/23 9:01 PM
Row 29 | @mathumala.nachiappan@penske.com moving to the appropriate status to assign to AO for review. I chose AO Maven. | Yvette Urso | 12/15/22 2:08 AM
| @yvette.urso@penske.com - This is not review from App Owner. This is a dependency on the approval to proceed to upload to Artifactory. For Action - @mark.weaver@penske.com . CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/15/22 10:11 AM
Row 29 | @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com @mark.weaver@penske.com - Reassigned this application from Kalrav to Mark per Kalrav response. Thank you | Yvette Urso | 12/02/22 2:13 AM
Row 29 | @rafiq.melath@penske.com / @kalrav.khamar@penske.com , cmsplus.war has a dependency on IAS_Agent.jar and iasservice-client.jar. But these jars are not available in artifactory and unable to find source code of these jars in SVN/BitBucket. Can we upload these jars into artifactory? FYI: @mathumala.nachiappan@penske.com | Gayam | 11/23/22 10:29 PM
Row 30 | @shawn.mcmurtry@penske.com - tagging you for test | Patel | 07/28/23 10:23 PM
Row 30 | Testing Shawn's email notification | Patel | 07/28/23 9:39 PM
Row 30 | Question: @shawn.mcmurtry@penske.com / @dave.kost@penske.com , cns_application.properties.ant file contains a variable 'version' having value @DEPLOYMENT_INSTANCE@. It looks like this value comes from the bamboo build for each environment. But after modernization, it is going to be environment agnostic build. So it needs to be rectified if this variable used in code. Please check. Thanks. | Gayam | 07/19/23 3:23 AM
Row 30 | AO confirmed that all secrets are false positives. No code changes required. | Gayam | 06/16/23 1:12 AM
Row 30 | @shawn.mcmurtry@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:51 AM
Row 31 | @dylan.price@penske.com , This app also relies on BillingUtility jar. We are currently discussing the details of this jar in the context of cmns.war application. Once we get the clarification overthere then it clarifies for this app also. | Gayam | 06/10/23 2:36 AM
| We are modernizing billing utility as we got the approval in another app. So changing the status to Cap maven. | Gayam | 07/18/23 6:11 PM
Row 31 | @praneeth.gayam@penske.com SVN link to use should be https://svn.penske.com/svn/fieldsys/other/customer-notification-system/trunk/Mailer/ | Dylan | 06/07/23 12:37 AM
| Sure @dylan.price@penske.com . We will check. thanks. | Gayam | 06/07/23 5:47 AM
Row 31 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 31 | @praneeth.gayam@penske.com - To discuss with AO on folder structure | Mathumala Nachiappan | 01/10/23 10:46 AM
| Question: @manish.sisodiya@penske.com , This application has complex folder structure at https://svn.penske.com/svn/fieldsys/other/customer-notification-system/tags/prod/1.0.3_20170621/ We are not sure on which folder we need to start working on it. Could you please check and guide us. Thanks. | Gayam | 02/02/23 1:03 AM
Row 32 | Duplicate of contextframework | Mathumala Nachiappan | 11/23/22 3:11 AM
Row 33 | Thank you for the support | Hugo Scavino | 02/10/23 12:18 AM
Row 33 | Bamboo DEV - The plan is coomplete. I wll deploy to DEV and if there are issues I will let you all know. https://bamboo.penske.com/browse/CONNECTIONMAINT-CONNECTIONMT0-5 | Hugo Scavino | 02/10/23 12:18 AM
Row 33 | I also reviewed the secrets. The word password is used for a column and does not actually store passwords | Hugo Scavino | 02/09/23 2:27 AM
Row 33 | Please proceed with the Bamboo plan for this application. The new plan should replace the below project and use the below Bitbucket repo https://bamboo.penske.com/browse/CONNECTIONMAINT-CONNECTIONMAINTDEV https://bitbucket.penske.com/projects/AR-SEC/repos/connectionmaint-web/browse?at=develop | Hugo Scavino | 02/09/23 2:26 AM
Row 33 | Blocker :removed. security_util is in artifactory. | Hugo Scavino | 02/09/23 2:25 AM
Row 33 | Blocker: security_util.jar | Yvette Urso | 02/01/23 8:29 PM
Row 33 | @hugo.scavino@penske.com , This app contains true positive secrets. I will send the zip which contains all of your apps secrets. Please check. | Gayam | 01/19/23 3:25 AM
Row 33 | @praneeth.gayam@penske.com - Dependency with security_util.jar | Mathumala Nachiappan | 12/02/22 5:23 PM
Row 34 | If it hasn't been done before we are signing off on Maven changes and log4j2 changes. Please create the agnostic Bamboo build plan. | David Graf | 07/06/23 5:10 PM
| Sure @david.w.graf@penske.com | Gayam | 07/07/23 12:19 AM
| @david.w.graf@penske.com , Onboarding to bamboo and build is successful after disabling tests. https://bamboo.penske.com/browse/CFWBP-CFRW0 Please deploy to QA. Thanks. | Gayam | 07/09/23 11:11 PM
Row 34 | @david.w.graf@penske.com , Following is the bitbucket location. https://bitbucket.penske.com/projects/AR-SEC/repos/contextframework-batch/browse?at=refs%2Fheads%2Fdevelop Regarding bamboo, from my documentation I can say that Hugo was looking into it and he said that it is a complex deployment structure. After that there was no progress on this app. | Gayam | 07/06/23 3:21 AM
Row 34 | where is the Bamboo build plan? | David Graf | 06/29/23 11:28 PM
Row 34 | I guess the jar that it builds is called contextframework | David Graf | 06/29/23 11:20 PM
Row 34 | I'm going to start Amit on this project instead of the one assigned earlier. | David Graf | 06/29/23 11:17 PM
Row 34 | I think the name of this Application is Connection Management Framework. For some reason the Bamboo project is called Context Framework but we should be naming based on the IT Contact information going forward. Here is SVN for some evidence: https://svn.penske.com/svn/architecture/security/connection_mngmt/ | David Graf | 06/29/23 11:17 PM
Row 34 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:27 AM
Row 34 | @hugo.scavino@penske.com working with Connect Fleet to provide a status on 12/20/22 | Yvette Urso | 12/15/22 2:25 AM
Row 34 | From Hugo. Custom deployment to be planned | Mathumala Nachiappan | 11/23/22 3:14 AM
Row 35 | @praneeth.gayam@penske.com can mark this complete | Mahipal | 05/04/23 7:10 PM
| @mahipal.podduturi@penske.com , make the app to Done is not the log4j team's responsibility. If it is deployed to production, you or yvette mark it as done. | Gayam | 05/05/23 6:19 AM
Row 35 | @hugo.scavino@penske.com tested the contribution report changes and confirmed it is working as expected with new modernization changes. | Mahipal | 05/04/23 7:09 PM
Row 35 | @praneeth.gayam@penske.com we see the deployed name "contribreport-batch.jar" it supposed to be "contribreport.jar" can you change POM and necessary location | Mahipal | 04/07/23 6:43 PM
| @mahipal.podduturi@penske.com , we will look into it. | Gayam | 04/07/23 10:39 PM
| @mahipal.podduturi@penske.com , Changes are completed in develop_log4j branch and created MR https://bitbucket.penske.com/projects/ARPROJ/repos/contribreport-batch/pull-requests/6/overview Please check and merge. Thanks. | Gayam | 04/10/23 11:58 PM
Row 35 | @mahipal.podduturi@penske.com , contribreport - build & Deploy plan onboarding completed. This is batch application. So it doesn't have dev environment and log4j team can't do the QA deployment. So please do the QA deployment and verify. Thanks. https://bamboo.penske.com/browse/CONTRIBREPORTBP-CONTRIBREPOR/deployments | Gayam | 04/04/23 11:17 PM
Row 35 | @praneeth.gayam@penske.com review completed and meraged can you work on next steps | Mahipal | 04/03/23 9:38 PM
Row 35 | @praneeth.gayam@penske.com can you check review comment https://bitbucket.penske.com/projects/ARPROJ/repos/contribreport-batch/pull-requests/3/overview | Mahipal | 03/22/23 9:11 AM
Row 35 | Review: @shane.myers@penske.com , this app is ready for your review. Could you please verify. Thanks. https://bitbucket.penske.com/projects/ARPROJ/repos/contribreport-batch/pull-requests/3/overview | Gayam | 03/16/23 12:56 AM
Row 35 | @praneeth.gayam@penske.com please create under Architecture Projects repo and you have my approval to add the sx.jar to artifactory in the location you specified above. Thanks! | William | 02/22/23 3:08 AM
Row 35 | @shane.myers@penske.com , contribreport app depends on the jar sx.jar and it is not available in artifactory. Could you please provide the approval to upload this jar into artifactory at following location. Thanks. groupid - com.smartxls artifactid - SX | Gayam | 02/21/23 10:14 PM
Row 35 | I believe https://svn.penske.com/svn/architecture/general/contributionreport/trunk/src is the correct source path - the other directory contained much older files. | William | 02/11/23 1:38 AM
| Thanks @shane.myers@penske.com . I think we can delete trunk\contributionreport folder as it contains older or duplicate files. | Gayam | 02/11/23 1:51 AM
| @shane.myers@penske.com , Is this application needs to be created under Architecture Projects or Commons or Security? | Gayam | 02/17/23 1:44 AM
Row 35 | @shane.myers@penske.com , There are multiple src folders for this app in trunk branch. 1. src folder under trunk\contributionreport 2. src folder under trunk Not sure which one is the correct one. Could you please clarify. Thanks. | Gayam | 02/11/23 1:16 AM
Row 35 | please start moving this forward and if you have questions or need clarification I will assist | William | 02/10/23 10:37 PM
Row 35 | After investigation, I found this confluence article, which contains a link to SVN and a bamboo build for this application. https://confluence.penske.com/display/ATSD/Contribution+Report | William | 02/10/23 10:37 PM
Row 35 | I am not sure I should be the owner of this, reaching out to Don for clarification. | William | 02/08/23 2:35 AM
Row 35 | This app has a complext folder structure. @hugo.scavino@penske.com to discuss with Don and to take the ownership. contribreport is owned by Corp. And Java app by Arch team. Requesting @hugo.scavino@penske.com 's support to resolve this confusion. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:32 AM
Row 35 | Need to ensure this is assigned to the team. | Yvette Urso | 11/30/22 12:29 AM
Row 36 | @hugo.scavino@penske.com , For this application we observed that log4j and maven changes are completed by you. https://bitbucket.penske.com/projects/AR-SEC/repos/csar/commits?until=refs%2Fheads%2Frelease%2Flog4j-remediation Could you please check and confirm whether my team needs to do anything else. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/14/23 1:24 AM
| No code changes required. This application is waiting for fleet insight to complete and then move to QA to regression test. But the secure bamboo is required. That was not available last year. The maven build is agnostic and there are NO secrets. | Hugo Scavino | 01/17/23 3:19 AM
| Sure @hugo.scavino@penske.com . Do you want my team to built Bamboo plans for this application? @haribabu.challa@penske.com , @mathumala.nachiappan@penske.com | Gayam | 01/17/23 3:23 AM
| Yes please, build the "secure bamboo" plans and I will retest. | Hugo Scavino | 01/18/23 2:10 AM
| @hugo.scavino@penske.com , csar application bamboo onboarding and dev deployment completed. war file location: https://artifactory.penske.com/artifactory/architecture-mvn-development-local/com/penske/architecture/csar/1.0.0-develop-SNAPSHOT/csar-1.0.0-develop-20230208.160821-1.war ghlx008ptlge.penske.com: /opt/websphere/profiles/internal/checkpoints/Delta-1675872550437/cells/ghlx008ptlgeCell-internal/applications/csar.ear/deployments/csar @haribabu.challa@penske.com | Gayam | 02/08/23 11:54 PM
Row 37 | Review: @dylan.price@penske.com , This app is ready for your review. Please review and merge. https://bitbucket.penske.com/projects/PBT/repos/csb-web/pull-requests/3/overview | Gayam | 07/14/23 6:44 AM
Row 37 | Hi @praneeth.gayam@penske.com 2. Yes please include production.properties with this application. I see the file out on our current build. 3. I checked with Mark Weaver and this file is no longer needed. Please delete out rentalservice.xml | Dylan | 06/07/23 1:01 AM
| Thanks @dylan.price@penske.com . we will work on them. | Gayam | 06/07/23 5:51 AM
Row 37 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/28/23 3:31 AM
| Thanks @venkatesh.hossalinever@penske.com . Could you please resolve the query which I asked above. | Gayam | 02/28/23 11:48 PM
| applicationcontext.xml file use from production target folder. | Venkatesh | 03/17/23 7:43 PM
| Thanks @venkatesh.hossalinever@penske.com . What about other 2 questions in the same messgae? | Gayam | 03/17/23 11:53 PM
Row 37 | Question: @mark.weaver@penske.com Adding to above secrets mitigation, we have below questions. Could you please clarify. 1.Under the targeted folder this app have different applicationcontext.xml files for different environments . Which one we need to use ? 2. production.properties file exist in prod folder, but not in qa and dev. So can we move that to resources folder ? 3.There is rentalservice.xml under dev and qa. It is not exist in prod folder . so do we need to delete this or need to keep it under resources ? | Gayam | 02/17/23 2:23 AM
Row 37 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 37 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:53 AM
Row 38 | We are seeing only master and develop branch in bamboo. what happens to rest of bitbucket branches. | Rajesh | 06/14/23 12:12 AM
| @rajesh.haravde@penske.com , As part of the process when we onboard to bamboo only master and develop will be onboarded. If you want any other branch, please let us know. we will add. | Gayam | 06/15/23 12:50 AM
Row 38 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:08 AM
| @rajesh.haravde@penske.com , this app is deployed to dev using develop branch - https://bamboo.penske.com/browse/CVIBP-CVIW2/deployments | Gayam | 06/10/23 1:40 AM
Row 38 | Its merged. please take it forward. | Rajesh | 04/26/23 8:24 PM
| @rajesh.haravde@penske.com , this app is deployed to dev using develop_log4j branch - https://bamboo.penske.com/browse/CVIBP-CVIW1/deployments Please verify and merge the code to develop branch. | Gayam | 04/27/23 1:34 AM
Row 38 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 38 | Bitbucket and maven validation completed. awaiting on development environment configuration to move forward. | Rajesh | 04/25/23 5:58 PM
| Thanks @rajesh.haravde@penske.com . PR is still in open status. Could you please merge. In the mean time we will onboard to bamboo. | Gayam | 04/26/23 1:20 AM
Row 38 | @rajesh.haravde@penske.com / @venkata.bobba@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/PTLCORP/repos/cvi-web/pull-requests/5/overview | Gayam | 03/03/23 1:36 AM
Row 38 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So changing the status to (Cap) Maven | Gayam | 02/16/23 11:26 PM
Row 38 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:47 PM
Row 38 | Validation work in progress | Rajesh | 01/18/23 8:21 PM
Row 38 | @rajesh.haravde@penske.com , log4j and maven changes are completed for this application. Could you please review them in the below PR and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/cvi-web/pull-requests/5/overview @mathumala.nachiappan@penske.com | Gayam | 12/14/22 10:36 AM
Row 38 | Need to determine who will work this app. Was notified by @hugo.scavino@penske.com we may not have an resource. | Yvette Urso | 11/22/22 2:43 AM
| we are the owner of the application. please let us know if you need any information on source URL. but we do want to move to maven and bitbucket. | Rajesh | 12/12/22 10:16 PM
Row 39 | Decision is to retire these applications | Yvette Urso | 05/01/23 9:17 PM
Row 39 | smvendors feeds cyclops.war. So dependent to this app. | Yvette Urso | 05/01/23 9:13 PM
Row 39 | @scott.bortzel@penske.com / @scott.pemrick@penske.com , For this application both SVN and Bamboo are not available. Could you please let us know the SVN and Bamboo details. Thanks. | Gayam | 01/14/23 1:06 AM
| @scott.bortzel@penske.com / @scott.pemrick@penske.com , Could you please provide the response to above question. Thanks. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 03/24/23 10:54 PM
Row 40 | @yvette.urso@penske.com / @mathumala.nachiappan@penske.com , This is mentioned as Dup App but I am not seeing any duplicate entry for delegatedAdmin. Could you please check. | Gayam | 02/13/23 11:46 PM
Row 40 | Duplicate of delegatedAdmin | Mathumala Nachiappan | 11/23/22 3:15 AM
Row 41 | @praneeth.gayam@penske.com Can you run the secret scan and see if it reports anything | Sherin | 06/23/23 12:49 AM
| Sure @sherin.basheer@penske.com | Gayam | 06/23/23 11:41 PM
| @sherin.basheer@penske.com , We did rescan and sent the file in the email. Please verify. Thanks. | Gayam | 06/27/23 5:27 AM
Row 41 | @praneeth.gayam@penske.com Was secrets removed from this application? | Sherin | 06/23/23 12:12 AM
| @sherin.basheer@penske.com , I am not sure but seeing some Hugo's commits in develop_log4j branch. | Gayam | 06/23/23 12:40 AM
Row 41 | Please send the secrets along. I will checkout the branch and remediate. | Hugo Scavino | 04/06/23 3:23 AM
| @hugo.scavino@penske.com , emailed the secrets to you. Thanks. | Gayam | 04/07/23 1:42 AM
Row 41 | @hugo.scavino@penske.com, We have completed the secrets scanning on this application and found that there are true positive exist. I will share the excel report in the email. Could you please check and remediate the secrets. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/06/23 1:10 AM
| @hugo.scavino@penske.com , When you get a chance, could you please check these. Thanks. | Gayam | 04/06/23 3:11 AM
Row 41 | @hugo.scavino@penske.com - True positives found in commented code need confirmation on this | Mathumala Nachiappan | 11/23/22 3:16 AM
Row 42 | Agree this should be marked duplicate and removed | William | 03/01/23 2:43 AM
Row 42 | @yvette.urso@penske.com , I think this is a duplicate row item. dasservice.war already exist in another row and comments/status updated correctly in that line item. Please mark this as Dup app. | Gayam | 02/13/23 11:44 PM
Row 43 | QA testing compelted | Gayam | 05/14/23 9:23 PM
Row 43 | @praneeth.gayam@penske.com can you mark this to complete | Mahipal | 05/04/23 7:03 PM
| @mahipal.podduturi@penske.com , make the app to Done is not the log4j team's responsibility. If it is deployed to production, you or yvette mark it as done | Gayam | 05/05/23 6:20 AM
Row 43 | This app can be marked complete - I have completed my testing in QA and gotten end user signoffs. | William | 03/01/23 2:42 AM
Row 43 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:29 AM
Row 43 | This is waiting on 1 final user signoff in QA. It has passed my testing and the testing of 2 other users. I will follow up with the tester for an update | William | 12/09/22 2:37 AM
| Thanks William. FYI - @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/12/22 4:31 PM
Row 43 | @shane.myers@penske.com - QA deployment done on 1st Nov. | Mathumala Nachiappan | 11/23/22 3:19 AM
Row 44 | @gregg.obst@penske.com / @sarath.mani@penske.com , This application has dta_qa.properties, dta_dev.properties and dta_prod.properties files which are specific to the enviroment. But as we are going to do the environment agnostic build we should use only 1 file under resources. So, please resolve this issue. Thanks. | Gayam | 07/14/23 12:50 AM
Row 44 | AO confirmed that there are no code changes required for secrets in the email. | Gayam | 06/14/23 2:02 AM
Row 44 | @gregg.obst@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:52 AM
Row 45 | @praneeth.gayam@penske.com done merged to develop | Mahipal | 05/23/23 6:42 PM
| Thanks @mahipal.podduturi@penske.com . we will onboard to Bamboo and will let you know | Gayam | 05/24/23 1:10 AM
| @mahipal.podduturi@penske.com , This is onbaorded to bamboo. Please deploy to QA. Thanks. | Gayam | 05/25/23 3:32 AM
Row 45 | @shane.myers@penske.com , We changed the scope of log4j jars from provided to compile scope. Could you please review and merge in below PR. https://bitbucket.penske.com/projects/AR-SEC/repos/dlinkappremoval/pull-requests/8/overview Also, not sure why this app (Cap/AO)Dev deploy/test status. The develop branch is not yet onboarded to Bamboo. It should be in Cap Bamboo status. Once you confirm the above merge, we will onboard develop branch to bamboo and will build it. Thanks | Gayam | 05/22/23 11:44 PM
Row 45 | @shane.myers@penske.com , We completed secrets scanning on this app and looks like all are false positives. I will send the sheet in email and please check and confirm. Thanks. | Gayam | 01/10/23 12:32 AM
| Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:30 AM
Row 45 | @shane.myers@penske.com I moved to AO Final Testing Status - Let us know what your next steps are. | Yvette Urso | 12/15/22 2:28 AM
Row 45 | @praneeth.gayam@penske.com - Pls. check is anything for us to support | Mathumala Nachiappan | 12/12/22 4:32 PM
Row 45 | application does not run in QA. Here is the output when the start script is invoked:[600123729@clelx150ptlge dlinkappremoval]$ sudo -u apps ./dlinkappremoval.sh [600123729@clelx150ptlge dlinkappremoval]$ Usage: java [-options] class [args... ] (to execute a class) or java [-options] -jar jarfile [args...] (to execute a jar file) where options include: -d32 use a 32-bit data model if available -d64 use a 64-bit data model if available -server to select the "server" VM The default VM is server, because you are running on a server-class machine. -cp <class search path of directories and zip/jar files> -classpath <class search path of directories and zip/jar files> A : separated list of directories, JAR archives, and ZIP archives to search for class files. -D<name>=<value> set a system property -verbose:[class¦gc¦jni] enable verbose output -version print product version and exit -version:<value> Warning: this feature is deprecated and will be removed in a future release. require the specified version to run -showversion print product version and continue -jre-restrict-search ¦ -no-jre-restrict-search Warning: this feature is deprecated and will be removed in a future release. include/exclude user private JREs in the version search -? -help print this help message -X print help on non-standard options -ea[:<packagename>...¦:<classname>] -enableassertions[:<packagename>...¦:<classname>] enable assertions with specified granularity -da[:<packagename>...¦:<classname>] -disableassertions[:<packagename>...¦:<classname>] disable assertions with specified granularity -esa ¦ -enablesystemassertions enable system assertions -dsa ¦ -disablesystemassertions disable system assertions -agentlib:<libname>[=<options>] load native agent library <libname>, e.g. -agentlib:hprof see also, -agentlib:jdwp=help and -agentlib:hprof=help -agentpath:<pathname>[=<options>] load native agent library by full pathname -javaagent:<jarpath>[=<options>] load Java programming language agent, see java.lang.instrument -splash:<imagepath> show splash screen with specified image See http://www.oracle.com/technetwork/java/javase/documentation/index.html for m ore details. | William | 12/09/22 2:53 AM
Row 45 | @shane.myers@penske.com - Deployed in QA on 21st Nov. Pls. go ahead with your testing and confirmation | Mathumala Nachiappan | 12/02/22 5:53 PM
Row 45 | @mathumala.nachiappan@penske.com - To check the deployment status | Mathumala Nachiappan | 11/23/22 3:22 AM
Row 46 | Application deployed to QA and working everything fine. | Sama | 05/16/23 7:45 PM
Row 46 | Hi @praneeth.gayam@penske.com dev deployment looks good so please proceed to deploy to QA. | Sama | 05/09/23 8:05 PM
| @bhagya.sama@penske.com , As per management, AO needs to take care of QA deployment. | Gayam | 05/09/23 10:58 PM
Row 46 | @praneeth.gayam@penske.com code is merged to develop branch. Please onboard the branch to Bamboo and deploy to dev.Thanks! | Sama | 05/02/23 1:34 AM
| @bhagya.sama@penske.com Dev deployment is done from develop branch. | Gayam | 05/03/23 1:28 AM
Row 46 | Hi Praneeth PR is approved and you can proceed for next steps.Thanks! | Sama | 04/29/23 12:04 AM
| Thanks @bhagya.sama@penske.com . Can you merge the code https://bitbucket.penske.com/projects/ARPROJ/repos/dlinks/pull-requests/42/overview Once you merge, we will onboard develop branch to Bamboo and deploy to dev from this branch. Thanks. | Gayam | 05/02/23 1:03 AM
Row 46 | Hi @praneeth.gayam@penske.com Dev deploy is successful and confirming that Please proceed to deploy to QA on Tuesday(04/25). Thanks! | Sama | 04/21/23 2:11 AM
| @bhagya.sama@penske.com , dev deployment is done from develop_log4j branch for your testing to complete. Could you please approve the PR https://bitbucket.penske.com/projects/ARPROJ/repos/dlinks/pull-requests/42/overview So thatwe will onbaord develop branch to Bamboo and deploy to dev from develop branch. | Gayam | 04/22/23 2:10 AM
Row 46 | Sure @praneeth.gayam@penske.com ,thank you for letting us know. | Sama | 04/19/23 3:56 AM
| @bhagya.sama@penske.com , We corrected the build and dev deployment is completed from develop_log4j branch. Please check. https://bamboo.penske.com/browse/DBP-DLINK/ | Gayam | 04/20/23 2:01 AM
Row 46 | Please compare with https://bamboo.penske.com/build/admin/edit/defaultBuildArtifact.action?buildKey=SECUTIL-CSARSECUTL-BLD and see WAR is missing from artifact definitions.https://bamboo.penske.com/build/admin/edit/defaultBuildArtifact.action?buildKey=DBP-DLINK-BLD | Sama | 04/14/23 12:21 AM
| Hi @bhagya.sama@penske.com , I don't have access to above urls. But I am seeing that develop_log4j branch is deployed to dev. https://bamboo.penske.com/browse/DBP-DLINK1/deployments | Gayam | 04/14/23 12:38 AM
| We corrected the issue. My team is deploying the app to Dev. We will let you know as soona s it completes. | Gayam | 04/19/23 3:36 AM
Row 46 | Hi @praneeth.gayam@penske.com I see that war is not deployed and can you see that here artifact is not defined. https://bamboo.penske.com/build/admin/edit/defaultBuildArtifact.action?buildKey=DBP-DLINK-BLD | Sama | 04/13/23 11:56 PM
Row 46 | Please build the new Bamboo plan for this web application. I reviewed the application and I can compile locally. @bhagya.sama@penske.com Please checkout the latest develop/log4j branch when you are ready and deploy locally. | Hugo Scavino | 04/07/23 11:31 PM
| Sure @hugo.scavino@penske.com Thanks! | Sama | 04/07/23 11:54 PM
| @hugo.scavino@penske.com / @bhagya.sama@penske.com , We have onboarded this app to Bamboo. Please check build plan: https://bamboo.penske.com/browse/DBP-DLINK/ deploy plan log: https://bamboo.penske.com/browse/LOG-DEPY-159/log App is deployed to Dev | Gayam | 04/12/23 11:11 PM
Row 46 | @david.w.graf@penske.com , this app is still in AO Review stage and new bamboo plans are not yet onboarded. | Gayam | 03/21/23 1:31 AM
| thanks. It must be the dev environment. @bhagya.sama@penske.com Please check the Dev environment to ensure that there is a working version there. For now, it can match the same as the last production deploy. https://confluence.penske.com/display/ATSD/DLinks | David Graf | 03/21/23 5:50 AM
Row 46 | The Dev environment does not seem to be working this morning when I tried. I'm not sure if it is related to this project or not. | David Graf | 03/20/23 6:03 PM
Row 46 | @sherin.basheer@penske.com - - This app is available for your final review. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/02/22 5:41 PM
Row 46 | @yvette.urso@penske.com - This app is ready for AO Review. What can be the App Status from the available ones? | Mathumala Nachiappan | 11/23/22 3:23 AM
| @mathumala.nachiappan@penske.com Please email the AO if you are ready for them to start their work. I do not need to be emailed. | Yvette Urso | 11/30/22 12:24 AM
Row 47 | until further notice please do not do any work on Dlinks Auth Filter, that includes running bamboo builds. We are attempting to deploy to production soon and that will require complete control from AO. CC: @praneeth.gayam@penske.com CC: @sherin.basheer@penske.com CC: @ritesh.bhattacharyya@penske.com | David Graf | 06/12/23 11:57 PM
Row 47 | @praneeth.gayam@penske.com I had to update the VARIABLES section in Bamboo for the dlinks auth filter to deploy to the shared library IN DEV Specifically, I had to update the variable instance to have the value shared. This will be true of all shared libraries. https://bamboo.penske.com/deploy/config/configureEnvironmentVariables.action?environmentId=129826820 | Hugo Scavino | 02/06/23 8:19 PM
| @praneeth.gayam@penske.com - Pls. check Hugo's message | Mathumala Nachiappan | 02/07/23 10:36 PM
| Yes @mathumala.nachiappan@penske.com . I already updated this message to @haribabu.challa@penske.com . | Gayam | 02/07/23 10:44 PM
| @hugo.scavino@penske.com , We have updated the spec file of dlinks_filter with 'shared' instance variable. https://bamboo.penske.com/deploy/config/configureEnvironmentVariables.action?environmentId=129826820 @haribabu.challa@penske.com | Gayam | 02/08/23 11:49 PM
Row 47 | Thanks @hugo.scavino@penske.com for your support. I have changed the App Status. | Mathumala Nachiappan | 02/08/23 11:14 AM
Row 47 | Great timing. The build suceeded. I will be deploying to DEV and QA tomorrow if all goes well https://bamboo.penske.com/browse/DFBP-DLINKAUTH0-3 | Hugo Scavino | 01/31/23 1:19 AM
Row 47 | This bamboo project did not run the first time due to an auth error trying to push to artifactory. I checked and there is a parent pom setup for batch. https://bamboo.penske.com/browse/DFBP-DLINKAUTH0-2/log Let me know if there is something wrong with the pom. | Hugo Scavino | 01/25/23 3:34 AM
| @hugo.scavino@penske.com https://bamboo.penske.com/browse/DFBP-DLINKAUTH0 We have changed the settings.xml file in build plan. Could you please run the develop branch and let us know if you still see any issues. @haribabu.challa@penske.com | Gayam | 01/27/23 10:29 PM
Row 47 | Issue: Code needs to modernized to move forward. Put in AO Code Work so @hugo.scavino@penske.com can work on it. | Yvette Urso | 12/15/22 2:32 AM
Row 47 | @praneeth.gayam@penske.com and @hugo.scavino@penske.com - As per the latest discussion, No FP tickets needed. ITs a peer review from the AO side. | Mathumala Nachiappan | 12/08/22 3:44 PM
Row 47 | I have made log4j changes and also maven agnostic changes. This will need a peer review with the architecture team before moving even to DEV. | Hugo Scavino | 11/24/22 2:34 AM
| Thanks @hugo.scavino@penske.com ! | Mathumala Nachiappan | 12/02/22 5:25 PM
| As discussed with @hugo.scavino@penske.com , this is getting reviewed by other architecture team. Once that confirms, hugo will merge the code. @mathumala.nachiappan@penske.com , I believe this should be in AO Maven status as Hugo is taking care of Maven things. | Gayam | 12/07/22 11:13 PM
Row 47 | @praneeth.gayam@penske.com - Pls. create a FP ticket for arch team review | Mathumala Nachiappan | 11/30/22 3:19 PM
Row 48 | Review: @venkata.bobba@penske.com / @rajesh.haravde@penske.com , this app is ready for your review. Please check. https://bitbucket.penske.com/projects/PTLCORP/repos/domicileservice/pull-requests/2/overview | Gayam | 04/25/23 12:56 AM
Row 48 | Review: @venkata.bobba@penske.com / @Raje | Gayam | 04/25/23 12:56 AM
Row 48 | @venkata.bobba@penske.com confirmed that there are no changes required for secrets in the email. | Gayam | 04/15/23 12:58 AM
Row 48 | Added per AO requested it. As this jar used in other corp projects which are migrating to java8 and this jar is not in java8. It may causes issues. | Yvette Urso | 03/29/23 12:54 AM
Row 49 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:08 AM
| @rajesh.haravde@penske.com , this is already onboarded to Bamboo. Please check at https://bamboo.penske.com/browse/DOM-DOMS0/ | Gayam | 06/09/23 1:55 AM
Row 49 | The PR is merged. We will deploy to dev and let you know. Thanks. | Gayam | 05/18/23 11:35 PM
| @rajesh.haravde@penske.com , Build is failing for this app due to test cases failure. Could you please work with your team to fix them. Thank you. https://bamboo.penske.com/browse/DOM-DOMS0-UTEST-2 | Gayam | 05/22/23 9:32 PM
Row 49 | The secrets of this app are false positives. please proceed with next steps of modernization | Rajesh | 04/15/23 12:50 AM
Row 49 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/domservice-web/pull-requests/3/overview Thanks. | Gayam | 02/16/23 11:30 PM
Row 49 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:48 PM
Row 49 | Validation work in progress | Rajesh | 01/18/23 8:21 PM
Row 49 | @krishna.tanga@penske.com / @yogesh.sinha@penske.com , Please review the code in MR https://bitbucket.penske.com/projects/PTLCORP/repos/domservice-web/pull-requests/3/overview and merge. | Gayam | 11/28/22 8:04 AM
| we will do the needful as requested and get back to you. | Rajesh | 12/12/22 10:17 PM
Row 50 | Kalrav looking into next steps for this application. | Yvette Urso | 06/05/23 9:07 PM
| @yvette.urso@penske.com This application is added to Penske Migration smart sheet and we've added comments in that file. Please update the App Status accordingly OR remove from this smart sheet. | Sreekanth | 06/08/23 11:17 PM
Row 50 | @yvette.urso@penske.com / @kalrav.khamar@penske.com , As per our discussion, ebill app is removed from Log4j team's scope. Thanks. @mathumala.nachiappan@penske.com @balu.mohan@penske.com | Gayam | 02/17/23 7:09 PM
| @yvette.urso@penske.com , If this app is removed from log4j team's scope, please remove from this list. | Gayam | 03/24/23 10:57 PM
Row 50 | @mathumala.nachiappan@penske.com moved status for this as well. Should be in the AO Bamboo status. | Yvette Urso | 12/15/22 2:22 AM
Row 50 | @rafiq.melath@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:33 AM
Row 51 | @yvette.urso@penske.com I don't see AO Code Work as a status | David Graf | 12/15/22 2:53 AM
Row 51 | Issue: Code needs to modernized to move forward. Put in AO Code Work so @david.w.graf@penske.com can work on it. | Yvette Urso | 12/15/22 2:32 AM
Row 51 | That right, I am working to remove the jar that cannot be placed in artifactory. | David Graf | 12/09/22 1:38 AM
Row 51 | Will be resumed once the dependency is cleared from AO | Mathumala Nachiappan | 12/08/22 8:00 PM
Row 51 | @david.w.graf@penske.com - ebsworker.jar dependency | Mathumala Nachiappan | 11/23/22 3:28 AM
Row 52 | This cannot move forward until I remove the references to ebsworker.jar | David Graf | 02/09/23 12:02 AM
Row 52 | Blocker: ebsworker.jar | Yvette Urso | 02/01/23 8:30 PM
Row 52 | I'm will address this after the ebs.war is complete | David Graf | 12/09/22 1:38 AM
Row 52 | Will be resumed once the dependency is cleared from AO | Mathumala Nachiappan | 12/08/22 8:01 PM
Row 52 | @david.w.graf@penske.com - ebsworker.jar dependency | Mathumala Nachiappan | 11/23/22 3:28 AM
Row 52 | Testing | Yvette Urso | 11/11/22 9:42 PM
Row 53 | sure I will check @david.w.graf@penske.com | Sama | 05/30/23 6:40 PM
Row 53 | @bhagya.sama@penske.com please see check the ebsservice.war is being created by Maven correctly. | David Graf | 05/26/23 7:37 PM
Row 53 | Review: @david.w.graf@penske.com , This app ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/ebsservice/pull-requests/7/overview | Gayam | 03/04/23 1:26 AM
Row 53 | I reviewed. There are no secrets in ebsservice | David Graf | 02/24/23 2:38 AM
| Thank you. Changed to (Cap)Maven | Gayam | 02/25/23 12:55 AM
Row 53 | Secrets: @david.w.graf@penske.com , I sent the secrets file previously. Please check and let us know your thoughs on secrets. Thanks. | Gayam | 02/23/23 1:44 AM
Row 53 | @praneeth.gayam@penske.com - To review the maven rework done. | Mathumala Nachiappan | 11/23/22 3:26 AM
Row 54 | @bhagya.sama@penske.com , This app is ready for your review. Please check. https://bitbucket.penske.com/projects/AC/repos/ebs_service_client/pull-requests/4/overview | Gayam | 06/14/23 4:16 AM
Row 55 | This app is completely done with all steps of modernization. | David Graf | 03/21/23 5:43 AM
Row 55 | Looks like RBAC is in place and working. I am moving this to complete. The next deploy of this app will have version 2.0.0 to signify it is modernized. | David Graf | 02/18/23 1:53 AM
Row 55 | Today's update is that we figured out the instance issue in the spec so that the jar deploys to var/tmp. Last Bamboo Item to complete is the RBAC groups. Please assign RBAC groups to ebsworker. | David Graf | 02/08/23 11:59 PM
Row 55 | @praneeth.gayam@penske.com Per @david.w.graf@penske.com this was deployed 1/19/23. I believe he may be out of the office so please give him time to complete. | Yvette Urso | 01/24/23 8:19 PM
Row 55 | @david.w.graf@penske.com , Please create a release branch from develop and run the build from release. It will create a production version of the code. Production deploy plan are already ready but till now no log4j projects deployed to production. @mathumala.nachiappan@penske.com / @hugo.scavino@penske.com | Gayam | 12/22/22 10:16 PM
Row 55 | I have merged my changes to develop and tested the Dev and QA deployments. Please confirm that prod deployment is set up correctly so that we can deploy in Jan. Also this Bamboo plan needs role based access. Right now, I have an override for my account which gives me access. @mathumala.nachiappan@penske.com @praneeth.gayam@penske.com | David Graf | 12/21/22 7:14 PM
Row 55 | No Problem @david.w.graf@penske.com . We finished the setup today and. Build and deployment to Dev is done from the bugfix branch. Please check the Bamboo https://bamboo.penske.com/chain/viewChain.action?planKey=ECBP-EBWYP6 Let us know if you need any other information. Thanks. @mathumala.nachiappan@penske.com | Gayam | 12/16/22 11:31 PM
| @praneeth.gayam@penske.com I don't have access. Link is Access Denied message | David Graf | 12/17/22 12:56 AM
Row 55 | I created a branch with the pom changes to use the suggested group id and properties. Please update the bamboo plan from template; effectively removing the manual changes. Let me know once done and I will test it out. | David Graf | 12/14/22 8:45 PM
| Sure @dave.graff@penske.com . We will let you know once build and deployment completes. @mathumala.nachiappan@penske.com | Gayam | 12/14/22 10:56 PM
| The branch is the following: https://bitbucket.penske.com/projects/ARPROJ/repos/ebsworker/browse?at=refs%2Fheads%2Fbugfix%2Fdwg-confirm-to-issue | David Graf | 12/15/22 10:36 PM
| @praneeth.gayam@penske.com I noticed in the last message that you annotated a david graff whom is not me. Please use David W Graf. my email address is david.w.graf@penske.com Sorry for the confusion. Is there any update on this request? | David Graf | 12/16/22 8:50 PM
Row 55 | @david.w.graf@penske.com - Soon will resolve the deployment issue | Mathumala Nachiappan | 12/06/22 7:55 PM
Row 55 | is there any update on the bamboo build plan from spec that was requested for this app? | David Graf | 12/02/22 2:07 AM
Row 55 | EBS worker is in QA with slf4j and log4j2. Because it is on the IFS we can deploy to production and plan to with the current changes on 11/29. | David Graf | 11/17/22 1:45 AM
Row 56 | @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: ecm-deploy New deployment project name: ecm-web-deploy Thank you. | Gayam | 05/14/23 9:34 PM
Row 56 | @sreekanth.kancharla@penske.com , This app is deployed to Dev. Please verify. Thanks. | Gayam | 03/30/23 12:47 AM
| @praneeth.gayam@penske.com We are waiting on resolution from @hugo.scavino@penske.com for issues we are facing in all web based applications related to SessionValidationFilter. Please change the status. @kalrav.khamar@penske.com | Sreekanth | 03/30/23 10:49 PM
| @sreekanth.kancharla@penske.com , There is no status to represent this. I think we can keep the Dev Deploy status as this is waiting from AO side. Please correct it if you have any other thoughts. | Gayam | 03/30/23 11:10 PM
Row 56 | @sreekanth.kancharla@penske.com , Also log4j/maven changes are completed. Please review them in the below MR. https://bitbucket.penske.com/projects/ITFIS/repos/ecm-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/09/22 2:57 AM
| @praneeth.gayam@penske.com I took a glance of the code & the file you shared. All the href links seems the request URLs (which we use to maintain usually in java script) & CSS file references. I don’t see any secrets in them. Hope we can leave them as it is. | Sreekanth | 12/09/22 8:17 PM
| Thanks @sreekanth.kancharla@penske.com . In that case please review the log4j,maven changes in the below MR and merge please. https://bitbucket.penske.com/projects/ITFIS/repos/ecm-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/10/22 12:42 AM
| @praneeth.gayam@penske.com The PR is merged. Please proceed with next steps. @mathumala.nachiappan@penske.com @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/04/23 3:44 AM
Row 56 | @james.minisce@penske.com - PR is raised for this app for your review and signoff to proceed for Dev deployment. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:04 PM
| Where do I review? | James | 12/01/22 9:08 PM
| @james.minisce@penske.com , Please review in the following PR and merge. https://bitbucket.penske.com/projects/ITFIS/repos/ecm-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/07/22 11:00 PM
| @sreekanth.kancharla@penske.com Can you please review and merge as per the above? Thank you. | James | 12/08/22 6:16 PM
| @praneeth.gayam@penske.com I've added comment to PR. Please check and reply back to take further action. @mathumala.nachiappan@penske.com @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 2:58 AM
| @sreekanth.kancharla@penske.com , I think you are referring to securityfilter in web.xml is different for diff regions and keeping those in targeted folder. But @hugo.scavino@penske.com suggested not to keep targeted folder and he is working on workaround to resolve this issue. Could you please check with @hugo.scavino@penske.com on this. Thanks. @mathumala.nachiappan@penske.com @yvette.urso@penske.com | Gayam | 01/27/23 10:08 PM
| Had discussion with @hugo.scavino@penske.com and came to know that Dlinkfilter is going to take care of everything. Once we get a working project and instructions on implementation, we'll implement the same in all the web applications wherever the filters are handled either with targeted folder or with java filters. @kalrav.khamar@penske.com | Sreekanth | 02/03/23 3:19 AM
Row 56 | Thanks @sreekanth.kancharla@penske.com for the updates on secrets part. I have changed the secret status as 'Not Needed'. This is FYI. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/12/22 4:28 PM
Row 56 | @sreekanth.kancharla@penske.com - In secret scanning process, Many hardcoded href links are found. Pls. check and confirm whether they need redaction. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 7:02 PM
| @mathumala.nachiappan@penske.com This is a very old application and we've no project to migrate this application. So we've to move forward with the hardcoded href links. Please advice incase this is a stopper for Log4j migration. | Sreekanth | 12/09/22 12:15 AM
| @sreekanth.kancharla@penske.com , We can share the secrets file to you with all the hardcoded links. Please check and let us know whether those are false positives. @mathumala.nachiappan@penske.com | Gayam | 12/09/22 2:32 AM
Row 57 | @praneeth.gayam@penske.com edi_encryption application will get retired as new batch application is developed and its been tested on QA. | Venkatesh | 06/21/23 6:00 PM
| @venkatesh.hossalinever@penske.com , Do we need to change the status of this app to retired? @yvette.urso@penske.com / @shane.myers@penske.com | Gayam | 06/22/23 3:14 AM
Row 57 | @praneeth.gayam@penske.com We are not going to do log4j changes. Please close this request. We have redesigned this batch application. | Venkatesh | 05/16/23 6:26 PM
| @venkatesh.hossalinever@penske.com , Do you mean is this application retired or no need of log4j/maven changes and Bamboo onboarding? FYI: @yvette.urso@penske.com , @shane.myers@penske.com | Gayam | 05/18/23 12:51 AM
Row 57 | Review: @venkatesh.hossalinever@penske.com this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/edi-encryption-batch/pull-requests/3/overview | Gayam | 04/13/23 1:00 AM
Row 57 | Completed reviewing the log4j secrets, no code changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 2:06 AM
Row 57 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 57 | @praneeth.gayam@penske.com - True positives found on this application. To review once and share it to AO | Mathumala Nachiappan | 01/10/23 10:44 AM
Row 57 | Per Sam S. on 11/23/22 - I am not certain on the EDI_encryption… I think ITDS Operations actually owns the encryption routines. Sreenivasulu is my all in one EDI specialist. If Brian thinks it should be mine just insert my name. | Yvette Urso | 11/24/22 2:10 AM
Row 58 | @praneeth.gayam@penske.com Changes related to old log4j property file was removed and merged the code to Develop branch, Please wait, we will confirm on deployment to QA environment. | Venkatesh | 05/16/23 6:24 PM
| @venkatesh.hossalinever@penske.com , We just onboard and build the app for batch apps. AO needs to deploy to QA. If you are ok we will onboard to Bamboo. Please confirm. | Gayam | 05/18/23 12:52 AM
Row 58 | @praneeth.gayam@penske.com Do we have any updates on above comments. Apart from above comments we are good with log4j and maven changes review. | Kadu | 05/11/23 6:55 PM
| @dhanashree.kadu@penske.com , We did complete the changes and committed to develop_log4j branch. Please verify and merge the PR. https://bitbucket.penske.com/projects/ARPROJ/repos/edi-batch/pull-requests/4/overview | Gayam | 05/11/23 11:30 PM
Row 58 | We have found below findings while reviewing Log4j and Maven changes in edi-batch application. Maven: We need below dependencies in the application which are not available in pom.xml. Can you please add them. These jars are already available in svn lib folder as well. <dependency> <groupId>commons-httpclient</groupId> <artifactId>commons-httpclient</artifactId> <version>3.0.1</version> </dependency> <dependency> <groupId>commons-dbcp</groupId> <artifactId>commons-dbcp</artifactId> <version>1.4</version> </dependency> Log4j: Can you move log4j.properties file from 'src\main\resources\conf' to 'src\main\resources'. So that application can read it properly. Batch application is using penskebatch.jar/contextframework.jar to use connection framework. And these jars are using older log4j version, it requires older log4j and mail dependencies to be available in pom.xml. Please add below dependencies in pom.xml. <!-- Logging --> <dependency> <groupId>log4j</groupId> <artifactId>log4j</artifactId> <version>1.2.17</version> </dependency> <!--mail dependencies --> <dependency> <groupId>javax.activation</groupId> <artifactId>activation</artifactId> <version>1.1.1</version> </dependency> <dependency> <groupId>com.sun.mail</groupId> <artifactId>javax.mail</artifactId> <version>1.6.0</version> </dependency> | Kadu | 05/08/23 4:17 PM
| Sure @dhanashree.kadu@penske.com . We will check your comments and will make the changes. | Gayam | 05/08/23 10:26 PM
Row 58 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. Please check. https://bitbucket.penske.com/projects/ARPROJ/repos/edi-batch/pull-requests/4/overview | Gayam | 03/24/23 11:09 PM
Row 58 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/27/23 10:25 PM
| Thanks @venkatesh.hossalinever@penske.com . Updated the status to Cap Maven. | Gayam | 02/27/23 11:36 PM
Row 58 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 58 | @rafiq.melath@penske.com / @sreenivasulu.mupparaju@penske.com , We have completed the secrets scanning and analysis on this app and found that all are false positives. I will send the sheet in the email. Could you please check and confirm. Thanks. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/10/23 1:16 AM
Row 59 | @venkatesh.hossalinever@penske.com , App is onboarded to bamboo and deployed to dev successfully. Please verify. bamboo plan: https://bamboo.penske.com/browse/EDICBOSBP-EDBSALBD Dev deployment: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151195129 | Gayam | 07/27/23 10:43 PM
Row 59 | We have found below findings while reviewing Log4j and Maven changes in edicbos web application. Maven: We need below dependency in the application which is not available in pom.xml. Can you please add it. This jar is already available in svn lib folder. <dependency> <groupId>org.springframework</groupId> <artifactId>spring-webmvc-struts</artifactId> <version>2.5</version> </dependency> We need to remove below jars from pom.xml as its conflicting the version with spring-webmvc 4.3.30 dependency. <dependency> <groupId>com.trigonic</groupId> <artifactId>spring-utils</artifactId> <version>0.3</version> </dependency> <dependency> <groupId>org.springframework</groupId> <artifactId>spring-core</artifactId> <version>${spring.version}</version> </dependency> <dependency> <groupId>org.springframework</groupId> <artifactId>spring-web</artifactId> <version>${spring.version}</version> </dependency> Log4j: We need to remove log4j.properties and InitializeLoggingServlet from the web code. We will make the code changes and commit them in develop_log4J branch. | Rane | 05/12/23 6:49 PM
| @praneeth.gayam@penske.com : Any update on the pom.xml | Kandasamy | 05/15/23 6:46 PM
| @revathi.kandasamy@penske.com , We have completed the changes in develop_log4j branch. Could you please verify. Thanks. | Gayam | 05/18/23 12:46 AM
| @praneeth.gayam@penske.com Please create the pull request. we will review the changes. | Venkatesh | 06/22/23 2:31 AM
| @venkatesh.hossalinever@penske.com , Please review https://bitbucket.penske.com/projects/PBTED/repos/edicbos-web/pull-requests/3/overview | Gayam | 06/22/23 3:55 AM
| @praneeth.gayam@penske.com Changes are merged, please deploy on dev environment. | Venkatesh | 07/26/23 7:47 PM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 07/27/23 8:56 AM
Row 59 | @venkatesh.hossalinever@penske.com , this app is ready for your review. Please verify. https://bitbucket.penske.com/projects/ARPROJ/repos/edicbos-web/pull-requests/3/overview | Gayam | 03/24/23 11:10 PM
Row 59 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/27/23 10:26 PM
| Thanks @venkatesh.hossalinever@penske.com . Updated the status to Cap Maven. | Gayam | 02/27/23 11:36 PM
Row 59 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 59 | @sreenivasulu.mupparaju@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:46 AM
Row 60 | @praneeth.gayam@penske.com Reviewed the changes and merged the code to Develop branch, Please wait, we will confirm deployment to QA environment. | Venkatesh | 05/16/23 6:21 PM
Row 60 | @praneeth.gayam@penske.com Thanks for the updates. We are good for log4j and maven changes review. Please deploy the changes in further environment. | Kadu | 05/11/23 7:01 PM
| Sure @dhanashree.kadu@penske.com . But could you please merge the PR. So that we will onboard develop branch to Bamboo. | Gayam | 05/11/23 11:28 PM
| @dhanashree.kadu@penske.com , We onboarded the develop branch to Bamboo. But build is failing. Could you please merge the PR https://bitbucket.penske.com/projects/ARPROJ/repos/edipostclient-batch/pull-requests/3/overview So that build will be successful. | Gayam | 05/13/23 2:16 AM
Row 60 | @dhanashree.kadu@penske.com , Please check the below comment from @hugo.scavino@penske.com . "BATCH apps can count on log4j 1.2 (legacy) being in the ./ptlcommon_1 and that directory will load first. BATCH apps do not need to add log4j (legacy) as a dependency in their pom's. penskebatch.jar/contextframework.jar will load the log4j legacy as WebServices will add ptl_common_1 at the beginning " So we don't need to add log4j 1 dependency in the pom. Please check and let us know if you have any questions. | Gayam | 05/10/23 12:17 AM
Row 60 | @praneeth.gayam@penske.com : can we proceed to retain the log4j.properties along with log4j2.xml. Kindly update us with the discussion with Hugo. | Kandasamy | 05/03/23 6:16 PM
Row 60 | @praneeth.gayam@penske.com Please confirm for log4j from Hugo. The penskebatch jar is not available in svn lib folder as this jar will be available in shared lib path and application will point from there. Almost all batch applications are using this jar for connection framework. | Kadu | 04/28/23 11:28 AM
Row 60 | We have found below findings while reviewing Log4j and Maven changes in edi-postclient batch application. Log4j: Batch application is using penskebatch.jar/contextframework.jar to use connection framework. And these jars are using older log4j version, it requires older log4j and mail dependencies to be available in pom.xml. Please add below dependencies in pom.xml. <!-- Logging for Batchframework --> <dependency> <groupId>log4j</groupId> <artifactId>log4j</artifactId> <version>1.2.17</version> </dependency> <!--mail dependencies --> <dependency> <groupId>javax.activation</groupId> <artifactId>activation</artifactId> <version>1.1.1</version> </dependency> <dependency> <groupId>com.sun.mail</groupId> <artifactId>javax.mail</artifactId> <version>1.6.0</version> </dependency> Maven: We have observed that the .tgz file created after maven build does not contain .jar file in it. Please make necessary changes to include .jar file in the bin.xml file. | Kadu | 04/27/23 6:59 PM
| @dhanashree.kadu@penske.com , If we use the log4j 1 jar then the purpose of log4j migration deviated. We need to discuss about this with @hugo.scavino@penske.com . Also, we are not seeing the penskebatch dependency in the lib folder. That is the reason we did not add that dependency and app also compiled successfully. | Gayam | 04/28/23 2:04 AM
Row 60 | @dylan.price@penske.com / @sreenivasulu.mupparaju@penske.com , this app is ready for your review. Please check. https://bitbucket.penske.com/projects/ARPROJ/repos/edipostclient-batch/pull-requests/3/overview | Gayam | 03/24/23 10:43 PM
Row 60 | @praneeth.gayam@penske.com please add cxml.jar to artifactory. We also do not need any updates for the secret file. | Dylan | 03/07/23 12:46 AM
| Thanks @dylan.price@penske.com . Changing the status to Cap Maven | Gayam | 03/07/23 11:57 PM
Row 60 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 60 | @sreenivasulu.mupparaju@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:47 AM
Row 60 | @rafiq.melath@penske.com / @sreenivasulu.mupparaju@penske.com , This application is dependent on the jar cxml.jar but this jar is not available in artifactory. Could you please provide your approval to upload this jar to artifactory. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/11/23 9:19 AM
Row 61 | Secrets: @stella.george@penske.com , I sent the secrets in the email. Please verify and let us know whether this app requires code changes. | Gayam | 06/28/23 12:44 AM
| False alert. no code change required. | Stella george | 07/06/23 8:01 PM
| Thanks @stella.george@penske.com . Changed the status to Cap Maven. | Gayam | 07/07/23 12:18 AM
Row 61 | @david.long@penske.com , Log4j team started working on modernizing this application. When we verified the old production bamboo build we are seeing following 2 repositories mentioned in the build. EDVIR_PROD - https://svn.penske.com/svn/fieldsys/maintenance/edvir/tags/PROD/_T_PROD_Build_20160721 SERVICEREQUESTUTTILITY_JAR (Jar repo)- https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/Jar/PROD I am expecting 2nd one is the dependency jar for the first repo. Is that correct? If yes, we need to do the log4j and mavanization for the dependency jars also. Could you please check and confirm. Thanks. FYI: @shane.myers@penske.com | Gayam | 05/18/23 1:36 AM
| @praneeth.gayam@penske.com Yes the second one is dependency jar. it should be included in Servicereqsvc.war.yes you need to do the log4j and mavanization to that dependency also. | Stella george | 06/14/23 1:46 AM
| Thanks @stella.george@penske.com . What option do you prefer for this app. 1. If SERVICEREQUESTUTTILITY_JAR is not used by any other application then this folder can be included inside the EDVIR app's source. It requires work from AO. Or 2. Need to extract the SERVICEREQUESTUTTILITY_JAR folder and create separate repo and bamboo build. Use this jar as a dependency in EDVIR app. It doesn't require work from AO. | Gayam | 06/14/23 2:25 AM
| Thanks @stella.george@penske.com . I got the response to create a separate bamboo build and bitbucket repo for serviceRequestUtility from you in different application 'servicereqbatch'. | Gayam | 06/14/23 3:31 AM
Row 61 | @praneeth.gayam@penske.com you should use below tag https://svn.penske.com/svn/fieldsys/maintenance/edvir/tags/PROD/20200804. I dont why bamboo build is showing wrong tag. please validate latest build tag. | Stella george | 06/14/23 2:11 AM
| Thanks @stella.george@penske.com . We will take the provided tag as base branch. | Gayam | 06/14/23 2:29 AM
Row 62 | @praneeth.gayam@penske.com , for efuel application, Dev changes looks good and logs also rolling correctly on Dev server. | Nayum | 06/12/23 8:24 PM
| Thanks @pathan.nayum@penske.com . Please deploy to QA and test it. | Gayam | 06/13/23 1:31 AM
Row 62 | @praneeth.gayam@penske.com Changes related to old log4j property file was removed and merged the code to Develop branch, Please deploy to Dev environment. | Venkatesh | 05/16/23 6:16 PM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 05/18/23 12:54 AM
| @venkatesh.hossalinever@penske.com , The develop branch for efuel.war has already been onboarded to Bamboo, and the dev deployment was successfully completed. Please verify. | Gayam | 05/18/23 10:43 PM
Row 62 | Created the pull request for Nayum's change. Pls approve and merge. | Kandasamy | 05/15/23 6:38 PM
Row 62 | Log4j/Maven Changes are looking good. Removed log4j.properties from the web code and committed to maven branch. Please deploy the changes to dev server. | Nayum | 05/11/23 7:00 PM
| @pathan.nayum@penske.com , Can you merge your changes to develop branch. So that we will onbaord develop branch to Bamboo. | Gayam | 05/11/23 11:33 PM
Row 62 | yes, working on changes to remove hardcoded changes to load old log4j file. | Venkatesh | 05/03/23 2:33 AM
Row 62 | @venkatesh.hossalinever@penske.com , bamboo build & deploy plan onboarding completed. Dev deployment done using develop_log4j branch. https://bamboo.penske.com/browse/EFUELBP-EFLALBD/ Also, please merge the code to develop branch. https://bitbucket.penske.com/projects/ARPROJ/repos/efuel-web/pull-requests/3/overview | Gayam | 04/19/23 3:09 AM
| @praneeth.gayam@penske.com Code has been merged. Currently we are working on code changes to remove loading of existing log4j property file from the code. | Venkatesh | 04/29/23 2:36 AM
| @venkatesh.hossalinever@penske.com , are you making the changes on top of develop_log4j branch? | Gayam | 05/02/23 1:06 AM
Row 62 | Yes, Please proceed with bamboo setup | Venkatesh | 04/17/23 8:25 PM
| Thanks @venkatesh.hossalinever@penske.com . We will let you know once it is onboarded to Bamboo. | Gayam | 04/18/23 3:14 AM
Row 62 | Log4j and Maven Changes are looking good. log4j.properties file location is hardcoded in the code, and hence required code fix to read the log4j2.xml and ensure the log files are created. | Nayum | 04/13/23 6:43 PM
| @pathan.nayum@penske.com , Can we onboard this app to Bamboo and deploy? | Gayam | 04/13/23 11:27 PM
Row 62 | @william.spohn@penske.com / @venkatesh.hossalinever@penske.com , Please review log4j/maven changes at https://bitbucket.penske.com/projects/ARPROJ/repos/efuel-web/pull-requests/3/overview | Gayam | 03/02/23 3:07 AM
Row 62 | Venkatesh has completed reviewing the log4j secrets - there are no coding changes required. | William Spohn | 02/23/23 3:03 AM
| Thanks @william.spohn@penske.com . Changing the status to (Cap)Maven | Gayam | 02/23/23 3:23 AM
Row 62 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 62 | @william.spohn@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:39 AM
Row 63 | @praneeth.gayam@penske.com , Logs are not rolling in dev as well as no mails were triggered, hence we need to add the attached Javamail dependencies in pom.xml. Kindly, update the pom.xml and deploy the same in dev. | Nayum | 06/16/23 6:49 PM
| @pathan.nayum@penske.com , we will add and get back to you. | Gayam | 06/16/23 10:27 PM
| @pathan.nayum@penske.com , We have updated the pom.xml with the mentioned dependencies. Please check and approve the PR. https://bitbucket.penske.com/projects/PBTFUEL/repos/efueladmin-web/pull-requests/7/overview | Gayam | 06/19/23 7:41 PM
| @praneeth.gayam@penske.com Merged the changes. Can you please deploy the changes on Dev. | Venkatesh | 07/26/23 8:00 PM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 07/27/23 8:58 AM
| @venkatesh.hossalinever@penske.com / @pathan.nayum@penske.com / @william.spohn@penske.com , App is deployed to dev. Please verify. | Gayam | 07/27/23 10:45 PM
Row 63 | @praneeth.gayam@penske.com , for efueladmin application, Dev URL is working correctly, but logs are not rolling in correct location in Dev log server. | Nayum | 06/12/23 8:25 PM
| @pathan.nayum@penske.com . Please provide where the logs are rolling out. Also provide the correct location where logs need to be rolled out. | Gayam | 06/13/23 1:32 AM
Row 63 | @praneeth.gayam@penske.com , efueladmin is working fine in local. But, In dev after deployment, Dev URL is not working. PFA for page loaded in dev. URL used for dev : https://web3dev.penske.com/efueladmin/entry/ApplicationEntry?LoginUserID=505025033 | Nayum | 06/08/23 8:33 PM
| @pathan.nayum@penske.com , Please debug the issue and check the logs. We don't know any information about the application other than mavanizing the application. | Gayam | 06/09/23 1:11 AM
Row 63 | @praneeth.gayam@penske.com Changes related to old log4j property file was removed and merged the code to Develop branch, Please deploy to Dev. | Venkatesh | 05/16/23 6:14 PM
| Sure @venkatesh.hossalinever@penske.com . We will onaboard the develop branhc to Bamboo and deploy to Dev. | Gayam | 05/18/23 12:48 AM
| @venkatesh.hossalinever@penske.com , The build plan and deploy plan for efueladmin.war have been successfully onboarded to Bamboo and completed the dev deployment through the develop branch. Please verify | Gayam | 05/18/23 10:42 PM
Row 63 | @praneeth.gayam@penske.com : Created Pull request for the changes. | Kandasamy | 05/15/23 6:42 PM
Row 63 | Log4j/Maven Changes are looking good. Removed log4j.properties from the web code and committed to maven branch. Please deploy the changes to dev server. | Nayum | 05/11/23 6:58 PM
| @pathan.nayum@penske.com Can you merge your changes to develop branch. | Gayam | 05/11/23 11:35 PM
Row 63 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. Please check. Thanks. https://bitbucket.penske.com/projects/ARPROJ/repos/efueladmin-web/pull-requests/3/overview | Gayam | 04/07/23 12:25 AM
Row 63 | Venkatesh has completed reviewing the log4j secrets - there are no coding changes required. | William Spohn | 02/23/23 3:03 AM
| Thanks @william.spohn@penske.com . Changing the status to (Cap)Maven | Gayam | 02/23/23 3:26 AM
Row 63 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 63 | @william.spohn@penske.com / @venkatesh.hossalinever@penske.com , @william.spohn@penske.com , Adding to Bamboo build question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:41 AM
Row 63 | Venkatesh Hossalinever provided me the following repo URL with folder and branch details for efueladmin.var Dev, QA, and Prod. Prod- https://svn.penske.com/svn/webprojects/admin/efueladmin/trunk/efueladmin7 Dev - https://svn.penske.com/svn/webprojects/admin/efueladmin/branches/dev_gh/efueladmin7 QA- https://svn.penske.com/svn/webprojects/admin/efueladmin/branches/qa/efueladmin7 | William Spohn | 12/09/22 11:15 PM
| Thanks @william.spohn@penske.com . Can we also get the Bamboo build for this project. @mathumala.nachiappan@penske.com | Gayam | 12/10/22 12:49 AM
| @william.spohn@penske.com / @venkatesh.hossalinever@penske.com, could you please provide the requested info when you get a chance. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 7:40 PM
Row 63 | Moved to AO Bamboo - Please move to CAP Bamboo when done @william.spohn@penske.com | Yvette Urso | 12/15/22 2:45 AM
Row 63 | Yes, we've made this request and are awaiting delivery. | William Spohn | 12/14/22 3:09 AM
Row 63 | Hi Praneeth, I will contact my GDC offshore web app contact for this information and get back to you. | William Spohn | 12/09/22 8:23 PM
Row 63 | @william.spohn@penske.com - Pls. share the Repo URL and confirm the folder/branch for log4J modernization CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 11:16 PM
Row 64 | Review: @sreekanth.kancharla@penske.com , This is ready for your review. Please verify. https://bitbucket.penske.com/projects/ITFIS/repos/employee-master-batch/pull-requests/4/overview | Gayam | 06/28/23 2:47 AM
| @praneeth.gayam@penske.com I'm not sure why the PR is created to a feature branch. By mistake offshore lead merged that but I didn't want that to be merged as we've not tested log4j2 changes in QA & there is some Oracle cloud migration testing going. I couldn't revert the merged commit. I may need to manually revert the changes. | Sreekanth | 06/28/23 7:11 PM
| @sreekanth.kancharla@penske.com , I think there is a confusion whether to merge to develop branch or to the branch which contains recent commits. Do you want us to raise the PR from develop_log4j to develop branch? | Gayam | 06/29/23 2:21 AM
| @praneeth.gayam@penske.com Yes. The PRs should be always to develop branch. | Sreekanth | 06/29/23 8:46 PM
| @sreekanth.kancharla@penske.com , Raised PR to develop branch. Please check. https://bitbucket.penske.com/projects/ITFIS/repos/employee-master-batch/pull-requests/5/overview | Gayam | 06/30/23 12:35 AM
Row 64 | @sreekanth.kancharla@penske.com , we are seeing that you already worked on this app and mavanized. Do you want log4j team to work on it anything or please close the status of this app. @yvette.urso@penske.com / @shane.myers@penske.com | Gayam | 06/07/23 3:02 AM
| @praneeth.gayam@penske.com Yes, this app is already mavenized. If your team could work on Log4j migration changes, then we can test this app. | Sreekanth | 06/08/23 8:02 PM
| Sure @sreekanth.kancharla@penske.com | Gayam | 06/09/23 1:35 AM
Row 65 | This application was deployed to PROD on 07/25/2023. | Sreekanth | 07/27/23 7:24 PM
Row 65 | @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: eram-deploy New deployment project name: eram-web-deploy Thank you. | Gayam | 05/14/23 9:36 PM
Row 65 | @sreekanth.kancharla@penske.com , app is onboarded to Bamboo. https://bamboo.penske.com/browse/EBP-ERAMW/ Please let us know whether we can deploy to dev. | Gayam | 03/10/23 11:23 PM
| @praneeth.gayam@penske.com Please proceed with DEV deployment. We don't have access to add "Plan branch" for any future builds. Please provide access on all the new admin projects. | Sreekanth | 03/13/23 10:17 PM
| Hi @sreekanth.kancharla@penske.com , Deployed the code to dev. Please verify. Also, to add a plan branch you need to be part of RBAC group PTL-Admin-Production. I believe currently you are not part of it. | Gayam | 03/15/23 11:43 PM
| @praneeth.gayam@penske.com We need the access to add the plan branch if they are not automatically being created in Bamboo as we'll be deploying whatever the branch we wanted to test. Please do the need. Schedule a meeting with architect team if needed. | Sreekanth | 03/16/23 12:28 AM
| @sreekanth.kancharla@penske.com , I will send an email to add the people to 'PTL-Admin-Production' RBAC group. Could you please give us the list of people whom you want to add to that group. Once you added to that gorup you will also have permission to deploy to production. | Gayam | 03/16/23 2:29 AM
| @praneeth.gayam@penske.com Developers also need access to add Plan branch in some cases but they shouldn't have PROD deployment access. Please consider this scenario and let us know how this can be handled | Sreekanth | 03/16/23 7:51 PM
Row 65 | Maven Review: @sreekanth.kancharla@penske.com , We ahve completed the modernization on this app. Please review and confirm for the next step. https://bitbucket.penske.com/projects/ITFIS/repos/eram-web/pull-requests/3/overview Thanks. | Gayam | 03/01/23 12:29 AM
| @praneeth.gayam@penske.com The PR is already merged by Jim. We are good with the changes. Please proceed with the further steps. @james.minisce@penske.com | Sreekanth | 03/04/23 2:56 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to Cap Bamboo | Gayam | 03/07/23 12:19 AM
Row 65 | @sreekanth.kancharla@penske.com , This app has some true positive secrets. I sent the file in email. Could you please check it. Thanks. | Gayam | 01/27/23 10:45 PM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. We are good to proceed further. true positives: SearchCompanyDAO.java - This file code is commented. BaseConstants.java - PASSWORD is just a string constant. All the remain are false positives. @mathumala.nachiappan@penske.com @james.minisce@penske.com | Sreekanth | 01/28/23 12:12 AM
Row 65 | @yvette.urso@penske.com , I asked the question regarding group above. It still needs to be resolved by @sreekanth.kancharla@penske.com . @mathumala.nachiappan@penske.com | Gayam | 12/10/22 2:43 AM
| @praneeth.gayam@penske.com If this is for cpe.jar file, then please proceed with creating new group in artifactory and make the required import changes in code. @james.minisce@penske.com Regarding the Bamboo, FP ticket 1765373 is created to Architect team to confirm whether this app's Java version in Bamboo is upgraded to 1.8 or not. | Sreekanth | 12/15/22 3:23 AM
| @praneeth.gayam@penske.com & @james.minisce@penske.com The bamboo plans of ERAM application are with Java 1.8 confirmed by Architect team. | Sreekanth | 12/15/22 7:37 PM
| Thanks @sreekanth.kancharla@penske.com . We will upload the jar and continue the maven changes. @mathumala.nachiappan@penske.com | Gayam | 12/15/22 8:00 PM
Row 65 | @sreekanth.kancharla@penske.com Please review the Bamboo plan for eRAM. Thank you. | James | 12/15/22 2:20 AM
Row 65 | @james.minisce@penske.com @mathumala.nachiappan@penske.com - James can you review the Bamboo for Mathu? | Yvette Urso | 12/15/22 2:12 AM
Row 65 | @rafiq.melath@penske.com / @james.minisce@penske.com , One more issue on this app. This application is using different version of cpe.jar which is not available in artifactory. thre is a different version of cpe.jar available artifactory which is not resolving the issues in this app. Do we need to upload the different version of cpe.jar in artifactory for this application ? Following class have the import from cpe. src/main/java/eram/actions/ViewProductAction.java @mathumala.nachiappan@penske.com | Gayam | 12/08/22 3:16 AM
| @sreekanth.kancharla@penske.com Please provide review the above and provide the necessary requested input. Thank you. | James | 12/08/22 6:17 PM
| @praneeth.gayam@penske.com When I search through the application source code, I found many classes are using the cpe.jar If the jar which is already available in Artifactory doesn't resolve the errors, then we need to have this version jar in artifactory. In this case my answer is "Yes" for your question. | Sreekanth | 12/08/22 7:30 PM
| Thanks @sreekanth.kancharla@penske.com . The current artifactory version of cpe is uplaoded with group com.penske.ebus which is working fine for ebus application. Do you want us to upload the eram version of cpe with group com.penske.eram? FYI: @mathumala.nachiappan@penske.com | Gayam | 12/08/22 10:49 PM
| @praneeth.gayam@penske.com If the group has to be changed, then the imports in java files also should be changed. Please correct me if I'm wrong. Are you planning to make those changes as well. If so, we are good, so that there will not be any issues in functionality of the application. | Sreekanth | 12/09/22 12:19 AM
| @sreekanth.kancharla@penske.com , Group is for where to upload in artifactory. It doesn't affect any code. @mathumala.nachiappan@penske.com | Gayam | 12/09/22 1:34 AM
Row 65 | @praneeth - Should this status change from blocked for this app or is there another reason you are still blocked? | Yvette Urso | 12/09/22 12:41 AM
Row 65 | Yes, the bamboo plan should be with Java 1.8. | James | 12/09/22 12:03 AM
Row 65 | @james.minisce@penske.com - Pls. confirm this Artifactory details. dnbi-acctmgmt.jar -------------------- Group ID - com.dnbi.eai Artifact ID - dnbi-acctmgmt Version - Default dnbi-creditapp.jar -------------------- Group ID - com.dnbi.eai Artifact ID - dnbi-creditapp Version - Default CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:40 PM
| I can confirm the above Artifactory details. CC: @sreekanth.kancharla@penske.com | James | 12/01/22 9:38 PM
| Thanks @james.minisce@penske.com . Jars are uploaded | Mathumala Nachiappan | 12/08/22 3:33 PM
Row 65 | @rafiq.melath@penske.com , This application has cpe.jar dependency for getting loggers in one class. But as per suggestion from Hugo/Architect team, it is good to create logger independently in each class. So we are doing this in all other apps. Same thing we are following in this app. FYI: @mathumala.nachiappan@penske.com | Gayam | 12/06/22 7:42 AM
Row 65 | @rafiq.melath@penske.com / @james.minisce@penske.com eram-web depends on below 2 jars. dnbi-acctmgmt.jar dnbi-creditapp.jar We are unable to find Bamboo build plan or SVN/BB Repo for these 2 jars. So need confirmation from you for uploading these 2 jars to Artifactory. FYI: @mathumala.nachiappan@penske.com | Gayam | 11/23/22 10:56 PM
| Yes, the identified jars will need to be uploaded to Artifactory. They are jars used to connect and get data from the DnBi web services. | James | 11/24/22 2:08 AM
Row 66 | @praneeth.gayam@penske.com Please proceed with Bamboo plan creation with develop branch. Once that is available, we'll test this app in DEV and if the app works fine with no issues, we'll merge our recent changes from SVN to Bitbucket. | Sreekanth | 06/08/23 6:38 PM
| @sreekanth.kancharla@penske.com , Build plan and deploy plan onboarded successfully. Deployed to dev also completed. Please verify. Thanks. | Gayam | 06/13/23 2:12 AM
Row 66 | @praneeth.gayam@penske.com We are good with all the secrets as those are in common files & used across all the Penske web applications. The java version in Bamboo DEV: 1.6, QA: 1.8, PROD: 1.6 We recommend 1.8 CC: @charles.csoky@penske.com | Sreekanth | 01/25/23 2:00 AM
| Thanks @sreekanth.kancharla@penske.com . We have completed the modernization changes. Please review and merge them. PR is https://bitbucket.penske.com/projects/ITFIS/repos/esr-web/pull-requests/3/overview Changed the status to (AO)Maven. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 11:13 PM
| @praneeth.gayam@penske.com The PR is merged to develop. We are currently working on some changes in this application. Mostly we'll deploy the changes before March. Post deployment, we can merge the same changes from SVN to the new bitbucket source code. CC: @mathumala.nachiappan@penske.com @charles.csoky@penske.com | Sreekanth | 01/26/23 2:38 AM
| Thanks @sreekanth.kancharla@penske.com . We will hold this app until you confirm. | Gayam | 01/26/23 9:05 PM
| @praneeth.gayam@penske.com Can we proceed with next step in configuring the bamboo plan, so that when we are don with our current development and get UAT sign off, we can use the new build plan and test the application in DEV. Post that we'll take care of merging the change from SVN to Bitbucket. | Sreekanth | 01/27/23 12:14 AM
| @praneeth.gayam@penske.com and @sreekanth.kancharla@penske.com - As the log4j and mven changes are done from Log4J team and the application is blocked for some other enhancements, i am chanding the status to Waiting on AO. CC: @yvette.urso@penske.com | Mathumala Nachiappan | 01/27/23 10:10 AM
| @praneeth.gayam@penske.com We are making the enhancements to this application and we'll close by this month (2/28/2023). Once that is done, we'll merge the changes to new branch and test the application. @mathumala.nachiappan@penske.com @charles.csoky@penske.com | Sreekanth | 02/15/23 3:18 AM
| @sreekanth.kancharla@penske.com , Could you please merge https://bitbucket.penske.com/projects/ITFIS/repos/esr-web/pull-requests/6/overview These changes are for making the scope of log4j2 to compile. Thanks. | Gayam | 05/30/23 8:48 AM
| @praneeth.gayam@penske.com Merge completed. | Sreekanth | 06/01/23 12:11 AM
| Thanks @sreekanth.kancharla@penske.com | Gayam | 06/01/23 10:47 PM
Row 66 | @charles.csoky@penske.com , We sent an email with secrets for this application. We observed all are false positives. Could you please verify and confirm. Thanks. | Gayam | 01/24/23 10:15 AM
Row 66 | @steve.mcmullen@penske.com / @charles.csoky@penske.com , Log4j and Mavn changes are completed. Could you please review and merge. PR is https://bitbucket.penske.com/projects/ITFIS/repos/esr-web/pull-requests/3/overview | Gayam | 12/03/22 12:19 PM
Row 67 | @sreekanth.kancharla@penske.com , App is onboarded to bamboo and ready to deploy to QA. Please deploy. https://bamboo.penske.com/browse/ESRBP-ESRBCH0/ | Gayam | 03/30/23 12:34 AM
| @sreekanth.kancharla@penske.com , Just want to inform you we are creating a new deploy plan to match the name of the deploy plan to bitbucket repo name and deleting the old deploy plan. Old deployment project name: esrbatch-deploy New deployment project name: esr-batch-deploy Thank you. | Gayam | 05/14/23 9:41 PM
| @sreekanth.kancharla@penske.com , We changed the scope of log4j jars from provided to compile. Could you please merge the changes. https://bitbucket.penske.com/projects/ITFIS/repos/esr-batch/pull-requests/6/overview | Gayam | 05/24/23 1:55 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 05/24/23 9:04 PM
Row 67 | @charles.csoky@penske.com - Found a hardcoded credential during secret scanning process. Pls. have a look for redaction. @praneeth.gayam@penske.com - Pls. share the secret report to Charles | Mathumala Nachiappan | 12/08/22 10:13 PM
| @praneeth.gayam@penske.com Please loop me while sharing the report. | Sreekanth | 12/16/22 3:34 AM
| @sreekanth.kancharla@penske.com / @charles.csoky@penske.com , Shared the secrets in the email. Please check. @mathumala.nachiappan@penske.com | Gayam | 12/16/22 3:40 AM
| @praneeth.gayam@penske.com The secrets seems fine to me. "database.properties" differs for each environment. For SUPPORT only this file is used from the source location. For QA & PROD, this file is maintained in a specific path in Batch Box server where no one has access except admins. FYI, we don't have any SUPPORT environments for Batch applications. Except this one file, all other seems good to me. One remediation I can think of is by using the Connection Framework instead of maintaining the credentials in a file which required some development effort. Hope we are not planning to make those changes as of now. Please let us know incase any issues/suggestions. CC: @charles.csoky@penske.com | Sreekanth | 12/23/22 2:07 AM
| @sreekanth.kancharla@penske.com , Any changes you are planning for this application or can we go forward for the next step? | Gayam | 01/06/23 1:16 AM
| @praneeth.gayam@penske.com we are good with all the secrets as most of them are related to database credentials and in QA & PROD those credentials are being referred from “conf” folder which admins only can access. Bamboo Java version is 1.8 for QA & PROD CC: @charles.csoky@penske.com | Sreekanth | 01/25/23 2:24 AM
| Thanks @sreekanth.kancharla@penske.com . Passwords are referred in java class files. Is that ok to keep them over there? @hugo.scavino@penske.com / @yvette.urso@penske.com / @mathumala.nachiappan@penske.com | Gayam | 01/25/23 11:16 PM
| @praneeth.gayam@penske.com The only java file that is provided in secrets is "TestCopyFilesWithJcifs.java" This file is not available in trunk branch in SVN and only available in offshore branch. Hope the log4j migration changes be done on top of trunk branch which is used for PROD deployment. If so, hope we should be good with this file. | Sreekanth | 01/26/23 3:18 AM
| Thanks @sreekanth.kancharla@penske.com for confirming. Yes we created log4j branch from trunk which is master in bitnucket. Changing the status to (Cap) Maven | Gayam | 01/26/23 8:43 PM
| @praneeth.gayam@penske.com I've added a comment to the existing PR. Please take care, so that I can merge the request. https://bitbucket.penske.com/projects/ITFIS/repos/esr-batch/pull-requests/3/overview | Sreekanth | 02/16/23 8:35 PM
| @sreekanth.kancharla@penske.com , I responded to the comment. Could you please check. | Gayam | 02/17/23 1:15 AM
| @sreekanth.kancharla@penske.com , Could you please check my response and provide your input. Thanks. | Gayam | 03/03/23 1:29 AM
| @praneeth.gayam@penske.com We've requested for new DL email for logger. Once that is created, we'll share that with you, so that can be added in log4j2.xml For now, I've approve the PR, so please proceed with further steps. @charles.csoky@penske.com @sampada.bhusari@penske.com | Sreekanth | 03/04/23 2:49 AM
Row 68 | Sure @dale.porter@penske.com . We will check and get back to you. | Gayam | 07/31/23 2:26 AM
| @dale.porter@penske.com CICD team checked build log of deployment to artifactory(archive) stage report and found that error statement is coming, but those errors are coming for all the applications and those are not causing any issues. https://bamboo.penske.com/download/ETSBP-ETSW0-DTA/build_logs/ETSBP-ETSW0-DTA-2.log. Then team verified whether the war is getting deployed to artifactory or not and found that it is deploying. Also verified in ghlx008 server and found that etimeservice.war is deploying in server also. So please validate the app. Thanks. | Gayam | 08/01/23 12:46 AM
| Hi all, I ran the buld again for develop branch and I do see the war file for etimeservice is being put to ghlx008 as noted. However, it is not running the ssh app deployment process as I check the application installed in websphere at /opt/websphere/profiles/wsv/installedApps/ghlx006ptlgeNetwork-remoting/etservice.ear and it is still dated as 7/18/2023. I also included a reference to the bamboo build log with errors. https://bamboo.penske.com/download/ETSBP-ETSW0-DTA/build_logs/ETSBP-ETSW0-DTA-3.log | Dale Porter | 08/01/23 8:20 PM
| @dale.porter@penske.com , dev server was down for the past couple of days. That is the reason deployment is failing. Now the server is up and deployment is successful. Please check. https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151196087. | Gayam | 08/04/23 1:04 AM
| Hi I ran a dev build and see that the deployment is being executed (the file folders at and under the below directory are dated today's deploy date 8/9/2023 I ran but the class object files were dated 8/1/2023. I do not think the build is working correctly as the class compiled files should also be dated with current build date. Please take a look. thank you. /opt/websphere/profiles/wsv/installedApps/ghlx006ptlgeNetwork-remoting/etservice.ear | Dale Porter | 08/09/23 11:50 PM
| @dale.porter@penske.com , I don't think there is any issue in the build. If you see the log4j2.xml file it is dated as 8/1. Not sure why the server dated them as 8/1 but total package is correctly built by bamboo. | Gayam | 08/10/23 12:57 AM
Row 68 | hi All, I am getting access denied error when clicking on the link above from Bamboo. Can I be given access to the above project in bamboo for the link. Thank you. | Dale Porter | 07/17/23 7:37 PM
| @dale.porter@penske.com , you have all the required access. Please check again. https://bamboo.penske.com/browse/ETSBP-ETSW/deployments | Gayam | 07/20/23 12:14 AM
| Hi, I am seeing errors in the Bamboo build for the final Archive stage and included link to bamboo for showing the error. Also, I did not see a war file created on ghlx008ptlge. Can you take a look. Thank you https://bamboo.penske.com/download/ETSBP-ETSW0-DTA/build_logs/ETSBP-ETSW0-DTA-2.log | Dale Porter | 07/28/23 1:35 AM
Row 68 | @dale.porter@penske.com , onboarded to bamboo and dev deployment is successful. Please verify. Thanks. https://bamboo.penske.com/browse/ETSBP-ETSW/deployments | Gayam | 07/12/23 1:39 AM
Row 68 | I have verified and merged. thank you | Dale Porter | 07/07/23 1:03 AM
| Thanks @dale.porter@penske.com . We will onboard to bamboo. | Gayam | 07/10/23 11:31 PM
Row 68 | Review: @dale.porter@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/etimeservice/pull-requests/4/overview | Gayam | 06/24/23 12:46 AM
Row 68 | The xml file in question “EncryptionKeyStoreDao” is a mybatis sql call to procedure GETENCRYPTIONKEY from EK_MASTER library. It does not have a specific key id or key password stored, it is just the variable placeholder for receiving the password when returned from the procedure call to be using in the application. This should not be an issue. | Dale Porter | 06/06/23 6:18 AM
| Thanks @dale.porter@penske.com . Changed the status to Cap Maven | Gayam | 06/06/23 8:30 AM
Row 68 | @dale.porter@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:48 AM
Row 69 | Review: @dylan.price@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/PBTCBOS/repos/fbwatermark-batch/pull-requests/5/overview | Gayam | 06/16/23 9:56 PM
Row 69 | Hi @praneeth.gayam@penske.com secrets look great. Please start with log4j/maven changes | Dylan | 06/07/23 1:07 AM
| Thanks @dylan.price@penske.com | Gayam | 06/07/23 5:52 AM
Row 69 | @mark.weaver@penske.com , Shared the secrets of this app in the email. Please check. Thanks. | Gayam | 03/24/23 12:13 AM
Row 69 | The other line item which has fbwatermark.jar has been marked a Dup App. So picking up this application for the next steps. | Gayam | 03/07/23 3:16 AM
Row 69 | This application is an internal CBOS batch application and deploys to ghlx097ptlge (our CBOS batch box). Not sure how you would mark this in your artifactory -- wondering if CBOS should have its own… | Dylan | 03/07/23 12:59 AM
Row 69 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:27 AM
Row 69 | @sam.skelding@penske.com / @mark.weaver@penske.com , Adding to above question, we have following query for this applicaiton. This application is a batch application but has Dev Env. Instance type is not found for dev environment. Instance type is necessary for creating deploy spec for dev deployment. Till now we found internal, external, wsv, service, shared, rental as instance typr throughout different bamboo plan that we had worked till now. For deploying in artifactory we use instance. From app owner side we need to know what is the instance type for this application. @mathumala.nachiappan@penske.com | Gayam | 12/21/22 1:59 AM
Row 69 | @mark.weaver@penske.com - Is this application repeated. #95 and #96. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 11:52 AM
Row 70 | @mark.weaver@penske.com and @rafiq.melath@penske.com - Marking this as duplicate of Row# 95. Pls. share the repo details if this is different. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:12 AM
Row 71 | @frank.d'angelo@penske.com , Could you please let us know whether this application is going away. If not could you please provide the production branch. We are unable to find from bamboo as the prod deploy never ran on this application. Thanks. | Gayam | 02/15/23 12:36 AM
Row 71 | @frank.d'angelo@penske.com - Per Frank please get with him prior to starting - this app may go away. | Yvette Urso | 01/25/23 2:54 AM
Row 72 | @rajesh.haravde@penske.com , Build and deployment completed in Dev. Please verify the application in dev. https://bamboo.penske.com/browse/FIXEDASSETBP-FXDAT1/deployments | Gayam | 05/22/23 9:29 PM
Row 72 | PR been executed please take it forward. Thanks for guidance on process Praneeth appreciated. | Rajesh | 05/18/23 1:48 AM
Row 72 | @rajesh.haravde@penske.com , If you are able to verify the develop_log4j branch, could you please merge the PR. https://bitbucket.penske.com/projects/PTLCORP/repos/fixedasset-web/pull-requests/3/overview | Gayam | 05/17/23 3:14 AM
| @rajesh.haravde@penske.com Onboarding both develop_log4j and develop branches to bamboo is completed. Running the develop branch failed as pom.xml is not in develop. Also, deployment in dev from develop_log4j is successful. Please merge abiove PR. | Gayam | 05/18/23 12:59 AM
Row 72 | I am not able to change App Status using my login can anyone please reset my profile, as i was able to update it last week. Thanks. | Rajesh | 05/16/23 6:50 PM
Row 72 | We able to build project using maven. please change status "(AO) Maven completed. | Rajesh | 05/16/23 6:49 PM
Row 72 | Thanks @rajesh.haravde@penske.com . We have completed log4j/maven changes for this application. Please review in below PR. https://bitbucket.penske.com/projects/PTLCORP/repos/fixedasset-web/pull-requests/3/overview | Gayam | 02/16/23 11:33 PM
Row 72 | we do not want to address secrete mitigation at this movement. please move forward with project upgrade with respect to bitbucket, maven and log4j | Rajesh | 02/16/23 3:41 AM
Row 72 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:49 PM
Row 72 | @april.ottey@penske.com / @yogesh.sinha@penske.com ,Please review the PR and provide your approval. https://bitbucket.penske.com/projects/PTLCORP/repos/fixedasset-web/pull-requests/3/overview FYI: @mathumala.nachiappan@penske.com | Gayam | 11/24/22 3:46 AM
Row 73 | @venkatesh.hossalinever@penske.com , this lineitem is Duplicate. For Flex Billing, please check the line item which has application name as flexbilling.war | Gayam | 03/29/23 9:04 PM
Row 73 | We are working on the changes, please wait for sometime. | Venkatesh | 03/24/23 8:59 PM
Row 73 | As per above comment, marking this as Dup App and flexbilling.war is the original one. | Gayam | 03/08/23 12:12 AM
Row 73 | they are indeed duplicated on this sheet. The repo for this application is https://svn.penske.com/svn/avolent/ptl_customization/billing/appserver/trunk | Dylan | 03/07/23 1:02 AM
Row 73 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 73 | @mark.weaver@penske.com and @elliott.eames@penske.com - Flex billing entries are replicated thrice. Ref. Row #97, #99 and #129. Pls. confirm and share the Repo details for these applications to consider for log4J Modernization CC: @rafiq.melath@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:10 AM
| @mark.weaver@penske.com - Pls. ignore the row #s mentioned above. Applications under confusion are 1. flexbilling.war 2. flexbilling 3. Flex Billing CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com | Mathumala Nachiappan | 02/06/23 6:45 PM
Row 74 | @dylan.price@penske.com , This app is ready for your review. Please verify and merge. Thanks. https://bitbucket.penske.com/projects/PBTCBOS/repos/flexbilling-acl-batch/pull-requests/4/overview | Gayam | 07/07/23 1:13 AM
Row 74 | Hi @praneeth.gayam@penske.com you are good to move xmlgen_common.jar to artifactory. As for the conf folder, please use the "database.properties" inside /conf and not in /src/conf. This will get wiped out when I make the property file changes after log4j/maven is finished. | Dylan | 06/07/23 1:11 AM
Row 74 | @venkatesh.hossalinever@penske.com , Question1: In this application we have two conf folders. One is under src folder and another one is outside the src folder. So which one we need to use? Question2: This app is dependent on xmlgen_common.jar. But this is not available in artifactory. Could you please approve to upload this jar to following location in artifactory. groupid: com.penske.nb.xmlgen.common , artifactid: xmlgen_common | Gayam | 03/10/23 2:20 AM
| @venkatesh.hossalinever@penske.com , could you pelase check above questions and provide your response. Thanks. | Gayam | 04/18/23 3:30 AM
Row 74 | Completed reviewing the log4j secrets there is no code changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 3:41 AM
| Thank you. Changing the app status to Cap Maven | Gayam | 03/02/23 1:33 AM
Row 74 | Completed reviewing the log4j secrets -the hardcoded values in properties are not being used in application code and no changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 3:26 AM
Row 74 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 74 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:53 AM
Row 75 | As per @dylan.price@penske.com marking this line item as Dup App | Gayam | 03/08/23 12:11 AM
Row 75 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 75 | @mark.weaver@penske.com and @elliott.eames@penske.com - Flex billing entries are replicated thrice. Ref. Row #97, #99 and #129. Pls. confirm and share the Repo details for these applications to consider for log4J Modernization CC: @rafiq.melath@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:10 AM
| @mark.weaver@penske.com Pls. ignore the row #s mentioned above. Applications under confusion are 1. flexbilling.war 2. flexbilling 3. Flex Billing CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com | Mathumala Nachiappan | 02/06/23 6:46 PM
Row 76 | Question: @dylan.price@penske.com , Targeted folder of this application contains different ApplicationProperties.properties files under different enviornment folders. 'DEFAULT_MACHINE' property value is different between different ApplicationProperties files. As we are going to do the environment agnostic build we should use only 1 file under resources. Could you please check and let us know which one we need to use. Thanks. | Gayam | 06/13/23 1:46 AM
Row 76 | Hi @praneeth.gayam@penske.com I am seeing "conf" and "conf_test". For the time being could you please bring both conf folders down and when I make the changes for the properties files I will consolidate them into 1 conf folder | Dylan | 06/07/23 6:17 PM
| Sure @dylan.price@penske.com | Gayam | 06/08/23 7:51 AM
Row 76 | HI @praneeth.gayam@penske.com secrets file looks great -- please start with log4j/maven changes | Dylan | 06/07/23 1:14 AM
| Thanks @dylan.price@penske.com . Also, could you please the question I posted above. | Gayam | 06/07/23 6:02 AM
Row 76 | Secrets: @elliott.eames@penske.com , Adding to above question, I sent secrets in the email. Please check and respond whether any changes required to remediate the secrets. | Gayam | 03/24/23 12:07 AM
Row 76 | Question: @elliott.eames@penske.com , In this application we have two conf folder one is under src folder and another one is outside the src folder so need confirmation which one we need to use? Thanks. | Gayam | 03/09/23 2:12 AM
Row 76 | As per @dylan.price@penske.com , the other 2 line items are Duplicates. This is the original one. Repo is https://svn.penske.com/svn/avolent/ptl_customization/billing/appserver/trunk | Gayam | 03/08/23 12:12 AM
Row 76 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 76 | @mark.weaver@penske.com and @elliott.eames@penske.com - Flex billing entries are replicated thrice. Ref. Row #97, #99 and #129. Pls. confirm and share the Repo details for these applications to consider for log4J Modernization CC: @rafiq.melath@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:10 AM
| @mark.weaver@penske.com Pls. ignore the row #s mentioned above. Applications under confusion are 1. flexbilling.war 2. flexbilling 3. Flex Billing CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com | Mathumala Nachiappan | 02/06/23 6:45 PM
Row 77 | Question: @rohit.sharma@penske.com , This application dependent on fmea.jar which is available under application's lib folder. https://svn.penske.com/svn/webmasters/web/fmea/trunk/WebContent/WEB-INF/lib/ We need to upload fmea.jar to artifactory to mavanize this app under below location. Could you please provide your approval to upload to artifactory. <groupid>com.penske.fmeajar</groupid> <artifactid>fmea</artifactid> <version>Default</version> | Gayam | 06/13/23 1:52 AM
| go for it | Rohit | 06/13/23 2:17 AM
| Thank you. | Gayam | 06/13/23 2:36 AM
Row 77 | Secrets: @rohit.sharma@penske.com , I sent the secrets in the email for this app. Please check them. Thanks. | Gayam | 06/02/23 1:18 AM
| There are no secrets for this app. | Gayam | 06/07/23 2:54 AM
Row 77 | https://svn.penske.com/svn/webmasters/web/fmea/trunk/ | Hugo Scavino | 05/01/23 9:25 PM
| Thanks @hugo.scavino@penske.com . Do we have any existing bamboo build for this app? | Gayam | 05/02/23 12:53 AM
Row 77 | Please use trunk | Hugo Scavino | 05/01/23 9:24 PM
Row 77 | this application is in WebMasters SVN repository https://fisheye.penske.com/changelog/~br=trunk/Webmasters | Hugo Scavino | 05/01/23 9:24 PM
Row 77 | @scott.bortzel@penske.com / @scott.pemrick@penske.com , For this application both SVN and Bamboo are not available. Could you please let us know the SVN and Bamboo details. Thanks. | Gayam | 01/14/23 1:06 AM
Row 78 | Question: @gregg.obst@penske.com / @sarath.mani@penske.com / @stella.george@penske.com , This app depends on following jars. 1. VehicleInformationUtility.jar: We started working on modernizing this jar as part of other apps and uploading to artifactory through Bamboo. 2. highavail.jar: bamboo : https://bamboo.penske.com/browse/HABP SVN repo: https://svn.penske.com/svn/architecture/general/highavail/branches/dev_gh Please let us know whether we need to modernize the highavail.jar. Following jars are in lib folder but app is not giving any compilation issues even if we don't add them to build path. Please let us know whether we need to modernize the below jars or upload directly to artifactory. 3. coversheet.jar: No SVN/bamboo found 4. pos.jar: No SVN/bamboo found but pos.jar is also using in this app. And its looks like a internal penske project which is having log4j1 imports and log4j.xml as well. Thanks. | Gayam | 06/23/23 12:53 AM
Row 78 | Secrets: @stella.george@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:55 AM
| AO confirmed no changes required for secrets. | Gayam | 06/16/23 10:32 PM
Row 79 | @praneeth.gayam@penske.com , wsdl files are configured inside conf folder. The wsdl file from targeted folder will not be used. Kindly, let us know once log4j/mavenization changes are done. | Nayum | 08/14/23 4:49 PM
Row 79 | @praneeth.gayam@penske.com 1. dev folder might be used for local configuration. so we can have dev configuration folder. 2. MessageReceiverService.wsdl file has to be used from respective environment folder. 3. penske-service-security-framework.jar is not required, it can be removed. | Nayum | 07/19/23 7:02 PM
| @pathan.nayum@penske.com , In environment agnostic build there will be no separate builds for each environment. It should be handled in the code. Please check with Architecture team i.e @shane.myers@penske.com if you have any questions. | Gayam | 07/19/23 11:56 PM
Row 79 | @pathan.nayum@penske.com , While working on converting this app to mavenization we found following things. Please clarify them. 1.This application has dev environment in the targeted folder. But the batch apps don't have the dev enironment. Please confirm whether we can ignore the dev configurations. 2.App has MessageReceiverService.wsdl file in dev,prod and qa folders under targeted folder. But we need to use only 1 wsdl as this is a environment agnostic build. Could you please let us know which one we need to use. 3. This app is having penske-service-security-framework.jar. But build is successful without using this jar. Do we need to include the dependency or not? | Gayam | 05/24/23 1:25 AM
Row 79 | We have verified the secrets shared in the email, And they are not secret or confidential info. So no change required. | Nayum | 05/12/23 9:33 PM
| Thanks @pathan.nayum@penske.com . Changed the status to Cap Maven. | Gayam | 05/17/23 3:21 AM
Row 79 | @praneeth.gayam@penske.com The following is the complete url deployed in the prod https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_spring @william.spohn@penske.com please correct us if any concerns. Can I get the secret codes for this particular branch(fuelnetbatch_spring). | Nayum | 04/28/23 11:33 AM
| @praneeth.gayam@penske.com @pathan.nayum@penske.com Yes Its the correct Prod branch. https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_springPraneeth can you please share the secrets for production branch. | Venkatesh | 04/29/23 2:33 AM
| @venkatesh.hossalinever@penske.com / @pathan.nayum@penske.com , I will discuss with my team and will let you know. | Gayam | 05/02/23 1:21 AM
| @venkatesh.hossalinever@penske.com / @pathan.nayum@penske.com , The provided secrets file is from https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_spring only. Secrets scanning tool provides all commit history secrets too. | Gayam | 05/03/23 1:24 AM
| No Praneet, If it consider the commit history the svn path should be same and in the list we can find different path. Can you point the above svn url and share the new list of secret codes. The secrets you shared earlier was having duplicate entries. Hence requesting to share the secret codes for the above link alone. | Kandasamy | 05/03/23 5:51 PM
| @revathi.kandasamy@penske.com , we will do the secrets scanning one more time and will send the list. | Gayam | 05/04/23 12:15 AM
| @revathi.kandasamy@penske.com / @venkatesh.hossalinever@penske.com / @pathan.nayum@penske.com , I sent the secrets file which is produced from the scanning of https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_spring branch in the email. Scanning tool is scanning all the branches when we scan the bitbucket but scanning only the provided branch when we scan the svn. | Gayam | 05/05/23 6:46 AM
Row 79 | While analysing the secret codes in fuelbatch_secrets.xlsx, we could find the following different svn locations for fuelbatch application. Kindly, confirm appropriate svn location to be verified for secret codes. https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/dev_gh/fuelnetbatch_spring https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet_batch_Spring_Migration https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet_batch https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet | Nayum | 04/27/23 3:29 PM
| @pathan.nayum@penske.com , You provided us the following URL for this repo. Please check above comments. Repository 1 name: FUELBATCH_PROD associated reposiory url: https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/ | Gayam | 04/28/23 1:59 AM
Row 79 | Secrets: @pathan.nayum@penske.com , We sent secrets file for this app in the email. Could you please verify. Thanks. | Gayam | 04/22/23 2:16 AM
Row 79 | Yes, we can refer it from the artifactory. | Nayum | 04/06/23 1:09 PM
Row 79 | Repository 1 name: FUELBATCH_PROD associated reposiory url: https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/ is the source code, the second repository is pointing to a jar. | Nayum | 04/05/23 4:47 PM
| @pathan.nayum@penske.com , that means can we add the jar which is pointing to repo2 as a dependency to repo1 app while mavanizing? | Gayam | 04/06/23 2:49 AM
Row 79 | @william.spohn@penske.com , Following is the old bamboo build. https://bamboo.penske.com/chain/viewChain.action?planKey=FBBP-FBPROD This Bamboo build have reference to 2 repositories. Repository 1 name: FUELBATCH_PROD associated reposiory url: https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/ Repository 2 name: SECURITYJAR_PROD associated reposiory url: https://svn.penske.com/svn/architecture/security/penske-service-security-framework Could you please check and clarify us which one is correct repo? | Gayam | 03/13/23 11:11 PM
Row 80 | @praneeth.gayam@penske.com , After deploying fuelcardsplit changes to QA, new logs are not created. Kindly, check if you have to restart the aplication. | Nayum | 07/19/23 6:49 PM
| @pathan.nayum@penske.com , will check. | Gayam | 07/19/23 11:50 PM
| @pathan.nayum@penske.com , Ritesh told me that he already updated you. Could you please run the application in local and check whether logs are getting generated. We can't run the application in our local. | Gayam | 07/24/23 11:58 PM
Row 80 | @praneeth.gayam@penske.com / @venkatesh.hossalinever@penske.com , for fuelcardsplit application, Dev URL is not working, while accessing the Dev URL it is redirecting to dlinks(https://logindev.penske.com/dlinks/app/dlinksMain?LoginUserID=null). | Nayum | 06/12/23 8:28 PM
Row 80 | @praneeth.gayam@penske.com Reviewed the changes and merged code to develop branch, Please deploy to Dev environment. | Venkatesh | 05/16/23 6:31 PM
| @venkatesh.hossalinever@penske.com , Onboarding develop branch to bamboo and deploying to dev completed. Please verify. | Gayam | 05/18/23 12:55 AM
| @venkatesh.hossalinever@penske.com , Because of recent architectural change from Hugo / @shane.myers@penske.com , we changed the scope of log4j jars from provided scope compile scope. Please verify and merge to develop branch. Thanks. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelcardsplit-web/pull-requests/6/overview | Gayam | 05/22/23 11:57 PM
Row 80 | @revathi.kandasamy@penske.com , Dev deployment is completed from develop_log4j. https://bamboo.penske.com/browse/FCARDBP-FCRDALBLD1/deployments Could you please verify. Also please merge the PR which is raised from develop_log4j to develop branch. | Gayam | 04/25/23 12:59 AM
Row 80 | @praneeth.gayam@penske.com : log4j and Maven changes looks good. Can you do dev deployment for testing. | Kandasamy | 04/20/23 6:49 PM
| Sure @revathi.kandasamy@penske.com . It looks like the PR is not yet merged. Could you please merge. | Gayam | 04/21/23 1:33 AM
Row 80 | Review: @venkatesh.hossalinever@penske.com , this is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelcardsplit-web/pull-requests/3/overview | Gayam | 03/08/23 2:35 AM
Row 80 | Venkatesh Hossalinever reports "No remediation is required for all False positives, these files are not using credentials. There are no code changes required to fuelcardsplit.var" | William Spohn | 02/24/23 9:16 PM
| Thank you. Changed the status to (Cap)Maven | Gayam | 02/25/23 12:51 AM
Row 80 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 80 | @william.spohn@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:42 AM
Row 80 | I am responsible for testing efuel.war, efueladmin.war, fuelbatch(UAT done), fuelcardsplit.war(UAT done), fuelnetsvc.war(UAT done), and fuelpricing.war. | William Spohn | 01/10/23 10:17 PM
Row 80 | @william.spohn@penske.com , we did not start the log4j/maven changes for this application. Could you please let us know whether you are providing sign off for any other changes. But this sheet is only for log4j/maven changes updates. @mathumala.nachiappan@penske.com | Gayam | 12/12/22 11:52 PM
Row 80 | Yes, Anju Nair emailed me on 11/24 that log4j2 changes to fuelcardsplit.var were ready for testing in QA. I completed my QA testing of this web app - all tests passed. Please consider this my QA testing signoff. | William Spohn | 12/08/22 7:44 PM
| Thanks @william.spohn@penske.com . Will take it forward. @praneeth.gayam@penske.com - Pls. ask Dev team to identify the rest other modernization changes requried | Mathumala Nachiappan | 12/12/22 4:53 PM
Row 80 | hi @william.spohn@penske.com - Is it related to Log4j modernization? | Mathumala Nachiappan | 12/08/22 3:53 PM
Row 80 | I tested "fuelcardsplit.war" in QA for Anju Nair and all tests passed. | William Spohn | 12/07/22 7:17 PM
Row 81 | Thanks @venkatesh.hossalinever@penske.com / @revathi.kandasamy@penske.com . I am changing the status to duplicate app as per your instructions. | Gayam | 05/31/23 12:56 AM
Row 81 | @praneeth.gayam@penske.com FuelNet application doesn't require migration. Please close this task. | Venkatesh | 05/30/23 9:36 PM
Row 81 | @praneeth.gayam@penske.com , the given bamboo build has only the test code. Hence it doesnt require any migration. The following is the svn path https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet_testing | Kandasamy | 05/26/23 4:46 PM
Row 81 | Hi Gayam, I have discussed with Venkatesh - he will review and confirm if this bamboo build and svn repo are related to fuelnet or not. | William Spohn | 05/09/23 3:03 AM
Row 81 | Hi Gayam. I know of only 2 Java applications for my Telapoint/FuelNet module: fuelnetsvc.war and fuelbatch.war. In my nearly 12 years as project lead for Fuel, I have never heard of a 3rd Java application. I will confirm with Venkatesh. | William Spohn | 05/04/23 6:42 PM
| Sure @william.spohn@penske.com . Thank you. | Gayam | 05/05/23 6:32 AM
| Hi Gayam. I checked with Venkatesh. We both think this entry "fuelnet" is a duplicate of "fuelnetsvc.war". | William Spohn | 05/06/23 1:04 AM
| Thanks @william.spohn@penske.com . Just for your info. We found following Bamboo build and SVN URL which are not related to fuelbatch and fuelnetsvc. https://bamboo.penske.com/browse/FNSVC-FNWSPROD SVN Repo associated with this bamboo build: https://svn.penske.com/svn/fieldsys/other/fuelnetbatch/branches/offshore_igate/fuelnet_testing/ Please check and confirm whether this bamboo build and svn repo are related to fuelnet or not. Depends on that we can take the decision whether it is a duplicate or not. | Gayam | 05/06/23 2:30 AM
Row 81 | @william.spohn@penske.com / @venkatesh.hossalinever@penske.com , We are unable to find the Bamboo build and svn repo for fuelnet batch application. Could you please help us to find the info. Thanks. | Gayam | 05/04/23 12:23 AM
Row 82 | @revathi.kandasamy@penske.com , Dev deployment is completed from develop_log4j. https://bamboo.penske.com/browse/FNSVC-FNSALBLD Could you please verify. Also please merge the PR which is raised from develop_log4j to develop branch. | Gayam | 04/25/23 1:01 AM
| @venkatesh.hossalinever@penske.com , Please merge https://bitbucket.penske.com/projects/PBTFUEL/repos/fuelnetsvc-web/pull-requests/3/overview and deploy the version from develop branch. | Gayam | 06/08/23 3:39 AM
| @praneeth.gayam@penske.com Code changes are merged. can you please deploy changes on dev branch. | Venkatesh | 06/22/23 2:26 AM
| @venkatesh.hossalinever@penske.com , Build is automatic once the code merged to develop branch. Please deploy to dev and QA and test it. Thanks. | Gayam | 06/22/23 3:18 AM
Row 82 | @praneeth.gayam@penske.com : Log4j and Maven changes looks good. Can you deploy app in dev for testing. | Kandasamy | 04/20/23 6:55 PM
| Sure @revathi.kandasamy@penske.com . It looks like the PR is not yet merged. Could you please merge. | Gayam | 04/21/23 1:36 AM
Row 82 | Review: @venkatesh.hossalinever@penske.com / @william.spohn@penske.com , This app is ready for your review. Please check. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelnetsvc-web/pull-requests/3/overview | Gayam | 03/04/23 2:01 AM
Row 82 | Venkatesh Hossalinever reports "No remediation is required for all False positives, these files are not using credentials. There are no code changes required for fuelnetsvc.war. | William Spohn | 02/24/23 9:40 PM
| Thank you. Changed to (Cap)Maven. | Gayam | 02/25/23 12:57 AM
Row 82 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 82 | @william.spohn@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:43 AM
Row 82 | @william.spohn@penske.com , This application is using sun.misc.* import statements from rt.jar which is part of java 6 version . But the rt.jar of java 1.8 doesn't have those packages. So code is not compiling. The code changes may required for this app. Could you please check it. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 01/17/23 12:32 AM
| I will update Venkatesh; then he/his team can assist you. | William Spohn | 01/17/23 7:19 PM
| Is this application in BItbucket or SVN still? Can you please sure the URL. Thank you. I can review. | Hugo Scavino | 01/18/23 2:09 AM
| @hugo.scavino@penske.com , https://svn.penske.com/svn/fieldsys/other/fuelnetwebservice/ is the URL. Branch is branches/fuelnetsvc/fuelnetsvc | Gayam | 01/18/23 2:14 AM
| I Moved the code to to src/main/ root. and also replaced the Base64 code with hopefully a JDK compliant replacement. Updated the imports to slf4j but still need a ported log4j2.xml Also added a maven pom.xml. The mavenization is not complete but the old compiler dependency should be resolved. In the pom.xml please update the development.distribution.url value and distributionManagement elements. More work is required but you should be over this blocker. see the branch here and proceed please https://svn.penske.com/svn/fieldsys/other/fuelnetwebservice/branches/maven/ | Hugo Scavino | 01/18/23 10:29 PM
| Thanks @hugo.scavino@penske.com . We will check and get back to you. Changing the status to (Cap)Log4j | Gayam | 01/18/23 11:19 PM
Row 82 | am responsible for testing efuel.war, efueladmin.war, fuelbatch(UAT done), fuelcardsplit.war(UAT done), fuelnetsvc.war(UAT done), and fuelpricing.war. | William Spohn | 01/10/23 10:17 PM
Row 82 | @william.spohn@penske.com , we did not start the log4j/maven changes for this application. Could you please let us know whether you are providing sign off for any other changes. But this sheet is only for log4j/maven changes updates. @mathumala.nachiappan@penske.com | Gayam | 12/12/22 11:52 PM
Row 82 | Yes, Anju Nair emailed me on 11/24 that log4j2 changes to fuelnetsvc.var were ready for testing in QA. I completed my QA testing - all tests passed. Please consider this my QA testing signoff. | William Spohn | 12/08/22 7:45 PM
| Thanks @william.spohn@penske.com . Will take it forward. @praneeth.gayam@penske.com - Pls. ask Dev team to identify the rest other modernization changes requried | Mathumala Nachiappan | 12/12/22 4:53 PM
Row 82 | hi @william.spohn@penske.com - Is it related to Log4j modernization? | Mathumala Nachiappan | 12/08/22 3:53 PM
Row 82 | I tested fuelnetsvc.war in QA for Anju Nair and all tests passed. | William Spohn | 12/07/22 7:18 PM
Row 83 | @revathi.kandasamy@penske.com , This app is ready for your review. Please check. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelpricing-web/pull-requests/3/overview | Gayam | 04/05/23 2:43 AM
| @praneeth.gayam@penske.com Changes looks good and merged to dev branch. please deploy application on dev environment. | Venkatesh | 06/22/23 2:30 AM
| Thanks @venkatesh.hossalinever@penske.com | Gayam | 06/22/23 3:25 AM
| @venkatesh.hossalinever@penske.com , This app is onboarded to bamboo but test cases are failing. Currently, we disabled the test cases. So build got successful an deployed to dev. | Gayam | 06/23/23 11:49 PM
Row 83 | PFA for the issue we get while executing application maven build. Architect team has recommended us to use a different version for below artifacts. <artifactId>security-author-filter</artifactId> <version>2.0.0-develop-20230220.233353-1</version> <artifactId>security-util</artifactId> <version>2.0.0-develop_log4j-20230202.213506-2</version> Kindly update the pom.xml with the above versions | Kandasamy | 03/29/23 6:19 PM
| @revathi.kandasamy@penske.com , Not sure for which app and which branch you are referring to. Log4j team is still working on this app and waiting for the response from AO to the question which we asked above. Question is regarding 'dassupport.jar'. Could you please check and provide your response. | Gayam | 03/29/23 9:02 PM
| I was referring to fuelpricing.war. While checking in local with svn code, dassupport.jar was not required. There was no compilation issue. Pls go ahead with your changes. | Kandasamy | 04/03/23 7:05 PM
Row 83 | @william.spohn@penske.com This app has dependency with 'dassupport.jar' is available. SVN repo is identified for this jar - https://svn.penske.com/svn/architecture/general/das_support/ Bamboo build is not available for this jar. So need confirmation on whether to upload this jar to artifactory or to consider for log4J modernization. If confirmed for Log4J changes, pls. share the reference folder/branch for log4J development. CC: @praneeth.gayam@penske.com , @rafiq.melath@penske.com | Mathumala Nachiappan | 01/10/23 10:54 AM
| @william.spohn@penske.com , Just want to update you, fuelpricing build is getting successful without using dassupport.jar. Do you want us to continue without including dassupport.jar. If not please let us know whether we can upload this jar to artifactory. | Gayam | 02/23/23 12:39 AM
Row 83 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 83 | Secrets Mitigation: @william.spohn@penske.com , Adding to above questions, we have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:44 AM
Row 83 | Let me know when fuelpricing.war is ready to test. | William Spohn | 01/10/23 10:18 PM
| @william.spohn@penske.com , Could you please check above question and provide your response. | Gayam | 01/11/23 8:58 AM
| I will update Venkatesh, then he/his team can assist you. | William Spohn | 01/17/23 7:20 PM
| @william.spohn@penske.com / @venkatesh.hossalinever@penske.com , Could you please provide the response to the question which i asked above. | Gayam | 01/27/23 11:55 PM
Row 84 | Secrets: @elliott.eames@penske.com , I sent the secrets of this app in an email. Please check and confirm whether it requires any code changes. Thanks. | Gayam | 07/18/23 1:33 AM
Row 84 | Hi @praneeth.gayam@penske.com https://bitbucket.penske.com/projects/PBTFUEL/repos/fuel-promotions-service/browse?at=refs%2Fheads%2Fdevelop should be the branch to use | Dylan | 06/07/23 1:37 AM
| Thanks @dylan.price@penske.com | Gayam | 06/08/23 7:58 AM
Row 84 | as per @elliott.eames@penske.com here is the Fuel Promotions Service out on BitBucket. It was placed in EBIZ CUSTOMER EXTRANET because that is where Saumya Bhatnagar and his team placed it when developing! https://bitbucket.penske.com/projects/EBCE/repos/fuel-promotions-service/browse?at=refs%2Fheads%2Felliott_upgrade_fuel_promotion | Dylan | 03/07/23 7:40 PM
| Thanks @dylan.price@penske.com . Which branch we need to take as base branch for the log4j changes? | Gayam | 03/07/23 11:54 PM
Row 84 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 84 | @elliott.eames@penske.com - As per the app details, bamboo project key mentioned is 'FP'. But this project is identified with the Bamboo project key as 'EXTSER'. Pls. confirm and share the Repo details as well as the branch to be referred for log4J Modernization. CC: @rafiq.melath@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:18 AM
Row 85 | @praneeth.gayam@penske.com merged the MR | Mahipal | 05/16/23 7:53 PM
| @mahipal.podduturi@penske.com , We will let you know once we onabord develop branch to bamboo and build it. | Gayam | 05/17/23 3:24 AM
| Onboarding develop branch to bamboo is done and build is completed. Please deploy to QA. | Gayam | 05/18/23 1:00 AM
Row 85 | @sherin.basheer@penske.com alreday tested this application good move completed status | Mahipal | 05/09/23 8:06 PM
| @mahipal.podduturi@penske.com , MR is still in open status. https://bitbucket.penske.com/projects/ARPROJ/repos/fuelrecpt-batch/pull-requests/8/overview Could you please merge. Then we will onboard develop branch to Bamboo. | Gayam | 05/09/23 10:38 PM
Row 85 | @praneeth.gayam@penske.com can you deploy this app as well in QA | Mahipal | 05/04/23 6:34 PM
| @mahipal.podduturi@penske.com we will update the main class in pom and will let you know. | Gayam | 05/05/23 6:28 AM
| @mahipal.podduturi@penske.com , Changed the pom file and committed to develop_log4j branch. we are not supposed to do the QA deployment. Only AO needs to do the QA deployment. Please build and do the deployment from develop_log4j branch which is already onbaorded in bamboo. thanks. | Gayam | 05/06/23 2:53 AM
Row 85 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:30 AM
Row 85 | I think the error above also applies to the issue with dlinkappremoval - please verify that the main class is being set by the bamboo plan in the manifest file | William | 12/23/22 11:07 PM
Row 85 | This batch is not running properly in QA. The message in the logs says "2022-11-04 10:00:43,195 FATAL (BatchMain.java:main():75) - There was an unhandled exception java.lang.IllegalArgumentException: The batch jar main class property [batch-jar-main-class] was not set. at com.penske.architecture.batchframework.config.PropertiesConfigurator.loadConfiguration(PropertiesConfigurator.java:48) at com.penske.architecture.batchframework.launcher.Launcher.<init>(Launcher.java:51) at com.penske.architecture.batchframework.BatchMain.main(BatchMain.java:71) | William | 12/23/22 11:07 PM
Row 85 | @mathumala.nachiappan@penske.com assuming you are done with everything and ready to handoff for AO to final test - I moved it to AO Final Testing. @shane.myers@penske.com Please work with Mathu on what is needed to complete this app. Thank you | Yvette Urso | 12/09/22 12:50 AM
Row 85 | @yvette.urso@penske.com - This App is available for testing in QA. Pls. suggest the status | Mathumala Nachiappan | 11/23/22 3:30 AM
Row 85 | @sherin.basheer@penske.com - QA Deployment done on 13th Nov. | Mathumala Nachiappan | 11/23/22 3:29 AM
Row 86 | Maven log4j changes were deployed to production. | Sherin | 06/20/23 11:53 PM
Row 86 | Application threw new error: The was an error: org.springframework.beans.factory.BeanInitializationException: Could not load properties; nested exception is java.io.FileNotFoundException: class path resource [conf/fuelreceiptbatch.properties] cannot be opened because it does not exist Properties file and mappers were inside conf folder pre-mavenizing. Moving them to conf folder should fix this issue. | Sherin | 03/02/23 3:20 AM
Row 86 | App threw start up error 2022-12-16 23:57:18,272 FATAL (BatchMain.java:main():75) - There was an unhandled exception java.lang.IllegalArgumentException: The batch jar main class property [batch-jar-main-class] was not set. at com.penske.architecture.batchframework.config.PropertiesConfigurator.loadConfiguration(PropertiesConfigurator.java:48) This was fixed by adding fuelrecpt-qa.prop file and including *.prop in bin.xml file | Sherin | 03/02/23 3:18 AM
Row 86 | @yvette.urso@penske.com - Repeated entry of #37. Pls. remove this | Mathumala Nachiappan | 11/23/22 3:59 AM
Row 87 | @sreekanth.kancharla@penske.com , This app is onboarded to Bamboo. Please verify. https://bamboo.penske.com/browse/GEWEBCASH-GEWEB | Gayam | 03/30/23 11:07 PM
| @sreekanth.kancharla@penske.com , We chagned the log4j2 jars scope from provided to compile. So please merge the code. https://bitbucket.penske.com/projects/ITFIS/repos/gewebcash-batch/pull-requests/5/overview | Gayam | 05/24/23 2:18 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 05/24/23 9:04 PM
Row 87 | @sreekanth.kancharla@penske.com , this app is onboarded to Bamboo. Please check and let us know whether it can be deployed to Dev. | Gayam | 03/23/23 11:05 PM
| @praneeth.gayam@penske.com Please change the name in bamboo from "gewebcash" to "gewebcash-batch" similar to bitbucket repo name. I suggest to make similar changes to keep the name in both Bamboo & Bitbucket as same for all the new plans. | Sreekanth | 03/25/23 2:22 AM
| @praneeth.gayam@penske.com Do you've any update on changing the names? This is batch app, so no DEV environment. We'll take care of deploying to QA once validated in local. | Sreekanth | 03/30/23 12:22 AM
Row 87 | @praneeth.gayam@penske.com The PR got auto declined by bitbucket, so I've re-opened it and merged also. Hope that won't cause any issues as the status is still with Cap team. | Sreekanth | 03/21/23 6:03 PM
| No Issues @sreekanth.kancharla@penske.com . Thanks. We will onbaord this app to Bamboo. | Gayam | 03/22/23 12:43 AM
Row 87 | @praneeth.gayam@penske.com Since the status is under Cap team, please remove me from the review list for the existing PR in bitbucket. https://bitbucket.penske.com/projects/ITFIS/repos/gewebcash-batch/pull-requests/3/overview You can add back, once the PR is available for my review. | Sreekanth | 03/16/23 1:01 AM
| Sure @sreekanth.kancharla@penske.com . Thanks. | Gayam | 03/17/23 2:59 AM
Row 87 | @praneeth.gayam@penske.com In that case please create a new project for this application in Bamboo as there is no existing plan available. @mathumala.nachiappan@penske.com @srinivasan.narayanan@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/03/23 2:10 AM
Row 87 | @rafiq.melath@penske.com / @srinivasan.narayanan@penske.com / @sreekanth.kancharla@penske.com , We found the SVN url for this app https://svn.penske.com/svn/webprojects/admin/gewebcash/ But there is no bamboo build. Could you please provide the production version of the branch and under which project we need to create Bamboo specs. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/11/23 9:08 AM
| @praneeth.gayam@penske.com This is a batch application running on IBMi server from IFS. There is no trunk svn source available, so we compared the production source with offshore source and committed the PROD source under https://svn.penske.com/svn/webprojects/admin/gewebcash/trunk FYI, this application has only 1 java file. @mathumala.nachiappan@penske.com @swati.saxena@penske.com @srinivasan.narayanan@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/02/23 3:06 AM
| Thanks @sreekanth.kancharla@penske.com . Do you want us to take up the https://svn.penske.com/svn/webprojects/admin/gewebcash/trunk and do the modernization? Also, under which project do you want us to create Bamboo builds for this project? | Gayam | 02/02/23 3:23 AM
| @praneeth.gayam@penske.com Yes, please continue modernization with trunk branch. Which project means? This is separate application comes under Admin group, so separate plan in Bamboo is required. OR If we can have "admin-as400-utilities" as a project and under that also we can've build plans as we've few more similar batch applications runs on IBMi. @kalrav.khamar@penske.com @srinivasan.narayanan@penske.com | Sreekanth | 02/02/23 3:47 AM
| @sreekanth.kancharla@penske.com , In Bamboo, every application or group of similar apps have project. For example, under the below project in bamboo all ACH(Batch, Service and Web) build & deploy plans are created. All these are old plans. But we know where to create the new plans for ACH as the project already exist in Bamboo. https://bamboo.penske.com/browse/ACH But for gewbcash, there is no old build plans i.e no project exist in Bamboo. So could you please let us know whether to create a new project or use any other existing Admin project? @haribabu.challa@penske.com @mathumala.nachiappan@penske.com | Gayam | 02/02/23 11:05 PM
Row 87 | @rafiq.melath@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for these applications. | Gayam | 11/23/22 12:31 AM
| @rafiq.melath@penske.com / @srinivasan.narayanan@penske.com / @sreekanth.kancharla@penske.com , Could you please respond to above question. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 1:12 AM
Row 87 | @rafiq.melath@penske.com @praneeth.gayam@penske.com @mathumala.nachiappan@penske.com Hi Rafiq, We are testing out the email functionality in Smartsheet confirming you are receiving emails from here. Regards, Yvette | Yvette Urso | 11/25/22 11:29 PM
Row 88 | @venkatesh.hossalinever@penske.com , Deploy plan onboarded and deployed to QA. Please check and verify. Thanks. deploy plan: https://bamboo.penske.com/browse/INVARCBATCHBP-INVSFTP/deployments qa deployment: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151196298 | Gayam | 08/04/23 1:07 AM
Row 88 | Review: @venkatesh.hossalinever@penske.com , This app is ready for your review. Please validate and merge. https://bitbucket.penske.com/projects/PA/repos/invarcsftpbatch/pull-requests/3/overview | Gayam | 06/30/23 1:06 AM
| @praneeth.gayam@penske.com code has been merged. Please deploy changes on QA. As we don't have Dev box for batch application. | Venkatesh | 08/02/23 2:58 AM
| Sure @venkatesh.hossalinever@penske.com | Gayam | 08/02/23 3:04 AM
Row 88 | @praneeth.gayam@penske.com Can you please share the secrets once again. | Venkatesh | 05/16/23 12:55 AM
| @venkatesh.hossalinever@penske.com , Sent secrets in email. | Gayam | 05/17/23 3:28 AM
| @praneeth.gayam@penske.com secrets has been reviewed there are no hardcoded values. Please proceed with the next step. | Venkatesh | 06/22/23 2:27 AM
| Thanks @venkatesh.hossalinever@penske.com . Changing the status to Cap Maven. | Gayam | 06/22/23 3:23 AM
Row 88 | @mark.weaver@penske.com , secrets of this app shared in the email. Please check. Thanks. | Gayam | 03/24/23 12:19 AM
Row 88 | Repo for this application is https://bitbucket.penske.com/projects/PBJB/repos/invarcsftpbatch/browse/src and bamboo link is https://bamboo.penske.com/browse/INVARCBATCHBP-INV | Dylan | 03/07/23 1:57 AM
Row 88 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 88 | Moved to AO Bamboo status | Yvette Urso | 12/15/22 2:45 AM
Row 88 | @mark.weaver@penske.com - Pls. share the Repo URL or the Bamboo project key for this applicaiton. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 12:00 PM
Row 89 | @sreekanth.kancharla@penske.com , We changed the log4j2 jars scope from provided to compile. So please merge the code. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/70/overview | Gayam | 05/24/23 2:25 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 05/24/23 9:03 PM
Row 89 | @sreekanth.kancharla@penske.com , Changes are completed for this app. For some reason, I am unable to merge the few maven changes to develop_log4j branch. Could you please merge below PR. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/66/overview Once you merge the above PR, please review the code in the below PR. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/67/overview Thanks. | Gayam | 04/19/23 3:24 AM
| @praneeth.gayam@penske.com The below PR is merged. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/66/overview I've added review comments to below PR. Please check and do the need. https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/67/overview | Sreekanth | 04/19/23 9:23 PM
| @sreekanth.kancharla@penske.com , We implemented the requested changes. Could you please merge them following PR https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/68/overview Then review the changes in PR https://bitbucket.penske.com/projects/ITFIS/repos/hrcc-web/pull-requests/67/overview Thanks. | Gayam | 04/22/23 1:55 AM
| @praneeth.gayam@penske.com Thank you for making the changes for review comments. Both the PR are merged. Since we already have bamboo plan for this app with mavenized source, if any changes requires in the plan as per the new log4j template, please proceed with those changes and update the status in the smartsheet. We'll start testing the app once it is delivered to AO. | Sreekanth | 04/24/23 8:18 PM
| @sreekanth.kancharla@penske.com , thank you. We will do the Bamboo setup and will let you know. | Gayam | 04/25/23 1:28 AM
| @sreekanth.kancharla@penske.com , this app is deployed to dev using develop branch - https://bamboo.penske.com/browse/HBP-HRCCALBP0/deployments Please verify. | Gayam | 04/27/23 1:32 AM
| @praneeth.gayam@penske.com This app source code was already available in Bitbucket and the bamboo plans also available. Separate plans for both Web & UI code. Now I see a new plan is created for web https://bamboo.penske.com/browse/HBP-HRCCALBP but no UI plan is created. Have you used existing https://bamboo.penske.com/browse/HBP-HRCCAL plan itself for DEV deployment. Since we've new plan for web, it is good to have new plan for UI also. | Sreekanth | 04/27/23 1:59 AM
| @sreekanth.kancharla@penske.com , we worked on only hrcc-web and the bamboo build for that is https://bamboo.penske.com/browse/HBP-HRCCALBP We did not work hrcc-ui project as this is not mentioned in our list or smartsheets. | Gayam | 04/27/23 3:11 AM
| @praneeth.gayam@penske.com hrcc-ui is not a separate project. That repo has front end code (angular) & hrcc-web has back end code (java). With both those sources only HRCC app can be tested. I suggest to have a new bamboo plan created for hrcc-ui as well, so that we can retire the old plans once we complete the log4j testing. If needed, please schedule a meeting with @raghuramredd.thummalapalli@penske.com / @balu.mohan@penske.com / @hugo.scavino@penske.com for further clarification. | Sreekanth | 04/27/23 6:54 PM
| Sure @sreekanth.kancharla@penske.com . But before onboarding bamboo plan for hrcc-ui, we need to modernize the hrcc-ui project. If you are ok, we can take up the work. | Gayam | 04/28/23 1:44 AM
| @praneeth.gayam@penske.com hrcc-ui is an angular app and available in bitbucket itself. Hope no need of any modernization for UI source code and new bamboo plan can be created with existing source code itself. We can discuss over call on code changes for modernization. | Sreekanth | 05/01/23 6:40 PM
| @sreekanth.kancharla@penske.com , if it contains total UI code and a Bamboo plan already exist, I don't think we need to re onboard any new plan. You can continue using the old bamboo plan of hrcc-ui. Please correct me if I am wrong. @hugo.scavino@penske.com | Gayam | 05/02/23 12:49 AM
| @praneeth.gayam@penske.com We are good to use the existing plan itself for UI. In that case, just to follow the naming convention, is it possible to change the name of the build plan https://bamboo.penske.com/browse/HBP-HRCCAL to "hrcc-ui" & the deploy plan also with the new naming convention. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=91160582 | Sreekanth | 05/02/23 7:24 PM
| @sreekanth.kancharla@penske.com , I think you need to raise a fp ticket to change the names of hrcc-ui . Because the plans of hrcc-ui not created by log4j team and we don't have control on that. Thanks. | Gayam | 05/03/23 1:49 AM
| @praneeth.gayam@penske.com Sure, thank you! | Sreekanth | 05/03/23 7:47 PM
Row 89 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:54 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets as all of them are related to mybatis xml files. You are good to proceed further. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 12:22 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (Cap) Maven | Gayam | 01/27/23 2:41 AM
Row 90 | @mahipal.podduturi@penske.com , As discussed develop branch already contains all the code. Please check. | Gayam | 05/31/23 12:58 AM
Row 90 | for build and deploy | Mahipal | 05/30/23 6:48 PM
Row 90 | @praneeth.gayam@penske.com i am not seeing develop _log4j branch | Mahipal | 05/30/23 6:48 PM
Row 90 | am not seeing the devlop branch | Mahipal | 05/04/23 6:33 PM
| We will onboard develop and will let you know. | Gayam | 05/05/23 6:12 AM
| @mahipal.podduturi@penske.com , Test cases are getting falied. But for now, we skipped the test cases. So build is getting successful. Please deploy to QA using below plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=142737434 Also, please fix the test cases. Because the manual configuration may be overridden in future. | Gayam | 05/06/23 3:01 AM
Row 90 | @praneeth.gayam@penske.com can you deploy the app | Mahipal | 05/04/23 6:33 PM
Row 90 | @shane.myers@penske.com - QA Deployment done on 17th Nov. @yvette.urso@penske.com - This app is available for testing in QA. Pls. suggest the status | Mathumala Nachiappan | 11/23/22 3:32 AM
Row 91 | Review: @sreekanth.kancharla@penske.com , This app is ready for youe review. https://bitbucket.penske.com/projects/PTLCORP/repos/hvutefile-batch/pull-requests/3/overview | Gayam | 07/09/23 11:50 PM
| @praneeth.gayam@penske.com Thank you! Merged the PR. We'll start testing this app. Please change the App Status accordingly. | Sreekanth | 07/10/23 7:09 PM
| @sreekanth.kancharla@penske.com , Do we need to onboard to bamboo? | Gayam | 07/10/23 11:27 PM
| @praneeth.gayam@penske.com Yes, please! | Sreekanth | 07/11/23 12:02 AM
| @praneeth.gayam@penske.com In develop branch, the version "2.0.0-feature-irs_Maven_XSD-to-java--20230628.124813-3" is provided. Do we need to have the version hard coded. We'll place the irs source in the irs repo and execute the build plan which should placed the jar in artifactory & this latest jar should be loaded in hvutefile batch app. Hope in this case, hard coded version would not work. | Sreekanth | 07/11/23 12:05 AM
| @sreekanth.kancharla@penske.com , I think if we remove the version, it always brings the latest version. But when you execute the build of irs, you should build the hvute also to get the latest irs files to hvute. | Gayam | 07/11/23 11:47 PM
| @praneeth.gayam@penske.com Yes, that is how the hvutefile app works. We always build the irs jar with latest source code and then once that build is successful, we'll initiate the build for hvutefile app, so latest irs will be used in the build. So getting the latest version of irs.jar is expected. | Sreekanth | 07/12/23 2:08 AM
| @sreekanth.kancharla@penske.com , Changed the version from specific number to 'RELEASE'. It is taking whatever latest IRS release from artifactory. | Gayam | 07/25/23 12:00 AM
| @praneeth.gayam@penske.com Perfect! We'll work on testing the app, once the issue with irs.jar is resolved. | Sreekanth | 07/25/23 5:35 PM
| irs issue is resolved. Please check this application. Thanks. | Gayam | 08/02/23 2:47 AM
| @praneeth.gayam@penske.com Great, we'll continue testing this application as well. Thank you! | Sreekanth | 08/03/23 9:20 PM
Row 91 | Query: @veronique.labeille@penske.com , Adding to above secrets validation, there is one more query. This app depends on irs.jar but it is not available in artifactory. Could you please provide your approval to upload this jar into artifactory at below location. Groupid: gov.irs.efile Artifactid: irs Thanks. | Gayam | 04/07/23 10:55 PM
| @praneeth.gayam@penske.com irs.jar file is not static dependency. Every 6 months, we get latest files from IRS and with those files the irs.jar file be created via existing bamboo plan (https://bamboo.penske.com/browse/HVUTBP-HVUTFDEV) used for the application jar creation as well. The current bamboo plan generates, both irs.jar and hvutefile.jar which is app specific jar. Post testing the irs.jar file in SUPPORT by users, the same will be pushed to QA & PROD. In this case, please suggest how the irs.jar file can be moved to artifactory. @veronique.labeille@penske.com | Sreekanth | 04/12/23 12:27 AM
| @sreekanth.kancharla@penske.com , what is the repo of irs.jar? If the repo exist, we can mavanize IRS and create a new bamboo plan which uploads the jar to artifactory. Update that dependency in hvutefile pom and rebuild and deploy the hvutefile app. I hope it resolves our issue. Let me know whether I did not understand the requirement correctly. | Gayam | 04/12/23 1:00 AM
| @praneeth.gayam@penske.com The repo for irs.jar also resides in same location of hvutefile i.e. "https://svn.penske.com/svn/webprojects/corp/hvutefile/branches/support/production_latest/xsd" Every time we get the files from IRS, we replace them under xsd folder. We are not sure how the existing bamboo plan generating the 2 jar files. Hope analyzing the bamboo script should help us how the irs.jar is being generated. | Sreekanth | 04/12/23 7:13 AM
| @sreekanth.kancharla@penske.com I extracted the irs.jar and it looks like it has the files from the folder https://bitbucket.penske.com/projects/PTLCORP/repos/hvutefile-batch/browse/irs%20java%20files?at=refs%2Fheads%2Fdevelop In my opinion, we have to segregate hvutefile and irs files into 2 separate projects in bitbucket and 2 separate bamboo builds. We can setup a call with @hugo.scavino@penske.com to discuss on this further. thanks. | Gayam | 04/13/23 12:50 AM
| @praneeth.gayam@penske.com Thank for the details. So are those irs java files not depending on the files from below folder which we need to replace yearly twice? https://bitbucket.penske.com/projects/PTLCORP/repos/hvutefile-batch/browse/xsd?at=refs%2Fheads%2Fdevelop Sure, we can connect with Hugo. Please proceed with scheduling the meeting. | Sreekanth | 04/13/23 1:14 AM
| @sreekanth.kancharla@penske.com , it doesn't seem like that jar has those xsd files. But I am not sure. Could you please check whether there is any relation. | Gayam | 04/13/23 11:25 PM
| @praneeth.gayam@penske.com FP ticket# 1834638 is created to architect team for clarification on irs.jar generation. | Sreekanth | 04/19/23 9:16 PM
| @praneeth.gayam@penske.com We received clarification from Architect team with FP# 1834638. The irs.jar is completely dependent on source/xsd/ETEC/2290/Return2290.xsd folder & source/lib/jaxb-xjc.jar With this the xsd folder is required to build the irs.jar file and these will be changed twice per year. If this can be built as a separate bamboo plan and add this jar as dependency in artifactory, we are ok with that. If so, please have this new plan under the existing bamboo project itself. We can connect with @hugo.scavino@penske.com on this for any further guidance if needed. | Sreekanth | 04/24/23 8:35 PM
| Thanks @sreekanth.kancharla@penske.com . So we need to create separate bitbucket repository for the irs files. Is that correct? @hugo.scavino@penske.com | Gayam | 04/26/23 1:15 AM
| @praneeth.gayam@penske.com Yes, if that needs to be maintained as a separate dependency. | Sreekanth | 04/26/23 6:15 PM
| Sure @sreekanth.kancharla@penske.com . Sent an email to Yvette to add one more line item irs.jar in smartsheets. We will start working on it. Thanks | Gayam | 04/28/23 2:19 AM
| @sreekanth.kancharla@penske.com , Yvette create a separate line item for irs.jar. We will complete that and add that dependency to this project and will let you know. Thanks | Gayam | 05/02/23 1:14 AM
| @sreekanth.kancharla@penske.com , Could you please confirm what are the folders from hvutefile repo need to move to irs repo. I know following. 1. You said source/xsd/ETEC/2290/Return2290.xsd folder. Do you mean total xsd folder source/xsd? 2. source/lib/jaxb-xjc.jar Any other folders are files need to move to irs repo? | Gayam | 05/03/23 2:05 AM
| @praneeth.gayam@penske.com Replied the answer in the irs.jar item. | Sreekanth | 05/03/23 7:46 PM
| @sreekanth.kancharla@penske.com , We are getting compilation issues because of irs.jar doesn't have required java classes. 1.import gov.irs.efile.ObjectFactory; 2.import gov.irs.efile.Return; I believe we need to add 'irs java files' fold r under hvutefile to irs.jar. Could you please check and confirm. Thanks. | Gayam | 05/25/23 3:09 AM
| @praneeth.gayam@penske.com These imports are part of irs.jar file only. Is that dependency added to hvutefile pom, if so we shouldn't get these compiler errors. | Sreekanth | 05/25/23 8:19 PM
| @sreekanth.kancharla@penske.com But irs.jar file doesn't have these java classes. Only schema files. | Gayam | 05/25/23 11:54 PM
| @praneeth.gayam@penske.com The irs.jar file should be generated with the xsd files available under xsd folder. Once the irs.jar file is generated, that needs to be uploaded to artifactory every time, so that hvutefile app used that as dependency. | Sreekanth | 06/01/23 12:14 AM
| @sreekanth.kancharla@penske.com , We are working on it. | Gayam | 06/01/23 10:48 PM
Row 91 | @veronique.labeille@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:28 AM
| @praneeth.gayam@penske.com Except the "conf/as400server.prop" file, no other file required any mitigation. "conf/as400server.prop" - To remove the dependency, we need to implement the connection framework which required some analysis. Either we'll implement the connection framework OR we'll continue with the prop file itself. Please proceed with the log4j changes. @veronique.labeille@penske.com | Sreekanth | 04/12/23 12:22 AM
| Sure @sreekanth.kancharla@penske.com . We will continue with the current code as you suggested. | Gayam | 04/12/23 1:21 AM
Row 91 | @praneeth.gayam@penske.com - SVN to BB migration issue | Mathumala Nachiappan | 02/02/23 10:28 AM
Row 91 | Sure @veronique.labeille@penske.com . Thanks for the confirmation | Mathumala Nachiappan | 02/01/23 8:12 PM
Row 91 | @mathumala.nachiappan@penske.com , would you please add this app to your plan? Thank you | Veronique Labeille | 01/27/23 10:38 PM
Row 91 | @mathumala.nachiappan@penske.com please share that information to me via email with the Fleet Service Team, hugo and Don included. I am not aware of any change to assignment for these. | Yvette Urso | 01/11/23 2:09 AM
Row 91 | @yvette.urso@penske.com - To confirm this application to be taken by CAP for Modernization activity. CC: @brian.hug@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:40 AM
Row 91 | hi @yvette.urso@penske.com - as per the previous communication, modernization will be taken care by the Fleet services team. from the latest update of yours, is it moved under CAP scope for modernization? | Mathumala Nachiappan | 12/08/22 3:51 PM
Row 91 | @mathumala.nachiappan@penske.com this will remain where it it per @veronique.labeille@penske.com - I moved to (Cap) Analysis. Please move to the correct status per your work. | Yvette Urso | 12/02/22 12:15 AM
Row 91 | @veronique.labeille@penske.com @mathumala.nachiappan@penske.com @praneeth.gayam@penske.com - Veronique, can you please confirm this application is no longer a part of Corp App Group and it should be moved to fall under the Fleet Services Team? Thank you | Yvette Urso | 12/01/22 8:39 PM
| @yvette.urso@penske.com , It is part of Fleet Services which is under CORP systems | Veronique Labeille | 12/01/22 9:22 PM
Row 91 | Scope is moved to Fleet services Team. CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com and @april.ottey@penske.com | Mathumala Nachiappan | 12/01/22 8:10 PM
Row 92 | Secrets: @mark.weaver@penske.com / @dylan.price@penske.com , I sent the secrets in the email. Please verify and let us know whether this app requires code changes. | Gayam | 06/28/23 12:55 AM
Row 92 | hi @praneeth.gayam@penske.com this application does not currently have a successful bamboo build for production. The SVN code location for this app is https://svn.penske.com/svn/webprojects/admin/ias/branches/dev_gh/ias-batch-broker7/ The current DEV bamboo build for this app is https://bamboo.penske.com/browse/IAS-IASD | Dylan | 06/13/23 4:56 PM
Row 92 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 92 | @praneeth.gayam@penske.com moved to AO Bamboo status | Yvette Urso | 12/15/22 2:47 AM
Row 92 | @sam.skelding@penske.com / @mark.weaver@penske.com , We are working modernizing(log4j and maven upgrades) the applications. we want to get the production reference branch for this application from bamboo build. We find the Plan branch 'branches/dev_gh/ias-batch-broker7' but there is no successful build from this branch. So could you please check and provide the production branch. @mathumala.nachiappan@penske.com | Gayam | 12/14/22 12:19 AM
Row 93 | @dylan.price@penske.com , This app relies on lbs-ias.jar which is generated from the app ias-lbs. Therefore, I am marking the status as blocker because this app cannot be completed until the ias-lbs app if finished. | Gayam | 06/30/23 12:52 AM
Row 93 | @dylan.price@penske.com , There are no secrets on this application. So continuing the mavanization. | Gayam | 06/27/23 5:32 AM
Row 93 | hi @praneeth.gayam@penske.com this application does not currently have a successful bamboo build for production. The SVN code location for this app is https://svn.penske.com/svn/webprojects/admin/ias/branches/qa/ias-batch/invoiceimage The current DEV bamboo build for this app is https://bamboo.penske.com/browse/IAS-IASM | Dylan | 06/13/23 4:58 PM
| Thanks @dylan.price@penske.com | Gayam | 06/23/23 5:35 PM
Row 93 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 93 | Issue: Cap is unable to find the code - Move status to AO Bitbucket Review. | Yvette Urso | 12/15/22 2:49 AM
Row 93 | Hi @mark.weaver@penske.com - For this App, we can see only the QA build. Is this deployed in PROD? Pls. confirm this. Also the folder/branch, we can consider for Log4J modernization | Mathumala Nachiappan | 12/07/22 12:04 PM
Row 94 | Questions: @dylan.price@penske.com 1. This application consists of a total of 4 classes, each of which contains a main method. i.LBSArchiveLaunch.java ii.LBSDailyArchive.java iii.OnFlyInvoiceTest.java iv.JMXEnvironment.java Which one we need to use? 2. Also, this app depends on LogisticsBilling.jar and need to upload this jar into artifactory. Please provide your approval. | Gayam | 06/16/23 3:14 AM
Row 94 | Hi @praneeth.gayam@penske.com there is one issue where a password is in the property file for this application. I will update this when I merge my changes with the "develop_log4j" changes like in other applications. Could you please start on log4j/maven changes? | Dylan | 06/13/23 5:01 PM
| Sure @dylan.price@penske.com | Gayam | 06/14/23 2:36 AM
Row 94 | Secrets: @mark.weaver@penske.com , secrets of this app shared in the email. Please check. Thanks. | Gayam | 03/24/23 12:11 AM
Row 94 | the repo for this application is https://svn.penske.com/svn/webprojects/admin/lbs/trunk/lbs-ias and the bamboo build is https://bamboo.penske.com/browse/LBS-LBSIASPROD | Dylan | 03/07/23 2:02 AM
| Thanks @dylan.price@penske.com . Changing the status to Cap log4j | Gayam | 03/07/23 6:24 AM
Row 94 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 94 | @mark.weaver@penske.com / @sam.skelding@penske.com , For this application, Bamboo key mentioned in the given excel sheet IAS. Following is the URL for this key. https://bamboo.penske.com/project/viewProject.action?projectKey=IAS But we found this project under the key LBS. URL is https://bamboo.penske.com/project/viewProject.action?projectKey=LBS Could you please check let us know which one is correct. Thanks. @mathumala.nachiappan@penske.com | Gayam | 12/17/22 2:00 AM
Row 95 | Hi @praneeth.gayam@penske.com getting the following error: Class path contains SLF4J bindings targeting slf4j-api versions 1.7.x or earlier. could you please look into the SLF4J bindings for this application? | Dylan | 06/14/23 2:26 AM
| Sure @dylan.price@penske.com . we will check | Gayam | 06/14/23 3:41 AM
| @dylan.price@penske.com , we fixed the issue. Please check. | Gayam | 06/16/23 1:40 AM
Row 95 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/ias-web/pull-requests/3/overview | Gayam | 03/23/23 11:40 PM
Row 95 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/27/23 11:15 PM
| Thanks @venkatesh.hossalinever@penske.com . Changing the status to (Cap)Maven. We will let you know when it is ready. | Gayam | 02/27/23 11:22 PM
Row 95 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 95 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:54 AM
Row 96 | @dylan.price@penske.com / @mark.weaver@penske.com , I sent the secrets file to you in the email. Please verify. Thanks. | Gayam | 07/09/23 11:25 PM
Row 96 | hi @praneeth.gayam@penske.com this application does not currently have a successful bamboo build for production. The SVN code location for this app is https://svn.penske.com/svn/architecture/general/iasarchiver/branches/qa The current QA bamboo build for this app is https://bamboo.penske.com/browse/IAS-IASARCHIVERQA | Dylan | 06/13/23 5:02 PM
Row 96 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 96 | Moved to AO Bamboo Status | Yvette Urso | 12/15/22 2:46 AM
Row 96 | @sam.skelding@penske.com / @mark.weaver@penske.com , We are working modernizing(log4j and maven upgrades) the applications. we want to get the production reference branch for this application from bamboo build. But couldn't figure it out. Could you please check and provide the info. @mathumala.nachiappan@penske.com | Gayam | 12/14/22 12:14 AM
Row 97 | @venkatesh.hossalinever@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/iasinvservice-web/pull-requests/3/overview | Gayam | 04/06/23 3:14 AM
Row 97 | Completed reviewing the log4j secrets - there are no code changes required. | Venkatesh | 02/27/23 10:11 PM
| Thanks @venkatesh.hossalinever@penske.com . Changing the status to (Cap)Maven. We will let you know when it is ready. | Gayam | 02/27/23 11:24 PM
Row 97 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 97 | @dylan.price@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:49 AM
Row 98 | Making as QA complete waiting for production deploy. | David Graf | 05/09/23 5:16 PM
Row 98 | @hugo.scavino@penske.com log4j2 isn't working please analyze for International Web. https://bitbucket.penske.com/projects/ARPROJ/repos/international-web/browse?at=develop_log4j | David Graf | 04/11/23 5:26 PM
Row 98 | @praneeth.gayam@penske.com just confirming if you saw my last message. | David Graf | 04/04/23 5:33 PM
| @david.w.graf@penske.com , We will onboard the develop_log4j to bamboo and will deploy to Dev. I already informed to my team. They are working on it. Thanks. | Gayam | 04/04/23 11:03 PM
| @david.w.graf@penske.com , develiop_log4j branch is onboarded to bamboo and dev deployment is done from this branch. Please verify. https://bamboo.penske.com/browse/INTRNL-INTERNL | Gayam | 04/06/23 2:35 AM
Row 98 | We can mvn install but cannot run locally so moving to Bamboo stage in order to gain access to testing in the dev environment. Confirming Maven. | David Graf | 03/30/23 5:24 PM
Row 98 | @david.w.graf@penske.com , Following is the PR for your review., Changing the status to (AO)Maven. https://bitbucket.penske.com/projects/ARPROJ/repos/international-web/pull-requests/8/overview | Gayam | 02/23/23 1:21 AM
Row 98 | I reviewed the secrets report. I don’t believe that any of them are true secrets. The closest one is the ApplicationConstants.MEMBER_COMPANY_FOREIGN_CAT_KEY but I think that is just a catalog key which the other system needs to identify us. I don’t think it is used for authentication. Still we could move it into the database table that it already connects to be safe: PSK_INTERNATIONAL.SECRET_VIEW | David Graf | 02/11/23 2:08 AM
| Thanks @david.w.graf@penske.com . Updated the status of the app to (Cap)Maven | Gayam | 02/14/23 11:47 PM
Row 98 | I have added this to work on next. | David Graf | 02/09/23 12:03 AM
Row 98 | @david.w.graf@penske.com , We have completed the secrets scanning on this application and found that there are couple of true positives. I will share the excel report in the email. Could you please check and confirm the true and false positives. Please remediate if there are true positives. Thanks. | Gayam | 01/06/23 1:27 AM
Row 98 | @david.w.graf@penske.com - This app has few hardcoded key values, which need to be confirmed from your side. Let me share this in mail . CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/06/22 8:41 PM
Row 98 | @david.w.graf@penske.com - This app is available for your final review. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/02/22 5:40 PM
Row 98 | @praneeth.gayam@penske.com - PR to raise for AO Review | Mathumala Nachiappan | 11/23/22 3:35 AM
Row 99 | @praneeth.gayam@penske.com can you please remove this app? it is a duplicate | Dylan | 05/25/23 1:36 AM
| Changed the status to Dup App. | Gayam | 05/25/23 2:35 AM
Row 99 | @yvette.urso@penske.com , This is duplicate line item. There is another line item which has app name as invarcbatch in which we are updating the comments. Please mark this line item as duplicate one. Thanks. | Gayam | 03/30/23 11:15 PM
Row 99 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 100 | @dylan.price@penske.com , This app is ready for your review. Please validate and merge. https://bitbucket.penske.com/projects/PA/repos/invarcbatch-batch/pull-requests/4/overview | Gayam | 06/30/23 12:58 AM
Row 100 | Hi @praneeth.gayam@penske.com this application is fine with secrets. It connects to the database using 2 data sources. Please start maven/log4j changes for this application. | Dylan | 06/02/23 12:52 AM
Row 100 | @praneeth.gayam@penske.com please add iasservice-client to artifactory. I also saw that the secrets file only contained a secret for me for TRSExtract. Could you please resend me the secrets file for invarcbatch? | Dylan | 03/30/23 9:16 PM
| Thanks @dylan.price@penske.com . I just sent secret file to you. Please verify, | Gayam | 03/30/23 11:24 PM
Row 100 | Secrets: @dylan.price@penske.com , shared the secrets in the email. Please check. Thanks. | Gayam | 03/24/23 12:25 AM
Row 100 | the invarcsftpbatch is actually the "High Radius" application. This application is located at https://svn.penske.com/svn/webprojects/admin/invarcbatch/trunk and the bamboo build is https://bamboo.penske.com/browse/INVARCBATCHBP-INVARCBATCHPROD | Dylan | 03/07/23 2:00 AM
| Thanks @dylan.price@penske.com for the clarification. This means the other line item which has same name 'invarcbatch' in this smartsheet is the duplicate one? | Gayam | 03/08/23 12:29 AM
| @dylan.price@penske.com , Could you please provide me the response for above question. Also we have another question on this app. This app has a dependency on iasservice-client.jar. But this jar is not available in artifactory and unable to find source code of this jar in SVN/BitBucket. Can we upload this jar into artifactory in the below location? Groupid: com.penske.ias.services Artfactid: iasservice-client Thanks. | Gayam | 03/16/23 6:58 PM
Row 100 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:28 AM
Row 100 | @dylan.price@penske.com / @mark.weaver@penske.com , In the smartsheets 2 apps named same invarcbatch and the sheet provided by penske to us have the same name but web filenames are different (invarcbatch, invarcabatch). Following are the more details which we observed. Both are pointing to same bamboo key following is the bamboo URL. "https://bamboo.penske.com/browse/INVARCBATCHBP" This has 2 different plans. One is "INVARCBATCH_PROD_BUILD" and it is generating artifacts "INVARCBATCH_PROD_TGZ". Another is "INVARCSFTPBATCH_PROD_BUILD" and it is generating "INVARCSFTPBATCH_PROD_TGZ" SVN urls are : https://svn.penske.com/svn/webprojects/admin/invarcbatch/ https://svn.penske.com/svn/webprojects/admin/invarcsftpbatch/ Could you please check and clarify the confusion. @mathumala.nachiappan@penske.com | Gayam | 12/16/22 12:43 AM
Row 101 | @praneeth.gayam@penske.com , did you get any response on this | Narsimhamurthy | 07/12/23 11:11 PM
| No response. | Gayam | 07/13/23 12:59 AM
Row 101 | Any update on this ? | Narsimhamurthy | 07/05/23 7:35 PM
| Still waiting for the response from @sherin.basheer@penske.com | Gayam | 07/07/23 12:21 AM
Row 101 | Question: Hi @shane.myers@penske.com , This is regarding irm.war application. irm app dependent on docserviceclient.jar and Rajesh said that you are the AO for this jar. We found 2 repos for this jar. https://svn.penske.com/svn/architecture/general/documentsvc/branches/dev_gh/JavaSource/com/penske/apps/documentservice/ https://svn.penske.com/svn/architecture/general/documentsvc_cmis/src/main/java/com/penske/apps/documentservice/ Could you please check and let us know which one is correct. Also, let us know whether modernization required for the docservice. | Gayam | 06/29/23 2:08 AM
| Sent an email about this issue to @shane.myers@penske.com and Shane forwarded the email to @sherin.basheer@penske.com. Waiting for the response. | Gayam | 07/03/23 10:56 PM
Row 101 | @praneeth.gayam@penske.com @yvette.urso@penske.com Please use following branch to implement changes with respect to log4j upgrade. Hugo work on maven and jdk 8 upgrade. https://bitbucket.penske.com/projects/PTLCORP/repos/irm-web/commits?until=refs%2Fheads%2Ffeature%2Fdevelop_jdk8_maven Thanks. | Rajesh | 06/26/23 8:37 PM
| Sure @rajesh.haravde@penske.com | Gayam | 06/27/23 3:22 AM
Row 101 | @narsimhamurthy.peddoju@penske.com / @rajesh.haravde@penske.com , If you are validating the branch 'feature/develop_jdk8_maven' then the work is completed by Hugo / Olukemi Olaewe only. Log4j team did not do any changes on this branch. Please verify with Olukemi Olaewe. | Gayam | 06/21/23 2:10 AM
| so which branch I have to take and check, Let us know the final branch to test in local and give to sign-off then move to QA | Narsimhamurthy | 06/21/23 8:46 PM
| @narsimhamurthy.peddoju@penske.com , As an AO please suggest which route we need to take. The toal migration work is completed by Penske team(Hugo and Olukemi) in the branch 'feature/develop_jdk8_maven'. So please verify and suggest whether we need to take this branch as base branch and start making the changes or do we need to take master branch as base branch? | Gayam | 06/22/23 3:58 AM
Row 101 | Below is the error in console while try to deploy on WAS server : [6/20/23 16:20:51:430 EDT] 000000b0 SystemErr R org.eclipse.jst.j2ee.commonarchivecore.internal.exception.ArchiveWrappedException Stack trace of nested exception: org.eclipse.jst.j2ee.commonarchivecore.internal.exception.NoModuleFileException: A file does not exist for module element having uri: irm-web.war | Narsimhamurthy | 06/21/23 1:52 AM
Row 101 | We are seeing below in eclipse problems. we are unable to deploy this on WAS server 'C:/apps/bamboows/maven/repository/com/penske/mis/common/sharedlib/dlinks_filter/2.0.0-develop-SNAPSHOT/dlinks_filter-2.0.0-develop-SNAPSHOT.jar' in project 'irm-web' cannot be read or is not a valid ZIP file irm-web Build path Build Path Problem | Narsimhamurthy | 06/21/23 1:50 AM
Row 101 | if we need to move this to appropriate status, validate this branch and let me know. we will move back as you suggested. Thanks | Rajesh | 06/15/23 8:40 PM
| @rajesh.haravde@penske.com , Do you want us to work on the above branch? But recently I am seeing a commit from Olukemi on this branch. Could you please let us know whether there is any active changes are going on on this app. | Gayam | 06/16/23 10:52 PM
Row 101 | This is the branch HUGO work on which is on bitbucke with maven integration. https://bitbucket.penske.com/projects/PTLCORP/repos/irm-web/browse?at=refs%2Fheads%2Ffeature%2Fdevelop_jdk8_maven | Rajesh | 06/15/23 8:39 PM
Row 101 | Hugo work on this application and created branch due of urgency of nature as per my information, But i will verify. | Rajesh | 06/14/23 9:14 PM
Row 101 | Please confirm if we can we start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:08 AM
| @rajesh.haravde@penske.com , Please check the above comments. I don't think mavanization completed on this app. We are waiting for the AO to resolve some queries which I mentioned above. Please check. Thanks. | Gayam | 06/09/23 1:54 AM
Row 101 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 101 | Please onboard fully local development environment qualified branch for IRM : https://bitbucket.penske.com/projects/PTLCORP/repos/irm-web/browse?at=refs%2Fheads%2Ffeature%2Fdevelop_jdk8_maven | Rajesh | 04/14/23 12:03 AM
| @rajesh.haravde@penske.com , We onboarded this app to bamboo. https://bamboo.penske.com/browse/IRMBUILD-IRMW0 But build is failing due to dlinks_filter.jar version is not available in artifactory. Could you please check with the developer who did work on this app mavanization. | Gayam | 04/18/23 2:59 AM
Row 101 | Praneeth, we got the information we look. Thank you. We are currently validation IRM on QA environment. if anything needed we will reach out to you. | Rajesh | 02/17/23 2:41 AM
Row 101 | Maven configuration implemented. awaiting on the reply from Praneeth | Rajesh | 01/18/23 8:22 PM
| Sorry @rajesh.haravde@penske.com . What is the thing you are waiting from me? | Gayam | 01/18/23 11:31 PM
Row 101 | Regarding irm secrets, We went over the irm.war_secrete.xlsx file. Above 95% of the file content information about the java doc html pages. Which is not actual application code. I don’t know if they can be classified as actual secrete violation. There is one function in the application, where we do use password key constant which is not real password. It’s a key info we are using to get generated encrypted password from database to send request to document management service to upload and retrieve document. We won’t mind changing that, but in that case, we need to involved document service group and take it forward. We will take look if we can deploy application without java doc html pages, which is over 95% violation content as per attached secrete file. If you have any other option for us to exclude java doc let us know. Thanks & Regards, Rajesh Haravde. | Yvette Urso | 12/16/22 12:48 AM
| @rajesh.haravde@penske.com , Log4j team don't know any details about the application. We are just doing log4j upgradation, mavenization, Secret scanning and Bamboo deployment. While doing these things if we encounter any problem or if we find any secrets then we need AO help. @hugo.scavino@penske.com may help you on this. Thanks. @mathumala.nachiappan@penske.com , @yvette.urso@penske.com | Gayam | 12/16/22 10:36 PM
Row 101 | @praneeth.gayam@penske.com - Changed status to AO Secrets and pending @shane.myers@penske.com response. | Yvette Urso | 12/15/22 2:54 AM
Row 101 | @shane.myers@penske.com , irm app has dependency docserviceclient.jar. we found 2 repos for this jar. https://svn.penske.com/svn/architecture/general/documentsvc/branches/dev_gh/JavaSource/com/penske/apps/documentservice/ https://svn.penske.com/svn/architecture/general/documentsvc_cmis/src/main/java/com/penske/apps/documentservice/ @rajesh.haravde@penske.com updated that you are AO for docservice. Not sure whether the above 2 repos are correct. Could you please check and let us know. Also, let us know whether modernization required for the docservice and can we upload this jar into artifactory? @mathumala.nachiappan@penske.com | Gayam | 12/14/22 12:49 AM
Row 101 | IRM do uses docservice to manage documents. This service app belongs to difference group. you can reach out to Myers, Shane for repo information. Thanks. | Rajesh | 12/14/22 12:43 AM
Row 101 | @krishna.tanga@penske.com - This jar is not available in Artifactory. So need confirmation on this. 1. Is Modernization required? If so, Pls. share the repo and the folder to be considered for modernization. 2. Are you planning to remove this dependency. Pls. confirm with your updates. CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com | Mathumala Nachiappan | 12/08/22 3:19 PM
| Here is IRM repo : | Rajesh | 12/08/22 10:24 PM
| PRE-Chrome: https://svn.penske.com/svn/webprojects/corp/irm/ branches/qa/irm_test Chrome : https://svn.penske.com/svn/webprojects/corp/irm/ branches/qa/irm_chrome | Rajesh | 12/08/22 10:25 PM
| @praneeth.gayam@penske.com and @rajesh.haravde@penske.com - Any update regd. docserviceclient.jar | Mathumala Nachiappan | 12/13/22 10:20 AM
Row 101 | @rajesh.haravde@penske.com - While scanning for secrets, this applicaiton has many hardcoded credentials and href links present. Pls. have a look whether redaction is required. @praneeth.gayam@penske.com - Pls. share the secret report to Rajesh | Mathumala Nachiappan | 12/08/22 10:10 PM
| Please share the report via email we will analyze the same and get back to you or resolution. | Rajesh | 12/08/22 10:26 PM
| @rajesh.haravde@penske.com , I have shared. Please check | Gayam | 12/09/22 1:44 AM
Row 101 | @krishna.tanga@penske.com / @yogesh.sinha@penske.com , irm app has dependency docserviceclient.jar. we found 2 repos for this jar. https://svn.penske.com/svn/architecture/general/documentsvc/branches/dev_gh/JavaSource/com/penske/apps/documentservice/ https://svn.penske.com/svn/architecture/general/documentsvc_cmis/src/main/java/com/penske/apps/documentservice/ Not sure whether these 2 app are correct. Could you please check and let us know. Also, can we upload this jar into artifactory? @mathumala.nachiappan@penske.com | Gayam | 11/26/22 1:00 AM
Row 102 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:09 AM
| @rajesh.haravde@penske.com , this is already onboarded to Bamboo. Please deploy to QA and verify. https://bamboo.penske.com/browse/IRMBUILD-IRMBACH1/ | Gayam | 06/09/23 1:50 AM
Row 102 | PR been executed please take it forward. Thanks for guidance on process Praneeth appreciated. | Rajesh | 05/18/23 1:48 AM
| @rajesh.haravde@penske.com , build on develop branch is successful. Please deploy to QA. | Gayam | 05/18/23 10:49 PM
Row 102 | @praneeth.gayam@penske.com We able to build project JAR FILE using maven. please change the status to next step. Thanks. | Rajesh | 05/17/23 1:32 AM
| @rajesh.haravde@penske.com , could you please merge the PR. https://bitbucket.penske.com/projects/PTLCORP/repos/irm-batch/pull-requests/3/overview | Gayam | 05/17/23 3:10 AM
| @rajesh.haravde@penske.com , Onboarding both develop_log4j and develop branches to bamboo are completed. Please merge the above PR. So that build on develop branch will be successful. | Gayam | 05/18/23 12:57 AM
Row 102 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/irm-batch/pull-requests/3/overview | Gayam | 02/16/23 11:41 PM
Row 102 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:49 PM
Row 102 | Work in progress. | Rajesh | 01/18/23 8:22 PM
Row 102 | @rajesh.haravde@penske.com - Pls. approve the PR after your review and confirmation. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:21 PM
Row 103 | @yvette.urso@penske.com , I think irs.jar app is already there. I don't think we need this line item. @hugo.scavino@penske.com / @sreekanth.kancharla@penske.com | Gayam | 05/03/23 1:51 AM
| @yvette.urso@penske.com , This is a duplicate item. Please mark this as Dup. | Gayam | 06/06/23 3:35 AM
Row 103 | @sreekanth.kancharla@penske.com | Yvette Urso | 05/02/23 7:16 PM
Row 103 | New jar added to support the irs.jar | Yvette Urso | 05/02/23 7:15 PM
Row 104 | @praneeth.gayam@penske.com You are correct. Even we've to use RELEASE version, shouldn't we've version? So should we use the dependency as below with no version at all? <dependency> <groupId>com.penske.corp</groupId> <artifactId>irs</artifactId> </dependency> OR as below <dependency> <groupId>com.penske.corp</groupId> <artifactId>irs</artifactId> <version>RELEASE</version> </dependency> | Sreekanth | 08/14/23 6:29 PM
Row 104 | @sreekanth.kancharla@penske.com , Following question already asked in hvutefile line item. Just moving the conversation from hvutefile line item to irs.jar line item. Could you please confirm what are the folders from hvutefile repo need to move to irs repo. I know following. 1. You said source/xsd/ETEC/2290/Return2290.xsd folder. Do you mean total xsd folder source/xsd? 2. source/lib/jaxb-xjc.jar Any other folders are files need to move to irs repo? | Gayam | 05/03/23 2:08 AM
| @praneeth.gayam@penske.com Those are the only files needed to build the jar. We can check on any other dependency when we have the bamboo build issues. | Sreekanth | 05/03/23 7:45 PM
| @praneeth.gayam@penske.com The status is "Waiting on AO". Please let us know in case any other details required from us. | Sreekanth | 05/08/23 9:32 PM
| @sreekanth.kancharla@penske.com , Changed to Cap. | Gayam | 05/08/23 10:21 PM
| @sreekanth.kancharla@penske.com , Completed the changes for irs.jar. Please check https://bitbucket.penske.com/projects/PTLCORP/repos/irs/pull-requests/2/overview | Gayam | 05/13/23 2:44 AM
| @praneeth.gayam@penske.com Added review comment. | Sreekanth | 05/17/23 2:39 AM
| @sreekanth.kancharla@penske.com , Modified the folder name. Please verify. | Gayam | 05/18/23 1:44 AM
| @praneeth.gayam@penske.com Merged the PR. | Sreekanth | 05/18/23 2:02 AM
| We are wokring on XSD to java files binding on this jar. | Gayam | 06/01/23 10:49 PM
| @sreekanth.kancharla@penske.com , This utility app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/irs/pull-requests/4/overview | Gayam | 06/24/23 12:28 AM
| @praneeth.gayam@penske.com PR is merged. | Sreekanth | 06/26/23 6:34 PM
| @sreekanth.kancharla@penske.com , This app is onboarded to Bamboo and jar is deployed to artifactory. Please verify. thanks. | Gayam | 06/28/23 12:57 AM
| @praneeth.gayam@penske.com We'll validate this once hvutefile app completed as the irs.jar is the dependency for another app. | Sreekanth | 06/28/23 2:46 AM
| @sreekanth.kancharla@penske.com , We created a release version of this jar and used in hvutefile. But we observed recently that build of irs is failing after the creation of release version. Team is checking on this. Thanks. | Gayam | 07/25/23 12:01 AM
| @praneeth.gayam@penske.com Ok, thank you! | Sreekanth | 07/25/23 5:33 PM
| @praneeth.gayam@penske.com Please let us know in case any update on above mentioned issue fix. | Sreekanth | 07/31/23 11:22 PM
| @sreekanth.kancharla@penske.com , Log4j CICD team is working with Architecture team to resolve the issue. Hopefully we will get some solution in a day. Thanks. | Gayam | 08/01/23 12:39 AM
| @sreekanth.kancharla@penske.com , issue got resolved and created a release version. Please check bitbucket and bamboo. Thanks. | Gayam | 08/02/23 2:46 AM
| @praneeth.gayam@penske.com We are using irs dependency in hvut as below which is giving error. Please provide the version value for the release version which you created. <dependency> <groupId>com.penske.corp</groupId> <artifactId>irs</artifactId> <version>2.0.0-develop_log4j-20230628.200202-3</version> </dependency> | Sreekanth | 08/11/23 6:25 PM
| @sreekanth.kancharla@penske.com , you said that you don't want to provide the version number..right? Instead you can provide RELEASE which brings the latest release version. | Gayam | 08/13/23 3:26 AM
Row 105 | Per Pramod - This application will be retired by Q2 2024. | Yvette Urso | 05/12/23 12:46 AM
Row 105 | Question: @pete.macmahon@penske.com , Could you please provide the response to above question. Thanks. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 03/24/23 10:53 PM
Row 105 | Peter - Currently off SVN. Will be moving Savion platform but not until 2024. We want to go ahead and upgrade this app by end of JSM project. | Yvette Urso | 03/24/23 7:10 PM
Row 105 | @pete.macmahon@penske.com , For this application both SVN and Bamboo are not available. Could you please let us know the SVN and Bamboo details. Thanks. | Gayam | 01/14/23 1:05 AM
Row 106 | @satish.polubothu@penske.com , I sent the secrets in the email. Could you please verify them. | Gayam | 03/10/23 1:58 AM
Row 106 | Bamboo Project Setup 2/1/23 - Yvette sent Tim Fox the below question via email: Tim, We are submitting a request for a Bamboo Project and would like to know who to add from the HR team as the Admin of that Project? That person can then create what ever they need for other access and repositories, etc. | Yvette Urso | 02/01/23 8:53 PM
Row 107 | @sherin.basheer@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/ARPROJ/repos/javapostop/pull-requests/14/overview | Gayam | 07/14/23 1:16 AM
Row 107 | application context.xml -use one under prod. Applicationcontext.xml should be same across all environments. Setting.properties file are different. we have to create setting-qa.properties and settings-prod.properties file. | Sherin | 06/23/23 12:17 AM
| Sure @sherin.basheer@penske.com . thanks. | Gayam | 06/27/23 3:26 AM
Row 107 | Question: @sherin.basheer@penske.com , This application having different settings.properties and applicationcontext.xml for different environments . Which one we need to use ? (the urls and properties are different in each environment in settings.properties) | Gayam | 04/06/23 3:08 AM
Row 107 | No we don't want to move rt jar to artifactory. We should use jaxws-rt jar instead. | Sherin | 03/29/23 1:02 AM
| @sherin.basheer@penske.com , we will try and let you know. | Gayam | 03/29/23 9:05 PM
Row 107 | Question: @sherin.basheer@penske.com, This application having rt.jar in lib folder. While doing mavenization we are getting issues as this jar is not available in artifactory. Can we upload this jar to artifactory? Class name : OTMWebServiceConfiguration.java import statements : import com.sun.xml.internal.ws.client.BindingProviderProperties; | Gayam | 03/24/23 10:49 PM
Row 107 | Secrets left over from testing are removed from the code. 2 out of 5 are not actual passwords they are key to passwords stored in a table. That is added to the comments. | Sherin | 02/24/23 2:48 AM
| Thanks @shawn.mcmurtry@penske.com . Is develop branch contains all the secrets code changes? | Gayam | 03/01/23 12:02 AM
| @praneeth.gayam@penske.com looks like you tagged wrong developer to the chat. Changes are in secrets remediation branch | Sherin | 03/01/23 10:40 PM
| Thanks @sherin.basheer@penske.com . Could you please let us know which branch we need to take as base branch for log4j/maven changes. Otherwise please merge your changes to develop branch and we will consider develop as base branch | Gayam | 03/02/23 2:09 AM
| Please use secrets remediation branch afor your changes | Sherin | 03/07/23 1:42 AM
| Thanks @sherin.basheer@penske.com . We will complete the log4j and maven changes on top of 'hotfix/secrets_remediation' branch. | Gayam | 03/08/23 12:23 AM
Row 107 | This is not Cap Blocked - moved to 2.2 Secrets Mitigation. | Yvette Urso | 12/09/22 12:51 AM
Row 107 | Hi @sherin.basheer@penske.com - Looks there are some hardcoded values for the property PWD. Pls. revisit the secret scanning report if redaction is required. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 7:18 PM
Row 107 | Question: @sherin.basheer@penske.com , As discussed in the call before your vacation, this app is using packages from rt.jar and rt.jar is part of java8 and causing several issues in the classes. It is a bad practice to use con.sun classes directly. These are not getting compiled in maven. These should be removed. | Gayam | 12/08/22 1:51 AM
Row 107 | @mathumala.nachiappan@penske.com What errors are you receiving? | Yvette Urso | 11/30/22 12:36 AM
Row 107 | @praneeth.gayam@penske.com - Blocked by Megha. Getting build errors while doing the maven because of rt.jar | Mathumala Nachiappan | 11/23/22 3:36 AM
Row 108 | Hi @praneeth.gayam@penske.com develop_log4j has been merged into develop branch. Could you please start the bamboo build? | Dylan | 06/06/23 7:22 PM
| Sure @dylan.price@penske.com . Thanks. | Gayam | 06/07/23 3:03 AM
| @dylan.price@penske.com , Onboarded develop branch to Bamboo and deployed to dev. Please verify. | Gayam | 06/09/23 2:02 AM
Row 108 | Hi @praneeth.gayam@penske.com I am seeing the following error when trying to run the application: [6/1/23 17:02:12:505 EDT] 0000003b SystemErr R SLF4J: No SLF4J providers were found. [6/1/23 17:02:12:505 EDT] 0000003b SystemErr R SLF4J: Defaulting to no-operation (NOP) logger implementation [6/1/23 17:02:12:505 EDT] 0000003b SystemErr R SLF4J: See https://www.slf4j.org/codes.html#noProviders for further details. [6/1/23 17:02:12:507 EDT] 0000003b SystemErr R SLF4J: Class path contains SLF4J bindings targeting slf4j-api versions 1.7.x or earlier. [6/1/23 17:02:12:507 EDT] 0000003b SystemErr R SLF4J: Ignoring binding found at [wsjar:file:/C:/ptl_mis/pbt-billing/.metadata/.plugins/com.genuitec.eclipse.blue.websphere.core/WebSphere_20_Application_20_Server_20_8_2e_5_20_at_20_localhost/lbs/lbs/WEB-INF/lib/log4j-slf4j-impl-2.20.0.jar!/org/slf4j/impl/StaticLoggerBinder.class] [6/1/23 17:02:12:507 EDT] 0000003b SystemErr R SLF4J: See https://www.slf4j.org/codes.html#ignoredBindings for an explanation. Looks like slf4j is not configured correctly? | Dylan | 06/02/23 2:39 AM
| @dylan.price@penske.com , we will check and get back to you. | Gayam | 06/03/23 12:11 AM
| @dylan.price@penske.com , We fixed the issue. Could you please check again. Thanks. | Gayam | 06/06/23 3:38 AM
Row 108 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. Please verify. https://bitbucket.penske.com/projects/ARPROJ/repos/lbs-web/pull-requests/3/overview | Gayam | 03/23/23 11:20 PM
Row 108 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/28/23 3:32 AM
| Thanks @venkatesh.hossalinever@penske.com . Changed the status to Cap Maven | Gayam | 02/28/23 11:56 PM
Row 108 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 108 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:54 AM
Row 109 | Maven/log4j changes are moved to production | Sherin | 06/23/23 8:11 PM
Row 109 | it is moved to QA and test was successful | Sherin | 06/20/23 11:20 PM
Row 109 | Yes, we have removed the dependency and app is deployed to qa and running. | Sherin | 04/12/23 1:22 AM
| Thanks @sherin.basheer@penske.com . Changed the app status to QA Test | Gayam | 04/13/23 12:41 AM
| @sherin.basheer@penske.com , we changed the scope of log4j2 jars to compile. Could you please deploy these changes to QA and test. Thanks. | Gayam | 06/03/23 12:49 AM
Row 109 | Thanks @sherin.basheer@penske.com . We will check and get back to you | Gayam | 04/04/23 11:11 PM
| @sherin.basheer@penske.com , without spring-ldap-resource jar also build is getting successful. So can we remove that dependency from the pom? | Gayam | 04/06/23 11:58 PM
Row 109 | Here is the transitive dependency error:The POM for com.penske.mis.common.customlib:spring-ldap-resource:jar:1.0.0 is invalid, transitive dependencies (if any) will not be available, enable debug logging for more details [INFO] | Sherin | 04/04/23 1:46 AM
Row 109 | reference : https://bitbucket.penske.com/projects/ARPROJ/repos/vdrfilebatch/browse/pom.xml?at=refs%2Fheads%2Fdevelop_log4j | Sherin | 04/04/23 1:44 AM
Row 109 | Not properties file, this was missing in pom file<plugin> <groupId>org.apache.maven.plugins</groupId> <artifactId>maven-jar-plugin</artifactId> <version>2.4</version> <configuration> <archive> <manifest> <addDefaultImplementationEntries>true</addDefaultImplementationEntries> <addDefaultSpecificationEntries>true</addDefaultSpecificationEntries> <addClasspath>true</addClasspath> <mainClass>com.penske.filetransferbatch.main.FileTransferBatchMain</mainClass> <classpathPrefix>lib/</classpathPrefix> </manifest> </archive> </configuration> </plugin> | Sherin | 04/04/23 1:43 AM
Row 109 | There are 2 issues in pom file. 1.manifest section where you mention main class is missing. 2) maven build throws transitive dependency on <artifactId>spring-ldap-resource</artifactId> | Sherin | 03/31/23 7:42 PM
| @sherin.basheer@penske.com , are you referring about .prop file which has a propeorty to point to main class? If so, we did not see this kind of file in original code of this app. Could you please provide the error which throws transitive dependency. | Gayam | 04/04/23 12:00 AM
Row 109 | @sherin.basheer@penske.com , This is onboarded to Bamboo. https://bamboo.penske.com/browse/LDAPISMGERBP-LDAPISMR1 But build is failing on develop branch because log4j/maven changes are not yet merged. Could you please merge if you satisfy the changes. Thanks. https://bitbucket.penske.com/projects/AR-SEC/repos/ldapismgr-batch/pull-requests/7/overview | Gayam | 03/29/23 12:56 AM
Row 109 | @praneeth.gayam@penske.com Please create bamboo plan if it has not been created yet. | Sherin | 03/23/23 1:05 AM
Row 109 | @sivagamasundari.suresh@penske.com is working on this app. | Sherin | 03/10/23 9:28 PM
Row 109 | @sherin.basheer@penske.com - This app is available for AO Review | Mathumala Nachiappan | 11/23/22 3:38 AM
| @sherin.basheer@penske.com , Following is the PR for your review https://bitbucket.penske.com/projects/AR-SEC/repos/ldapismgr-batch/pull-requests/7/overview | Gayam | 02/16/23 2:04 AM
Row 110 | @yvette.urso@penske.com - mailreader_1_0 is not a separate application. Its part of mailreader_2_0. Hence not applicable for modernization. Pls. remove it from the scope or suggest us with the correct App status cc: @praneeth.gayam@penske.com , @kalrav.khamar@penske.com | Mathumala Nachiappan | 02/17/23 1:15 PM
Row 110 | @rafiq.melath@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:32 AM
| @praneeth.gayam@penske.com We're looking into JEUPLOAD application in SVN. It create mailreader.jar to use in start_journal.sh script. This application runs from GNRHILLS IFS. We will update you as soon as, we find correct svn location. | Kalrav | 12/21/22 3:07 AM
| @praneeth.gayam@penske.com Mailreader_1_0 is not indivudual application. is uses mailreder.jar file which get generated through mailreader_2_0 and used in JEUPLOAD application. Once you update the code for mailreader_2_0, we will use mailreder.jar file in JEUPLOAD script and verify changes. | Kalrav | 01/10/23 2:14 AM
Row 110 | See outside email for info. @mathumala.nachiappan@penske.com please update this with the results of that email. | Yvette Urso | 12/15/22 2:21 AM
| @yvette.urso@penske.com - Its a blocker for CAP as we are not sure about the Repo details. This app hasnt entered the log4J stage. Hope (AO) Bamboo Review would be the better choice. | Mathumala Nachiappan | 12/15/22 8:17 PM
Row 111 | Review: @sreekanth.kancharla@penske.com / @kalrav.khamar@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ITFIS/repos/mailreader_2_0-batch/pull-requests/5/overview | Gayam | 05/02/23 2:33 AM
| @praneeth.gayam@penske.com I've merged the PR. One small suggestion. We don't need to maintain the app name as "mailreader_2_0-batch", instead we can've it as "mailreader-batch" Please change the repo name and the same new name can be used for Bamboo plan as well. @kalrav.khamar@penske.com | Sreekanth | 05/08/23 9:31 PM
| Sure @sreekanth.kancharla@penske.com . We will make the change and will let you know. Thanks. | Gayam | 05/08/23 10:16 PM
| @sreekanth.kancharla@penske.com , Repo name and Bamboo build/deploy plan names are changed to mailreader-batch. Please check and confirm. | Gayam | 05/10/23 12:24 AM
| @praneeth.gayam@penske.com the repo name & bamboo build/deploy plan names are good now. | Sreekanth | 05/10/23 2:45 AM
| @sreekanth.kancharla@penske.com , Please merge https://bitbucket.penske.com/projects/ITFIS/repos/mailreader-batch/pull-requests/7/overview The changes are for making log4j2 scope to compile. Thank you. | Gayam | 05/30/23 8:54 AM
| @praneeth.gayam@penske.com Merge completed. | Sreekanth | 06/01/23 12:10 AM
| Thanks @sreekanth.kancharla@penske.com . Build is done | Gayam | 06/01/23 10:45 PM
Row 111 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:55 AM
| @praneeth.gayam@penske.com Passowrd is used to access mailbox details. This utility extract file from mail box and load data in AP or JE system. | Kalrav | 03/08/23 2:01 AM
| @kalrav.khamar@penske.com , So it is not a secret? | Gayam | 03/08/23 2:55 AM
| @praneeth.gayam@penske.com yes, its not secrets. | Kalrav | 03/08/23 11:32 PM
Row 111 | @rafiq.melath@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:32 AM
| @praneeth.gayam@penske.com We're looking into JEUPLOAD application in SVN. It uses .jar file from this folder. We will update you as soon as, we find correct svn location. | Kalrav | 12/21/22 3:05 AM
| @praneeth.gayam@penske.com use follow svn path to update code. https://svn.penske.com/svn/webprojects/admin/as400_utilities/trunk/mailreader | Kalrav | 01/10/23 2:10 AM
Row 111 | @mathumala.nachiappan@penske.com changed status. | Yvette Urso | 12/15/22 2:21 AM
Row 112 | Those should be the variables which have to defined in bamboo plan for each environment. | Vaddi Mani | 08/04/23 7:26 PM
| @sarath.mani@penske.com , there will be no separate builds for each environment after modernization. Please check the files below and provide your decision what to do for the next step. Thanks. build_script/maintconfig_specificBuild.xml src/conf/maintconfig.properties.build | Gayam | 08/08/23 1:23 AM
Row 112 | Query: @sarath.mani@penske.com / @falgun.patel@penske.com , In this application build folder having maintconfig_specificBuild.xml. The build is including maintconfig.properties on environment basis. how to implement this in environment agnostic build as we don't have separate builds for each environment. | Gayam | 07/25/23 9:15 PM
| Can you tell which variables from maintconfig_specificBuild.xml & maintconfig.properties? | Vaddi Mani | 07/28/23 2:07 AM
| @sarath.mani@penske.com , check the 39th to 45 line. | Gayam | 07/31/23 2:40 AM
Row 112 | Sarath already replied to the email on 6/27 that this application does not require any code changes related to secret. Please proceed. | Patel | 06/29/23 1:46 AM
| Thanks. Changed the status to Cap Maven. | Gayam | 06/29/23 2:37 AM
Row 112 | Secrets: @sarath.mani@penske.com / @falgun.patel@penske.com , I sent the secrets in the email. Please verify and let us know whether this app requires code changes. | Gayam | 06/28/23 12:47 AM
Row 112 | @sarath.mani@penske.com - may you please assist Gayam with the question? | Patel | 06/08/23 11:09 PM
| @praneeth.gayam@penske.com that was very old tag. you should use https://svn.penske.com/svn/fieldsys/maintenance/maint-config/tags/prod/maint-config20230605 | Stella george | 06/14/23 2:08 AM
| Thanks @stella.george@penske.com | Gayam | 06/14/23 3:39 AM
Row 112 | @david.long@penske.com , In the current bamboo build the prod reference mentioned as complete "https://svn.penske.com/svn/fieldsys/maintenance/maint-config/tags/prod/maint-config20201215". But this path doesn't exist in svn. Could you please help us to find the prod reference branch. Thanks. | Gayam | 05/09/23 2:42 AM
Row 113 | Thanks @dylan.price@penske.com . Changing the status to Retired. @yvette.urso@penske.com , @shane.myers@penske.com | Gayam | 06/08/23 7:59 AM
Row 113 | Hi @praneeth.gayam@penske.com we have determined that this application is no longer being used. Could you please delete out the Bitbucket repo, as well as remove it from the smartsheet? | Dylan | 06/07/23 1:15 AM
Row 113 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/mileageforecast-web/pull-requests/3/overview | Gayam | 03/23/23 11:42 PM
Row 113 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/28/23 3:32 AM
| Thanks @venkatesh.hossalinever@penske.com . Changed the status to Cap Maven | Gayam | 02/28/23 11:50 PM
Row 113 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:54 AM
| @yvette.urso@penske.com Hello, this application should be assign to 'Billing' App group and AO Manager should change to Rafiq Melath. | Kalrav | 02/13/23 9:28 PM
| Thanks @kalrav.khamar@penske.com @praneeth.gayam@penske.com - For your note and to share the updates to the team, as this has the dependency with distribution management | Mathumala Nachiappan | 02/15/23 2:06 PM
Row 114 | Review: @venkatesh.hossalinever@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/mileagereporting-web/pull-requests/3/overview | Gayam | 04/06/23 3:12 AM
Row 114 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 02/28/23 3:33 AM
| Thanks @venkatesh.hossalinever@penske.com . Changed the status to Cap Maven | Gayam | 02/28/23 11:51 PM
Row 114 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 114 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:55 AM
Row 115 | @dale.porter@penske.com , Bamboo build is completed. Please deploy to QA and verify. https://bamboo.penske.com/browse/OROSBBP-OROSSUMM | Gayam | 07/20/23 12:06 AM
| Hi, I am seeing errors in the Bamboo build for the final Archive stage and included link to bamboo for showing the error. Also, I did not see a war file created on ghlx008ptlge. Can you take a look. Thank you https://bamboo.penske.com/download/OROSBBP-OROSSUMM0-DTA/build_logs/OROSBBP-OROSSUMM0-DTA-2.log | Dale Porter | 07/28/23 1:41 AM
| @dale.porter@penske.com , we will check. | Gayam | 07/31/23 2:30 AM
| @dale.porter@penske.com , This is a batch application. So it doesn't have war package. Also, whatever the errors you are seeing are not causing@dale.porter@penske.com , This is a batch application. So it doesn't have war package. Also, whatever the errors you are seeing are not causing any issues. Jars are pushed to artifactory successfully and tgz file is pushed to targeted location correctly. Please check. | Gayam | 08/01/23 12:43 AM
| Hi all, I ran the deploy to QA but it did not place the tgz file of the build in the /var/tmp of the qa deploymanager (clelx150ptlge). I included url of qa build log, thank you https://bamboo.penske.com/browse/OROSBBP-OROSSUMM0-DTA-3/log | Dale Porter | 08/05/23 1:15 AM
| We will check and get back to you. | Gayam | 08/08/23 1:11 AM
| @dale.porter@penske.com , we have completed the QA deployment and tgz file also generated. Please verify and let us know if you have any questions. Thanks. | Gayam | 08/10/23 12:46 AM
Row 115 | I have reviewed and merged pull request. Thank you. | Dale Porter | 07/17/23 7:30 PM
Row 115 | Review: @dale.porter@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/MAIN/repos/openrepairsumm-batch/pull-requests/3/overview | Gayam | 07/16/23 9:21 PM
Row 115 | Thanks @dale.porter@penske.com | Gayam | 06/14/23 4:18 AM
Row 115 | I approve of adding velocity-1.7 to artifactory as needed for the application. Thank you. | Dale Porter | 06/14/23 2:20 AM
Row 115 | Regarding Secrets: I went ahead to analyze this and see this appears to be the guest user id and password for SVN repository access. I removed these on all of the property files as Bamboo does not use this. I believe this was from prior to using Bamboo back in the day. After removing the id and password references, I made a new qa tag and run a qa build in Bamboo without any issue. This should be fine now. | Dale Porter | 06/06/23 6:25 AM
| Thanks @dale.porter@penske.com . Could you please check the query mentioned above regarding the dependency jar and provide your response | Gayam | 06/06/23 8:36 AM
Row 115 | Secrets: @shawn.mcmurtry@penske.com , adding to above question, I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:53 AM
Row 115 | Query: @shawn.mcmurtry@penske.com , This app depends on velocity-1.7-dep.jar which is not availabe in artifactory. Could you please provide your approval to uplaod to artifactory in the following location. <groupid>org.apache.velocity</groupid> <artifactid>velocity-1.7-dep</artifactid> <version>Default</version> | Gayam | 06/01/23 1:59 AM
Row 116 | Yes it is needed in all batch applications to start up. | Sherin | 06/23/23 12:29 AM
| Thanks @sherin.basheer@penske.com . We have been implementing this section in all batch apps. | Gayam | 06/23/23 11:44 PM
Row 116 | <plugin> <groupId>org.apache.maven.plugins</groupId> <artifactId>maven-jar-plugin</artifactId> <version>2.4</version> <configuration> <archive> <manifest> <addDefaultImplementationEntries>true</addDefaultImplementationEntries> <addDefaultSpecificationEntries>true</addDefaultSpecificationEntries> <addClasspath>true</addClasspath> <mainClass>com.penske.filetransferbatch.main.FileTransferBatchMain</mainClass> <classpathPrefix>lib/</classpathPrefix> </manifest> </archive> </configuration> </plugin> | Sherin | 04/19/23 2:10 AM
| @sherin.basheer@penske.com , Do we need to keep this section for all batch applications? If yes, please point out to the confluence page which has this info. So that I will inform to my team to update this in every batch app. FYI: @hugo.scavino@penske.com | Gayam | 04/20/23 2:08 AM
Row 116 | @praneeth.gayam@penske.com This section is missing in this application as well | Sherin | 04/19/23 2:09 AM
Row 116 | @sherin.basheer@penske.com , this app is onboarded to Bamboo. Please check. https://bamboo.penske.com/browse/ORACLE2LDAPBP-ORACLE2LDP/ | Gayam | 04/13/23 11:44 PM
Row 116 | @praneeth.gayam@penske.com Thank you. Build is successful in local now. COuld you create Bamboo plan for this application. | Sherin | 04/12/23 1:22 AM
Row 116 | @praneeth.gayam@penske.com Getting this error when you run the build. Could not resolve dependencies for project com.penske.architecture:oracle2ldap:jar:1.0.0-SNAPSHOT: Failure to find com.penske.salesnet.common.dev:enterprise:jar:3.0.0 in https://artifactory.penske.com/artifactory/architecture-mvn-virtual was cached in the local repository | Sherin | 04/04/23 2:04 AM
| @sherin.basheer@penske.com , we will check and get back to you. | Gayam | 04/04/23 11:07 PM
| @sherin.basheer@penske.com , salesnet-mvn-development-local repo is added to architecture-mvn-virtual repo for oracle2ldap applicaion to download the enterprise:jar. Please check now. | Gayam | 04/06/23 2:42 AM
Row 116 | Review: @sherin.basheer@penske.com , Please review the app at https://bitbucket.penske.com/projects/AR-SEC/repos/oracle2ldap-batch/pull-requests/3/overview | Gayam | 03/23/23 11:14 PM
Row 116 | @praneeth.gayam@penske.com what is the next step on this application | Sherin | 03/23/23 9:05 PM
Row 116 | I have verified the secrets and can confirm they are all false positives | Sherin | 03/09/23 2:38 AM
Row 116 | Yes ,I'm looking into this one. will get back to you | Sherin | 03/09/23 2:25 AM
Row 116 | @sherin.basheer@penske.com - There are many hardcoded values found during secret scanning. Pls. review it once CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 6:23 PM
| @sherin.basheer@penske.com , We reviewed the secrets again and it looks like all are false positives. I will send all of your apps secrets files in a zip. Please verify them. Thanks. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/19/23 11:55 PM
| @sherin.basheer@penske.com , Could you please check the secrets and respond. | Gayam | 03/09/23 1:39 AM
Row 116 | @sherin.basheer@penske.com - This app is available for AO Review | Mathumala Nachiappan | 11/23/22 3:39 AM
Row 117 | Update from the DBA's is that the app will become obsolete around July-August 2023 but it is not confirmed yet. I am moving this app into retired status or whatever is equivalent. We can reevaluate in September. | David Graf | 02/28/23 10:08 PM
Row 117 | I agree. We shouldn't be doing any modernization work on this app as this will be retired soon. | Sherin | 02/28/23 1:10 AM
Row 117 | We just got notice that this app will be retired in the future. We may not want to go forward with modernization. I'll leave it to @sherin.basheer@penske.com to decide. | David Graf | 02/24/23 10:36 PM
Row 117 | Hi @yvette.urso@penske.com - Hope (AO) Final Testing would be correct. Once @sherin.basheer@penske.com is back from her PTO, she can look into this | Mathumala Nachiappan | 12/12/22 4:39 PM
Row 117 | @mathumala.nachiappan@penske.com - What was deployed? I do not think this is blocked. I picked a bucket - please work with @sherin.basheer@penske.com with specifically what you need. | Yvette Urso | 12/09/22 12:52 AM
Row 117 | @sherin.basheer@penske.com - Deployed in QA on 2nd Nov | Mathumala Nachiappan | 11/23/22 3:40 AM
Row 118 | Review: @karthikeyan.srinivasan@penske.com / @stella.george@penske.com , This app is ready for your review. Please validate and merge. Thanks. https://bitbucket.penske.com/projects/MAIN/repos/partspo-batch/pull-requests/3/overview | Gayam | 06/30/23 1:01 AM
Row 118 | Secrets: @stella.george@penske.com I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:56 AM
| @praneeth.gayam@penske.com There is no secrets in this application. | Stella george | 06/14/23 1:38 AM
| Thanks @stella.george@penske.com . We will do the mavanization. | Gayam | 06/14/23 3:10 AM
Row 119 | @satish.polubothu@penske.com , Can we take this app for modernization? | Gayam | 03/24/23 10:56 PM
| @satish.polubothu@penske.com informed us that we need to reconnect in August or September regarding this app. | Gayam | 06/09/23 7:48 PM
Row 119 | Bamboo Project Setup 2/1/23 - Yvette sent Tim Fox the below question via email: Tim, We are submitting a request for a Bamboo Project and would like to know who to add from the HR team as the Admin of that Project? That person can then create what ever they need for other access and repositories, etc. | Yvette Urso | 02/01/23 8:53 PM
| @praneeth.gayam@penske.com - FYA | Mathumala Nachiappan | 02/06/23 6:49 PM
Row 119 | @mathumala.nachiappan@penske.com based on the comment above it looks like you are ready to start doing this work. Did you send out a question you are waiting to have answered? I moved to Cap Analysis based on your 1/9/23 comment. Thanks | Yvette Urso | 01/24/23 3:43 AM
Row 119 | @praneeth.gayam@penske.com - To check with AO on the APP ready for log4J Modernization | Mathumala Nachiappan | 01/10/23 10:21 AM
Row 120 | @satish.polubothu@penske.com , Can we take this app for modernization? | Gayam | 03/24/23 10:55 PM
| @satish.polubothu@penske.com informed us that we need to reconnect in August or September regarding this app. | Gayam | 06/09/23 7:48 PM
Row 120 | Bamboo Project Setup 2/1/23 - Yvette sent Tim Fox the below question via email: Tim, We are submitting a request for a Bamboo Project and would like to know who to add from the HR team as the Admin of that Project? That person can then create what ever they need for other access and repositories, etc. | Yvette Urso | 02/01/23 8:53 PM
| @praneeth.gayam@penske.com - FYA | Mathumala Nachiappan | 02/06/23 6:49 PM
Row 120 | @mathumala.nachiappan@penske.com based on the comment above it looks like you are ready to start doing this work. Did you send out a question you are waiting to have answered? I moved to Cap Analysis based on your 1/9/23 comment. Thanks | Yvette Urso | 01/24/23 3:44 AM
Row 120 | @praneeth.gayam@penske.com - To check with AO on the APP ready for log4J Modernization | Mathumala Nachiappan | 01/10/23 10:21 AM
Row 121 | Confirmed. This JAR is at its end. It will not be modernized and is now available in artifactory if there are any dependencies. | Hugo Scavino | 04/15/23 1:36 AM
Row 121 | After further review, please add this JAR to artifactory. This JAR will not be modernized. Take JAR from here https://svn.penske.com/svn/webprojects/admin/pops/trunk/pops/WebContent/WEB-INF/lib/ group id: com.penske.architecture artifact id: penske-secure-logger version: 1.0.0 Do not add the number as the name in the artifact ID Thank You | Hugo Scavino | 02/10/23 9:45 PM
| Thanks @hugo.scavino@penske.com . We will upload and will let you know. | Gayam | 02/10/23 11:33 PM
| @hugo.scavino@penske.com , penske-secure-logger-1.0.0.jar is uploaded into artifactory <dependency> <groupId>com.penske.architecture</groupId> <artifactId>penske-secure-logger</artifactId> <version>1.0.0</version> </dependency> | Gayam | 02/13/23 11:41 PM
Row 121 | I will review on Friday Feb 10 | Hugo Scavino | 02/10/23 3:51 AM
Row 121 | Moved to AO Log4j Review | Yvette Urso | 12/15/22 2:40 AM
Row 121 | @hugo.scavino@penske.com - popsbatch app is dependent on this jar. Any suggestion on how to proceed that application? CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 3:38 PM
Row 121 | Update from @hugo.scavino@penske.com - this app totally dependent on log4j1 and it is not supposed to be modernized | Mathumala Nachiappan | 12/08/22 10:33 AM
Row 121 | @yvette.urso@penske.com - Original Scope is 'No' for this jar | Mathumala Nachiappan | 11/23/22 4:13 AM
Row 121 | @yvette.urso@penske.com - This is an additional scope. This jar is used in b2busercreation.war and pops_batch. This jar needs modernization before it is used in the above said applications. | Mathumala Nachiappan | 11/23/22 4:13 AM
Row 121 | Need to determine who can work on this application. Missing resource @hugo.scavino@penske.com | Yvette Urso | 11/22/22 2:39 AM
Row 122 | one thing I'm noticing is that there are two bitbucket repositories for the watchlist client: this one was created by Michael Johnson: https://bitbucket.penske.com/projects/WL/repos/watchlistclient/browse this one looks like it was created by modernization team: https://bitbucket.penske.com/projects/ARPROJ/repos/penske-watchlist-client/browse However, let's assume that Michael was first and may have developed new code after migration. Unless you can prove they both have the exact same commits | David Graf | 06/23/23 6:15 PM
| @david.w.graf@penske.com , Looks like https://bitbucket.penske.com/projects/WL/repos/watchlistclient/browse contains new code and mavanized. Do you want to close the app which modernization team opened? | Gayam | 06/23/23 11:40 PM
| We are putting this back on the backlog. Mahipal will be doing the watchlist client deploy and the confusion about penske-watchlist-client will be figured out later. | David Graf | 07/05/23 7:32 PM
Row 122 | I'm going to see if this can be started back up and worked on by Amit. | David Graf | 06/23/23 5:58 PM
Row 122 | Going to ask for help on how to test this project. https://bitbucket.penske.com/projects/ARPROJ/repos/penske-watchlist-client/browse?at=refs%2Fheads%2Fdevelop_log4j | Hugo Scavino | 01/31/23 9:56 PM
Row 122 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:28 AM
Row 122 | @hugo.scavino@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:16 AM
Row 123 | I am still the AO for this project but ankita.tiwary@penske.com is performing the active development. She is working on unit tests at the moment. | Hugo Scavino | 02/09/23 2:02 AM
Row 123 | @hugo.scavino@penske.com , One more question for this app. There is no existing bamboo build for this app. So under which project we need to create bamboo specs for this app. | Gayam | 01/11/23 9:23 AM
Row 123 | @hugo.scavino@penske.com , Adding to above question, we completed secrets scanning on this app and found that all are false positives. Could you please review them and confirm. @mathumala.nachiappan@penske.com @swati.saxena@penske.com @mankala.narendra@penske.com | Gayam | 01/10/23 12:19 AM
Row 123 | @hugo.scavino@penske.com , We have completed log4j/maven changes for this app but we are seeing java class files under targeted folder for each environment. Could you please verify this app. https://bitbucket.penske.com/projects/ARPROJ/repos/penskesso-ws-client/pull-requests/1/overview | Gayam | 12/07/22 10:55 AM
Row 124 | artifactory is confirmed. | Hugo Scavino | 04/15/23 2:39 AM
Row 124 | Secrets - No code changes are required | Hugo Scavino | 02/10/23 9:34 PM
Row 124 | I have deployed to artifactory. This is the JAR's final destination. | Hugo Scavino | 02/10/23 3:49 AM
| Thanks @hugo.scavino@penske.com . Also, please confirm the secrets part also whether the app requires any code changes. | Gayam | 02/10/23 9:27 PM
Row 124 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:28 AM
Row 124 | @hugo.scavino@penske.com - Artifactory upload is done for this jar. Pls. confirm and change to appropriate App Status Jar location in artifactory - https://artifactory.penske.com>artifactory>architecture-mvn-development-local>com>penske>architecture>penskesso>2.0.0-develop-SNAPSHOT>penskesso-2.0.0-develop-20221213.104211-1.jar. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/13/22 5:45 PM
| I have some questions on the "-SNAPSHOT" which was added to the version. I do not think that should be be there for artifacts we expect other teams to use. This is not a problem with WAR and application JARs but shared JARs should not be "SNAPSHOT"s. The CI/CD scripts will not allow a deployment with SNAPSHOT to PROD eventually. Please redeploy without "-SNAPSOT" in the version. <groupId>com.penske.architecture</groupId> <artifactId>penskesso</artifactId> <version>2.0.0-develop-SNAPSHOT</version> | Hugo Scavino | 12/13/22 8:57 PM
| This would be true for all shared JAR's | Hugo Scavino | 12/13/22 8:58 PM
| Hugo scheduled a meeting with Iswarya and raghu on to check whether Bamboo build is going to have multiple options to create the release or snapshot versions and other build questions. | Gayam | 12/14/22 12:31 AM
Row 124 | @hugo.scavino@penske.com - - This app is available for your final review. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/02/22 5:47 PM
Row 124 | Uploading to Artifactory is in Progress | Mathumala Nachiappan | 11/23/22 4:10 AM
Row 125 | Review: @sreenivasa.papannagari@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/MAIN/repos/peoplenet-batch/pull-requests/3/overview | Gayam | 07/20/23 12:42 AM
Row 125 | @praneeth.gayam@penske.com : Sreeni will be the contact person for this. Please direct all questions to Sreeni. | Patel | 06/08/23 11:15 PM
| @sreenivasa.papannagari@penske.com , let me know whether you have the secrets of this app to validate. Otherwise I will send. Thanks. | Gayam | 06/09/23 1:40 AM
| @praneeth.gayam@penske.com There is no hardcoded secrets in this batch application. This is using connectionframe work and using Penske's EncryptionSecureId | Stella george | 06/14/23 1:43 AM
| Thanks @stella.george@penske.com | Gayam | 06/14/23 3:12 AM
Row 125 | @david.long@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:51 AM
Row 126 | This application is deployed to PROD on 07/20/2023 | Sreekanth | 07/21/23 10:42 PM
Row 126 | Post reverting the dlink_filter changes, we've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD. | Sreekanth | 07/05/23 7:33 PM
Row 126 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD but waiting on dlink-filter.jar PROD deployment by Architect team. | Sreekanth | 06/08/23 11:24 PM
Row 126 | @sreekanth.kancharla@penske.com , app is on boarded to Bamboo. https://bamboo.penske.com/browse/PETBP-PETTYC/ please let us know whether we can deploy this to dev. | Gayam | 03/10/23 11:20 PM
| @praneeth.gayam@penske.com Please proceed with DEV deployment. | Sreekanth | 03/13/23 10:17 PM
| @sreekanth.kancharla@penske.com , Dev deployment is completed. Please check. | Gayam | 03/15/23 11:44 PM
| @praneeth.gayam@penske.com DEV testing is in-progress @kalrav.khamar@penske.com | Sreekanth | 04/19/23 9:35 PM
| @praneeth.gayam@penske.com Please delete the old deploy plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=132710422 | Sreekanth | 05/09/23 7:19 PM
| Sure @sreekanth.kancharla@penske.com . Will do | Gayam | 05/09/23 10:30 PM
| @sreekanth.kancharla@penske.com , Old deploy plans are deleted. | Gayam | 05/10/23 11:19 PM
Row 126 | Secrets: @srinivasan.narayanan@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file to you in the email. Could you please check and provide your response over here. | Gayam | 02/25/23 1:22 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. I've validated the trunk branch files alone even though offshore branch is also included secrets. @srinivasan.narayanan@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/25/23 1:45 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the app status to Cap Maven | Gayam | 02/27/23 11:47 PM
| @praneeth.gayam@penske.com PR is merged. Please proceed with next steps. | Sreekanth | 03/04/23 3:21 AM
| Thanks @sreekanth.kancharla@penske.com . We will implement the next step which is Cap Bamboo. | Gayam | 03/07/23 12:02 AM
Row 126 | @srinivasan.narayanan@penske.com / @yvette.urso@penske.com , in this app logger classes are getting created with custom configuration using fileappender(getallappender) and simplelayout . Not able to configure using the slf4j and log4j2. providing link for class file. https://svn.penske.com/svn/webprojects/admin/pettycash/trunk/pettycash6/JavaSource/com/penske/apps/pettyCash/util/FileFunctions.java. Also @hugo.scavino@penske.com confirmed that he needs to discuss with app owner who needs to change the code. @mathumala.nachiappan@penske.com | Gayam | 12/07/22 11:04 PM
| @praneeth.gayam@penske.com Please share the remediation plan if we've any for such kind of custom configurations. Kindly loop me for future communications. | Sreekanth | 12/16/22 3:36 AM
| @praneeth.gayam@penske.com From the FileFunctions class file, we observed that readFile & readFileLines methods alone are being used and not any other methods. We can comment those unused methods and look for any compiler errors. If no compiler errors, we should be good. Moreover, this logging is already implemented with log4j.xml which is available under JavaSource folder, so hope we can migrate that. @hugo.scavino@penske.com @srinivasan.narayanan@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/03/23 3:14 AM
| Thanks @sreekanth.kancharla@penske.com . Hugo also suggested same thing for other apps. We will make the change and let you know if we face any other issues. Thanks | Gayam | 02/03/23 11:51 PM
Row 126 | Moved to AO Log4J status. @mathumala.nachiappan@penske.com | Yvette Urso | 12/15/22 2:14 AM
Row 126 | @mathumala.nachiappan@penske.com What is this dependency? | Yvette Urso | 12/02/22 2:14 AM
Row 126 | @srinivasan.narayanan@penske.com - Log4J1 dependency to be cleared or confirmed . CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:41 PM
Row 127 | @praneeth.gayam@penske.com I've already has the bamboo plan created for this application. We are good. We'll continue to test this app in DEV/QA. | Sreekanth | 07/27/23 7:26 PM
Row 127 | @sreekanth.kancharla@penske.com , I think you already merged the code to develop branch for this application and created another branch feature/IFS-1494 from develop branch. Do you want us to onboard this app to bamboo? | Gayam | 07/27/23 2:35 AM
Row 127 | Added psndmail application due to needed for the pextfl. | Yvette Urso | 02/16/23 12:23 AM
Row 127 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed few true positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:59 AM
Row 128 | @david.long@penske.com , We are just compiling the applications in local. We are not running the app as we are modernizing several apps and we don't know the functionality of each app. | Gayam | 07/15/23 1:57 AM
Row 128 | Review: @david.long@penske.com , This app is ready for your review. Please verify andmerge. https://bitbucket.penske.com/projects/MAIN/repos/phonesvc/pull-requests/3/overview | Gayam | 07/11/23 6:49 PM
| @praneeth.gayam@penske.com Looks good! Reviewed and merged to develop. Can you please continue with the bamboo build and all? Also there is a pending change that needs to be done for the phone service, so if you could prioritize this before the other maint apps in this list that would be awesome! Thanks :) | David | 07/11/23 7:29 PM
| sure @david.long@penske.com | Gayam | 07/12/23 1:35 AM
| @david.long@penske.com , onboarded to bamboo and deployed to dev. Please verify. Deployment link: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151192150 build & Deploy plan: https://bamboo.penske.com/browse/PBP-PHNSVC | Gayam | 07/13/23 1:58 AM
| @praneeth.gayam@penske.com I can access the bamboo build but I can't hit the dev endpoint. I'm getting a 500 error and I believe it can't find http related jars or classes in the logs | David | 07/13/23 9:01 PM
| @david.long@penske.com , We can't run the application as we don't know the details of the application. Could you please check and let us know the run time issues. Thanks. | Gayam | 07/14/23 12:36 AM
| @praneeth.gayam@penske.com I'll let you know. I've brought it down locally and it looks like it's issues with either log4j or just how the pom.xml file is? I don't have an answer just yet. When you do the maven migration does any developers try it on their local machine first or anything like that? | David | 07/14/23 6:09 PM
Row 128 | @david.long@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:51 AM
| @praneeth.gayam@penske.com I have removed the class that was marked for containing secrets. We no longer use the "AutoDialService" class as that was a retired integration. We now store our creds in an encrypted maint table in the CORP library. Pushed changes to dev branch, and merged changes with log4j update branch on SVN. | David | 06/06/23 10:08 PM
| Thanks @david.long@penske.com . we will do the mavanization and will let you know. | Gayam | 06/07/23 3:09 AM
Row 129 | Query: @dale.porter@penske.com , The jdbc configuration is configured in applicationcontext.xml file and depends on the environment the respective configuration loaded from different properties files. But when we modernize the app, the build is going to be environment agnostic. Means 1 build should be deployed to all environments. So, the current way of implementation doesn't work for jdbc configuration. Could you please check with Architecture team to resolve this issue. Thanks. | Gayam | 07/14/23 12:43 AM
| I have created ticket with architect team to help with the datasource configuration. This is not using connection framework and thinking it may need to be changed to do so. Footprint ticket# 1893601 | Dale Porter | 08/09/23 10:59 PM
Row 129 | I went ahead and analyzed PM Mailer as well and see this appears to be the guest user id and password for svn repository access. I removed these on all of the property files as Bamboo does not use this. Certain this was from prior to using Bamboo long back. After removing the id and password reference, I made a new qa tag and ran a qa build in Bamboo without any issue. This should be fine now. | Dale Porter | 06/06/23 6:51 AM
| Thanks @dale.porter@penske.com . Changed the status to Cap Maven. | Gayam | 06/06/23 8:31 AM
Row 129 | @dave.kost@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:50 AM
Row 130 | @falgun.patel@penske.com @shawn.mcmurtry@penske.com - test 2 | Patel | 07/28/23 10:30 PM
Row 130 | Test email two..... | Patel | 07/28/23 10:23 PM
Row 130 | @shawn.mcmurtry@penske.com / @falgun.patel@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:52 AM
| AO confirmed that all secrets are false positives. No code changes required. | Gayam | 06/16/23 1:13 AM
Row 131 | Thanks @sreekanth.kancharla@penske.com for the secrets confirmation. We have 1 more question on this app. This application using the loggers from penske-secure-logger jar. If we use this jar we need to include log4j1 . You gave the confirmation for pops_batch app to replace the loggers from penske-secure-logger with slf4j loggers. For pops.war app also do you want us to replace the loggers from penske-secure-logger jar with slf4j? Please provide your confirmation. Thanks. | Gayam | 02/25/23 12:02 AM
| @praneeth.gayam@penske.com I could see penske-secure-logger is used only for logging. Please replace this with slf4j We'll test in DEV. Are you we good with other dependency jars which is marked as blocker security_util.jar security_author_filter.jar | Sreekanth | 02/25/23 4:00 AM
| Yes @sreekanth.kancharla@penske.com . Those 2 jars are already modernized and uploaded to artifactory. | Gayam | 02/27/23 11:19 PM
| @praneeth.gayam@penske.com Please find the commented added to the PR. | Sreekanth | 03/04/23 3:17 AM
| @sreekanth.kancharla@penske.com , Please don't review or merge until the app status is in (AO)Maven status. (Cap)Maven means, still CG/Log4j team still working on this application. We will review the comment and complete the required things. | Gayam | 03/07/23 12:06 AM
| @praneeth.gayam@penske.com Since the status is under Cap team, please remove me from the review list for the existing PR in bitbucket. https://bitbucket.penske.com/projects/ITFIS/repos/pops-web/pull-requests/3/overview You can add back, once the PR is available for my review. | Sreekanth | 03/16/23 1:02 AM
| Sure @sreekanth.kancharla@penske.com . Thanks for the notification and this is ready for the review. Changed the status to AO Maven | Gayam | 03/17/23 2:58 AM
| @praneeth.gayam@penske.com Added review comment, please check. | Sreekanth | 03/21/23 8:26 PM
| @sreekanth.kancharla@penske.com , Completed the changes provided in review comments. Please check. Thanks. | Gayam | 03/23/23 11:18 PM
| @praneeth.gayam@penske.com Thank you. PR is merged. | Sreekanth | 03/24/23 8:49 PM
| Thanks @sreekanth.kancharla@penske.com . We will let you know once onboarding to Bamboo and deploymnet to Dev completed. Thanks | Gayam | 03/24/23 11:04 PM
| @sreekanth.kancharla@penske.com , Bamboo build is onboarded. Dev deployment done using develop branch. Please verify. https://bamboo.penske.com/browse/POPBP-PP/ | Gayam | 04/20/23 2:03 AM
Row 131 | @praneeth.gayam@penske.com We've received new secrets on this application on 2/23/2023 and the secrets are on QA branch & also on offshore branches. Hope we should only worry on qa branch as that is the one you would've used for log4j changes and we are using for QA & PROD deployments. We may've multiple offshore branches and all wouldn't be in sync with production code. In QA SVN branch, no remediations required for the shared secrets. @kalrav.khamar@penske.com | Sreekanth | 02/24/23 9:18 PM
Row 131 | @rafiq.melath@penske.com - Holding on for the modernization of Dependency Jars security_util.jar security_author_filter.jar CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:37 PM
| @praneeth.gayam@penske.com we need both of following jars. security_util.jar security_author_filter.jar | Kalrav | 01/25/23 3:40 AM
| @kalrav.khamar@penske.com Thanks for confirming. Modernization is going on both of above apps. Until it completes, we can not work on this app. @hugo.scavino@penske.com / @mathumala.nachiappan@penske.com | Gayam | 01/25/23 11:35 PM
| @praneeth.gayam@penske.com @yvette.urso@penske.com Do you know who is working on these security related jars? Can we assign 'Major Blocker' to person who is working on security jars? | Kalrav | 01/31/23 10:10 PM
| @kalrav.khamar@penske.com , Hugo is working on Security_util and he almost completed the work. Security_author_filter depends on security_util. So CG team is waiting on security_util to complete. | Gayam | 02/03/23 3:02 AM
Row 131 | Blocker - security_util.jar security_author_filter.jar | Yvette Urso | 02/01/23 8:27 PM
Row 132 | @sreekanth.kancharla@penske.com , This app is onboarded to bamboo. Following is the url. https://bamboo.penske.com/browse/POPBP-POPSBCH0/ Please deploy to QA and test it. Thanks. | Gayam | 03/29/23 12:51 AM
Row 132 | Review: @sreekanth.kancharla@penske.com , This app ready for your review. https://bitbucket.penske.com/projects/ITFIS/repos/pops-batch/pull-requests/3/overview | Gayam | 03/16/23 12:49 AM
| @praneeth.gayam@penske.com The PR is merged. | Sreekanth | 03/16/23 12:54 AM
| Thanks @sreekanth.kancharla@penske.com . We will onboard to bamboo and will let you know. | Gayam | 03/16/23 2:33 AM
Row 132 | Question: @sreekanth.kancharla@penske.com , This application having different dao-spring-context.xml files in targeted folder for each environment. But for the environment agnostic build we have to keep only 1 xml file. Which one we need to move to resouces folder? | Gayam | 02/28/23 12:00 AM
| @praneeth.gayam@penske.com We can't have single dao-spring-context.xml file as there is 1 difference in all 3 environment specific files. We should load these from targeted folder or need to see the possibility of how we can change the implementation. The difference is we are using Remoting EBS Service with URL provider and that URL changes based on the environment, so we've 3 files for 3 environments (DEV/QA/PROD) @kalrav.khamar@penske.com | Sreekanth | 03/02/23 2:41 AM
| @sreekanth.kancharla@penske.com , Once we migrate to maven and new bamboo plans there is no option trigger separate builds. It is going to be only 1 build. Are you in the plans to change the implementation? @hugo.scavino@penske.com | Gayam | 03/03/23 12:29 AM
| @praneeth.gayam@penske.com We've no plans now to make any changes, but we can plan for that under this log4j migration ITG itself. @kalrav.khamar@penske.com | Sreekanth | 03/07/23 12:39 AM
| @sreekanth.kancharla@penske.com , Log4j team shouldn't make any application level changes. As per management decision, all app level changes needs to be done by App team. Could you please let us know the next step. | Gayam | 03/07/23 1:05 AM
| @praneeth.gayam@penske.com We'll look through the possible solutions in bring this app environment agnostic and make those changes. @kalrav.khamar@penske.com | Sreekanth | 03/07/23 3:50 AM
| Thanks @sreekanth.kancharla@penske.com . Do you want us to hold this app until you confirm or can we use the prod one and complete the mavanization and gave it to you to resolve the above issue in mavanized branch? | Gayam | 03/07/23 11:44 PM
| @praneeth.gayam@penske.com Please have the mavenized branch ready. Post that we'll work on dao-spring-context.xml environment agnostic changes. @kalrav.khamar@penske.com | Sreekanth | 03/08/23 3:04 AM
| Sure @sreekanth.kancharla@penske.com . We will use the targeted/prod one for dao-spring-context.xml. Thanks | Gayam | 03/09/23 12:09 AM
Row 132 | @praneeth.gayam@penske.com We've receive email on secrets for this app on 02/23/2023. Only 1 files is valid https://svn.penske.com/svn/webprojects/admin/pops/branches/qa/pops_batch/database.properties That too, in batch box server where this application is deployed in QA & PROD, this file is being referred from different location (which admin only have access) and not from the source location. So, we don't need any remediation for this file. The other secrets seem to be on offshore branches and also seems from commit history as well. Hope we don't need to worry on those. @kalrav.khamar@penske.com | Sreekanth | 02/24/23 9:27 PM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (Cap)Maven. | Gayam | 02/25/23 12:08 AM
Row 132 | Blocker: penske-secure-logger-1.0.0.jar | Yvette Urso | 02/01/23 8:29 PM
Row 132 | @kalrav.khamar@penske.com @mathumala.nachiappan@penske.com Can you look at this blocker and let us know what the next steps should be? Thank you | Yvette Urso | 12/02/22 2:19 AM
| @praneeth.gayam@penske.com we will look into penske-secure-logger-1.0.0.jar and see it required in app or not. Will update you soon. | Kalrav | 01/25/23 3:43 AM
| @praneeth.gayam@penske.com penske-secure-logger-1.0.0.jar is being used for logger only. If you are replacing this with SLF4j logger OR If this jar is being modernized and placed in artifactory, then reusing the same logger. We should be good with both the approaches as we could see only logger object being used from this jar file. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/30/23 11:40 PM
Row 132 | @kalrav.khamar@penske.com - Waiting for the modernization of the dependent jar penske-secure-logger-1.0.0.jar CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:43 PM
Row 133 | @Review: @venkatesh.hossalinever@penske.com , This app is ready for your review. Please check. Thanks. https://bitbucket.penske.com/projects/PBJB/repos/printapplication/pull-requests/3/overview | Gayam | 03/30/23 11:37 PM
Row 133 | Completed reviewing the log4j secrets there is no code changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 3:42 AM
| Thank you. Changed the status to Cap Maven. | Gayam | 03/02/23 1:22 AM
Row 133 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 133 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:52 AM
Row 134 | @sreekanth.kancharla@penske.com , Build and Deploy plans are onboarded to Bamboo. As this this the batch app, AO needs to do the QA deployment. Currently the build will deploy to /var/tmp folder of QA server. | Gayam | 03/20/23 11:44 PM
Row 134 | @praneeth.gayam@penske.com PR is merged. This application is a batch app running on IFS. We should've SUPPORT environment for IFS deployed apps as it is AS400 database system. @hugo.scavino@penske.com mentioned that the deployment to IFS also can be done from bamboo. We can test that auto deploy from bamboo for this app. Please let us know incase any information required while configuring the bamboo build & deploy plans. | Sreekanth | 03/16/23 12:32 AM
| @sreekanth.kancharla@penske.com , One of the @david.w.graf@penske.com 's app was deployed to IFS. But it was manual. Bamboo deploys to regular QA server's /var/tmp folder and after that David did the manual process to deploy to IFS server. Hope David will reach out to you regarding this. Thanks. | Gayam | 03/18/23 1:00 AM
Row 134 | Review: @sreekanth.kancharla@penske.com , Please review https://bitbucket.penske.com/projects/ITFIS/repos/psndmail-batch/pull-requests/4/overview | Gayam | 03/02/23 3:04 AM
Row 134 | Secrets: @kalrav.khamar@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/24/23 2:00 AM
| @praneeth.gayam@penske.com We don't need any remediation for the shared secrets as all the secrets are just variable name "password" and no password is stored inside the code. @kalrav.khamar@penske.com | Sreekanth | 02/24/23 9:30 PM
| Thanks @sreekanth.kancharla@penske.com . Changed the app status to (Cap)Maven | Gayam | 02/25/23 12:18 AM
Row 134 | As per our discussion with @kalrav.khamar@penske.com / @yvette.urso@penske.com This is the new application which is onboarded to log4j team's scope. @mathumala.nachiappan@penske.com / @balu.mohan@penske.com | Gayam | 02/17/23 7:21 PM
Row 135 | @yvette.urso@penske.com the modernization for this JAR is complete. One for your status report. | Hugo Scavino | 01/26/23 8:34 PM
Row 135 | We confirmed there are no secrets. Also we decided not to modernize this application and instead leave the source code in bitbucket and the binary in artifactory. No Bamboo will be created. No addiational work or bug fixes are ever intended. | Hugo Scavino | 01/25/23 10:46 PM
Row 135 | @praneeth.gayam@penske.com Most likely Secrets are False Postives | Yvette Urso | 01/25/23 12:44 AM
Row 135 | @praneeth.gayam@penske.com per @shane.myers@penske.com and @hugo.scavino@penske.com - Would like to move this to Bitbucket but not upgrade Maven | Yvette Urso | 01/25/23 12:43 AM
Row 135 | This is deprecated, but is being used so must be upgraded | Yvette Urso | 01/25/23 12:38 AM
Row 135 | @hugo.scavino@penske.com , One more question for this app. There is no existing bamboo build for this app. So under which project we need to create bamboo specs for this app. | Gayam | 01/11/23 9:23 AM
| So this should be under architecture and its own project for ptldao. There does seem some clients still using this package | Hugo Scavino | 01/19/23 3:42 AM
Row 135 | @hugo.scavino@penske.com ,Secret scanning and analysis are completed and found that true positives exist. We will send the sheet in email. Please check. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/10/23 12:24 AM
Row 136 | @praneeth.gayam@penske.com this application moved to the bitbucket looks good me . you can keep in your list it is done . we are not deploying this application . | Mahipal | 05/16/23 11:58 PM
| Sure @mahipal.podduturi@penske.com . I changed to Done status as there is no deployment. | Gayam | 05/17/23 1:58 AM
Row 136 | @praneeth.gayam@penske.com please point to new bitbucket url | Mahipal | 04/06/23 2:08 AM
| https://bitbucket.penske.com/projects/ARPROJ/repos/queryrunner-batch/browse | Gayam | 04/06/23 2:43 AM
Row 136 | @ yes can point that | Mahipal | 04/06/23 2:07 AM
Row 136 | @shane.myers@penske.com / @mahipal.podduturi@penske.com , Do you want us to point out the old Bamboo builds to new bitbucket URL? | Gayam | 04/03/23 9:44 PM
Row 136 | @praneeth.gayam@penske.com can you work on next steps | Mahipal | 04/03/23 9:41 PM
Row 136 | bitbucket looks good. @praneeth.gayam@penske.com @yvette.urso@penske.com should I just change the status to 6.3 AO app deployed - DONE? Not sure if that is the right step and don't want to mess up your process. | William | 03/01/23 2:44 AM
Row 136 | @praneeth.gayam@penske.com @mathumala.nachiappan@penske.com I discussed this app with Don - please simply move to bitbucket. No other steps needed at this time. | William | 02/08/23 7:12 PM
| In that case, we just need to do following things for this app. 1. SVN to BB migration of production branch 2. Change the Bamboo build to point to bitbucket @shane.myers@penske.com / @hugo.scavino@penske.com , Correct me if you think any other tasks we need to do for this app. @mathumala.nachiappan@penske.com , @haribabu.challa@penske.com | Gayam | 02/09/23 12:05 AM
| That is correct, please just migrate to bitbucket and we can consider this complete. | William | 02/10/23 10:31 PM
| @shane.myers@penske.com , queryrunner project is migrated to bitbucket. Following is the bitbucket URL https://bitbucket.penske.com/projects/ARPROJ/repos/queryrunner-batch/browse Changed the status to '(AO)Bitbucket Review' Could you please check and push the status to final stage as there is no further work on this project. | Gayam | 02/23/23 12:23 AM
Row 136 | @praneeth.gayam@penske.com - Pls. confirm the modernization steps required for this application? | Mathumala Nachiappan | 02/08/23 11:03 AM
Row 136 | @praneeth.gayam@penske.com per @shane.myers@penske.com - Would like to move this to Bitbucket but not upgrade Maven | Yvette Urso | 01/25/23 12:42 AM
Row 137 | Hi @praneeth.gayam@penske.com we are not finding any applications that rely on this jar file. Could you please retire this application? | Dylan | 06/13/23 5:12 PM
| Thanks @dylan.price@penske.com . As per your instructions, changing the status to retired. @yvette.urso@penske.com / @shane.myers@penske.com | Gayam | 06/14/23 2:41 AM
Row 137 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 137 | Question: @mark.weaver@penske.com , Is the modernization for this app going to take care by app team? From @rafeeq.ahamed@penske.com , we heard that, this app has big scope and changes are happening in this app. So want to make sure whether this is in CG scope for log4j/maven modernization changes. Thanks. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 02/03/23 12:43 AM
Row 137 | @rafiq.melath@penske.com - Is this App group correct for this application. CC: @yvette.urso@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/23/23 7:33 PM
Row 138 | @shane.myers@penske.com will look at who to assign this to as the AO. | Yvette Urso | 01/25/23 12:48 AM
Row 138 | This is not really an app, but a utility. | Yvette Urso | 01/25/23 12:38 AM
Row 138 | @hugo.scavino@penske.com , This is ready for AO review. Please review in the below PR and merge. https://bitbucket.penske.com/projects/ARPROJ/repos/restfilter/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/16/22 3:08 AM
Row 141 | @praneeth.gayam@penske.com tested working as excepted you can close this | Mahipal | 04/06/23 2:07 AM
| @mahipal.podduturi@penske.com , I believe it will be closed only after prod deployment and AO is the owner to close it. And I think you tested in Dev environment only. It needs to be deployed to QA by AO and test over there. | Gayam | 04/06/23 2:40 AM
Row 141 | @praneeth.gayam@penske.com can you create the conf folder under resources folder and move db.porp | Mahipal | 04/03/23 9:59 PM
| @mahipal.podduturi@penske.com , It is done. Please check the develop branch. Thanks. | Gayam | 04/04/23 11:26 PM
Row 141 | I am doing testing it is not loading the database properties. | Mahipal | 03/31/23 6:40 PM
Row 141 | @mathumala.nachiappan@penske.com Please choose the appropriate bucket and specify what you are wanting @shane.myers@penske.com to do. Thank you | Yvette Urso | 12/09/22 12:53 AM
| Sure @yvette.urso@penske.com . Thought App Owner can understand the activity after deployment and change to their appropriate status once they start working on it. As the deployment is done long back, CAP is waiting for the confirmation on the changes | Mathumala Nachiappan | 12/12/22 4:41 PM
Row 141 | @shane - QA Deployment done on 14th Nov | Mathumala Nachiappan | 11/23/22 3:43 AM
Row 142 | Secrets: @david.long@penske.com , I sent the secrets in the email. Please verify and let us know whether this app requires code changes. | Gayam | 06/28/23 12:44 AM
| @praneeth.gayam@penske.com Just validated and all secrets found were false positives. No code change needed. | David | 06/28/23 1:28 AM
| @david.long@penske.com confirmed all secrets are false positives in the email. | Gayam | 06/28/23 2:23 AM
Row 143 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:09 AM
| @rajesh.haravde@penske.com , This is already onbaorded to bamboo and deployed to Dev. https://bamboo.penske.com/browse/RSIBP-RSIB2/deployments | Gayam | 06/09/23 1:48 AM
Row 143 | Done. Please take it forward. | Rajesh | 04/26/23 8:28 PM
| @rajesh.haravde@penske.com , this app is deployed to dev using develop_log4j branch - https://bamboo.penske.com/browse/RSIBP-RSIB1/deployments Please verify and merge the code to develop branch. | Gayam | 04/27/23 2:07 AM
Row 143 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 143 | Validation with bitbucket & Maven done. we are awaiting on development environment configuration and validation. | Rajesh | 04/25/23 5:57 PM
| Thanks @rajesh.haravde@penske.com . PR is still in open status. Could you please merge. In the mean time we will onboard to bamboo. | Gayam | 04/26/23 1:19 AM
Row 143 | @rajesh.haravde@penske.com , I hope according to your email, all of the secrets of this app are false positives. So could you please review the PR https://bitbucket.penske.com/projects/PTLCORP/repos/rsi-web/pull-requests/3/overview | Gayam | 02/16/23 11:45 PM
Row 143 | @rajesh.haravde@penske.com , Adding to above we sent secrets of all of your apps in the email. For this app all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:49 PM
Row 143 | Work in progress. | Rajesh | 01/18/23 8:22 PM
Row 143 | @rajesh.haravde@penske.com , We have completed the log4j/maven changes. Please review them and merge in below MR. https://bitbucket.penske.com/projects/PTLCORP/repos/rsi-web/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/09/22 6:43 AM
| We will do the needful as requested and get back to you on build results. Thanks. Please do the same thing as requested earlier for CVI project too. | Rajesh | 12/12/22 10:21 PM
Row 144 | as per my understanding we have only web application and that the URL for that. | Rajesh | 04/14/23 12:06 AM
Row 144 | Web project URL : https://svn.penske.com/svn/webprojects/corp/safety/ branches/dev_gh/ | Rajesh | 02/10/23 2:56 AM
| Thanks @rajesh.haravde@penske.com . This is batch project. I am posting the above URL in the safetydata.war project. | Gayam | 02/10/23 3:09 AM
| @praneeth.gayam@penske.com - Are we still looking details for safetydata? CC: @rajesh.haravde@penske.com | Mathumala Nachiappan | 02/14/23 10:32 AM
| Yes @mathumala.nachiappan@penske.com . We got the details for safetyData web app but not on the batch app. This line item is for batch app. | Gayam | 02/14/23 11:39 PM
| @rajesh.haravde@penske.com , This line item is for safetydata batch app. We got the details for only web app. Changing the status to 'Waiting for AO' | Gayam | 02/16/23 7:48 PM
Row 144 | we will confirm about the batch but for web project that the url. | Rajesh | 02/10/23 2:55 AM
Row 144 | SafetyData has both batch and web applications pointing to same repo which is discussed in safetydata.war app. So following these things in that app. | Gayam | 01/26/23 12:09 AM
Row 144 | Safety Data’s repository is empty. Praneeth been informed , awaiting on reply. | Rajesh | 01/18/23 8:23 PM
Row 144 | @rajesh.haravde@penske.com - Pls. share the repo details for this application. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:17 PM
| I shared the info on safetydata war project. | Rajesh | 12/09/22 1:37 AM
| Please find details of repo and bamboo build for QA environment. Repo: https://svn.penske.com/svn/webprojects/corp/safety/ Branch : branches/dev_gh/ Bamboo Build : https://bamboo.penske.com/browse/SAF-SAFQA Thanks. | Rajesh | 12/12/22 10:24 PM
Row 144 | Thanks @rajesh.haravde@penske.com . Let me discuss with @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/12/22 4:56 PM
Row 144 | Thanks @yvette.urso@penske.com . | Mathumala Nachiappan | 12/01/22 9:16 PM
Row 144 | @mathumala.nachiappan@penske.com please proceed with resources assigned. If you have any questions, we can discuss. This should be resolved. | Yvette Urso | 12/01/22 8:32 PM
Row 144 | @don.kichline@penske.com @hugo.scavino@penske.com @yvette.urso@penske.com - How do we resolve the Resource Issue with corp for this application? | Yvette Urso | 11/30/22 12:33 AM
| The resource issue has to be resolved by the application owner. From our team we move on. However, at a certain point they will need to prioritize people to work on this. This is a production issue that impacts security on multiple platforms. If they need further clarification on priorities, have their manager talk to me. | Donald Kichline | 11/30/22 12:41 AM
| @don.kichline@penske.com @hugo.scavino@penske.com Understood, thank you | Yvette Urso | 11/30/22 2:24 AM
Row 144 | Need to determine resource for this application - was notified by @hugo.scavino@penske.com we may not have anyone to work this app. | Yvette Urso | 11/22/22 2:41 AM
Row 145 | @rajesh.haravde@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/PTLCORP/repos/safetydata-web/pull-requests/3/overview | Gayam | 06/16/23 4:02 AM
Row 145 | This application requires Bamboo to be upgraded to JDK8 Prior to any other work. | Yvette Urso | 04/26/23 11:24 PM
Row 145 | On Secrete with respect to Safety data, we are not implementing any code change at this time. please take forward as it is. | Rajesh | 04/26/23 8:02 PM
Row 145 | Secrets: @rajesh.haravde@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:34 AM
Row 145 | @rajesh.haravde@penske.com confirmed following URL for web application. Web project URL : https://svn.penske.com/svn/webprojects/corp/safety/ branches/dev_gh/ | Gayam | 02/10/23 3:10 AM
Row 145 | @rajesh.haravde@penske.com , Both web and Batch bamboo plan is connecting to same repo. Not sure whether that is correct or are we missing nay info. Usually web and batch projects should be separate..right? @mathumala.nachiappan@penske.com | Gayam | 12/09/22 1:57 AM
| Safetydata and safetydata.war are same project. here the info as requested. Please find details of repo and bamboo build for QA environment. Repo: https://svn.penske.com/svn/webprojects/corp/safety/ Branch : branches/dev_gh/ Bamboo Build : https://bamboo.penske.com/browse/SAF-SAFQA | Rajesh | 12/12/22 10:26 PM
| @hugo.scavino@penske.com , Both web and batch projects related to this app have same repository. Not sure how it is going as we have to have separate bamboo builds and repos in mavanization. Could you please suggest. Thanks. @rajesh.haravde@penske.com | Gayam | 01/26/23 12:03 AM
Row 145 | Changed status to AO Bamboo | Yvette Urso | 12/15/22 2:54 AM
Row 145 | @rajesh.haravde@penske.com - Issue with Folder structure. Pls. share the folder reference to start the log4J changes. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:12 PM
| what do you mean by folder reference ?please schedule team call to take it forward thanks. | Rajesh | 12/01/22 9:52 PM
| @rajesh.haravde@penske.com , Web and Batch both source code, configuration files commit in single SVN repo....So they are used same repo to both WEB and Batch build plan... It is required to separate the source code, configuration files for Web and Batch. https://svn.penske.com/svn/webprojects/corp/safety/ and same branch "branches/dev_gh/ " but artifact generation is different for both @mathumala.nachiappan@penske.com | Gayam | 12/08/22 3:10 AM
| SafetyData QA : https://bamboo.penske.com/browse/SAF-SAFQA SafetyData PROD: | Rajesh | 12/09/22 1:36 AM
| https://bamboo.penske.com/browse/SAF-SAFPROD | Rajesh | 12/09/22 1:36 AM
Row 146 | @veronique.labeille@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:29 AM
| @praneeth.gayam@penske.com I've provided the source as https://bitbucket.penske.com/projects/PTLCORP/repos/hvut-web/browse The shared secrets looks something different and the excel file doesn't has the source path. We don't have the below file in the bitbucket source "src/main/liberty/config/server.xml" which is part of the secret. Please clarify. @veronique.labeille@penske.com | Sreekanth | 02/25/23 2:34 AM
| @sreekanth.kancharla@penske.com , In the file we have inserted 2 columns Columns B & C. These 2 columns are from the Log4j team's review. Column B gives the info about whether it is a True/False positive. Column C gives the info about why it is a False or True positive. For the current issue, we provided the reason 'The file is not available,It is from the commit history'. Secrets scanning tool gives the secrets even if the commit history contains any secrets. Please check and let us know if you have any more questions. | Gayam | 02/27/23 11:43 PM
| @praneeth.gayam@penske.com Thank you for the clarification. We've made small change in this application and yet to be deployed to PROD. The code is not yet merged to master branch and still available in develop only. I'll have the code merged to master branch, so your team can work on log4j migration. | Sreekanth | 03/04/23 3:02 AM
| Thanks @sreekanth.kancharla@penske.com . Are these changes as part of secrets mitigation or something else? Also, please let us know once you merge your chagnes to develop branch. | Gayam | 03/07/23 12:17 AM
| @praneeth.gayam@penske.com These changes are not part of secrets. We are making changes as part of ongoing projects. The changes are merged to develop branch and yet to merge with master. | Sreekanth | 03/07/23 12:37 AM
| @sreekanth.kancharla@penske.com once your changes are deployed to production, are you planning to merge the develop_log4j to develop branch? develop_log4j contains the log4j team's changes | Gayam | 03/08/23 12:03 AM
| @praneeth.gayam@penske.com Sure, we'll take care of merging the log4j changes from develop_log4j to develop post prod deployment of current changes. | Sreekanth | 03/08/23 3:02 AM
| @praneeth.gayam@penske.com FYI, we've scheduled the PROD deployment with our changes today 04/11/2023. All the code is merged to master branch and develop branch. Could you please create PR from develop_log4j to develop branch tomorrow? | Sreekanth | 04/11/23 11:42 PM
| Sure @sreekanth.kancharla@penske.com | Gayam | 04/12/23 1:11 AM
| @praneeth.gayam@penske.com FYI, the deployment to PROD is completed. You are good to create PR for log4j changes to develop branch. | Sreekanth | 04/12/23 8:26 PM
| @sreekanth.kancharla@penske.com , Created PR https://bitbucket.penske.com/projects/PTLCORP/repos/hvut-web/pull-requests/41/overview | Gayam | 04/13/23 12:26 AM
| @praneeth.gayam@penske.com The PR has conflict. Could you please resolve and push the changes. | Sreekanth | 04/13/23 12:47 AM
| @praneeth.gayam@penske.com I've merged both the PR. We are good now. We'll continue testing the changes in local and use the existing Bamboo plan https://bamboo.penske.com/browse/HVUTBP-HVUTW itself to deploy to DEV and test once we are good with local testing. @veronique.labeille@penske.com | Sreekanth | 04/14/23 8:03 PM
| @praneeth.gayam@penske.com We've started testing this application in local & DEV. Please change the "App Status" accordingly. | Sreekanth | 04/19/23 9:17 PM
| @praneeth.gayam@penske.com We've tested this app in QA & got signoff from Users as well. Please update the "App Status". | Sreekanth | 05/22/23 8:50 PM
| @sreekanth.kancharla@penske.com , Changed the status. | Gayam | 05/22/23 10:13 PM
Row 146 | @veronique.labeille@penske.com , We couldn't find the SVN location and Bamboo build for this application. Could you please provide the requested info. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/18/23 2:09 AM
| @praneeth.gayam@penske.com This application is redesigned with a new name and the artifact name is "hvutirsforms.war". hvutirsforms is already in bitbcket. https://bitbucket.penske.com/projects/PTLCORP/repos/hvut-web/browse @mathumala.nachiappan@penske.com @veronique.labeille@penske.com | Sreekanth | 01/27/23 10:06 PM
| Thanks @sreekanth.kancharla@penske.com . From which branch you want us to create log4j branch. Also, please provide the bamboo location. | Gayam | 01/27/23 10:11 PM
| @praneeth.gayam@penske.com master branch is good to use for migration. Bamboo: https://bamboo.penske.com/browse/HVUTBP-HVUTW | Sreekanth | 01/27/23 10:17 PM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (Cap)Log4j | Gayam | 02/01/23 12:35 AM
Row 146 | @veronique.labeille@penske.com Testing Email | Yvette Urso | 01/25/23 1:25 AM
Row 146 | @yvette.urso@penske.com - To confirm this application to be taken by CAP for Modernization activity. CC: @brian.hug@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:40 AM
Row 146 | hi @yvette.urso@penske.com - as per the previous communication, modernization will be taken care by the Fleet services team. from the latest update of yours, is it moved under CAP scope for modernization? | Mathumala Nachiappan | 12/08/22 3:50 PM
Row 146 | @mathumala.nachiappan@penske.com this will remain where it it per @veronique.labeille@penske.com - I moved to (Cap) Analysis. Please move to the correct status per your work. | Yvette Urso | 12/02/22 12:15 AM
Row 146 | @veronique.labeille@penske.com @mathumala.nachiappan@penske.com @praneeth.gayam@penske.com - Veronique, can you please confirm this application is no longer a part of Corp App Group and it should be moved to fall under the Fleet Services Team? Thank you | Yvette Urso | 12/01/22 8:39 PM
| @yvette.urso@penske.com , It is part of Fleet Services which is under CORP systems | Veronique Labeille | 12/01/22 9:20 PM
Row 146 | Scope is moved to Fleet services Team. CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com and @april.ottey@penske.com | Mathumala Nachiappan | 12/01/22 8:10 PM
Row 147 | Review: @sreekanth.kancharla@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/PTLCORP/repos/scorecard-batch/pull-requests/3/overview | Gayam | 05/03/23 2:13 AM
| @praneeth.gayam@penske.com Added review comment to the PR. please check and do the need. | Sreekanth | 05/08/23 10:58 PM
| @praneeth.gayam@penske.com I could the review comment is taken care. I've merged the PR. Please proceed with further process. | Sreekanth | 05/09/23 7:12 PM
| @sreekanth.kancharla@penske.com , Onboarded develop branch to Bamboo--------https://bamboo.penske.com/browse/CBP-CEFLEETB0 Please deploy to QA. | Gayam | 05/11/23 11:22 PM
| @praneeth.gayam@penske.com We've started validating the changes in our local environment, post that we'll deploy this to QA. Hope the "App Status" needs to be changed to AO team. | Sreekanth | 05/22/23 8:42 PM
| Yes @sreekanth.kancharla@penske.com . I already kept this app in (AO)Bamboo Review status. | Gayam | 05/22/23 10:09 PM
Row 147 | @veronique.labeille@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:29 AM
| @praneeth.gayam@penske.com Apart from 1 secret related to "src/conf/DB.properties" no other required any mitigation. For "src/conf/DB.properties", as per my analysis, this file seems unused. Please proceed with log4j changes. While testing this application, we'll remove the "src/conf/DB.properties" and test. Post testing, we'll remove this file and corresponding changes in the code. | Sreekanth | 04/12/23 12:02 AM
| Sure @sreekanth.kancharla@penske.com . Thanks | Gayam | 04/12/23 1:18 AM
Row 147 | Thanks @yvette.urso@penske.com . Following is the repo and bamboo details for this project. Batch: - https://svn.penske.com/svn/webprojects/corp/cefleetBatch/trunk/cefleetBatch Bamboo: https://bamboo.penske.com/browse/CBP | Gayam | 02/01/23 2:54 AM
Row 147 | @praneeth.gayam@penske.com I created a Batch and Web for Scorecard. Moved the status to (Cap) Analysis - please update the status to the right one from here. Thank you | Yvette Urso | 02/01/23 2:24 AM
Row 148 | @praneeth.gayam@penske.com We've received confirmation from Manager that we'll continue with "scorecard" name. With this, we'll have to change the artifact name to "cefleetservices" in pom.xml as that is the context root of the application. We'll make this code change from our end. The other change should be in bamboo deploy plan(s) variable "appname" should also be as "cefleetservices" along with this, please delete the old deploy plan https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=140509192 | Sreekanth | 05/09/23 7:17 PM
| @sreekanth.kancharla@penske.com , Changed variable Appname from 'scorecard' to 'cefleetservices' in the deploy spec. Also, deleted the old deploy plans and run feature branch according to deleted deploy plans. https://bamboo.penske.com/browse/CBP-CEFLEETW/deployments https://bamboo.penske.com/deploy/config/configureEnvironmentVariables.action?environmentId=142802994 | Gayam | 05/11/23 11:21 PM
| @praneeth.gayam@penske.com Seems still the app is not deploying fine and I could see somewhere the name of the war is still scorecard.war & scorecard.tgz but we've changed that to cefleetservices.war and the same is available in target folder of artifact in bamboo. Please check below deployment logs and do the need. https://bamboo.penske.com/deployment-download/142802994/build_logs/142737427-142802994-141069075.log | Sreekanth | 05/12/23 6:49 PM
| @sreekanth.kancharla@penske.com , We observed following things. Changes for artifact id has done in "feature/FS-132-Log4j2-Testing" .But recently 2 more branches were created and artifact id is still "scorecard" . So need to make changes in those 2 branches pom file . https://bamboo.penske.com/deployment-download/142802994/build_logs/142737427-142802994-141068843.log - Deployment with "feature/FS-132-Log4j2-Testing" https://bamboo.penske.com/deployment-download/142802994/build_logs/142737427-142802994-141069010.log - Deployment with "develop-log4j-ao-testing" Could you please check. | Gayam | 05/15/23 11:33 PM
| @praneeth.gayam@penske.com We kept the artifact id as "scorecard" to have no change artifactory folder path but we've changed the final-name to "cefleetservices". Even then the artifact name is creating as scorecard-2.0.0-feature-sree-peer-review-20230515.190735-7.war Is that based on the artifactId attribute from pom file, if so then we've no choice other than making the artifactId to "scorecard" so the path in artifactory also would be as com/penske/cefleetservices instead of com/penske/scorecard Since the correct app name is scorecard we wanted to have the same everywhere except the artifact name as "cefleetservices" Hope you understand, please suggest on this. | Sreekanth | 05/16/23 2:19 AM
| @sreekanth.kancharla@penske.com , Theoretically it is possible but this has to be discussed with the broad team as environment has multiple steps to deploy to the server like build, deployment to artifactory, deployment to /opt location and a websphere script deploys to desire websphere server. | Gayam | 05/17/23 3:06 AM
| We've changed the artifact id in pom file to "cefleetservices" only so artifact name also will be the same. | Sreekanth | 05/22/23 8:41 PM
Row 148 | Review: @sreekanth.kancharla@penske.com , this app is ready for review. https://bitbucket.penske.com/projects/PTLCORP/repos/scorecard-web/pull-requests/3/overview | Gayam | 03/18/23 1:11 AM
| @praneeth.gayam@penske.com Added review comments. Please check. | Sreekanth | 04/11/23 11:53 PM
| @sreekanth.kancharla@penske.com , As discussed we implemented the review comments. Please check and merge. Thanks | Gayam | 04/15/23 12:44 AM
| @praneeth.gayam@penske.com The PR is merged. Please proceed with further steps. | Sreekanth | 04/15/23 12:55 AM
| Thanks @sreekanth.kancharla@penske.com . We will onboard to bamboo and deploy to Dev | Gayam | 04/19/23 3:26 AM
| @sreekanth.kancharla@penske.com , Bamboo build onboarding completed. Dev deployment done using develop branch. Please verify. Thanks. https://bamboo.penske.com/browse/CBP-CEFLEETW | Gayam | 04/20/23 2:05 AM
| @praneeth.gayam@penske.com Thank you for the update. We'll start testing this app in DEV. | Sreekanth | 04/24/23 8:35 PM
| @praneeth.gayam@penske.com If possible, please change the name of the plan in Bamboo from "scorecard-Web" to "scorecard-web" to maintain the consistency between Bamboo & Bitbucket. | Sreekanth | 04/24/23 11:41 PM
| Sure @sreekanth.kancharla@penske.com . we will let you know once the change implemented. | Gayam | 04/25/23 1:11 AM
| @sreekanth.kancharla@penske.com , changes are completed. Please verify. | Gayam | 04/27/23 2:12 AM
| @praneeth.gayam@penske.com Thank you for making the naming corrections as same as bitbucket repo name for both build & deploy plans. Started using new deploy plan. Please delete old deploy plan. | Sreekanth | 04/27/23 7:01 PM
Row 148 | @praneeth.gayam@penske.com No remediation required for the shared secrets. @veronique.labeille@penske.com | Sreekanth | 02/25/23 2:36 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to Cap Maven | Gayam | 02/27/23 11:45 PM
Row 148 | @praneeth.gayam@penske.com The status is as (AO). Please remind us in case you are waiting on something from us. CC: @veronique.labeille@penske.com | Sreekanth | 02/22/23 8:40 PM
| @sreekanth.kancharla@penske.com , Secrets need to be confirmed. I will share all the secrets of new corp apps. Thanks. | Gayam | 02/23/23 3:29 AM
| @veronique.labeille@penske.com / @sreekanth.kancharla@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:29 AM
Row 148 | @praneeth.gayam@penske.com I created a Batch and Web for Scorecard. Moved the status to (Cap) Analysis - please update the status to the right one from here. Thank you | Yvette Urso | 02/01/23 2:24 AM
Row 148 | @veronique.labeille@penske.com , We couldn't find the SVN location and Bamboo build for this application. Could you please provide the requested info. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/18/23 2:08 AM
| @praneeth.gayam@penske.com This application has 2 projects. Web - https://svn.penske.com/svn/webprojects/corp/cefleet/trunk/cefleetservices Batch: - https://svn.penske.com/svn/webprojects/corp/cefleetBatch/trunk/cefleetBatch Bamboo: https://bamboo.penske.com/browse/CBP Not sure why we've only 1 application in this file. @mathumala.nachiappan@penske.com @veronique.labeille@penske.com | Sreekanth | 01/27/23 10:09 PM
| @sreekanth.kancharla@penske.com , Please let us know whether we need to modernize both batch and war applicaitons for this app. If yes, @yvette.urso@penske.com please insert 1 more column for batch app. @mathumala.nachiappan@penske.com | Gayam | 01/27/23 10:17 PM
Row 148 | @yvette.urso@penske.com - To confirm this application to be taken by CAP for Modernization activity. CC: @brian.hug@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 01/10/23 10:40 AM
Row 148 | hi @yvette.urso@penske.com - as per the previous communication, modernization will be taken care by the Fleet services team. from the latest update of yours, is it moved under CAP scope for modernization? | Mathumala Nachiappan | 12/08/22 3:51 PM
Row 148 | @mathumala.nachiappan@penske.com this will remain where it it per @veronique.labeille@penske.com - I moved to (Cap) Analysis. Please move to the correct status per your work. | Yvette Urso | 12/02/22 12:15 AM
Row 148 | @veronique.labeille@penske.com @mathumala.nachiappan@penske.com @praneeth.gayam@penske.com - Veronique, can you please confirm this application is no longer a part of Corp App Group and it should be moved to fall under the Fleet Services Team? Thank you | Yvette Urso | 12/01/22 8:39 PM
| @yvette.urso@penske.com , It is part of Fleet Services which is under CORP systems | Veronique Labeille | 12/01/22 9:24 PM
Row 148 | Scope is moved to Fleet services Team. CC: @praneeth.gayam@penske.com , @yvette.urso@penske.com and @april.ottey@penske.com | Mathumala Nachiappan | 12/01/22 8:11 PM
Row 149 | @shane.myers@penske.com , For this jar we changed the scope of log4j jars from provided to compile. Please check and merge the code to develop branch. PR is https://bitbucket.penske.com/projects/ARPROJ/repos/security-author-filter/pull-requests/6/overview | Gayam | 05/22/23 9:11 PM
Row 149 | I have reviewed the changes. I had to decline the pull request. That was an accident on my part. I did take the changes and eventually merged them into the develop branch. Please proceed to the Bamboo step. Recall the final step for this JAR is artifactory. | Hugo Scavino | 02/10/23 10:55 PM
| @hugo.scavino@penske.com , Bamboo onboarding is completed. https://bamboo.penske.com/browse/SECUTIL-AUTHOR Could you please check. | Gayam | 02/13/23 11:32 PM
Row 149 | dependency with security_util.jar | Mathumala Nachiappan | 12/02/22 5:32 PM
| @yvette.urso@penske.com - This is just an update. Dependency is mentioned in #76. And Hugo is already tagged and the App status is updated | Mathumala Nachiappan | 12/12/22 4:50 PM
| @mathumala.nachiappan@penske.com let's re-mention the dependency here so the AO does not have to hunt or the details. Thanks | Yvette Urso | 12/15/22 2:42 AM
| @hugo.scavino@penske.com , After adding the latest security_util dependency, this app is getting following issue. security-author-filter/src/main/java/com/penske/security/filter/AuthorFilter.java:[57,65] constructor SecurityDesign in class com.penske.security.factory.SecurityDesign cannot be applied to given types; required: no arguments found: no arguments reason: SecurityDesign() has protected access in com.penske.security.factory.SecurityDesign SecurityDesign is from securityutil.jar and the constructor is a protected method. That is the reason we are seeing the above issue. | Gayam | 02/03/23 1:13 AM
| That is my fault. I will repair this. | Hugo Scavino | 02/03/23 2:57 AM
| Completed02 Feb 2023, 4:35:43 PM – < 1 second ago Please attempt the build. | Hugo Scavino | 02/03/23 3:06 AM
| Thanks @hugo.scavino@penske.com . We will check and update you. | Gayam | 02/03/23 11:45 PM
Row 149 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:28 AM
Row 149 | @hugo.scavino@penske.com | Yvette Urso | 12/09/22 1:02 AM
| @yvette.urso@penske.com - The dependent jar has to be cleared first. Presently no action required from Hugo now. | Mathumala Nachiappan | 12/12/22 4:49 PM
Row 150 | Thanks @hugo.scavino@penske.com for your support. This is perfectly fine now for the team to proceed on the dependent application. Can we update the status to deploy done? CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 02/15/23 10:22 AM
| Yes, this is done as the JAR is now in artifactory. | Hugo Scavino | 02/15/23 10:25 AM
| Thanks @hugo.scavino@penske.com . Changed the status to (AO)App Deploy Done. | Gayam | 02/16/23 1:16 AM
Row 150 | Team, great job. I repaired an issue with a unit test and we have another JAR ready for downstream clients. This JAR should be used for new mavenization <groupId>com.penske.architecture</groupId> <artifactId>security-util</artifactId> <version>2.0.0-develop_log4j-SNAPSHOT</version> https://bamboo.penske.com/browse/SECUTIL-SEUTL0/history | Hugo Scavino | 01/31/23 4:40 AM
Row 150 | I have completed the peer review and adding required unit tests. I remved the other branches and only have develop now. https://bitbucket.penske.com/projects/ARPROJ/repos/security_util/branches Next step is to create the Bamboo project for this one. The old Bambo project https://bamboo.penske.com/browse/SECUTIL | Hugo Scavino | 01/25/23 3:21 AM
| Sure @hugo.scavino@penske.com . We will create and let you know. Thanks. @haribabu.challa@penske.com @mathumala.nachiappan@penske.com | Gayam | 01/25/23 11:33 PM
| @hugo.scavino@penske.com , Bamboo is onboarded for this application. Location is https://bamboo.penske.com/browse/SECUTIL-SEUTL We only onboarded master. If we onboard develop branch, it builds and deploys to artifactory. That is the reason we did not onboard develop yet. @haribabu.challa@penske.com | Gayam | 01/31/23 2:15 AM
Row 150 | I am going to rename the bitbucket repo to security_util from security_util_batch to match the name of the JAR | Hugo Scavino | 01/19/23 8:31 PM
Row 150 | @hugo.scavino@penske.com | Yvette Urso | 12/15/22 2:59 AM
Row 150 | @hugo.scavino@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:17 AM
Row 151 | @praneeth.gayam@penske.com what will happen in this case? as in this case dependant project is not getting updated? | Rajesh | 07/05/23 8:24 PM
| @rajesh.haravde@penske.com , We sent an email about Utimage long time back but no response. Either Utimage has to be manually uploaded to artifactory or it needs to be modernized. AO needs to decide what way we need to go. Thanks. | Gayam | 07/06/23 3:15 AM
Row 151 | Praneeth did you hear anything from Utimage team . | Rajesh | 04/26/23 8:03 PM
| No @rajesh.haravde@penske.com . | Gayam | 04/28/23 2:00 AM
Row 151 | On Secrete with respect to Safety data, we are not implementing any code change at this time. please take forward as it is. | Rajesh | 04/14/23 12:07 AM
| Thanks @rajesh.haravde@penske.com . Changed the status to Blocker as this app depends on Utimageclient.jar | Gayam | 04/14/23 12:21 AM
Row 151 | Secrets: Adding to above questions, sent the secrets in the email. Please check and respond. | Gayam | 03/18/23 12:56 AM
Row 151 | Also the dependant JAR utimageservice.jar needs to be added to artifactory. I created the maven pom.xml with a local version but this cannot be the final solution. | Hugo Scavino | 01/31/23 3:04 AM
| @hugo.scavino@penske.com , We found a Bamboo build and repo for utimageservice.jar. Following are the details. Do you want us to modernize this application also? Bamboobuild: https://bamboo.penske.com/browse/USEDTRUCKS-UTIMAGECLIENT BB Repo: https://bitbucket.penske.com/projects/EBUT/repos/ut-image-service/browse | Gayam | 02/10/23 1:18 AM
| for UTImageClient jar please contact @Joseph, Brian (Penske). | Rajesh | 02/17/23 2:48 AM
Row 151 | Sure @hugo.scavino@penske.com . We will do the required things and let you know. | Gayam | 02/01/23 12:10 AM
Row 151 | Please move this to bitbucket. The AO still needs to perform regression and spot checking. It would be worth the effort to create unit tests. see below for examples https://bitbucket.penske.com/projects/ARPROJ/repos/security_util/browse/src/test/java/com/penske/security | Hugo Scavino | 01/31/23 3:01 AM
Row 151 | I migrated this project to log4j2, maven and redacted some passwords where are used by local development. I did not find any issues with JDK 1.6 or 1.8 https://svn.penske.com/svn/fieldsys/maintenance/fleetnet/branches/sellsheet_modernization/ | Hugo Scavino | 01/31/23 2:57 AM
Row 151 | I am reviewing. I created a SVN branch https://svn.penske.com/svn/fieldsys/maintenance/fleetnet/branches/sellsheet_modernization | Hugo Scavino | 01/31/23 1:42 AM
Row 151 | @hugo.scavino@penske.com will review this | Yvette Urso | 01/24/23 3:42 AM
Row 151 | @hugo.scavino@penske.com assisting with this issue. | Yvette Urso | 12/15/22 2:55 AM
Row 151 | @rajesh.haravde@penske.com , This application is using commondatasource class . Upto java 1.6 its working fine. From java1.7 the commondatasource class having the getParentLogger() abstractmethod , the app should implement the method as we are upgrading java version to 1.8. Could you please check this. | Gayam | 11/29/22 1:56 AM
| @krishna.tanga@penske.com | Yvette Urso | 12/01/22 8:33 PM
| @rajesh.haravde@penske.com / @krishna.tanga@penske.com , Adding to above question, please provide existing bamboo build for this project. @mathumala.nachiappan@penske.com | Gayam | 12/08/22 11:02 PM
| Can you please provide the repo details to take forward. Thanks | Rajesh | 12/12/22 10:28 PM
| @rajesh.haravde@penske.com , Repo details provided above. Please check. @mathumala.nachiappan@penske.com | Gayam | 12/13/22 12:42 AM
Row 151 | @april.ottey@penske.com, @rajesh.haravde@penske.com confirmed the sellsheet svn location in the email. https://svn.penske.com/svn/fieldsys/maintenance/fleetnet/branches/offshore_standalone/sellsheet | Gayam | 11/29/22 1:55 AM
Row 151 | @april.ottey@penske.com / @veronique.labeille@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:35 AM
Row 152 | Kalrav is not familiar with this app but will ask his offshore team. | Yvette Urso | 05/11/23 12:59 AM
Row 152 | Per Kathy Marko - As indicated in my previous email, this application can be retired. I believe this would fall under Steve McMullen and/or Kalrav to retire the application as I am just the business process owner. Thank you, Kathy | Yvette Urso | 05/11/23 12:14 AM
Row 152 | Changing owner of this application and need to work with April to determine who to work with for this application. | Yvette Urso | 05/01/23 9:12 PM
Row 152 | @scott.bortzel@penske.com , For this application SVN repo available https://svn.penske.com/svn/webprojects/admin/SEM/. But Bamboo plan is not available. We need production branch confirmation for log4j-Migration and without existing bamboo build we could not find this. Could you please let us know what is the latest production branch. Thanks. | Gayam | 01/14/23 1:03 AM
| @scott.bortzel@penske.com , Could you please provide the response to above question. Thanks. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 03/24/23 10:53 PM
Row 153 | @dale.porter@penske.com , build plan onboarded and deployment to artifactory is successful. Deploy plan onboarding is also successful. Please deploy to QA and test it. Thanks. Build plan: https://bamboo.penske.com/browse/SERVICENETBATCH-SVCNETB0 Deploy Plan: https://bamboo.penske.com/browse/SERVICENETBATCH-SVCNETB/deployments | Gayam | 08/03/23 12:49 AM
| HI all, I ran the deploy to QA but it did not place the tgz file of the build in the /var/tmp of the qa deploymanager (clelx150ptlge). I included url of qa build log, thank you https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151196764 | Dale Porter | 08/05/23 1:07 AM
| @dale.porter@penske.com , we will check and get back to you. | Gayam | 08/08/23 1:05 AM
| @dale.porter@penske.com , issue got fixed. Qa deployment done and tgz file generated in clelx150ptlge. Thank you | Gayam | 08/11/23 12:18 AM
Row 153 | Review: @dale.porter@penske.com , this app is ready for your review. Please check and merge the PR. https://bitbucket.penske.com/projects/MAIN/repos/servicenet-batch/pull-requests/3/overview | Gayam | 07/27/23 11:50 PM
| I reviewed and merged the code. Thank you. | Dale Porter | 07/28/23 1:48 AM
| will onboard to bamboo. | Gayam | 07/31/23 2:32 AM
Row 153 | @stella.george@penske.com / @dale.porter@penske.com , This application dependent on servicenet-models.jar. This jar is not available in artifactory Could you please provide your approval to upload it to artifactory in the below location. GroupId: com.penske.apps ArtifactId: servicenet-models Version:default Location: common-mvn-development-local | Gayam | 06/30/23 12:56 AM
| Yes, please upload the servcienet-models.jar to the Penske artifactory. | Dale Porter | 07/07/23 12:54 AM
| Thanks @dale.porter@penske.com . We have uploaded the dependency jar to artifactory. | Gayam | 07/10/23 11:36 PM
Row 153 | Had a discussion with @dale.porter@penske.com and confirmed that we need to use the latest prod reference branch as base brach for modernization changes. | Gayam | 06/29/23 3:11 AM
Row 153 | Query: @stella.george@penske.com , Adding to secrets, we have a query on this app. This application dependent on servicenet-models.jar. This jar is not available in artifactory Could you please provide your approval to upload it to artifactory in the below location. GroupId: com.penske.apps ArtifactId: servicenet-models Version:default Location: common-mvn-development-local | Gayam | 06/15/23 2:02 AM
| @dale.porter@penske.com , Please provide your response for above query. Thanks. | Gayam | 06/21/23 1:06 AM
| @dale.porter@penske.com , Could you please respond to above query. | Gayam | 06/27/23 3:31 AM
Row 153 | It will be deploy later for production, please use the branch as instructed. Thank you. | Dale Porter | 06/24/23 12:44 AM
| Thanks @dale.porter@penske.com . We will use the following as base branch as instructed. https://svn.penske.com/svn/fieldsys/maintenance/batch/servicenetbatch/branches/servicenetbatch_Log4jChanges | Gayam | 06/27/23 3:28 AM
Row 153 | I have merged prior code changes we have in QA that are planned to deploy in future and do not want to lose in the bit bucket migration to the branch https://svn.penske.com/svn/fieldsys/maintenance/batch/servicenetbatch/branches/servicenetbatch_Log4jChanges | Dale Porter | 06/23/23 12:41 AM
| @dale.porter@penske.com , Do we need wait until you confirm your changes goes to production? or let us know what is the step we need to take? | Gayam | 06/23/23 11:46 PM
Row 153 | I have removed the test user User name and secret for the iBMI connection in the applicationContext.xml file and checked in the change in SVN. The other files were not senstive data (just false positives). Thank you. | Dale Porter | 06/16/23 3:02 AM
| @dale.porter@penske.com , We are seeing your changes in the dev_gh branch. Also, we are seeing latest commits in this branch. https://svn.penske.com/svn/fieldsys/maintenance/batch/servicenetbatch/branches/dev_gh But we took the https://svn.penske.com/svn/fieldsys/maintenance/batch/servicenetbatch/tags/prod/20230309 as base branch. Bamboo prod build is pointing to this branch. Which one we need to consider as base branch and start doing log4j changes? | Gayam | 06/21/23 1:05 AM
Row 153 | Secrets: @stella.george@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:52 AM
Row 154 | @subramanian.vennimalayan@penske.com / @sarath.mani@penske.com , I sent the secrets file of this app in the email. Please check. Thanks. | Gayam | 08/05/23 12:23 AM
Row 154 | @praneeth.gayam@penske.com The status shows "Waiting on AO" for this app. Could you please let us know if you need more information. | Subramanian | 07/28/23 2:10 AM
| Changed to Cap Analysis | Gayam | 07/31/23 2:45 AM
Row 154 | @david.long@penske.com , Log4j team started working on modernizing this application. When we verified the old production bamboo build we are seeing following 2 repositories mentioned in the build. SERVICEREQBATCH_PROD - https://svn.penske.com/svn/fieldsys/maintenance/batch/servicerequestbatch/tags/prod/PROD_20220428 DICTIONARYJAR_PROD (Jar repo) - https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/Jar/PROD/ I am expecting 2nd one is a dependency jar for the first repo. Is that correct? If yes, we need to do the log4j and mavanization for the dependency jar also. Could you please check and confirm. Thanks. FYI: @shane.myers@penske.com | Gayam | 05/18/23 1:22 AM
| @praneeth.gayam@penske.com Yes that is a dependency Jar. but that should be covered under Servicereqsvc,war. this jar will be used by edvir.war, servicereqbatch and servicereqweb | Stella george | 06/14/23 1:49 AM
| @stella.george@penske.com , So Servicereqsvc,war, edvir.war, servicereqbatch and servicereqweb are depending on serviceRequestUtility.jar. The source code available under https://svn.penske.com/svn/fieldsys/maintenance/service-request-service | Gayam | 06/14/23 3:29 AM
| @praneeth.gayam@penske.com we need to use the source code available in serviceRequestUtility folder for serviceRequestUtility.jar. FYI: @stella.george@penske.com | Subramanian | 06/27/23 7:53 PM
Row 155 | @david.long@penske.com , This application having multiple src folders . We are expecting that service-request-service folder is the original source which builts servicereqsvc.war and other folder(serviceRequestUtility) is the dependency jar. SVN Location: https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/tags/prod/PROD_2023-04-06 Servicerequestutility jar build plan: https://bamboo.penske.com/browse/SVCRQ-UTILPROD servicereqsvc.war application build plan: https://bamboo.penske.com/browse/SVCRQ-SRSPROD Following are the 2 suggestions. 1. Build a new repo for serviceRequestUtility folder and mavanize and create a new bamboo plan which builds the jar and uploads to artifactory. Then servicereqsvc.war application uses that jar as a dependency in pom. 2. If serviceRequestUtility folder is not a shared jar then AO can include that folder inside the servicereqsvc.war application. Then no need of separate repo and bamboo plan for the serviceRequestUtility . Please verify and confirm. Thanks. @shane.myers@penske.com | Gayam | 06/01/23 1:49 AM
| @praneeth.gayam@penske.com Service Request utility is jar used by multiple applications. We should go with option 1. | Stella george | 06/14/23 1:52 AM
| Thanks @stella.george@penske.com | Gayam | 06/14/23 3:20 AM
Row 156 | @praneeth.gayam@penske.com ServiceReqApp the SVN URL you are having is worng. the latest build is from below URL> https://svn.penske.com/svn/fieldsys/other/service-request/tags/prod/PROD_BUILD_2021-11-09. the second one is a dependency jar, but that will be covered under Service REq Service.war. 3 one also dependency, but we are going make code change to invoke their REST API. will be removing this jar from application. 4th attachment service jar will be done by Penske Team. | Stella george | 06/16/23 10:08 PM
| Thanks @stella.george@penske.com for the confirmation of the dependencies and correct branch of ServiceReApp. Regarding the 3rd point, locationservice dependency, you said that you are trying to remove this dependency from servicereweb.war application. So do we need to wait to do the modernization until you complete the coding? | Gayam | 06/19/23 8:15 PM
Row 156 | @david.long@penske.com , Log4j team started working on modernizing this application. When we verified the old production bamboo build we are seeing following 4 repositories mentioned in the build. SERVICEREQAPP_PROD - https://svn.penske.com/svn/fieldsys/other/service-request/tags/prod/PROD_BUILD_2019-07-16 DICTIONARYJAR_PROD (Jar repo)- https://svn.penske.com/svn/fieldsys/maintenance/service-request-service/Jar/PROD LOCATIONSERVICE_PROD (Jar repo) - https://svn.penske.com/svn/fieldsys/rental/services/locationmaintainence/trunk/LOCATIONMAINT_LIBS/client-jar/ ATTACHMENTSVC_PROD (Jar repo) - https://svn.penske.com/svn/fieldsys/other/attachment-service/Jar/prod/ I am expecting 2nd, 3rd and 4th are the dependency jars for the first repo. Is that correct? If yes, we need to do the log4j and mavanization for the dependency jars also. Could you please check and confirm. Thanks. FYI: @shane.myers@penske.com | Gayam | 05/18/23 1:24 AM
Row 157 | @praneeth.gayam@penske.com , I tested the application in DEV and checked the logs. In Develop branch, committed a small change in "Timestamp pattern" - pattern layout in log4j2.xml file. and merged the changes that created Build #3. I tried to deploy the release for this Build #3 to DEV env. This caused an error. dev_was8_deploy failed. Please find the screen shot as .png image | Sivagamasundari Suresh | 07/27/23 7:43 PM
| Sure @sivagamasundari.suresh@penske.com . We will check and get back to you. | Gayam | 07/27/23 10:46 PM
| @sivagamasundari.suresh@penske.com , Deployment issue is resolved. Please check. | Gayam | 08/01/23 12:40 AM
| Thank you!. I checked it and though the dev deployment was success, I was not able to find the deployed .war in the DEV server. I searched through folders (WInSCP). Reached out to @raghuramredd.thummalapalli@penske.com . It is resolved now. I could view changes in the logs of sessionmgmtsvc app. | Sivagamasundari Suresh | 08/04/23 9:56 PM
| Thanks @sivagamasundari.suresh@penske.com | Gayam | 08/08/23 1:03 AM
Row 157 | Develop Branch Repaired : Thank you for letting my know. I repaired the branch and Bamboo plan now runs. Also this is an API so there are no front end resources so there is no tgz required. | Hugo Scavino | 02/10/23 11:03 PM
| @hugo.scavino@penske.com , dev deployment is completed for this app. Could you please verify. Thanks. | Gayam | 03/28/23 12:35 AM
Row 157 | Bamboo: Please create a secure bamboo plan for this application. No secrets issues. All mavenized | Hugo Scavino | 02/09/23 2:50 AM
| @hugo.scavino@penske.com , There is no parent declaration in pom and bin.xml is not defined. Do you want us to take care of thise? Also, jtests are getting failed. | Gayam | 02/10/23 10:38 PM
Row 157 | @mathumala.nachiappan@penske.com @hugo.scavino@penske.com This is not blocked. Changed status to Secrets Scanning | Yvette Urso | 12/09/22 12:54 AM
Row 157 | @hugo.scavino@penske.com - Secret scanning resulted with True positives. But the respective statements are not available in the current code. For your secret analysis once. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 7:33 PM
Row 157 | @yvette.urso@penske.com - There are other related testing activities by Brad from webservices team. @hugo.scavino@penske.com to confirm to move to QA | Mathumala Nachiappan | 12/02/22 5:22 PM
Row 157 | @mathumala.nachiappan@penske.com Can you update where this is in the process? ie.. what has been complete and what is pending. | Yvette Urso | 11/30/22 12:34 AM
Row 157 | Update from Hugo - This app is available in Dev. @hugo.scavino@penske.com will move to QA | Mathumala Nachiappan | 11/23/22 3:45 AM
Row 158 | @praneeth.gayam@penske.com this application testing completed move this Deploy/Test | Mahipal | 05/17/23 12:00 AM
| @mahipal.podduturi@penske.com , Changed to QA Deploy/Test | Gayam | 05/17/23 1:56 AM
Row 158 | I deployed dev and qa and tested as well | Mahipal | 05/16/23 11:48 PM
Row 158 | I will check and let you know | Mahipal | 04/03/23 9:47 PM
Row 158 | @mahipal.podduturi@penske.com , this app is onboarded to Bamboo. Please review and let us know whether we can deploy to Dev. | Gayam | 03/23/23 11:06 PM
Row 158 | @praneeth.gayam@penske.com i am goof with PR you can star next steps | Mahipal | 03/22/23 9:15 AM
Row 158 | @praneeth.gayam@penske.com looks good to me the POM changes | Mahipal | 03/15/23 6:35 PM
| @mahipal.podduturi@penske.com , If you complete the review, can you merge the code to develop branch . https://bitbucket.penske.com/projects/ARPROJ/repos/shoptalkreg-web/pull-requests/4/overview | Gayam | 03/15/23 10:39 PM
Row 158 | @praneeth.gayam@penske.com updated the comments https://bitbucket.penske.com/projects/ARPROJ/repos/shoptalkreg-web/pull-requests/4/diff#pom.xml | Mahipal | 03/09/23 7:33 PM
| @mahipal.podduturi@penske.com , We have implemented the suggestions mentioned in the comment. Please check. | Gayam | 03/12/23 9:42 PM
Row 158 | @shane.myers@penske.com , Could you please review this app at https://bitbucket.penske.com/projects/ARPROJ/repos/shoptalkreg-web/pull-requests/4/overview | Gayam | 03/07/23 6:35 AM
Row 158 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:31 AM
Row 158 | @shane.myers@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 3:46 AM
Row 159 | Per Rafiq on 11/18/22 - Obsolete. There are other sics war/batch active | Yvette Urso | 11/19/22 12:50 AM
Row 160 | Post reverting the dlink_filter changes, we've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD. | Sreekanth | 07/05/23 7:32 PM
Row 160 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD but waiting on dlink-filter.jar PROD deployment by Architect team. | Sreekanth | 06/08/23 11:24 PM
Row 160 | @praneeth.gayam@penske.com As per the naming convention, all the apps in bitbucket follow a standard and the same name being used in bamboo plan as well. If possible, please change the name from "sic" to "sics-web" for https://bamboo.penske.com/browse/SCSBP-SICSW | Sreekanth | 04/24/23 8:43 PM
| @sreekanth.kancharla@penske.com , we completed the change for all the apps. Please verify. Thanks. | Gayam | 04/27/23 2:13 AM
| @praneeth.gayam@penske.com Thank you for making the naming corrections as same as bitbucket repo name for both build & deploy plans. Started using new deploy plan. Please delete old deploy plan. | Sreekanth | 04/27/23 7:01 PM
| @praneeth.gayam@penske.com We've started using the new deploy plan and good to delete the old deploy plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=132710402 | Sreekanth | 05/03/23 8:00 PM
| @sreekanth.kancharla@penske.com , Not sure whether deleting the old plans part of Log4j project. But I will check and confirm. | Gayam | 05/04/23 12:17 AM
| @sreekanth.kancharla@penske.com , Deleted the old deploy plan. | Gayam | 05/08/23 10:13 PM
Row 160 | @praneeth.gayam@penske.com We started testing this application and had some issues with dlinkfilter. The issue was resolved with the help of @hugo.scavino@penske.com by removing unwanted dependency "dom.jar". Post that we are getting issue with sessionvalidationfilter which @hugo.scavino@penske.com will be working on common solution. Only then we can resume the testing. The pending sessionvalidationfilter change does applies for all the web applications to proceed with environment agnostic web.xml. @kalrav.khamar@penske.com | Sreekanth | 03/20/23 9:12 PM
| @praneeth.gayam@penske.com The latest dlinkfilter changes are working fine for this app in DEV server. Once we complete the application-level testing, we'll post update. Meanwhile we are waiting on confirmation from @hugo.scavino@penske.com to deploy the changes to QA for further testing. | Sreekanth | 04/06/23 11:59 PM
Row 160 | @praneeth.gayam@penske.com The PR is merged to develop. CC: @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 2:26 AM
| Thanks @sreekanth.kancharla@penske.com . Could you please confirm the secrets too. | Gayam | 01/26/23 8:19 PM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. Most of the files are jsp & js. The 2 files that has password as a word are CPMApplication.java & CPUReportServlet.java In both these files the code is commented and not used. You are good to proceed with next steps. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 12:33 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (Cap)Maven | Gayam | 01/27/23 2:45 AM
| @sreekanth.kancharla@penske.com , There is a small change in the artifactid. So we changed and created the PR. Could you please merge. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/sics-web/pull-requests/5/overview | Gayam | 02/02/23 11:57 PM
| Thanks @sreekanth.kancharla@penske.com for merging the code. Can we go for the next step which is build & deploy plans onboarding and Dev deployment? | Gayam | 02/03/23 12:12 AM
| @praneeth.gayam@penske.com Sure, please proceed with dev plan build & deployment. @kalrav.khamar@penske.com | Sreekanth | 02/03/23 2:15 AM
| @sreekanth.kancharla@penske.com , Dev deployment is completed for this application Could you please verify. Thanks. @haribabu.challa@penske.com | Gayam | 02/07/23 2:13 AM
| @praneeth.gayam@penske.com Dev deployment completed means, was that through Bamboo? Please share the bamboo plan as I couldn't find any new plan for SICS under existing project https://bamboo.penske.com/browse/SCSBP | Sreekanth | 02/15/23 3:06 AM
| @sreekanth.kancharla@penske.com Following is the Bamboo plan. https://bamboo.penske.com/browse/SCSBP-SICSW yes. It is deployed through Bamboo. | Gayam | 02/16/23 2:47 AM
| @praneeth.gayam@penske.com We'll wait till we get the access to Bamboo plans. Meanwhile we are getting below issue when we access the DEV application. Error: Error 500: javax.servlet.ServletException: Filter [CPUSessionValidationFilter]: com.penske.apps.sics.ui.CPUSessionValidationFilter was found, but is corrupt: URL: https://web3dev.penske.com/sics/entry/ApplicationEntry?LoginUserID=600123805 | Sreekanth | 02/18/23 12:05 AM
| @sreekanth.kancharla@penske.com , for sics.war RBAC roles are updated. Please check the access now. | Gayam | 02/18/23 12:37 AM
| @praneeth.gayam@penske.com I'm still unable to view the new plans in bamboo under https://bamboo.penske.com/browse/SCSBP | Sreekanth | 02/22/23 8:42 PM
| @sreekanth.kancharla@penske.com , Following thing mentioned by @kalrav.khamar@penske.com in the email. "PTL-Admin-Development = Can execute Build Plans Once we’ve BB-Admin role, we will add eligible developers to this role." Because of this no one added to above roles. I am expecting this is the issue. @haribabu.challa@penske.com / @balu.mohan@penske.com | Gayam | 02/23/23 3:19 AM
| @praneeth.gayam@penske.com My name is also available under BB-Admin role but still I'm unable to view the bamboo plan. If admin doesn't have the access, how can he/she provide access to developers. | Sreekanth | 02/23/23 3:32 AM
| @sreekanth.kancharla@penske.com , As discussed BB-Admin role is only bitbucket projects. We sent an email to respective person to add the provided users to the requested role. We will let you know once it is completed. | Gayam | 02/25/23 12:17 AM
| @praneeth.gayam@penske.com We got access to new bamboo plans but we are unable to add a "Plan branch". Please check and do the need. | Sreekanth | 03/13/23 10:14 PM
Row 160 | @kalrav.khamar@penske.com / @sreekanth.kancharla@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:57 AM
Row 160 | @rafiq.melath@penske.com / @sreekanth.kancharla@penske.com, This is a web application but when we check the targeted folder it contains jee-resources and batchconfig properties files for each environment. Usually these 2 files are exist for batch apps only. Could you please check and clarify us whether these are required or not. Also, there is a extra file sicsbatch.properties in targeted folder. Please check whether this file is required. Thanks. @mathumala.nachiappan@penske.com / @hugo.scavino@penske.com | Gayam | 12/17/22 2:05 AM
| @praneeth.gayam@penske.com All the 3 files jee-resources, batchconfig properties, sicsbatch.properties are not required. CC: @kalrav.khamar@penske.com @rafiq.melath@penske.com | Sreekanth | 12/22/22 12:12 AM
| Thanks @sreekanth.kancharla@penske.com . We will make the changes accordingly. @mathumala.nachiappan@penske.com | Gayam | 12/22/22 3:04 AM
Row 160 | @mathumala.nachiappan@penske.com Moved to CAP Bitbucket status - Did you create a Footprints ticket for the Bitbucket Team (plus @hugo.scavino@penske.com ) | Yvette Urso | 12/15/22 2:17 AM
| @yvette.urso@penske.com - CAP is able to rectify this issue and this is in Maven stage now.. So moving to (Cap) Maven. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/15/22 10:14 AM
Row 160 | facing SVN to BB migration issue @kalrav.khamar@penske.com . Looking forward to discuss with Architecture team regd. permission issues from SVN or BB. Planned for Monday. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 8:45 PM
Row 161 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD. | Sreekanth | 07/05/23 7:32 PM
Row 161 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD but waiting on dlink-filter.jar PROD deployment by Architect team. | Sreekanth | 06/08/23 11:24 PM
Row 161 | @praneeth.gayam@penske.com As per the naming convention, all the apps in bitbucket follow a standard and the same name being used in bamboo plan as well. If possible, please change the name from "sicsbatch" to "sics-batch" for https://bamboo.penske.com/browse/SCSBP-SICSB | Sreekanth | 04/24/23 8:42 PM
| Sure @sreekanth.kancharla@penske.com , We will check and get back to you. | Gayam | 04/25/23 1:17 AM
| @praneeth.gayam@penske.com I do see the changes made in bamboo plans. Thank you. Appreciate if you could make similar changes to deploy plans as well for all 3 SICS apps. | Sreekanth | 04/25/23 6:17 PM
| Sure @sreekanth.kancharla@penske.com . We are in the process of doing all the changes. | Gayam | 04/26/23 1:21 AM
| @sreekanth.kancharla@penske.com , we completed the change for all the apps. Please verify. Thanks. | Gayam | 04/27/23 2:14 AM
| @praneeth.gayam@penske.com Thank you for making the naming corrections as same as bitbucket repo name for both build & deploy plans. Started using new deploy plan. Please delete old deploy plan. | Sreekanth | 04/27/23 7:01 PM
| @praneeth.gayam@penske.com We've started using the new deploy plan and good to delete the old deploy plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=132710401 | Sreekanth | 05/03/23 8:03 PM
| @sreekanth.kancharla@penske.com , Deleted the old deploy plan. | Gayam | 05/08/23 10:14 PM
Row 161 | @praneeth.gayam@penske.com This application is deployed in QA and verified the logs. The logs are printing fine. We'll continue the integration testing of SICS Web, Service & Batch apps and post update. @kalrav.khamar@penske.com | Sreekanth | 04/07/23 12:00 AM
Row 161 | @sreekanth.kancharla@penske.com , As the PR merged we onboarded this application to bamboo. Following is the URL. https://bamboo.penske.com/browse/SCSBP-SICSB Please run the 'develop' branch to onboard the deploy plan. We can't onboard the deploy plan because if we onboard it automatically deploys it to QA as this is the batch app there is no Dev environment. As per Hugo, Log4j team can't deploy to QA. Thanks. | Gayam | 02/04/23 12:44 AM
| @praneeth.gayam@penske.com Thank you. We can't deploy the application to QA. Since no DEV environment for batch app, we need to test the changes in local first. @kalrav.khamar@penske.com | Sreekanth | 02/04/23 3:48 AM
| Sure @sreekanth.kancharla@penske.com . Changed the status to (AO)Bamboo Review. We will wait for your confirmation. | Gayam | 02/07/23 12:01 AM
| @praneeth.gayam@penske.com We've no access to bamboo plan. Please grant the access. | Sreekanth | 02/15/23 3:11 AM
| @sreekanth.kancharla@penske.com , We sent an email to AO Manager and other team to get the details about whom we need to add different Admin RBAC groups. Devops team decided that they are not going to provide the individual accesses. So could you please respond to that email. Once we add the team members to different RBAC groups, depends on the permissions members will see the build plans. | Gayam | 02/15/23 7:02 AM
| @praneeth.gayam@penske.com Please provided access to have Add Plan branch option on all the new bamboo plans. We don't have access to the plans created as part of this log4j migration. For any other new apps, we are getting the access to add the Plan branch by default. Please check with Architect team on this and do the need. | Sreekanth | 03/16/23 12:57 AM
| There is a discussion going on this in the email. | Gayam | 03/17/23 3:00 AM
Row 161 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:58 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. Most of the files are mybatis files. We are good to proceed with next steps. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 12:35 AM
Row 161 | @praneeth.gayam@penske.com - Changing the status to (AO) Maven as the PR is raised | Mathumala Nachiappan | 12/19/22 8:23 PM
| @praneeth.gayam@penske.com The PR is merged to develop. CC: @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/26/23 2:27 AM
| Thanks @sreekanth.kancharla@penske.com . Could you please check the secrets and confirm. | Gayam | 01/26/23 8:11 PM
Row 161 | @rafiq.melath@penske.com / @kalrav.khamar@penske.com , Log4j and maven changes are completed by log4j team. Could you please review the below PR and merge. https://bitbucket.penske.com/projects/ITFIS/repos/sics-batch/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/16/22 3:11 AM
Row 162 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD. | Sreekanth | 07/05/23 7:32 PM
Row 162 | We've tested this app in QA with new log4j2 and everything works fine. We are ready to deploy this in PROD but waiting on dlink-filter.jar PROD deployment by Architect team. | Sreekanth | 06/08/23 11:24 PM
Row 162 | @praneeth.gayam@penske.com As per the naming convention, all the apps in bitbucket follow a standard and the same name being used in bamboo plan as well. If possible, please change the name from "sicssvc" to "sics-service" for https://bamboo.penske.com/browse/SCSBP-SICSSVCP | Sreekanth | 04/24/23 8:43 PM
| @sreekanth.kancharla@penske.com , we completed the change for all the apps. Please verify. Thanks. | Gayam | 04/27/23 2:14 AM
| @praneeth.gayam@penske.com Thank you for making the naming corrections as same as bitbucket repo name for both build & deploy plans. Started using new deploy plan. Please delete old deploy plan. | Sreekanth | 04/27/23 7:01 PM
| @praneeth.gayam@penske.com We've started using the new deploy plan and good to delete the old deploy plan. https://bamboo.penske.com/deploy/viewDeploymentProjectEnvironments.action?id=129728520 | Sreekanth | 05/03/23 7:59 PM
| @sreekanth.kancharla@penske.com , Deleted the old deploy plan. | Gayam | 05/08/23 10:14 PM
Row 162 | @kalrav.khamar@penske.com , We have completed the secrets scanning on this app and we observed all are false positives. I sent an email with all of your secrets. Could you please check the secrets and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/25/23 1:58 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 12:36 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the status to (AO)Maven as MR is already created and provided in above comment. | Gayam | 01/27/23 2:47 AM
| @praneeth.gayam@penske.com The MR is merged and good to proceed with next steps. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 7:43 PM
| Thanks @sreekanth.kancharla@penske.com . We will onboard to Bamboo and will deploy to dev. Please confirm whether you are ok for the Dev deployment. @mathumala.nachiappan@penske.com | Gayam | 01/27/23 8:01 PM
| @praneeth.gayam@penske.com We should be good with the Dev deployment of this application. Please share the Bamboo plan details once it is available. @mathumala.nachiappan@penske.com @kalrav.khamar@penske.com | Sreekanth | 01/27/23 8:11 PM
| @sreekanth.kancharla@penske.com , Dev deployment is completed. Following is the Bamboo URL. https://bamboo.penske.com/browse/SCSBP-SICSSVCP Please validate dev. Thanks. | Gayam | 02/04/23 12:36 AM
| @praneeth.gayam@penske.com Seems we need to access to the new bamboo plans. Please grant the access. | Sreekanth | 02/04/23 3:49 AM
| @sreekanth.kancharla@penske.com , You need to be added to one of the admin RBAC group. I sent an email to admin group few days back whom to be added to the different groups. Waiting fthe response. | Gayam | 02/06/23 11:49 PM
Row 162 | @rafiq.melath@penske.com / @kalrav.khamar@penske.com , Log4j team completed log4j and maven changes. Could you please review them in below PR and merge. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/sics-service/pull-requests/3/overview @mathumala.nachiappan@penske.com | Gayam | 12/17/22 3:05 AM
Row 163 | Decision is to retire these applications | Yvette Urso | 05/01/23 9:17 PM
Row 163 | @scott.bortzel@penske.com / @scott.pemrick@penske.com , For this application both SVN and Bamboo are not available. Could you please let us know the SVN and Bamboo details. Thanks. | Gayam | 01/14/23 1:06 AM
| @scott.bortzel@penske.com / @scott.pemrick@penske.com , Could you please provide the response to above question. Thanks. @hugo.scavino@penske.com / @yvette.urso@penske.com | Gayam | 03/24/23 10:51 PM
Row 164 | Query: @sreenivasa.papannagari@penske.com , In this application build folder having sos_specificbuild.xml. The build is including dispatcher-servlet.xml on environment basis. how to implement this in environment agnostic build as we don't have separate builds for each environment. | Gayam | 07/25/23 12:06 AM
Row 164 | @shawn.mcmurtry@penske.com , This app depends on the sosutility.jar . Sosutility having the svn repo . Can we continue to migrate sosutility also ? https://svn.penske.com/svn/fieldsys/other/sos-service/tags/prod/2023-05-04/SosUtility/ There are other apps soservice.war and 24*7custnotify also depend on Sosutility jar. | Gayam | 05/18/23 10:57 PM
| @david.long@penske.com confirmed to create a separate repo and Bamboo plan for sosutility. We will take up this app for migration once Sosutiloity work completed. Thanks. | Gayam | 06/12/23 7:42 AM
Row 164 | I have validated the secretes , looks good for me ... except these 3 build_script/prod.properties build_script/dev.properties build_script/qa.properties. Remaining all are not secrets. | Sreenivasa | 06/09/23 7:30 PM
| Thanks @sreenivasa.papannagari@penske.com . We will remove build_script folder while doing the mavanization. | Gayam | 06/12/23 7:37 AM
Row 164 | Secrets: @shawn.mcmurtry@penske.com , adding to above question, I sent the secrets of this app in an email. Please check. | Gayam | 06/02/23 1:53 AM
Row 165 | Query: @sreenivasa.papannagari@penske.com / @stella.george@penske.com , We have following queries in this application. 1.Targeted folder contains different sosProperties.properties files for different environments. These properties are referred in web.xml and InitializationServlet. The main difference is upload path Production UploadPath = \\GRNHILLS/ROOT/applications/pcard/ Qa UploadPath = \\QAGH/ROOT/applications/pcard/) 2.Targeted folder contains different web.xml files for different environments. In environment agnostic build there will be no separate builds for each environment. But it seems above files are environement specific. Could you please check and resolve this issue. Thanks. | Gayam | 07/25/23 12:16 AM
Row 165 | Verified the secrets, I don't see any PI data hardcoded in the code.. most of them are getting from back end(DB). So we should be ok with it. | Sreenivasa | 06/15/23 10:56 PM
| Thank you. | Gayam | 06/16/23 1:13 AM
Row 165 | @stella.george@penske.com / @sreenivasa.papannagari@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:52 AM
Row 166 | @david.long@penske.com , This app is ready for review. Please check and merge the PR. https://bitbucket.penske.com/projects/MAIN/repos/sosservice/pull-requests/3/overview | Gayam | 08/08/23 11:25 PM
Row 166 | Responded to the email! THanks! | David | 07/18/23 2:19 AM
| Thanks @david.long@penske.com | Gayam | 07/18/23 9:56 PM
Row 166 | Secrets: @david.long@penske.com , @falgun.patel@penske.com , I sent the secrets file of this app in an email. Please check and confirm. Thank you. | Gayam | 07/18/23 1:29 AM
Row 166 | @praneeth.gayam@penske.com Yes please create a separate repo and bamboo plan for sos utility. I believe this also addresses some other wars that were pending this question. | David | 06/09/23 6:20 PM
| Sure @david.long@penske.com . I will request @yvette.urso@penske.com to create new line item in smartsheet for sosutility jar. Thanks. | Gayam | 06/10/23 1:49 AM
Row 166 | @shawn.mcmurtry@penske.com , In this application prod reference in Bamboo is having 2 folder sos-service and sos-utility folders. Expecting sos-utility is a dependency jar and sos-service is the orginal application. Following are the 2 folders. Could you please check and confirm whether our expectation is correct or not. https://svn.penske.com/svn/fieldsys/other/sos-service/tags/prod/2023-05-04/sos-service/ https://svn.penske.com/svn/fieldsys/other/sos-service/tags/prod/2023-05-04/SosUtility/ | Gayam | 05/10/23 11:15 PM
| @praneeth.gayam@penske.com That is correct. sos-service is the original application, and the sos-utility is a dependency jar containing objects for sos service. | David | 06/06/23 10:09 PM
| Thanks @david.long@penske.com for the response. Not only sosservice but also 24x7custnotif, sos.war apps are depend on SosUtility jar. Can we extract SosUtility and create separate repo and bamboo plan? | Gayam | 06/07/23 3:33 AM
| Yes, but I would investigate the nature of the sos utility jar first among the other apps. I checked the 24x7 cust notif batch and the only place it uses the sosUtility jar is to call the spring remoting method: getRoadReportPDF. The batch does not make use of any objects from the utility. So, if the getRoadReportPDF was updated to a restful method in sos service, the batch would only need to call the restful service and we would be able to remove the sos utility jar as a dependency for the 24x7 cust notif batch | David | 06/07/23 4:49 AM
| Sure @david.long@penske.com . Let us know whether we need to create a separate repo and bamboo plan for sosutility. | Gayam | 06/08/23 7:55 AM
Row 167 | @praneeth.gayam@penske.com I found the Bitbucket build, but I don't have access to it, so I'm getting access and then will confirm that it's up on artifactory | David | 07/11/23 1:31 AM
| @david.long@penske.com , We referred a different source repo for this app. We are reworking on this app as each application's prod reference have different sosutility folders. Trying to compare all these and we will ask the question if there are any differences. Thanks. Changing the status of the app to Cap. | Gayam | 07/11/23 6:53 AM
| Thanks for the update @praneeth.gayam@penske.com Keep me posted if there are any questions | David | 07/11/23 7:30 PM
| @david.long@penske.com , All the changes are completed and deployed to artifactory. Following is the bamboo build. https://bamboo.penske.com/chain/viewChain.action?planKey=SOSSBP-SOSUTIL | Gayam | 07/13/23 2:12 AM
Row 167 | @david.long@penske.com , This is onboarded to Bamboo and deployed to artifactory. Please check and confirm. Thanks. | Gayam | 07/07/23 1:34 AM
| Sorry for the delay. What's the bamboo build URL? I can't seem to find it @praneeth.gayam@penske.com | David | 07/11/23 1:26 AM
Row 167 | Review: @david.long@penske.com / @falgun.patel@penske.com , This app is ready for your review. Please check and merge. https://bitbucket.penske.com/projects/MAIN/repos/sosutility/pull-requests/2/overview | Gayam | 06/28/23 2:53 AM
| @praneeth.gayam@penske.com I reviewed the PR and merged it into the develop branch! Thanks! | David | 07/04/23 2:51 AM
| Thanks @david.long@penske.com . We will onboard to bamboo and let you know. | Gayam | 07/06/23 3:10 AM
Row 167 | No secrets found on this jar. So changing the status to Cap Maven | Gayam | 06/23/23 12:16 AM
Row 167 | Hi Yvette, I wanted to bring to your attention that the shared jar "sosutility" requires a new repository and a bamboo build. This jar is utlized by three Maintenance apps: 24x7custnotif, sosservice and sos.war. David has confirmed the need to create a separate repository and Bamboo build for "sosutility" and it also requires to implement all modernization steps. Therefore I kindly request you to include a new line item "sosutility" in the smartsheet. Thanks, Praneeth | Yvette Urso | 06/12/23 9:11 PM
Row 168 | they are false positives and no code change is required, please proceed. | Vaddi Mani | 07/31/23 8:39 PM
| Thank you | Gayam | 08/01/23 12:36 AM
Row 168 | Secrets: @dale.porter@penske.com / @sarath.mani@penske.com , I sent secrets file in an email. Please verify. Thanks. | Gayam | 07/21/23 10:48 PM
Row 168 | I checked the last production build and see it was part of that release. Yes, it needs to be modernized as well Thank you. | Dale Porter | 06/24/23 1:01 AM
| Thanks @dale.porter@penske.com . | Gayam | 06/27/23 3:43 AM
Row 168 | @stella.george@penske.com / @dale.porter@penske.com , This application having multiple src folders . We are expecting that Penske-spelling-service folder is the original source which builts spellingservice.war and other folder(Penske_Spelling_Utility) is the dependency jar. SVN Location: https://svn.penske.com/svn/fieldsys/maintenance/Penske-Spelling-Service/tags/prod/prod_2012-08-14/ penske_spellingutility jar build plan: https://bamboo.penske.com/browse/PNSKESPLNGBP-PNSKESPLINGUTLYPROD spellingservice.war application bamboo : -https://bamboo.penske.com/browse/PNSKESPLNGBP-PNSKESPLINGSVCPROD Following are the 2 suggestions. 1. Build a new repo for penske_spellingutility folder and mavanize and create a new bamboo plan which builds the jar and uploads to artifactory. Then spellingservice.war application uses that jar as a dependency in pom. 2. If penske_spellingutility folder is not a shared jar then AO can include that folder inside the spellingservice.war application. Then no need of separate repo and bamboo plan for the penske_spellingutility . Please verify and confirm. Thanks. @shane.myers@penske.com | Gayam | 06/03/23 12:35 AM
| @praneeth.gayam@penske.com Pensk_spellingutility is a shared jar. you should go with option1 | Stella george | 06/14/23 2:01 AM
| Thanks @stella.george@penske.com . We are also seeing another folder Penske_Spelling_ClientJar and the bamboo build for this is https://bamboo.penske.com/browse/PNSKESPLNGBP-PNSKESPLINGPROD Is this dependency also needs to modernized? | Gayam | 06/21/23 2:23 AM
Row 169 | @praneeth.gayam@penske.com Can you please deploy suspended ticket portal on Dev | Venkatesh | 08/03/23 2:53 AM
| @venkatesh.hossalinever@penske.com , looks like dev deployment is completed yesterday. Please check. https://bamboo.penske.com/browse/SUSP-SSPT0/deployments | Gayam | 08/04/23 12:57 AM
Row 169 | Web Dev looking good with Log4j & Maven changes. We will proceed with QA deployment and keep you posted. | Nayum | 07/19/23 6:47 PM
Row 169 | @praneeth.gayam@penske.com @venkatesh.hossalinever@penske.com Retrofitted Recent PBT-567 (deployed) Changes to Develop_Log4J branch. I've submitted a pull request to push to develop branch. | Hernandez | 07/10/23 11:45 PM
| @nicolas.hernandez@penske.com , I believe changes are application specific and not related to modernization project. Do you want to deploy your changes and modernization changes to prod together? If yes, please review with your peer. Thanks. | Gayam | 07/11/23 11:37 PM
| @praneeth.gayam@penske.com Yes, we are intending to push the changes from PBT-567 with the modernization changes. | Hernandez | 07/13/23 1:44 AM
| Sure @nicolas.hernandez@penske.com . Please work with your team and merge the PR. | Gayam | 07/13/23 3:07 AM
Row 169 | @shilpaashok.rane@penske.com , Build plan and deploy plan of this app onboarded successfully. Also, deployment to dev is completed. Pelase verify. Thanks. | Gayam | 06/13/23 2:09 AM
Row 169 | Review: @shilpaashok.rane@penske.com This app is ready for AO review. Please check at https://bitbucket.penske.com/projects/ARPROJ/repos/ssptktportal-web/pull-requests/3/overview Thanks. | Gayam | 04/25/23 1:07 AM
| @praneeth.gayam@penske.com Code changes has been merged. Please deploy the application on dev. | Venkatesh | 06/08/23 8:02 PM
| We will onboard to Bamboo and will let you know. | Gayam | 06/09/23 1:38 AM
Row 169 | We have verified the secrets shared in the email, some are key events in jsp and js files. Some of the values used in UI. And they are not secret or confidential info. So no change required. | Rane | 04/10/23 6:06 PM
| Thanks @shilpaashok.rane@penske.com . We will work on the next step. | Gayam | 04/11/23 8:39 AM
Row 169 | Secrets: @dylan.price@penske.com / @william.spohn@penske.com , I have shared the secrets in the email. Please check and confirm. | Gayam | 03/24/23 12:05 AM
Row 169 | the bamboo build for this is https://bamboo.penske.com/browse/SUSP-SUSPPROD and the repo is https://svn.penske.com/svn/webprojects/admin/suspendedticketsportal/trunk/STP_Web | Dylan | 03/07/23 2:05 AM
| Thank you. Changed the app status to Cap Log4j | Gayam | 03/08/23 12:06 AM
Row 169 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 169 | Moved to AO Bamboo status | Yvette Urso | 12/15/22 2:49 AM
Row 169 | Hi @sam.skelding@penske.com - we couldnt trace the Bamboo key and the Repo url for this applicaiton. Pls. share those details. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 12:01 PM
Row 170 | We have prepared documents to deploy this on 08/03/2023 | Dylan | 08/02/23 7:10 PM
| Thanks @dylan.price@penske.com . Please let me know once it is deployed. i will change the status to Done. | Gayam | 08/03/23 12:42 AM
Row 170 | Hi @praneeth.gayam@penske.com Nicolas will be deploying his changes for StopBilling with Maven/log4j2. There is no other work for Capgemini team that needs completed. Thank you! | Dylan | 07/10/23 8:22 PM
Row 170 | @praneeth.gayam@penske.com I pushed my changes to dev. everything in develop looks good on my end. Are you able to build develop? | Hernandez | 05/22/23 6:43 PM
| @nicolas.hernandez@penske.com , Develop branch build is successful and it is deployed to dev environment. https://bamboo.penske.com/browse/STOPBILLINGBP-STOPBILL0/deployments Please verify in Dev. | Gayam | 05/22/23 10:03 PM
| @praneeth.gayam@penske.com I am not seeing the changes made from old log4j in dev. I made changes and merged to 'develop' branch. | Hernandez | 05/22/23 10:51 PM
| @nicolas.hernandez@penske.com , Could you please verify now. We changed the artifactid to stopbilling. Hope it works now. Thanks. | Gayam | 05/24/23 1:28 AM
| @praneeth.gayam@penske.com I've verified the changes are now on dev. Thank you. Is QA bamboo plan ready? | Hernandez | 05/24/23 2:17 AM
| @nicolas.hernandez@penske.com , QA deploy plan is already ready. | Gayam | 05/25/23 2:42 AM
Row 170 | @praneeth.gayam@penske.com , There are two changes I made to the XML file to get log4j2 running: 1. Added a <Loggers> tag and added <Root> tag inside (Error in console gone) 2. SMTP Apender syntax error (Error in console) Also noticed that log4j2 is creating a new log file after each mvn clean build. Is that happening on your end? We can setup a discussion for further details. I made code changes to the application to remove old log4j properties and configuration. Please Review | Hernandez | 05/18/23 6:54 PM
Row 170 | @praneeth.gayam@penske.com Thanks. Nicolas validated changes in his local and he is not able to see the logs getting generated in his local. Also on dev server the logs are not rolling when he tested the changes. Error from his local system: [5/15/23 15:13:25:015 EDT] 0000004f SystemOut O 2023-05-15 15:13:25,015 server.startup : 0 ERROR Unknown object "Root" of type org.apache.logging.log4j.core.config.LoggerConfig is ignored: try nesting it inside one of: ["Appenders", "Loggers", "Properties", "Scripts", "CustomLevels"]. [5/15/23 15:13:25:017 EDT] 0000004f SystemOut O 2023-05-15 15:13:25,016 server.startup : 0 WARN No Loggers were configured, using default. Is the Loggers element missing? | Venkatesh | 05/16/23 12:45 AM
| @venkatesh.hossalinever@penske.com , As discussed in the call, one of the log4j team member able to build the app successfully in local using billing settings. | Gayam | 05/18/23 1:02 AM
Row 170 | @praneeth.gayam@penske.com We will using ARPROJ repo. Please deploy develop_log4j changes on dev environment. | Venkatesh | 05/10/23 1:06 AM
| @venkatesh.hossalinever@penske.com We will do that and will let you know. | Gayam | 05/11/23 6:41 AM
| @venkatesh.hossalinever@penske.com , Onboarded develop_log4j to bamboo and deployed to Dev. Please verify https://bamboo.penske.com/browse/STOPBILLINGBP-STOPBILL1/deployments | Gayam | 05/11/23 11:23 PM
Row 170 | @venkatesh.hossalinever@penske.com / @mark.weaver@penske.com , We observed there is a new repo created for stopbilling recently. Following is the repo details. https://bitbucket.penske.com/projects/PBJB/repos/stopbilling-web/browse?at=refs%2Fheads%2Ffeature%2FPBT-141-Cancel-Code-Feature But we already create a repo for this application and mavanized. Repo which we created is https://bitbucket.penske.com/projects/ARPROJ/repos/stopbilling-web/browse?at=refs%2Fheads%2FDevelop_Log4j Do you know why there is a new repo created? | Gayam | 04/07/23 12:02 AM
Row 170 | Review: @venkatesh.hossalinever@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/stopbilling-web/pull-requests/3/overview | Gayam | 03/18/23 1:08 AM
Row 170 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 2:02 AM
| Thank you. Changed the status to Cap Maven | Gayam | 03/02/23 2:02 AM
Row 170 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 170 | @rafiq.melath@penske.com / @mark.weaver@penske.com , We completed the secrets scanning on this application and found that all are false positives. I will send the sheet to you in the email. Could you please check and confirm. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/10/23 12:39 AM
Row 171 | This application is no longer needed and no modernization effort is required on this. | Sherin | 04/21/23 12:09 AM
Row 171 | @sherin.basheer@penske.com , There are no secrets found in this app. So we completed log4j/maven work. Please review at https://bitbucket.penske.com/projects/ARPROJ/repos/synchghdbc-batch/pull-requests/3/overview | Gayam | 03/02/23 3:11 AM
Row 171 | production source code is decompiled and checked in to svn. Branch prod should be used for new changes. | Sherin | 02/18/23 12:42 AM
| Thanks @sherin.basheer@penske.com . Changing the status to (Cap)Log4j | Gayam | 02/18/23 1:03 AM
| @sherin.basheer@penske.com , As discussed in the chat, we are are making SqlMapClientCallback empty args and this.val$emplist will be replaced with emplist. Also, we will provide this info in Reamdeme file. Thanks. | Gayam | 02/22/23 3:20 AM
Row 171 | I will get back to you on the question on which branch to work on. | Sherin | 02/14/23 12:47 AM
Row 171 | This application can go under Architecture commons. https://bitbucket.penske.com/projects/ARPROJ. Bamboo plan should match application name. | Sherin | 02/14/23 12:44 AM
Row 171 | @sherin.basheer@penske.com , Unable to find bamboo build plans. Bamboo build plans required for prod reference. Following are the Svn and respective branches info. https://svn.penske.com/svn/architecture/general/synchghdbc/ dev_gh/ offshore_pol/ (This is the Latest branch. Last modifications done in May-6-2014 ) qa/ @mathumala.nachiappan@penske.com | Gayam | 11/26/22 1:59 AM
| @sherin.basheer@penske.com , Adding to above question, as there is no existing bamboo build, under which project we need to create new bamboo specs? | Gayam | 01/11/23 9:25 AM
| Yes application is very old and there is no bamboo plan existing for this. Please create new one. | Sherin | 02/01/23 12:53 AM
| Question: @sherin.basheer@penske.com , We have 2 questions on this application. 1. There is no old bamboo build. So we are not sure what is the latest branch deployed to production. Could you please let us know on what branch we need start working on modernization. 2. For the new build plans in Bamboo, do you want to create a new project. If so please suggest the name. Or do you want us to create under any other Arch project? If so, under which project we need to create? Thanks. @haribabu.challa@penske.com @mathumala.nachiappan@penske.com | Gayam | 02/02/23 11:15 PM
Row 171 | @mathumala.nachiappan@penske.com moved to AO Bamboo Review. | Yvette Urso | 12/15/22 2:38 AM
Row 172 | @ravi.daram@penske.com / @krishna.tanga@penske.com , We sent a secret file to you for this app and it looks like all are false positives. Could you please check and confirm. Thanks. | Gayam | 01/25/23 11:41 PM
Row 173 | I'll be looking at this next. Hope to have an update soon. | David Graf | 02/09/23 12:01 AM
Row 173 | @praneeth.gayam@penske.com per @david.w.graf@penske.com - he will work on this when he returns to the office. Please keep status as is. | Yvette Urso | 01/24/23 8:20 PM
Row 173 | Moved to AO Code Work | Yvette Urso | 12/15/22 2:38 AM
Row 173 | I am hoping to work on this next week. | David Graf | 12/09/22 1:39 AM
Row 173 | @praneeth.gayam@penske.com @mathumala.nachiappan@penske.com Moved to Cap Blocked since Capgemini is blocked from moving forward, not the AO. | Yvette Urso | 12/01/22 8:42 PM
| yes @yvette.urso@penske.com . Thanks! | Mathumala Nachiappan | 12/02/22 5:50 PM
Row 173 | @david.w.graf@penske.com - Hope you progressed on this. Pls. share the present status | Mathumala Nachiappan | 11/30/22 3:17 PM
| I have not made progress since my last update. I'm working on a production deploy and will resume this after I am finished. | David Graf | 11/30/22 7:27 PM
Row 173 | I attempted to confirm the dev deploy but ran into an issue with the datasource. This is something that I need to work on from my end. | David Graf | 11/17/22 1:33 AM
Row 174 | @praneeth.gayam@penske.com it is already on boarded bambboo now is Faling build as well https://bamboo.penske.com/browse/TLMSBP-TLMS2-BLD-1 | Mahipal | 05/16/23 7:56 PM
| @mahipal.podduturi@penske.com , The PR is not yet merged. That is the reason it is failing. Please review and merge. https://bitbucket.penske.com/projects/ARPROJ/repos/telematicssvc-web/pull-requests/4/overview | Gayam | 05/17/23 2:10 AM
Row 174 | can you do | Mahipal | 05/16/23 7:48 PM
Row 174 | yes | Mahipal | 05/16/23 7:48 PM
Row 174 | @praneeth.gayam@penske.com can you mark this to complete | Mahipal | 05/04/23 7:13 PM
| @mahipal.podduturi@penske.com , Do you mean go to next step which is Bamboo onboarding? | Gayam | 05/05/23 6:15 AM
Row 174 | tested the application working as excepted. | Mahipal | 05/04/23 7:12 PM
Row 174 | @praneeth.gayam@penske.com can you deploy the devlop_log4j branch to dev | Mahipal | 04/03/23 10:02 PM
| @mahipal.podduturi@penske.com , telematicssvc.war - build & Deploy plan onboarding completed and dev deployment done from develop_log4j branch. Please verify. https://bamboo.penske.com/browse/TLMSBP-TLMS/deployments | Gayam | 04/04/23 11:19 PM
Row 174 | PR for this is https://bitbucket.penske.com/projects/ARPROJ/repos/telematicssvc-web/pull-requests/4/overview | Gayam | 04/03/23 9:41 PM
Row 174 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:31 AM
Row 174 | @shane.myers@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 3:50 AM
Row 175 | @sreekanth.kancharla@penske.com , Could you please merge the below PR. https://bitbucket.penske.com/projects/ITFIS/repos/tririga-integrations-batch/pull-requests/2/overview Then review the below PR. https://bitbucket.penske.com/projects/ITFIS/repos/tririga-integrations-batch/pull-requests/3/overview | Gayam | 07/13/23 8:53 AM
| @praneeth.gayam@penske.com Both PRs are merged. Please proceed with Bamboo plan configuration. | Sreekanth | 07/13/23 7:21 PM
| Sure @sreekanth.kancharla@penske.com . Thanks | Gayam | 07/14/23 12:34 AM
| @sreekanth.kancharla@penske.com , It is onboarded to Bamboo. Please deploy to QA. https://bamboo.penske.com/browse/TRGBP-TRIGBCH/deployments | Gayam | 07/15/23 1:34 AM
Row 175 | Question: @sreekanth.kancharla@penske.com , In this application TestMain.java has the main method. But the batchconfig file in this application referred to trinity.jar and the main class which is referred in batchconfig file exist in this jar. Could you please check and let us know which main class we need to use. Thanks. | Gayam | 06/16/23 3:04 AM
| @praneeth.gayam@penske.com I've checked the PROD deployed batchconfig.properties & it has the main class as "class=com.tririga.integration.InterfaceController" Please use the same. | Sreekanth | 06/26/23 6:37 PM
| Sure. Thank you. | Gayam | 06/27/23 3:15 AM
Row 175 | @sreekanth.kancharla@penske.com , this application has dependecy on following jars and need to upload them in artifactory 1.TririgaCustomTask.jar (groupid: com.tririga.pub, artifactid:TririgaCustomTask ) 2.trinity-dep.jar (after com which folder can i take) 3.trinity.jar (groupid: com.tririga, artifactid: trinity ) 4.PENSKE-test.jar (there is no folder structure to find the group id) PENSKE-test.jar, trinity-dep.jar groupid details. Could you please help us to get the groupid. All these jars are availabe in https://svn.penske.com/svn/webprojects/admin/Tririga_Batch/branches/qagh/Tririga/lib/ | Gayam | 02/01/23 1:20 AM
| @praneeth.gayam@penske.com 2.trinity-dep.jar (this jar has apache logger package, spring util package and others) This has all the dependencies which trinity.jar requires. We need to see whether we can eliminate this jar and include the dependencies such as log4j, spring etc. explicitly. If that works with no compiler errors, then we can test in QA. If application works with no issues, then we can remove this jar so no need to have any dependency. We can't create 1 group id for this jar as it has many packages in it. 4.PENSKE-test.jar - This jar does not have any files. By taking this out from build path, no compiler errors, so hope we can rid of this jar and that can be confirmed only after testing this application in QA. | Sreekanth | 02/01/23 3:41 AM
| Thanks @sreekanth.kancharla@penske.com . So are you going to work on eliminating both jars from the application? What about other jars? are you ok to upload? | Gayam | 02/01/23 3:45 AM
| @praneeth.gayam@penske.com We don't have any plans to remove the dependencies now. Can't that be taken care by your team and check for compiler errors. If we don't get any compiler errors, then we can deploy that app in QA and test later. We don't have DEV as this is batch app. | Sreekanth | 02/01/23 3:58 AM
| @sreekanth.kancharla@penske.com , We removed the dependencies and facing several issues in different files. There are approx 10-11 java files which are having error related to import statement. All import statement are from trinity.jar Following are sample 3 files. 1.FileTransferActivity.java 2.FTPActivity.java 3.FiletoDbtoApiActivity.java | Gayam | 02/03/23 12:56 AM
| @praneeth.gayam@penske.com Didn't we add trinity.jar (groupid: com.tririga, artifactid: trinity) to artifactory as you previously stated. | Sreekanth | 06/08/23 6:44 PM
| @sreekanth.kancharla@penske.com , Based on our previous discussions, I'm uncertain if we actually uploaded trinity jar to artifactory. I will debug with my team to check what is the status on this. Thanks. | Gayam | 06/09/23 1:34 AM
| @praneeth.gayam@penske.com Thank you, please change the "App Status" accordingly. | Sreekanth | 06/09/23 7:14 PM
| @sreekanth.kancharla@penske.com , let me summarize the required dependency jars from above chat. 1.TririgaCustomTask.jar (groupid: com.tririga.pub, artifactid:TririgaCustomTask ) 2.trinity.jar (groupid: com.tririga, artifactid: trinity ) 3. Ftp4j-1.9jar Please provide your approval to upload above jars to artifactory? | Gayam | 06/10/23 2:09 AM
| @praneeth.gayam@penske.com Please proceed. | Sreekanth | 06/13/23 2:14 AM
Row 175 | @charles.csoky@penske.com / @steve.mcmullen@penske.com , We completed the secrets scanning on this app and we found that there are true positives. I will send the file in the email. Could you please check and let us know whether you are planning mitigate the secrets. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 3:03 AM
| @praneeth.gayam@penske.com a. The password related secrets are fine as the properties file is being referred from specific location in QA & PROD servers which admins only can access. b. The file People_Inbound.xml – the provided secret is not available in QA & PROD code. CC: @mathumala.nachiappan@penske.com, @charles.csoky@penske.com | Sreekanth | 01/25/23 3:13 AM
| Thanks @sreekanth.kancharla@penske.com . Changed the App Status to (Cap) Maven | Gayam | 01/25/23 11:27 PM
Row 175 | @mathumala.nachiappan@penske.com Moved to the AO Log4j Status. | Yvette Urso | 12/15/22 2:18 AM
Row 175 | @charles.csoky@penske.com - Log4J1 dependency. @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/01/22 9:08 PM
Row 176 | Hi @manish.sisodiya@penske.com - Is this app duplicated with line # 122? CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/07/22 11:57 AM
Row 177 | Review: @dylan.price@penske.com , This app is ready for your review. Please check and merge. https://bitbucket.penske.com/projects/PBTCBOS/repos/trs-extract-batch/pull-requests/3/overview | Gayam | 07/10/23 11:45 PM
Row 177 | hi @praneeth.gayam@penske.com I will update the property file when I merge my changes with develop_log4j like I have done for other applications. Could you please start on log4j/maven changes? | Dylan | 06/13/23 5:17 PM
| Sure @dylan.price@penske.com | Gayam | 06/14/23 2:44 AM
Row 177 | @praneeth.gayam@penske.com found a violation with passwords in properties file. Will work on a solution to avoid these visible passwords. | Dylan | 03/30/23 9:27 PM
Row 177 | Secrets: @dylan.price@penske.com , secrets are shared in the email. Please check and confirm. Thanks. | Gayam | 03/24/23 12:00 AM
Row 177 | The trs_extract and trs_extract.jar are the same aplication. Please delete out the duplicate. | Dylan | 03/07/23 2:07 AM
| Thanks @dylan.price@penske.com . We will start working on it | Gayam | 03/07/23 11:48 PM
Row 177 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 177 | @dylan.price@penske.com - Have you checked for this? | Mathumala Nachiappan | 12/19/22 8:47 PM
Row 177 | Hi @manish.sisodiya@penske.com / @dylan.price@penske.com - There are 2 entries with the same name trs_extract. One is named as trs_extract and another is trs_extract.jar. Could you please check whether these 2 are same? @mathumala.nachiappan@penske.com , @yvette.urso@penske.com | Gayam | 12/16/22 12:19 AM
Row 177 | @mathumala.nachiappan@penske.com moved to Backlog due to missing comments with no information | Yvette Urso | 12/15/22 2:50 AM
Row 178 | @praneeth.gayam@penske.com , As the jar is currently being referenced by existing application, let's keep that jar in the build for now. | Patel | 07/28/23 12:47 AM
| @falgun.patel@penske.com , That mean do you want us to maually upload the coversheet jar to artifactory? | Gayam | 07/31/23 2:24 AM
Row 178 | Question: @david.long@penske.com , There is a coversheet jar in the lib folder of this app but without that jar also build is getting successful. Do you want us to upload this jar to artifactory and include that dependency in pom? | Gayam | 07/19/23 3:31 AM
Row 178 | Query: @david.long@penske.com , This application dependent on attachservice-client.jar(shared jar) latest version but the latest version is not available in artifactory. Old version is available in artifactory which is used by several other apps. The latest jar build is done by you from the below branch. SVN-URL: https://svn.penske.com/svn/fieldsys/other/attachment-service/ tags/qa/_T_QA-2022-06-16 Can we upload latest version to artifactory? | Gayam | 07/06/23 4:27 AM
| That may be a question for @stella.george@penske.com and @subramanian.vennimalayan@penske.com as they work with attachment service more than I do. I built that last year, but I'm sure some things have been changed since then | David | 07/06/23 7:27 PM
| @stella.george@penske.com / @subramanian.vennimalayan@penske.com , Could you please check the above comment and provide your response. Thanks. | Gayam | 07/07/23 12:16 AM
| @praneeth.gayam@penske.com please use the latest jar for attachment artifactory. | David | 07/11/23 1:28 AM
Row 178 | @praneeth.gayam@penske.com Emailed you back. no code changes are required as all secrets found were false positives. | David | 07/03/23 11:21 PM
| Thanks @david.long@penske.com . Chaning the status to Cap Maven. | Gayam | 07/03/23 11:23 PM
Row 178 | @david.long@penske.com / @falgun.patel@penske.com , I sent the secrets to you in the email. Please analyze and let me know wether this requires any code changes. Thanks. | Gayam | 07/03/23 11:14 PM
Row 178 | @praneeth.gayam@penske.com This is still in the "waiting on AO" status. Is there something I need to address? yea the attach svc client jar may already be in artifactory. | David | 06/09/23 6:21 PM
| @david.long@penske.com , Do we need to modernize the UnitJacket_ATTACHSVCCLIENT_JAR (Jar repo)- https://svn.penske.com/svn/fieldsys/other/attachment-service/Jar/prod too? | Gayam | 06/10/23 2:06 AM
| I don't think you need to. To my knowledge the attachment svc client jar is already on artifactory which means it should be running on maven, but I'm not totally sure. If it's not, then yes the attach svc client jar would need to be modernized | David | 06/15/23 1:33 AM
| Sure @david.long@penske.com . We will check and come back to you. | Gayam | 06/15/23 1:50 AM
| @david.long@penske.com , We found the dependency in artifactory. We will use this dependency in unitjkt. <dependency> <groupId>com.penske.mis.common.sharedlib</groupId> <artifactId>attachservice-client</artifactId> <version>1.0.0-20210310.061729-1</version> </dependency> | Gayam | 06/16/23 1:06 AM
| @david.long@penske.com , As indicated in the comment of 'servicereqweb.war' app, the penske team is doing the modernization of attachservice-client jar. So, we will be including the following dependency in the unitjkt.war. <dependency> <groupId>com.penske.mis.common.sharedlib</groupId> <artifactId>attachservice-client</artifactId> <version>1.0.0-20210310.061729-1</version> </dependency> | Gayam | 06/19/23 7:59 PM
| Sounds good thank you @praneeth.gayam@penske.com | David | 06/21/23 7:55 PM
Row 178 | @yojando.drullard@penske.com , Log4j team started working on modernizing this application. When we verified the old production bamboo build we are seeing following 2 repositories mentioned in the build. UnitJacket_PROD - https://svn.penske.com/svn/fieldsys/maintenance/unit-jacket/tags/prod/20220623/unitjkt UnitJacket_ATTACHSVCCLIENT_JAR (Jar repo)- https://svn.penske.com/svn/fieldsys/other/attachment-service/Jar/prod I am expecting 2nd one is a dependency jar for the first repo. Is that correct? If yes, we need to do the log4j and mavanization for the dependency jar also. Could you please check and confirm. Thanks. FYI: @shane.myers@penske.com | Gayam | 05/18/23 1:16 AM
| @praneeth.gayam@penske.com Yojando is no longer an employee at Penske. You are correct that the 2nd one is the dependency jar. The jar supports attachments in unit jacket. The attach svc client jar is already in artifactory i believe. I am not sure on the status of log4j for attach service | David | 06/06/23 10:30 PM
| @david.long@penske.com . Thanks for the info. we need to modernize the attach svc client jar also. @yvette.urso@penske.com , Could you please add one line in smartsheets for UnitJacket_ATTACHSVCCLIENT_JAR. | Gayam | 06/07/23 3:37 AM
Row 179 | I attempted the Prod deployment in bamboo which was a success. Changing status. | David Graf | 07/05/23 10:54 PM
Row 179 | if maven hasn't already been signed off on. This message is sign off for maven. | David Graf | 06/30/23 6:59 PM
Row 179 | Soon, I will attempt to run Prod deployment. This will complete the bamboo testing. | David Graf | 06/30/23 6:58 PM
Row 179 | confirmed, looks good; thanks | David Graf | 06/30/23 6:56 PM
Row 179 | We deployed to QA without issue continuing testing to run Prod deploy, but first can you clean up the two deployments? I see two: userlookup-svc-deploy userlookup-web-deploy | David Graf | 06/28/23 7:31 PM
| Sure @david.w.graf@penske.com . we will remove userlookup-web-deploy | Gayam | 06/29/23 2:35 AM
| @david.w.graf@penske.com , Deleted userlookup-web-deploy. | Gayam | 06/30/23 1:23 AM
Row 179 | @praneeth.gayam@penske.com another thing that we might have to check is the deploy pattern that it is using. If it was originally set up was a web deploy then that could be the reason that it is including a tgz with the war. The Web Services scripts only expects the war and so far the tgz has been left in the var/tmp directory each time we build. My suggestion is to have the deploy use a service implementation instead of web deploy implementation which should only deliver the war to var/tmp. | David Graf | 06/14/23 7:34 PM
| @david.w.graf@penske.com , For web applications, the tgz file contains only static content and it should be copied to the location /opt/webcontent/<instance>/<app>/. Is there anything different for this application? | Gayam | 06/15/23 12:43 AM
| this is not a web application. It is a service (svc) that deploys on wsv which has no need for static content. | David Graf | 06/16/23 4:38 PM
| Sure @david.w.graf@penske.com . We will fix the issue and will deploy the war to /var/tmp. | Gayam | 06/16/23 10:16 PM
| @david.w.graf@penske.com , WE removed the assembly configuration which generates the tgz file with static content. Please check the changes in below PR. https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-svc/pull-requests/5/overview | Gayam | 06/19/23 7:36 PM
Row 179 | @praneeth.gayam@penske.com The bamboo build plan is incorrectly labeled as userlookup-web but it should be userlookup-svc. I think @ankita.tiwary@penske.com created a footprint ticket that requests the same. Please let us know when the bamboo is fixed to have svc. | David Graf | 06/12/23 7:56 PM
| Sure @david.w.graf@penske.com . We will work on it. | Gayam | 06/13/23 1:28 AM
| @david.w.graf@penske.com , We changed the build plan name to userlookup-svc. https://bamboo.penske.com/browse/ULSBP-USELO/ Do you want us to change the deploy plan name too? | Gayam | 06/14/23 3:48 AM
| yes, please change the deploy name too. And can you link to the spec and template for this app in Bitbucket? so that I may confirm | David Graf | 06/14/23 5:12 PM
| @david.w.graf@penske.com , Deploy name changed to userlookup-svc-deploy. Please deploy to dev and qa. We will delete old deploy plan once you confirm the new deploy plans. | Gayam | 06/16/23 2:52 AM
Row 179 | we overcame an issue with logging this morning and hope to continue with dev deployment soon. | David Graf | 06/12/23 7:54 PM
Row 179 | @david.w.graf@penske.com , We did complete the mavanization on this app. But Hugo took over to add the unit tests. Latest code is in the branch https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-web/commits?until=refs%2Fheads%2Fdevelop_log4j&merges=include Bamboo plan is https://bamboo.penske.com/browse/ULSBP-USELO/ Please let us know if you are looking for any other info. Thanks | Gayam | 04/21/23 1:32 AM
Row 179 | looks like even web-inf is in svn. So during modernization it may not be needed because maven may create those directories from scratch. | David Graf | 04/20/23 6:46 PM
Row 179 | Hugo provided SVN location: https://svn.penske.com/svn/architecture/general/userlookup/branches/dev_gh/ | David Graf | 04/20/23 6:45 PM
Row 179 | shouldn't this bitbucket be userlookup-svc? https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-web/browse the app does not have a front end and is deployed to wsv instance. I'm not sure it needs a web-inf directory either. Where is the SVN archive location to refer to? | David Graf | 04/20/23 6:30 PM
Row 179 | @hugo.scavino@penske.com @sherin.basheer@penske.com We are tasking Ankita with this modernization work. Please let me know if you have any issues with that. @praneeth.gayam@penske.com let us know where this left off | David Graf | 04/20/23 5:28 PM
Row 179 | @hugo.scavino@penske.com , userlookup - build & Deploy plan onboarding completed and Dev deployment done. Please verify. https://bamboo.penske.com/browse/ULSBP-USELO/ | Gayam | 04/04/23 11:14 PM
Row 179 | Sure @hugo.scavino@penske.com . Can you also verify the secrets which we sent earlier and let us know whether any code changes required. Thanks. | Gayam | 02/10/23 12:56 AM
Row 179 | Bamboo (CAP) - I have completed my peer review and unit tests. Please proceed with the Bamboo build using the develop branch. https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-web/branches | Hugo Scavino | 02/09/23 10:06 PM
Row 179 | I will review project. It requires a new unit and integration test before deploying to DEV https://bitbucket.penske.com/projects/ARPROJ/repos/userlookup-web/browse?at=refs%2Fheads%2Fdevelop_log4j | Hugo Scavino | 01/31/23 9:49 PM
Row 179 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:28 AM
Row 179 | @hugo.scavino@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 3:51 AM
Row 180 | Question: @karthikeyan.srinivasan@penske.com / @sarath.mani@penske.com / @stella.george@penske.com , Based on bamboo the prod ref is https://svn.penske.com/svn/fieldsys/maintenance/usermaint/tags/_T_PROD_BUILD_2016-12-13/ But looks like the tag is moved to here https://svn.penske.com/svn/fieldsys/maintenance/usermaint/tags/old_tags/_T_QA_BUILD_2016-12-13 We need a confirmation on the branch? Could you please check it. Thanks. Bamboo: https://bamboo.penske.com/chain/viewChain.action?planKey=USERMAINTBP-USERMAINTPROD | Gayam | 06/27/23 5:37 AM
Row 181 | I see the plan but running into issues with the intial deployment: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=147554384 | David Graf | 07/07/23 4:56 PM
| @david.w.graf@penske.com , We will check and get back to you. | Gayam | 07/10/23 11:29 PM
| @david.w.graf@penske.com issue is resolved. Please check. instancetype was missing initally. | Gayam | 07/12/23 1:44 AM
Row 181 | @praneeth.gayam@penske.com Please add a third deployment for QA 2 which will deploy an artifacts called usermgmt2.war and usermgmt2.tgz. | David Graf | 06/30/23 9:20 PM
| @david.w.graf@penske.com , I am not sure about the ask here. Build needs to be environment agnostic..right? One build and same war/tgz needs to be deployed to all environments. Could you please let me know whether I am missing anything. | Gayam | 07/01/23 1:34 AM
| it is the same agnostic artifact, the name of the artifact needs to change to usermgmt2 so that the QA server can host it using the usermgmt2 scripts. | David Graf | 07/03/23 4:39 PM
| I see there was an attempt to create a branch which alters the pom. I don't think that is the best way to proceed. The pom will support prod by default so it should be usermgmt. For usermgmt2, there should be a bamboo tasked added after the jar was pulled from artifactory which renames it with a 2 at the end (ex: usermgmt2) | David Graf | 07/05/23 7:30 PM
| @david.w.graf@penske.com , That is what I suggested to team. CICD team is looking into this. | Gayam | 07/06/23 3:11 AM
| @david.w.graf@penske.com , We have created another deploy plan 'qa2_was8-deploy' to satisfy the given requirement. Please check. Thanks. https://bamboo.penske.com/browse/USRMGMT-UMGMT/deployments | Gayam | 07/07/23 1:36 AM
Row 181 | @praneeth.gayam@penske.com Here are some details: User Management has the following Deployments: QA, QA2, Prod There is no DEV and QA2 deploys to the sam location as QA but the artifact is called usermgmt2.war. Currently the user-management build plan has two deployments and that should be fixed to only be one: https://bamboo.penske.com/browse/USRMGMT-UMGMT/deployments | David Graf | 06/29/23 1:30 AM
| @david.w.graf@penske.com We will delete the usermgmt-deploy plan and retain the user-management-deploy plan that has a matching name with the bitbucket project. | Gayam | 06/30/23 12:46 AM
| confirmed, looks good. Thanks. | David Graf | 06/30/23 6:57 PM
Row 181 | @praneeth.gayam@penske.com we have deployed changes succesfully to production on 05/09 so we can close this app. | Sama | 05/17/23 2:04 AM
| Thanks @bhagya.sama@penske.com . Changed the status to Done. | Gayam | 05/17/23 3:12 AM
| @bhagya.sama@penske.com , Do the log4j and maven changes are deployed to production? | Gayam | 06/06/23 9:51 AM
| @praneeth.gayam@penske.com log4j and maven changes are in production. However, we had to use the old bamboo build ALL_BUILD plan to deploy. We are starting the Bamboo effort back up. So that it can be completed. | David Graf | 06/29/23 1:15 AM
Row 181 | after that we will have to return to the bamboo plan. @hugo.scavino@penske.com @bhagya.sama@penske.com | David Graf | 04/11/23 12:16 AM
Row 181 | we have a deploy scheduled for 4/18 which contains all of the changes placed in develop_log4j. | David Graf | 04/11/23 12:14 AM
Row 181 | @bhagya.sama@penske.com - QA Deployment done on 16th Nov | Mathumala Nachiappan | 11/23/22 3:53 AM
Row 182 | we are going to be starting this effort back up. We will be doing the Dev deploy test. | David Graf | 06/29/23 1:31 AM
Row 182 | As per @hugo.scavino@penske.com , RBAC updates for usermgmtsvc.war are working fine and provided approval for reonboarding RBAC updates for all other arch apps. @mathumala.nachiappan@penske.com @balu.mohan@penske.com @haribabu.challa@penske.com | Gayam | 02/16/23 3:23 AM
Row 182 | I'm going to delete the branch that you created for me for javadoc after I transfer what I've learned to a different app. | David Graf | 01/18/23 11:31 PM
Row 182 | @david.w.graf@penske.com , As requested for javadoc changes we created following branch. https://bitbucket.penske.com/projects/AR-SEC/repos/usermgmtsvc/branches?base=refs%2Fheads%2Ffeature%2Fjavadoc_implementaion FYI: @hugo.scavino@penske.com , @mathumala.nachiappan@penske.com | Gayam | 12/08/22 11:14 PM
| how do I run the JavaDoc creation locally? I want to see the errors preventing JavaDoc creation. | David Graf | 01/18/23 8:52 PM
| I used intelliJ to generate and there were some errors and warnings but the javadoc generated. "C:\Program Files\Amazon Corretto\jdk1.8.0_322\bin\javadoc.exe" -protected -splitindex -d C:\PTL_MIS\git\usermgmtsvc\javadoc @C:\Users\600212113\AppData\Local\Temp\javadoc_args | Hugo Scavino | 01/18/23 9:36 PM
| I remember having talked to someone about this and that I could run it from the command line. I think that doing a mvn install was sufficient. I was able to see it fail miserably with this app due to javadoc errors. I'm thinking about maybe putting this one the ebs client jar instead of this service which should be well documented through swagger instead of javadocs. But a shared library jar the ebs client would be perfect for javadoc. | David Graf | 01/18/23 11:29 PM
Row 182 | Now that we have a valid bamboo plan. I was able to make minor changes. The appilcation was deployed to DEV and is logging at /logs/apps/usermgmtsvc as expected. Once QA is available we can regression test there. | Hugo Scavino | 01/13/23 3:07 AM
| Thanks @hugo.scavino@penske.com . We will deploy the app to QA and will let you know. @haribabu.challa@penske.com | Gayam | 01/13/23 9:42 AM
| @hugo.scavino@penske.com , usermgmtsvc Qa deployment done but jtest reports are not published in DTP server. @haribabu.challa@penske.com is checking on this. | Gayam | 01/14/23 12:21 AM
Row 182 | @hugo.scavino@penske.com , Secret scanning is completed on this application and in our analysis all are false positives. I will send the sheet in the email. Could you please check and confirm. @mathumala.nachiappan@penske.com @swati.saxena@penske.com | Gayam | 01/10/23 12:03 AM
Row 182 | Sure @hugo.scavino@penske.com . @praneeth.gayam@penske.com - Pls. note this for the changes | Mathumala Nachiappan | 12/02/22 5:42 PM
Row 182 | The project should be here https://bamboo.penske.com/browse/USRMGMT and NOT https://bamboo.penske.com/browse/CSP-USM Thank you | Hugo Scavino | 12/01/22 3:24 AM
Row 182 | @praneeth.gayam@penske.com and @mathumala.nachiappan@penske.com I opened a ticket to moderize the Bamboo project for usermgmtsvc. There is an issue in QA and I would rather solve it with a newer branch and code - FYI FP - 1758286 | Hugo Scavino | 12/01/22 3:23 AM
Row 182 | @praneeth.gayam@penske.com - To confirm the Maven rework | Mathumala Nachiappan | 11/23/22 3:55 AM
Row 183 | @sherin.basheer@penske.com , Please review the below PR. https://bitbucket.penske.com/projects/AR-SEC/repos/userstoreclient-rest/pull-requests/3/overview | Gayam | 02/16/23 2:09 AM
Row 183 | @mathumala.nachiappan@penske.com This is not blocked. I picked AO Final Testing - but please find the proper stage you are in. @sherin.basheer@penske.com can you work with Mathu on what is needed for this? Thank you | Yvette Urso | 12/09/22 12:58 AM
Row 183 | @praneeth.gayam@penske.com - Pls. follow up with Hari on the Artifact upload process | Mathumala Nachiappan | 12/02/22 5:29 PM
Row 183 | @yvette.urso@penske.com - Deployment is not required for these jars. Can we have this as one of the deliverables as Needed/Not Needed? | Mathumala Nachiappan | 11/23/22 3:57 AM
Row 183 | @praneeth.gayam@penske.com - To upload artifacts to Artifactory. No Deployment Required | Mathumala Nachiappan | 11/23/22 3:56 AM
Row 184 | I have reviewed the secrets and cOnfirming secrets are false positives. | Sherin | 06/20/23 11:33 PM
| Thanks @sherin.basheer@penske.com . Could you please provide the response for the question asked above. | Gayam | 06/21/23 12:57 AM
Row 184 | Question: @sherin.basheer@penske.com , adding to secrets mitigation, targeted folder of this app contains dev/prod/qa subfolders and each have multiple xsd and wsld files. Do we need to include them in the build path? If yes, which folder files we need to include them because different env files have diff data. | Gayam | 02/03/23 1:03 AM
Row 184 | Secrets Mitigation: @sherin.basheer@penske.com , We completed the secrets scanning of this app and in my team's analysis all are false positives. I will send the secrets in an email. Please verify and confirm. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/19/23 11:59 PM
Row 184 | @sherin.basheer@penske.com - Modernized version of Penskesso.jar is uploaded to artifactory. This application is good to proceed for further changes, CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/13/22 5:46 PM
Row 184 | penskesso.jar is awaiting for PR review. | Mathumala Nachiappan | 12/02/22 5:30 PM
| @yvette.urso@penske.com - This is just an update tracked for this app. No action required presently for this Application. 'CAP is blocked' as the dependency Penskess.jar is not progressed. And that is in #71. | Mathumala Nachiappan | 12/12/22 4:48 PM
Row 184 | @mathumala.nachiappan@penske.com this is not blocked. Please specify who you are requesting to review and at what stage. Thank you | Yvette Urso | 12/09/22 1:00 AM
Row 184 | Missing denendency not available in artifactory-->penskesso.jar | Mathumala Nachiappan | 11/23/22 3:59 AM
Row 185 | sorry about that confusion, merge is complete | David Graf | 06/01/23 1:31 AM
| Thanks @david.w.graf@penske.com . We will onboard feature/maven branch to bamboo. | Gayam | 06/03/23 12:16 AM
| @david.w.graf@penske.com , feature/maven branch is onbaorded to Bamboo. Please check. https://bamboo.penske.com/browse/UCSVC-USRSVCCLT1/ | Gayam | 06/10/23 2:12 AM
Row 185 | @praneeth.gayam@penske.com I don't want to merge to develop. That isn't mandatory is it? I would prefer to leave develop as close to production as possible so that I can deploy a change if I need to. | David Graf | 05/25/23 5:33 AM
| Sure @david.w.graf@penske.com . You don't have to merge to develop. But can you merge the PR. https://bitbucket.penske.com/projects/AC/repos/usrcreationsvc-client/pull-requests/4/overview This is merging to feature/maven branch which is the base branch all of lo4j team's changes. | Gayam | 05/26/23 12:01 AM
Row 185 | maven is confirmed please move to Bamboo stage. | David Graf | 05/24/23 5:10 PM
| @david.w.graf@penske.com , PR is still in open status. Could you please merge. Also, once you merge the below, I think need to merge feature/maven branch to develop. Then we will onboard the develop branch to Bamboo. https://bitbucket.penske.com/projects/AC/repos/usrcreationsvc-client/pull-requests/4/overview | Gayam | 05/25/23 2:41 AM
Row 185 | @praneeth.gayam@penske.com please enter the needed and not needed information into the analysis columns for this app. | David Graf | 05/03/23 5:19 PM
| Review: @david.w.graf@penske.com / @mahendra.kalyan@penske.com , Log4j team completed the required changes and created PR. Please check. https://bitbucket.penske.com/projects/AC/repos/usrcreationsvc-client/pull-requests/4/overview | Gayam | 05/04/23 12:14 AM
Row 185 | Mahendra reviewed the secrets and they are all false positives. Please move to next step. | David Graf | 05/02/23 5:24 PM
Row 185 | @mahendra.kalyan@penske.com Sent secrets in the email. Please check and confirm. | Gayam | 04/26/23 1:49 AM
Row 185 | @praneeth.gayam@penske.com complete your analysis, and don't trust that the mavenization was done to the Security Modernization standards. I expect there to be changes in the pom and also the need for new bamboo builds. | David Graf | 04/21/23 4:32 PM
| Sure @david.w.graf@penske.com . We will verify and complete the requested work. | Gayam | 04/22/23 2:08 AM
Row 185 | changed status to CAP analysis. Mahendra will do work after the analysis stage is over. | David Graf | 04/19/23 5:11 PM
| @david.w.graf@penske.com , Are you expecting any work on this. It looks like already mavanized. | Gayam | 04/21/23 1:49 AM
Row 185 | @sherin.basheer@penske.com , It looks like this is already mavanized by AO. https://bitbucket.penske.com/projects/AC/repos/usrcreationsvc-client/browse?at=feature%2Fmaven Is this needs any more work? FYI: @yvette.urso@penske.com , @hugo.scavino@penske.com | Gayam | 04/19/23 3:15 AM
Row 185 | @praneeth.gayam@penske.com Per Arch Team this is a companion Jar to usrcreationsvc.war. I added this new today. | Yvette Urso | 04/14/23 8:54 PM
| Thanks @yvette.urso@penske.com . We will check. | Gayam | 04/18/23 3:05 AM
Row 186 | We testing in QA and test is passing with logs being created. | David Graf | 06/19/23 5:10 PM
Row 186 | @praneeth.gayam@penske.com We attempted to test this morning and found that the build plan is missing some configuration or security for myself and Mahendra. We cannot create a plan branch the button is missing. We cannot test without using our plan branch. | David Graf | 06/13/23 5:17 PM
| @david.w.graf@penske.com , I will check with CICD team and let you know. | Gayam | 06/14/23 2:48 AM
| @david.w.graf@penske.com , Ritesh added your id as admin for this app and you can create plan branches now. | Gayam | 06/15/23 12:53 AM
| I think the branches that I need have been created but the admin setting must have been temporary. Because this morning I do not see the add branch button. | David Graf | 06/16/23 4:39 PM
Row 186 | Please create bamboo for the service | David Graf | 04/13/23 5:31 PM
| Sure @david.w.graf@penske.com . we will onboard to bamboo and will let you know. | Gayam | 04/13/23 11:22 PM
| @david.w.graf@penske.com usrcreationsvc dev deployment is completed from develop_log4j branch. Please verify. https://bamboo.penske.com/browse/UCSVC-USRSVC/deployments | Gayam | 04/15/23 12:35 AM
Row 186 | we cannot go to dev because bamboo is ant so we will move to Bamboo stage. | David Graf | 04/13/23 5:30 PM
Row 186 | Last step for mavenization from AO is to deploy using old bamboo into Dev and test. Then we will move to next step. | David Graf | 04/11/23 5:31 PM
Row 186 | https://jira.penske.com/browse/WRPSUP-148 Mahendra is working on this. | Sherin | 03/10/23 9:26 PM
Row 186 | @mathumala.nachiappan@penske.com this is not blocked - moved to AO Secrets Mitigation | Yvette Urso | 12/09/22 1:00 AM
| Got it @yvette.urso@penske.com | Mathumala Nachiappan | 12/12/22 4:48 PM
Row 186 | @sherin.basheer@penske.com - In Secret scanning, found hardcoded href links and hardcoded credentials. Pls. check it for redaction. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/08/22 7:47 PM
Row 186 | @sherin.basheer@penske.com , We have completed log4j/maven changes. Please revie and merge them. https://bitbucket.penske.com/projects/AR-SEC/repos/usrcreationsvc/pull-requests/10/overview | Gayam | 12/07/22 10:25 AM
Row 186 | Pending for the modernization of usrcreationservice-client.jar | Mathumala Nachiappan | 12/02/22 5:31 PM
Row 187 | @hugo.scavino@penske.com @praneeth.gayam@penske.com Hugo - and you look at this open item - whether utimageservice should be taken into log4j/mavan upgradation. | Yvette Urso | 03/29/23 12:57 AM
Row 187 | Sellsheet application depends on this jar. Sellsheet is a corp app. But utimageservice's owner is Brian Joseph. | Yvette Urso | 03/29/23 12:56 AM
Row 188 | @praneeth.gayam@penske.com Shouldn't log4j scope be updated? | Sherin | 06/24/23 2:03 AM
| @sherin.basheer@penske.com , Not getting you. Please elaborate. | Gayam | 06/27/23 3:11 AM
Row 188 | Tested in QA and got signoff from users | Sherin | 06/24/23 12:00 AM
Row 190 | Confirmed by @sherin.basheer@penske.com | Mathumala Nachiappan | 11/23/22 4:02 AM
Row 191 | @rajesh.haravde@penske.com , Build is already successful on develop_log4j branch. Please deploy to QA. | Gayam | 07/10/23 11:31 PM
Row 191 | log4j commits not merged into main develop branch. develop branch is failing to build. But log4j_develop branch is getting successfully build. please guide. | Rajesh | 07/07/23 11:38 PM
Row 191 | Please confirm if we can start validating the bamboo script for this project and which branch | Rajesh | 06/09/23 12:09 AM
| @rajesh.haravde@penske.com , PR is not yet merged. But we will onboard the develop_log4j branch to bamboo for you to validate. Once validation completes, please merge. | Gayam | 06/09/23 1:45 AM
| @rajesh.haravde@penske.com , develop_log4j branch is onboarded successfully and build is successful. Please verify. | Gayam | 06/13/23 2:11 AM
Row 191 | pom.xml not found , please look look into it. | Rajesh | 05/16/23 6:51 PM
| @rajesh.haravde@penske.com , Develop_log4j branch has pom.xml. | Gayam | 05/17/23 3:31 AM
Row 191 | Review: @rajesh.haravde@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/PTLCORP/repos/vehicleimageupdate-batch/pull-requests/4/overview | Gayam | 05/02/23 2:04 AM
Row 191 | We are not going to implement any code change at this moment. please take it forward the source as it with maven and bitbucket upgradation efforts. Thank you. | Rajesh | 04/14/23 12:10 AM
| Thanks @rajesh.haravde@penske.com . Changed the status to Cap Maven. | Gayam | 04/14/23 12:22 AM
Row 191 | @april.ottey@penske.com / @veronique.labeille@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:36 AM
| @krishna.tanga@penske.com | Yvette Urso | 12/01/22 8:33 PM
| @rajesh.haravde@penske.com updated the svn url in the email. https://svn.penske.com/svn/fieldsys/maintenance/fleetnet/branches/offshore_standalone/vehicleimageupdate Rajesh, could you please provide the existing bamboo plan too. Thanks. @mathumala.nachiappan@penske.com | Gayam | 12/08/22 11:04 PM
| There is not bamboo plan for this one. this are get deployed on JDK box as JAR. I will verify with previous lead and get back to you if any. but as of now no bamboo plan available for this one. | Rajesh | 12/12/22 11:54 PM
| @rajesh.haravde@penske.com , As there is no existing bamboo build, under which project we need to create new bamboo specs for this app? | Gayam | 01/11/23 9:28 AM
| As discussed with @rajesh.haravde@penske.com , log4j team needs to create a new Bamboo project for vehicleimageupdate. Changing the status to (Cap)Log4j | Gayam | 02/21/23 4:56 AM
| Created the project in Bamboo https://bamboo.penske.com/browse/VIGBP | Gayam | 03/02/23 2:19 AM
Row 191 | Secrets: @rajesh.haravde@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/25/23 1:34 AM
Row 191 | Changed status to AO Bamboo | Yvette Urso | 12/15/22 2:56 AM
Row 191 | @krishna.tanga@penske.com can you assist Mathu with the Bamboo Plan for this app? | Yvette Urso | 12/09/22 1:04 AM
Row 192 | @sarath.mani@penske.com / @dale.porter@penske.com , I sent a secret file of this app in email. Please verify. | Gayam | 07/25/23 9:34 PM
| Hi, I checked the secrets referenced in the excel file and in the SVN repository. I did not see any issues as no "actual" password or key value secrets security wise are found. You can move forward with the modernization process, thank you. | Dale Porter | 07/28/23 2:49 AM
| Sure @dale.porter@penske.com . thanks. | Gayam | 07/31/23 2:50 AM
Row 192 | Hi all, these changes are not deployed yet to production and I was not sure if I was supposed to merge new changes to the logr4j branch. I know understand that I should not have. Can you please use the last production release like you originally branched from and disregard the changes I checked in as I will have to do a feature Jira tasks once this is moved to bitbucket (git) and then I can have the latest changes merged then. Thank you. | Dale Porter | 07/17/23 7:23 PM
| Thanks @dale.porter@penske.com | Gayam | 07/19/23 1:06 AM
Row 192 | @dale.porter@penske.com , We observed that you committed some of your changes to log4j branch. But this branch is specifically for log4j migration. Are you planning to implement any new application specific changes for this app? Log4j branch: https://svn.penske.com/svn/fieldsys/maintenance/vehicle-information-service/branches/vehicleinfosvc_Log4jChanges/ | Gayam | 07/12/23 2:52 AM
Row 192 | Question: @dale.porter@penske.com , This app is having multiple src folders. We are expecting vehicle-information-service folder is the vehicleinfosvc.war application and the other folder(vehicleInformationUtility) is the dependency jar. SVN location(vehicleinfosvc): https://svn.penske.com/svn/fieldsys/maintenance/vehicle-information-service/tags/prod/1.0_20220809 Bamboo for vehicleInformationUtility. https://bamboo.penske.com/browse/VEHICLEINFO-VICPROD As we are modernizing the application, we have 2 choices for the vehicleInformationUtility fodler. 1. If vehicleInformationUtility is not used by any other application then this folder can be included inside the vehicleinfosvc app's source. It requires work from AO. Or 2. Need to extract the vehicleInformationUtility folder and create separate repo and bamboo build. Use this jar as a dependency in vehicleinfosvc app. It doesn't require work from AO. Please let us know which route you want to take. Thanks. @shane.myers@penske.com | Gayam | 06/13/23 1:58 AM
| @praneeth.gayam@penske.com VehicleInformationUtility.jar is a sharded jar used by different application. you need to go with option#2 | Stella george | 06/14/23 2:01 AM
| Thanks @stella.george@penske.com . I will ask @yvette.urso@penske.com to add one more line item for vehicleInformationUtility | Gayam | 06/14/23 2:18 AM
Row 192 | Confirmed in PC2 and SVN, The last production tag in SVN is https://svn.penske.com/svn/fieldsys/maintenance/vehicle-information-service/tags/prod/1.0_20220809 | Dale Porter | 06/06/23 6:58 AM
| Thanks @dale.porter@penske.com | Gayam | 06/06/23 8:32 AM
Row 192 | @yojando.drullard@penske.com , In bamboo, prod reference to "https://svn.penske.com/svn/fieldsys/maintenance/vehicle-information-service/tags/prod/1.0_20190620" But this path doesn't exist in svn. Could you please help us to find the correct prod reference. | Gayam | 05/10/23 11:12 PM
Row 193 | Review: @david.long@penske.com / @payel.ganguly@penske.com , This app is ready for your review. Please verify. https://bitbucket.penske.com/projects/MAIN/repos/vendordvir-batch/pull-requests/3/overview | Gayam | 07/21/23 10:55 PM
Row 193 | @david.long@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:53 AM
| AO confirmed no changes required for secrets. | Gayam | 06/16/23 10:32 PM
| Thank you for the update @praneeth.gayam@penske.com I am included on this app as one of it's contacts, but as you saw in our email chain for secrets, Stella and her team will be taking care of this mostly. Thanks again :) | David | 06/21/23 7:56 PM
Row 193 | @praneeth.gayam@penske.com Is there any update on this batch? | David | 06/13/23 7:54 PM
| @david.long@penske.com , We have started working on this applciation. | Gayam | 06/14/23 2:50 AM
Row 195 | @praneeth.gayam@penske.com can you create the build and deploy job | Mahipal | 05/30/23 8:05 PM
| @mahipal.podduturi@penske.com , If your review completes, can you merge the code to develop branch. https://bitbucket.penske.com/projects/ARPROJ/repos/bill-apprunner-batch/pull-requests/8/overview | Gayam | 05/31/23 12:59 AM
Row 195 | @mahipal.podduturi@penske.com | Sherin | 05/25/23 8:42 PM
Row 195 | @sherin.basheer@penske.com - This app is available for your final review. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 12/02/22 5:46 PM
| @sherin.basheer@penske.com , This is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/vendorreg-web/pull-requests/3/overview | Gayam | 03/03/23 1:15 AM
Row 195 | @praneeth.gayam@penske.com - To review Maven changes | Mathumala Nachiappan | 11/23/22 4:02 AM
Row 196 | We are not supporting this project anymore. it belongs to different team. | Rajesh | 02/10/23 2:59 AM
| @rajesh.haravde@penske.com - Can you share the reference if you have? CC: @yvette.urso@penske.com , @praneeth.gayam@penske.com | Mathumala Nachiappan | 02/10/23 11:14 AM
| @yvette.urso@penske.com - As this app belongs to different team, Pls. help us with the new AO for this. CC: @praneeth.gayam@penske.com | Mathumala Nachiappan | 02/14/23 10:33 AM
| @yvette.urso@penske.com , Rajesh mentioned that this app belongs to a different team. Could you please help us to find the new AO and team details. @balu.mohan@penske.com | Gayam | 02/24/23 1:09 AM
| @rajesh.haravde@penske.com mentioned following in the email. "You can keep that project on my name currently. Here is the svn url information : https://svn.penske.com/svn/ecomm/webprojects/vfjexcelupload/branches/dev_gh/vfjexcel it’s a java batch will get more information in coming days on if we need bamboo, maven and log4j or not. It’s a OLD project, last modification happened in 2019 as per email notes. Let me verify and get back to you on it." So Log4j team is waiting for the confirmation from Rajesh. @yvette.urso@penske.com | Gayam | 02/27/23 11:51 PM
Row 196 | @krishna.tanga@penske.com We are unable to find Bamboo plans and SVN/Bit Bucket repos for this app. Could you please provide the details for this application. | Gayam | 11/23/22 12:36 AM
| @rajesh.haravde@penske.com , Could you please check above comment and provide your response. @mathumala.nachiappan@penske.com | Gayam | 12/16/22 12:21 AM
Row 196 | @praneeth.gayam@penske.com moved status to AO Bamboo | Yvette Urso | 12/15/22 2:56 AM
Row 197 | @praneeth.gayam@penske.com added comment in bitbucket push request | Dylan | 05/03/23 9:18 PM
| @dylan.price@penske.com We will check and provide the response. | Gayam | 05/04/23 12:20 AM
| @dylan.price@penske.com , I responded in the PR. Please check. thanks. | Gayam | 05/06/23 2:58 AM
Row 197 | @venkatesh.hossalinever@penske.com , This app is ready for your review. Please verify in below PR. https://bitbucket.penske.com/projects/ARPROJ/repos/viewpdf-web/pull-requests/3/overview | Gayam | 03/30/23 11:33 PM
Row 197 | Completed reviewing the log4j secrets - there are no coding changes required. | Venkatesh | 02/27/23 10:09 PM
| Thanks @venkatesh.hossalinever@penske.com. Updated the status to (Cap)Maven | Gayam | 02/27/23 11:31 PM
Row 197 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 197 | @dylan.price@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:49 AM
Row 198 | @david.long@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/virtualpay-web/pull-requests/3/overview | Gayam | 07/07/23 1:16 AM
| @praneeth.gayam@penske.com merged! :) | David | 07/11/23 1:29 AM
| @david.long@penske.com , onboarded to bamboo and deployed to dev. Please verify. Deployment link: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151192149 build & Deploy plan: https://bamboo.penske.com/browse/VIR-VIRPW | Gayam | 07/13/23 1:04 AM
Row 198 | @david.long@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:53 AM
| AO confirmed that all secrets are false positives. No code changes required. | Gayam | 06/16/23 1:14 AM
Row 198 | @praneeth.gayam@penske.com I believe that wsdl can be removed from the project. | David | 06/06/23 10:31 PM
| @david.long@penske.com , We will remove that wsdl and let you know whether we are facing any problems. Thanks. | Gayam | 06/07/23 3:39 AM
Row 198 | @david.long@penske.com , We are facing following issue in this app. Could you please check. Thank you. The application having error in one file under conf folder - AccessOnlineWebServices.wsdl . Its look like application error. Error message : - The part 'userNameToken' has an invalid value 'userNameToken' defined for its element. Element declarations must refer to valid values defined in a schema. | Gayam | 05/25/23 3:26 AM
Row 198 | @David | Gayam | 05/25/23 3:25 AM
Row 199 | @sarath.mani@penske.com , Build and Deploy plans are onboarded and deployment to artifactory is successful. plan onboarding is also successful. Dev deployment completed. Please verify. Thanks. Build plan: https://bamboo.penske.com/browse/VOICEPMSVC-VOICPMABLD0 Deploy Plan: https://bamboo.penske.com/browse/VOICEPMSVC-VOICPMABLD/deployments | Gayam | 08/03/23 12:47 AM
Row 199 | @stella.george@penske.com / @sarath.mani@penske.com , This app is ready for your review. Please verify and merge. Thanks. https://bitbucket.penske.com/projects/MAIN/repos/voicepmsvc/pull-requests/3/overview | Gayam | 07/20/23 11:17 PM
| I reviewed and merged the code. Thank you. | Vaddi Mani | 07/28/23 2:04 AM
| Will onboard to bamboo and deploy to dev. | Gayam | 07/31/23 2:37 AM
Row 199 | @praneeth.gayam@penske.com I didn't get any email yet. | Vaddi Mani | 06/15/23 10:28 PM
| Just sent now. Please check | Gayam | 06/16/23 1:46 AM
| AO confirmed no changes required for secrets. | Gayam | 06/16/23 10:32 PM
Row 199 | @stella.george@penske.com / @sarath.mani@penske.com , I sent the secrets of this app in an email. Please check. | Gayam | 06/15/23 1:54 AM
Row 200 | @dale.porter@penske.com , build plan onboarded and deployment to artifactory is also successful. Please verify. Build plan: https://bamboo.penske.com/browse/PNSKESPLNGBP-PENSKESPLNGCLT0 | Gayam | 08/03/23 12:50 AM
Row 200 | @dale.porter@penske.com , This app is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/MAIN/repos/penske_spelling_client/pull-requests/3/overview | Gayam | 07/27/23 2:26 AM
| I reviewed and merged the code. Thank you. | Dale Porter | 07/28/23 1:50 AM
| Will onbaoard to bamboo. | Gayam | 07/31/23 2:33 AM
Row 200 | I approve and please move forward with uploading the needed jars. | Dale Porter | 07/10/23 11:58 PM
| Thanks @dale.porter@penske.com | Gayam | 07/11/23 6:55 AM
Row 200 | @dale.porter@penske.com , This app depends on RapidSpellMDict.jar and RapidSpellWeb.jar jars. They are not available in artifactory. Please provide your approval to upload to artifactory in below location@dale.porter@penske.com , This app depends on RapidSpellMDict.jar and RapidSpellWeb.jar jars. They are not available in artifactory. Please provide your approval to upload to artifactory in below lcoation. Thanks. groupid - com.keyoti.rapidSpell | Gayam | 07/06/23 4:18 AM
Row 200 | No secrets found on this app. So changing the status to Cap Maven. | Gayam | 07/03/23 11:02 PM
Row 201 | Hi @praneeth.gayam@penske.com this is also in the BillingUtility jar that was mentioned in the cmns application. I believe we should build BillingUtility out into its own application so we can deploy into Artifactory. Could you please set that up? We will then use that jar for this application. Thank you! | Dylan | 06/13/23 7:59 PM
| Thanks @dylan.price@penske.com . Can we take the source code of billingutility from below folder. https://svn.penske.com/svn/fieldsys/other/billing-service/trunk/BillingUtility | Gayam | 06/14/23 2:54 AM
| Hi @praneeth.gayam@penske.com yes that location looks great | Dylan | 06/14/23 5:17 PM
| sure @dylan.price@penske.com | Gayam | 06/15/23 12:48 AM
Row 201 | @manish.sisodiya@penske.com , we are experiencing following issue in this app. We are getting errors in below import statements. import com.penske.cns.maintenance.exceptions.EmailNotSentException; import com.penske.cns.maintenance.services.CustomerNotificationService; We couldn't find the dependent jar for these errors in ptlcommon or project's library. Could you please help us to find the correct jar | Gayam | 03/10/23 11:36 PM
Row 201 | please use the url https://svn.penske.com/svn/fieldsys/other/customer-rolodex-service/tags/prod/1.0.3_20140806/Wambea/src/ as the source for this application | Dylan | 03/07/23 2:09 AM
Row 201 | @sam.skelding@penske.com / @manish.sisodiya@penske.com , This applications in SVN contains multiple src folders. Ideally each application should have only 1 src folder. Could you please check and clarify us. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 1:31 AM
Row 202 | Q2 Ans: use QA for now but we need to check how to implement to get the Prod based on the environment | Mahipal | 05/25/23 10:49 PM
| Thanks @mahipal.podduturi@penske.com . What about 3rd? | Gayam | 05/25/23 11:57 PM
Row 202 | @praneeth.gayam@penske.com Q1 Ans: yes no dev for batch | Mahipal | 05/25/23 10:47 PM
Row 202 | @praneeth.gayam@penske.com | Mahipal | 05/25/23 10:46 PM
Row 202 | @mahipal.podduturi@penske.com , We have following queries on this app. Q1:This application have the dev folder in the targeted folder. But this is a batch app and batch apps do not have dev environment.Could you please clarify this. Q2: In the settings.xml there is email.properties and settings.properties configured. But all 3 environment folders under targeted folder have these 2 files. Which one we need to use? Q3: In all the environment folders under targeted folder we have settings.properties which have database.properties config. But we have databse.properties only in dev folder. Please confirm whether we can use this database.proprties file for all environments? | Gayam | 05/25/23 2:59 AM
Row 202 | @praneeth.gayam@penske.com I am not seeing develop branch https://bamboo.penske.com/browse/BUILWLSDEV-WCHLT | Mahipal | 05/17/23 1:58 AM
| @mahipal.podduturi@penske.com , We will onboard develop branch to Bamboo and will let you know. In the mean time could you please review and merge below PR. https://bitbucket.penske.com/projects/WL/repos/watchlistbatch/pull-requests/9/overview This is recent change as per Hugo's suggestions, log4j2 scope should be compile. | Gayam | 05/17/23 2:05 AM
| @mahipal.podduturi@penske.com , Onboarding develop branch to bamboo is completed. | Gayam | 05/18/23 12:42 AM
Row 202 | @mahipal.podduturi@penske.com , This app is onboarded to bamboo. Please deploy to QA and verify. Thanks. https://bamboo.penske.com/browse/BUILWLSDEV-WCHLT0/deployments | Gayam | 03/30/23 12:50 AM
Row 202 | @praneeth.gayam@penske.com yes you can start the next step | Mahipal | 03/09/23 1:03 AM
Row 202 | @david.w.graf@penske.com , the new bamboo plans not yet on boarded. Once AO reviews the changes and provides the approval for the changes then we are going for the next step which is Bamboo onboarding and build. @mahipal.podduturi@penske.com , It looks like you already completed the review, so can we go for the next step? | Gayam | 03/04/23 12:15 AM
Row 202 | I don't see any builds. Are we sure we should have merged that? | David Graf | 03/03/23 8:30 PM
Row 202 | reviewed the PR and merged | Mahipal | 03/03/23 7:45 PM
Row 202 | @shane.myers@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/WL/repos/watchlistbatch/pull-requests/4/overview | Gayam | 03/03/23 1:19 AM
Row 202 | Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:31 AM
Row 202 | @shane.myers@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:03 AM
Row 203 | @praneeth.gayam@penske.com changes looks good to me. Please proceed for further steps.Thanks! | Sama | 03/25/23 12:57 AM
| Thanks @bhagya.sama@penske.com . @mahipal.podduturi@penske.com , I am seeing that you are doing some changes in develop branch. But we did the log4j and maven changes in develop_log4j branch which is created from master branch. But we can't merge to master unless it is deployed to production. So to verify the changes we have to merge to develop branch. But develop have your changes. So could you please change develop branch name to related to your changes. So that I will create a develop branch from master and merge log4j changes to develop. | Gayam | 03/27/23 11:47 PM
Row 203 | Sure @david.w.graf@penske.com . Maven chagnes also completed on this app. Please review https://bitbucket.penske.com/projects/WL/repos/watchlistservice/pull-requests/37/overview | Gayam | 03/02/23 1:37 AM
Row 203 | can we consider the secrets step finished and move to Maven step? | David Graf | 03/01/23 7:47 PM
Row 203 | It is odd how I don't see the value in SVN either. I guess there are no secrets then but I'm not sure where that row came from. | David Graf | 02/24/23 2:36 AM
| I believe this secret from commit history. That is the reason we are unable see the mentioned secret in the current branch. | Gayam | 02/25/23 12:49 AM
Row 203 | I found a Bitbucket Repo for watchlistsvc.war. I'm not sure which is correct but the Bitbucket repo does not have the secret. Can you compare the two repos and try to figure out which one was used for the last prod deploy? https://bitbucket.penske.com/projects/WL/repos/watchlistservice/browse | David Graf | 02/24/23 2:28 AM
Row 203 | @david.w.graf@penske.com - In secret scanning, one entry with hardcoded credential is found. Pls. check it for redaction. CC: @praneeth.gayam@penske.com @yvette.urso@penske.com - Pls. update the AO as David | Mathumala Nachiappan | 12/08/22 7:49 PM
Row 203 | @yvette.urso@penske.com - New app Owner is @david.w.graf@penske.com . Pls. update. @david.w.graf@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:06 AM
Row 204 | Hi @praneeth.gayam@penske.com, can you please prcoeed with log4j migration and use the following source code. https://svn.penske.com/svn/webprojects/admin/mileagereporting/wbmusernotifier/branches/dev_gh | Venkatesh | 08/03/23 12:55 AM
| @venkatesh.hossalinever@penske.com , Do you want us to ignore the changes which we have completed previously and start from above source code again? | Gayam | 08/04/23 1:00 AM
Row 204 | Review: @venkatesh.hossalinever@penske.com , This app is ready for your review. https://bitbucket.penske.com/projects/ARPROJ/repos/wbmusernotifier-batch/pull-requests/3/overview | Gayam | 03/04/23 1:21 AM
Row 204 | Completed reviewing the log4j secrets - there are no coding changes required. Please let us know in case any further clarifications required. | Venkatesh | 03/01/23 2:03 AM
| Thanks you. Changed the status to Cap Maven | Gayam | 03/02/23 1:59 AM
Row 204 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 204 | @mark.weaver@penske.com , We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:55 AM
Row 205 | please modernize this jar, and add it into artifactory. thank you! also, i do not see any secrets files that need updated. | Dylan | 03/07/23 2:12 AM
| @dylan.price@penske.com Thanks for your response on secrets. Could you please also provide the response for the question asked above. | Gayam | 03/07/23 6:19 AM
| We are working on the changes on this application, please wait for sometime. | Venkatesh | 03/24/23 8:56 PM
Row 205 | Per Rafiq - They will work in their sprint starting 2/20/23 | Yvette Urso | 02/15/23 2:29 AM
Row 205 | @mark.weaver@penske.com , Adding to above question, We have completed the secrets scanning for this app and sent the secrets file in the email. Could you please check and confirm whether the app needs any code changes to remove the secrets. Thanks. | Gayam | 01/31/23 1:56 AM
Row 205 | Question: @rafiq.melath@penske.com / @mark.weaver@penske.com , Following things are we observed in this application. Please check and provide your response. The lib folder contains following jars. servicenetsvc-client.jar serviceRequestUtility.jar. While mavanizing it build is getting successful with out adding these dependencies into pom. Let us know whether we need add these dependencies. If yes, serviceRequestUtility.jar is available in artifactory. So, we can add this dependency. But servicenetsvc-client.jar is not available in artifactory. Please let us know whether we can upload this jar into artifactory. Also we found the bamboo build plan for this jar. The link for this jar is https://bamboo.penske.com/browse/SVCN-SNSVCPROD . Please check it and let us know whether we need to modernize and upload to artifactory. Thanks. @mathumala.nachiappan@penske.com | Gayam | 12/17/22 2:15 AM
Row 206 | Review: @dylan.price@penske.com , This app is ready for your review. Please check and merge. Thanks. https://bitbucket.penske.com/projects/PB/repos/billingutility/pull-requests/3/overview | Gayam | 06/28/23 3:00 AM
Row 206 | there are no secrets in this utility jar. So changing the status to Cap maven | Gayam | 06/23/23 12:09 AM
Row 207 | We ran into an issue when running the PROD deploy. Please investigate: https://bamboo.penske.com/deploy/viewDeploymentResult.action?deploymentResultId=151197905 @praneeth.gayam@penske.com | David Graf | 08/12/23 2:18 AM
Row 207 | we confirm that QA deploy was successful. | David Graf | 04/06/23 5:21 PM
Row 207 | Confirming that artifact is in Artifactory and then announcing a QA deploy. | David Graf | 03/17/23 5:44 PM
Row 207 | Dev deploy is confirmed with develop_log4j branch | David Graf | 03/17/23 5:23 PM
Row 207 | yes please deploy to dev environment | David Graf | 03/09/23 6:23 PM
Row 207 | Maven and log4j changes have been confirmed. Moving this app to the next step which is Bamboo. | David Graf | 02/28/23 6:29 PM
| Thanks @david.w.graf@penske.com . We will let you know once we onbaord the app to Bamboo | Gayam | 02/28/23 11:45 PM
| @david.w.graf@penske.com , We onboarded the app to Bamboo. https://bamboo.penske.com/browse/WRP-WEBRP Can we deploy to Dev? | Gayam | 03/02/23 2:17 AM
Row 207 | I am assigning Amit, from WRP development team, to start the review. | David Graf | 02/22/23 7:25 PM
Row 207 | @david.w.graf@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:07 AM
Row 208 | Deployment: @sreekanth.kancharla@penske.com , Dev deployment is completed for this app. Please check. | Gayam | 03/17/23 2:49 AM
| @sreekanth.kancharla@penske.com , Please merge https://bitbucket.penske.com/projects/ITFIS/repos/wje-web/pull-requests/5/diff#pom.xml The changes are for making log4j2 scope to compile. Thank you. | Gayam | 05/30/23 8:58 AM
| @praneeth.gayam@penske.com Merge completed. | Sreekanth | 06/01/23 12:09 AM
| Thanks @sreekanth.kancharla@penske.com . Build is already completed | Gayam | 06/01/23 10:44 PM
Row 208 | Review: @sreekanth.kancharla@penske.com , this app is ready for your review. https://bitbucket.penske.com/projects/ITFIS/repos/wje-web/pull-requests/3/overview | Gayam | 03/09/23 1:19 AM
| @praneeth.gayam@penske.com PR is merged. Please proceed with further steps. | Sreekanth | 03/13/23 10:19 PM
| Thanks @sreekanth.kancharla@penske.com . We will onboard the app to Bamboo. | Gayam | 03/13/23 11:03 PM
Row 208 | Secrets: @sreekanth.kancharla@penske.com / @kalrav.khamar@penske.com / @james.minisce@penske.com , I sent the secrets file of this app to you in the email. Could you please check and respond whether any code changes required as part of secrets mitigation. Thanks. | Gayam | 02/24/23 1:57 AM
| @praneeth.gayam@penske.com No remediation required for the shared secrets. @james.minisce@penske.com @kalrav.khamar@penske.com | Sreekanth | 02/24/23 2:37 AM
| Thanks @sreekanth.kancharla@penske.com . Changing the status to (Cap)Maven | Gayam | 02/25/23 12:19 AM
Row 208 | @sreekanth.kancharla@penske.com , In this app, same db.prop file exist in dev and prod folders under targeted folder but different db.prop file exist for QA. Could you please check and clarify us. Thanks. https://bitbucket.penske.com/projects/ITFIS/repos/wje-web/browse?at=develop_log4J | Gayam | 02/14/23 12:44 AM
| @praneeth.gayam@penske.com The difference in QA is not required as the hard coded credentials are removed from prod file itself. Please keep the same db.prop for QA as well. Since there is no change between dev & prod specific files and we are going to keep the qa also the same. With this, hope we don't need to maintain this file in targeted folder at all. | Sreekanth | 02/15/23 3:03 AM
| @praneeth.gayam@penske.com Sreekanth has replied to you. Can you change the 'App Status'? | Kalrav | 02/18/23 12:43 AM
| Thanks @kalrav.khamar@penske.com . Changing the status (Cap)Log4j | Gayam | 02/18/23 12:59 AM
Row 208 | @sreekanth.kancharla@penske.com Can you address the app logger replacement query? Thank you. | James | 12/15/22 2:19 AM
| @sreekanth.kancharla@penske.com Did you address the app logger replacement question from 12/09? I think this is still outstanding. | James | 01/25/23 2:22 AM
| @james.minisce@penske.com I've replied already on 12/14. No further questions from the team. | Sreekanth | 01/25/23 7:00 AM
Row 208 | @james.minisce@penske.com - errors on fileappender configuration. @praneeth.gayam@penske.com to follow up | Mathumala Nachiappan | 12/01/22 8:47 PM
| Please be specific as to what you need from me to remove this block. | James | 12/09/22 5:52 PM
| @james.minisce@penske.com , in this app, logger classes are getting created with custom configuration using fileappender(getallappender) and simplelayout . Not able to configure using the slf4j and log4j2. providing link for class file. https://svn.penske.com/svn/webprojects/admin/wje/trunk/wje_prod/JavaSource/com/penske/ebus/journal/filter/DummySecurityFilter.java Could you please check whether these logger classes can be replaced. As we don't have enough info of athe application we can't modify other than what requested. @mathumala.nachiappan@penske.com | Gayam | 12/10/22 12:45 AM
| @praneeth.gayam@penske.com DummySecurityFilter.java is used only for DEV application. I do see in other class files also, the custom logger is implemented. This application is very old application. If these can be replaced with slf4j & log4j2, we are good. Please proceed with changes. | Sreekanth | 12/15/22 3:18 AM
Row 208 | Changed Status | Yvette Urso | 12/15/22 2:19 AM
Row 209 | @praneeth.gayam@penske.com PR looks good can start the next steps | Mahipal | 03/22/23 9:17 AM
| @mahipal.podduturi@penske.com , PR is still in open status. Could you please lerge. https://bitbucket.penske.com/projects/WL/repos/watchlistweb/pull-requests/17/overview | Gayam | 05/22/23 11:51 PM
Row 209 | @mahipal.podduturi@penske.com , this app is onboarded to Bamboo. Please check and let us know whether you are ok to deploy to Dev? | Gayam | 03/23/23 11:07 PM
Row 209 | https://bitbucket.penske.com/projects/WL/repos/watchlistweb/pull-requests/17/diff#pom.xml | Mahipal | 03/15/23 6:45 PM
| Sure @mahipal.podduturi@penske.com . We will check and fix them | Gayam | 03/15/23 11:38 PM
| @mahipal.podduturi@penske.com , We implemented the changes. Could you please check. Thanks. | Gayam | 03/21/23 1:40 AM
Row 209 | @praneeth.gayam@penske.com update the POM with comments | Mahipal | 03/15/23 6:45 PM
Row 209 | Maven Review: @shane.myers@penske.com , We have completed the modernization work on this application. Could you please review in the below PR and provide your approval for the next step. https://bitbucket.penske.com/projects/WL/repos/watchlistweb/pull-requests/17/overview Thanks. | Gayam | 03/01/23 12:19 AM
Row 209 | @shane.myers@penske.com, We completed the secrets scanning for this application and in my team's analyzation all are false positives. But could you please check them and confirm. I will send the sheet in the email. Thanks. @mathumala.nachiappan@penske.com | Gayam | 01/05/23 3:09 AM
| Shane confirmed that all the secrets are false positives for this app in the email. | Gayam | 01/21/23 3:32 AM
Row 210 | I'm changing the status to Major Blocker. This action cannot move forward until thdpaymentsvc goes through Security Modernization. We stopped before deploying into the dev environment. | David Graf | 06/06/23 12:54 AM
Row 210 | nvm, the log4j changes are already in develop so I completed the merge. | David Graf | 06/06/23 12:52 AM
Row 210 | the target is the develop branch but we aren't merging there yet. Please advise. | David Graf | 06/06/23 12:50 AM
Row 210 | @david.w.graf@penske.com , Changed the scope of log4j2 jars from provided to compile. Could you please merge the code. https://bitbucket.penske.com/projects/AC/repos/ws-authorizationfilter/pull-requests/8/overview | Gayam | 05/24/23 2:29 AM
Row 210 | I just noticed that the bitbucket repo is in Architecture-Project but since this repo is for a shared library jar it should reside in Architecture-Commons. Pleas advise: @praneeth.gayam@penske.com | David Graf | 04/28/23 8:00 PM
| Sure @david.w.graf@penske.com . We will push to commons. | Gayam | 04/29/23 1:49 AM
| @david.w.graf@penske.com , this app is moved from Architecture-Project to Architecture-Commons and corresponding Bamboo plans also changed. | Gayam | 05/04/23 12:01 AM
Row 210 | @david.w.graf@penske.com , This app is deployed to ptlcommon_1 folder in dev region. Please check. Thanks. https://bamboo.penske.com/browse/WBPA-WSAUTHZ0/deployments | Gayam | 03/30/23 1:02 AM
Row 210 | @praneeth.gayam@penske.com did you get your answer from Hugo? | David Graf | 03/24/23 5:19 PM
| @david.w.graf@penske.com , if we keep the instanceType variable as shared in bamboo script then app will be deployed to ptlcommon folder. We started working on onboarding to Bamboo. | Gayam | 03/24/23 5:44 PM
| Thanks | David Graf | 03/27/23 7:03 PM
Row 210 | To help with clarifications 1) All WARs, JAR, EAR builds use artifactory as their binary repository. The result of these builds is uploaded to artifactory. 2) Some "JARs" are shared within or amongst teams. This way, teams do not copy JARs but add them to their maven dependency. There is nothing special in artifactory to denote these as shared. 3) Then a subset of these JARs are copied to ./ptlcommmon_1 on each WAS and BATCH server that IBM has called "SHAREDLIBS." Some JARs are third-party, like log4j, and some are Penske proprietary, like reuse. Unfortunately, these JARs do not have the version number as part of the filename, which is the maven standard. But that is another problem. These JARs have an additional deployment step beyond artifactory which is to deploy to the shared library (aka ../ptlcommon_1) directory. See dlinks authentication and reuse for examples. HAppy to discuss more | Hugo Scavino | 03/21/23 6:31 PM
| So @hugo.scavino@penske.com , is webservices script going to deploy to ./ptlcommmon_1 if we provide the instanceType variable value as 'shared' in Bamboo? | Gayam | 03/22/23 12:15 AM
Row 210 | @david.w.graf@penske.com , Shared Library jar means, is it needs to upload only to antifactory? | Gayam | 03/21/23 1:28 AM
| @hugo.scavino@penske.com please straighten out this confusion around the term Shared Library. CC: @yvette.urso@penske.com Shared Library jars are deployed to WebSphere instances and so they are not bundled with application war. That means there need to be a deployment task for each environment (DEV, QA, and PROD) | David Graf | 03/21/23 4:43 AM
Row 210 | @praneeth.gayam@penske.com please see my last message. | David Graf | 03/20/23 5:21 PM
Row 210 | please revisit the bamboo template, this is a Shared Library jar and needs deployments to the environment. | David Graf | 03/17/23 5:46 PM
Row 210 | Confirming that artifact is in Artifactory and then announcing a QA deploy. | David Graf | 03/16/23 5:25 PM
| ignore this for ws_auth it was meant for wrp. | David Graf | 03/17/23 5:44 PM
Row 210 | @david.w.graf@penske.com , Log4j team is not supposed to do the QA deployment as per the instructions from Hugo. AO needs to do the QA deployment. So changed the status to AO QA Deploy/Test. Thank you. | Gayam | 03/17/23 3:06 AM
Row 210 | Dev environment confirmed. | David Graf | 03/16/23 5:26 PM
Row 210 | @hugo.scavino@penske.com / @david.w.graf@penske.com , this is onbaorded to Bamboo. https://bamboo.penske.com/browse/WBPA-WSAUTHZ Please run the develop branch to deploy the artifacts to artifactory | Gayam | 03/02/23 2:18 AM
Row 210 | Ankita confirmed the Maven and now we are moving to the Bamboo stage. | David Graf | 02/24/23 6:27 PM
Row 210 | https://bitbucket.penske.com/projects/ARPROJ/repos/ws-authorizationfilter/browse/src/main/filters/com/penske/ws/filter/WSAuthorizationFilter.java?at=refs%2Fheads%2Fdevelop_log4j | Hugo Scavino | 01/31/23 10:01 PM
Row 210 | This project is a single filter. This will require a single unit test and then ultimate promotion to artifactory. | Hugo Scavino | 01/31/23 10:01 PM
Row 210 | @hugo.scavino@penske.com , This app contains false positive secrets only. I will send the zip which contains all of your apps secrets. Please check and confirm. | Gayam | 01/19/23 3:28 AM
Row 210 | @hugo.scavino@penske.com - Ready for AO Review | Mathumala Nachiappan | 11/23/22 4:20 AM
Row 211 | @brian.joseph@penske.com / @sree.gopal@penske.com , We couldn't find Bamboo and code repo for this app. Could you please help us to find them. Thanks. | Gayam | 07/27/23 11:20 PM
Row 213 | @jeremiah.ashway@penske.com / @frank.d'angelo@penske.com , We are seeing recent activity on this application. So, do you want us to start modernizing this application or need to wait until you complete all of your changes? What is the branch we need to take as base branch if you want us to start modernizing? Bamboo build: https://bamboo.penske.com/browse/CEP-BCC BB repo : https://bitbucket.penske.com/projects/EBCE/repos/cedadatachanges/browse | Gayam | 08/08/23 2:03 AM
Row 215 | @jeremiah.ashway@penske.com / @frank.d'angelo@penske.com , We couldn't find Bamboo and code repo for this app. Could you please help us to find them. Thanks. | Gayam | 07/27/23 11:22 PM
Row 219 | @shweta.gupta@penske.com , I sent the secrets file in an email for this app. Please check and let us know if app requires any code changes. Thanks. | Gayam | 08/10/23 1:17 AM
Row 220 | Query: @jeremiah.ashway@penske.com , We are able to find the bitbucket repo for this app but not bamboo build. Without bamboo build we couldn't figure out the production branch. Could you please let us know the latest branch which is deployed to production. BB Repo: https://bitbucket.penske.com/projects/EBCE/repos/fimigration/browse | Gayam | 07/27/23 8:50 AM
Row 221 | @sree.gopal@penske.com , I sent the secrets file in an email for this app. Please check and let us know if app requires any code changes. Thanks. | Gayam | 08/10/23 1:19 AM
Row 222 | @sree.gopal@penske.com , I sent secrets in an email. Could you please verify it. Thanks. | Gayam | 08/05/23 12:33 AM
Row 224 | @jeremiah.ashway@penske.com , I sent the secrets file in an email for this app. Please check and let us know if app requires any code changes. Thanks. | Gayam | 08/10/23 1:16 AM
Row 226 | @shweta.gupta@penske.com / @frank.d'angelo@penske.com , We observed that there are recent commits in this application. Do you want log4j team need to stop modernize this app until you completed your changes? Because, once it is modernized, total folder structure is going to changes. Please let us know what step we need to take. Thanks. | Gayam | 08/01/23 1:01 AM
Row 227 | @elanchezhian.ochathevan@penske.com / @sree.gopal@penske.com , We couldn't find Bamboo and code repo for this app. Could you please help us to find them. Thanks. | Gayam | 07/27/23 11:41 PM
Row 229 | @kenneth.french@penske.com , I sent secrets in an email. Could you please verify it. Thanks. | Gayam | 08/05/23 12:34 AM
Row 230 | @praneeth.gayam@penske.com path is correct: tags/_T_PROD_20210510 . smsserviceutility.jar is part of the smsservice repo. Once the smsservice is modernized that should include the smsserviceutility.jar | Shawn | 08/10/23 8:24 PM
| Thanks @shawn.mcmurtry@penske.com. Looks like smsserviceutility is used in multiple applications. So it should be created as a separate jar and needs to be uploaded into artifactory. We will extract smsserviceutility to a separate repo and will modernize and create a separate bamboo plan to upload to artifactory. Thanks. | Gayam | 08/11/23 12:15 AM
Row 230 | @shawn.mcmurtry@penske.com / @dave.kost@penske.com , For this app's bamboo prod build mentioned build branch name is differed with branch path. Following are the details. Could you please confirm whether the path is correct. Svn url:https://svn.penske.com/svn/architecture/general/sms-batch/ Branch name: _T_PROD_20131104 Branch Path: tags/_T_PROD_20210510 (latest commit done by shane) This app also dependent on smsserviceutility.jar. Do we need to modernize this jar? Following are the details of this dependency jar. bamboo:https://bamboo.penske.com/chain/admin/config/editChainRepository.action?buildKey=SMSBATCHBP-UTILPROD Svn url:https://svn.penske.com/svn/architecture/general/sms-service/ branch path:tags/_T_PROD_20210510 | Gayam | 07/31/23 3:15 AM
Row 231 | @praneeth.gayam@penske.com Path is correct: tags/_T_PROD_20210510 | Shawn | 08/10/23 8:19 PM
| Thanks @shawn.mcmurtry@penske.com | Gayam | 08/10/23 11:49 PM
Row 231 | @shawn.mcmurtry@penske.com / @dave.kost@penske.com , For this app's bamboo prod build mentioned build branch name is differed with branch path. Following are the details. Could you please confirm whether the path is correct. SVN url: https://svn.penske.com/svn/architecture/general/sms-service/ Branch name:_T_PROD_20131112 Branch Path: tags/_T_PROD_20210510 | Gayam | 07/31/23 3:17 AM
Row 232 | @kenneth.french@penske.com / @sree.gopal@penske.com , There are commits recently done in this application. Is there any active development on this app? Is this app ready for the modernization work? Please clarify. Thanks | Gayam | 08/03/23 1:04 AM
Row 233 | @jeremiah.ashway@penske.com , I sent secrets in an email. Could you please verify it. Thanks. | Gayam | 08/05/23 12:36 AM
Row 235 | @jeremiah.ashway@penske.com , I sent secrets in an email. Could you please verify it. Thanks. | Gayam | 08/05/23 12:35 AM
Row 238 | @jeremiah.ashway@penske.com / @frank.d'angelo@penske.com , This application's resources folder has different xml files for each environment and virtual-host name variable is different in prod, qa ibm-web-bnd.xml files. As modernization involves environment agnostic build which means 1 build needs to be deployed to different environments. In this case, we can't use different xml files for diff environments. Could you please check how to resolve this issue. Thanks. | Gayam | 08/01/23 1:08 AM
Row 239 | @shweta.gupta@penske.com / @frank.d'angelo@penske.com , We found the BB repo for this app but not Bamboo build. Could you please let us know the production branch which we need to use as base branch for modernization work. https://bitbucket.penske.com/projects/EBMS/repos/updlatlong-batch/browse | Gayam | 08/03/23 1:11 AM
Row 240 | @shweta.gupta@penske.com / @frank.d'angelo@penske.com , We couldn't find Bamboo and code repo for this app. Could you please help us to find them. Thanks. | Gayam | 07/27/23 11:43 PM
Row 241 | @brian.joseph@penske.com , I sent secrets in an email. Could you please verify it. Thanks. | Gayam | 08/05/23 12:35 AM
Row 242 | @sherin.basheer@penske.com / @david.w.graf@penske.com , This dependency jar is ready for your review. Please verify and merge. https://bitbucket.penske.com/projects/PTLCORP/repos/docservice-client/pull-requests/2/overview | Gayam | 07/21/23 12:10 AM
Sheet | @praneeth.gayam@penske.com Please use the folder with bodyshop6 | Subramanian | 06/15/23 1:25 AM

## Summary
Capgemini App Summary | Capgemini Migration
Field 2 | 2023-02-01
Not Started | 9
Total Apps "Cap is Working on" | 45
Total Apps "Waiting on AO" | 149
Grand Total of Apps "In Progress" | 151
Done | 11
Retire/Duplicate | 27
Billing - Not Started | 0
Billing - Waiting on AO | 34
Billing - Total In Progress | 38
Billing - Done | 0
Billing - Retire/Duplicate | 9
Finance & Biz Auto - Not Started | 0
Finance & Biz Auto - Waiting on AO | 16
Finance & Biz Auto - Total In Progress | 20
Finance & Biz Auto - Done | 2
Finance & Biz Auto - Retire/Duplicate | 3
Architect - Not Started | 0
Architect - Waiting on AO | 37
Architect - Total In Progress | 36
Architect - Done | 9
Architect - Retire/Duplicate | 7
Fleet Services - Not Started | 0
Fleet Services - Waiting on AO | 14
Fleet Services - Total In Progress | 18
Fleet Services - Done | 0
Fleet Services - Retire/Duplicate | 3
Cust Digital Engineer - Not Started | 9
Cust Digital Engineer - Waiting on AO | 20
Cust Digital Engineer - Total In Progress | 10
Cust Digital Engineer - Done | 0
Cust Digital Engineer - Retire/Duplicate | 0
HR - Not Started | 0
HR - Waiting on AO | 5
HR - Total In Progress | 3
HR - Done | 0
HR - Retire/Duplicate | 0
Web - Not Started | 0
Web - Waiting on AO | 0
Web - Total In Progress | 1
Web - Done | 0
Web - Retire/Duplicate | 2
Maintenance - Not Started | 0
Maintenance - Waiting on AO | 23
Maintenance - Total In Progress | 25
Maintenance - Done | 0
Maintenance - Retire/Duplicate | 1
Savvion - Retire/Duplicate | 1
Security - Retire/Duplicate | 1